Annual Review – Summary Sheet

Title: Assets to Adolescent Girls Programme (SPRING)
Programme Value £ (full life): £17, 286, 687 (£14,668,570 is DFID’s total contribution – 84%)		Review Date: 17/12/2019
Programme Code: 203375	Start Date: 17/12/2013	End Date: 31/03/2022

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020	2021
Programme Score	A	A	A+	A	A+	A
Risk Rating	High	High	High	High	High	Major

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

SPRING supported 74 enterprises operating across nine countries to develop innovative solutions that have, to date, reached over 2.5 million[1] girls and attracted £13.8m in investment[2].
[1] 2,156,880 through one business in Tanzania and 377,334 through other SPRING businesses
[2] This is comprised of equity (42%), grants (36%) and debt (16%)

The SPRING programme was a pioneering 5-year accelerator funded by DFID, Australia’s Department of Foreign Affairs and Trade (DFAT), United States Agency for International Development (USAID), and, formerly, Nike Foundation. SPRING set out to demonstrate that business could develop and offer commercially viable products and services to meaningfully improve the lives of girls aged 10-19. SPRING supported businesses followed a nine-month accelerator programme, starting with a two-week residential bootcamp where participants received world-class training covering business fundamentals, human-centred design (a design tool which includes intended beneficiaries in the design process and ends with a product tailor-made to their needs) linked to the experience of adolescent girls in their respective countries. In addition to the support provided at bootcamps, SPRING participants received research into the feasibility of their prototype, investment readiness and Capital Raising Support, ongoing coaching and mentorship, and other tailored support on the ground from country and regional managers to launch and scale prototypes with the potential to benefit adolescent girls.

A total of four cohorts completed the SPRING programme, and the programme moved into its monitoring and evaluation (M&E) phase in October 2019. This phase will evaluate business performance, and the impact of businesses’ prototypes on adolescent girls and women.

The economic empowerment of girls and women is a strategic priority. DFID’s Business Plan (2011-15) highlights the critical role of wealth creation and gender equality in poverty reduction. DFID’s Strategic Vision for Gender Equality has women’s economic empowerment as one of five pillars (especially access to assets) which are crucial to gender equality. The Economic Development Strategy also emphasises improved access to markets, finance, property and employment opportunities for girls and women. SPRING supports DFID’s objectives by assisting the delivery of a variety of consumer products and services, which can help reduce girls’ time-poverty, reduce gender specific barriers to education or employment, or improve their human capital, in turn contributing to girls’ economic empowerment.

Summary supporting narrative for the overall score in this review (1/2 page)

In its final year of implementation, SPRING continued to deliver and has exceeded all logframe milestones despite increasing targets in most of these in the programme’s final year to ensure stretch. The programme has continued to respond to lessons learned in previous cohorts and the support provided to businesses has been continually refined.
The final six months of implementation focused on sharing lessons learned and best practices identified by the SPRING programme with donors and other development actors, in addition to handing over to the external evaluation partner, Coffey International.

The programme has been awarded an A. Outputs 1 and 3 scored an A, while Outputs 2 and 4 scored A+. All outputs exceeded their milestones for this reporting period. Over the last year, SPRING has:
- Delivered 21 new prototypes developed and launched by SPRING businesses
- Shifted support to help SPRING businesses access financing beyond what SPRING can provide through the Capital Raising Support (CRS) stream and the Business Assistance Fund (BAF)
- Produced 29 knowledge and communications products, highlighting lessons learned
- Participated in panels, hosted side events, and held high-level meetings with donors, SPRING businesses and investors, among others, at international events in Singapore, San Francisco, London, Oxford, Vancouver and Brussels
- Collaborated with 4 other accelerators in Southern Africa and South Asia, sharing best practices and lessons learned from the SPRING accelerator model

In July 2019, SPRING released a series of reports that summarise key lessons from the implementation phase of the programme, reflection on accelerator design, applying Human Centred Design (HCD), supporting businesses to secure investment, and business models for impacting girls. Highlights from those reports include the following:
- Businesses do not necessarily need to introduce new products, services or models to create impact for girls, they just need to be thoughtful about including them in their existing offer
- Business can include girls in various ways, but it starts from listening to them to understand their needs, preferences and constraints, and considering their daily lives
- HCD adds value for businesses and is more than just applying a toolkit. In order to reap the benefits, a practical, applied approach to learning and expert facilitation are key
- Small to medium-size enterprises in developing markets have diverse funding and support needs at different times, which should be matched accordingly
- Local knowledge and networks are crucial when it comes to selecting the right businesses, providing tailored business support and helping businesses to secure follow-on investment
- Residential boot camps are important for providing time and headspace to brainstorm ideas and collaborate with others, but businesses also need ongoing local advice and coaching
- Investors need better information about what it means to invest for girl impact across various sectors and geographies

Recommendations for the year ahead (1/2 page)

The recommendations below focus largely on monitoring and evaluation, as the programme has now transitioned into a phase of independent M&E.

1. As agreed, SPRING’s M&E partner should consider investigating the investor environment in their Programme Performance Evaluation (PPE) report, due in February 2020, which looks at how successful the SPRING programme was. The ‘investor environment’ in this instance, refers to the make-up of the investor landscape in a given context.
2. Human centred design has been a core feature of the SPRING accelerator. As part of the Business Performance Evaluation Summative report, due in June 2020, the M&E partner should, as agreed, conduct research into which aspects of this approach were crucial to SPRING businesses, which were less relevant, and if certain aspects have been dropped or replaced in future prototypes, why this is the case.
3. SPRING has developed an extensive network of contacts which was crucial to sharing lessons learned during the programme lifetime. The SRO should record this network to prevent duplication of efforts in rebuilding this network for future programmes, by March 2020.
4. Given the M&E contract has fixed costs and fixed outputs, DFID SRO should assess the best way to measure value for money (VFM) in the M&E phase of the programme, by March 2020.
5. The DFID SRO and PM should draw up a dissemination plan for sharing lessons that emerge from the M&E phase of the programme, no later than 6 months after the annual review, byJune 2020. These lessons should be shared with other DFID teams leading programmes that engage with SMEs, or those with a specific sector focus covered by SPRING businesses.
## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	SPRING participants launch prototypes designed to reach and benefit adolescent girls
Output number per LF		1	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Cumulative number (% in brackets) of businesses that launch prototypes designed to reach and benefit adolescent girls	Target (August 2019): 60 / (94% in Cohort 1; 78% in C2; 79% in C3; and 70% in C 4)	Slightly exceeded expectations - 64 businesses / (94% in Cohort 1; 78% in C2; 79% in C3; and 90% in C4)

Provide supporting narrative for the score

This output measures the number of businesses that launched prototypes designed to reach adolescent girls. Activity against this output came to an end in August 2019 when the implementation of the programme had concluded. As of August 2019, 64 businesses had launched prototypes that could benefit girls, exceeding the target of 60 businesses. 21 of these businesses have launched their prototypes in year 5. The independent End of Cohort 4 report, produced by the external M&E partner in May 2019, revealed that 74% of SPRING businesses were ‘very satisfied’ with the design support provided when developing a prototype, with the remaining 26% of businesses ‘satisfied’. On the basis that the output marginally exceeded its milestone for this reporting period, and the high levels of satisfaction reported by SPRING businesses, it has been awarded an A.

Furthermore, the End of Cohort 4 report stated that businesses reported that SPRING has improved their understanding of girls. In particular, the opportunity to conduct HCD research with girls had allowed them to test their assumptions about girls and that they had deepened their understanding about girls’ needs, and therefore became more important and visible in the prototype. Some businesses developed a more direct focus on girls by adjusting part of their business to focus more on the needs of girls. One business was creating girl spaces for adolescent girl micro-entrepreneurs. Another business that already had a strong girl focus before SPRING now had more girl targeted content.
Quotes from anonymised cohort 4 SPRING businesses collected by M&E partner:

Business 11: So, earlier, it was, for us, girls were just girls but now we try to understand a day in their lives.

Business 3: We have reached cumulatively, say, five hundred/six hundred girls in the last three/four years, [but], a thousand, just in this year alone. … So, I think that it’s definitely helping us increase our reach, that’s what I think is the most important thing

Business 16: A year ago, we had maybe…I don’t remember exactly but many ninety-nine percent male entrepreneurs, or ninety-eight percent. Now we have a target of kind of at least twenty-five percent or twenty [percent women], going forward.

SPRING businesses that launched prototypes in the reporting period:

#	Business	Date
Cohort 2
1	Zoya	Sept 2018
Cohort 3
2	Deciwatt	Sept 2018
3	Illuminum Greenhouses	Dec 2018
Cohort 4
4	Leaping Boundaries	Jun 2018
5	Maya Apa	Aug 2018
6	Sabaq	Oct 2018
7	Rizq	Dec 2018
8	Women in Digital (WID)	Dec 2018
9	Himalayan Rabbits	Dec 2018
10	Edkasa	Apr 2019
11	Koe Koe Tech	Jan 2019
12	Build Up Nepal	Aug 2018
13	Doh Eain	Mar 2019
14	Jeeon	Jan 2019
15	Sparrow Pay (Khalti)	Feb 2019
16	Play Nepal	Oct 2018
17	Pan Ka Lay	Mar 2019
18	Learnobots	Mar 2019
19	Wondertree	Mar 2019
20	360ed	Jun 2019
21	Eden	Jul 2019

SPRING supports businesses to launch prototypes primarily by:
- Providing technical design and development support during the bootcamps
- Conducting research to inform prototype design and launch
- Releasing tailored Prototype Development Funds (PDF) to businesses

For its fourth cohort (which launched Spring 2018 and ran to Winter 2019) SPRING refined support provided to businesses developing prototypes by adding ‘Bootcamp 0’, which consisted of remote consultations with select businesses identified in conjunction with SPRING country manager. SPRING team members visited all finalist applicants to assess whether they would be a good fit for SPRING. As part of these visits, the team explored potential prototype ideas with the candidate businesses. After selection, those businesses whose prototypes were less well defined were invited to participate in Bootcamp 0, with the aim of honing the prototype concept they would develop during the SPRING programme. This bootcamp identified business challenges and possible prototypes ahead of Bootcamp 1 and was found to be valuable by the evaluation partner.
Case Study: Koe Koe Tech, Myanmar
At the start of the cohort, Koe Koe Tech, a tech company with 60 full-time employees and five years in operation, was growing quickly. Its ‘MayMay’ app, focused on maternal and child health, was the most popular mHealth app in the country, with over 80,000 users. Though the app had some general content on sexual and reproductive health aimed at adolescent girls, Koe Koe Tech’s own ethnographic research showed that girls were put off by the title and positioning of MayMay (which means ‘mother’ in Myanmar). Given this, the company applied to SPRING with the aim of developing a new sexual and reproductive health app for adolescent girls. HCD research conducted through SPRING helped Koe Koe Tech decide what content and features to include in the app, particularly that which would be acceptable to parents (whose phones would likely be needed for girls to access the content). The new app, ‘Phyo Phyo May’, or ‘single women’, was launched in January 2019 and already has over 37,500 girl users. Though the app is not yet generating revenues, the business hopes to build a large enough user base to attract advertising revenues in order to finance it on an ongoing basis.

In order to qualify for Prototype Development Funding (PDF), businesses had to be able to demonstrate business viability and growth potential, in addition to commitment from business leaders and a plausible impact pathway for girls. The amount of support depended on the strength of the case put forward by the business, in line with the above criteria, and not all businesses received the same amount of funding. SPRING delivered further differentiated support to select businesses across all four cohorts through the Business Assistance Fund (BAF), in order to better help businesses launch their prototypes and successfully target adolescent girls. Businesses eligible for BAF were invited to apply for support on specific projects that could help them overcome challenges to development or success of their prototypes. A total of 65 BAF projects and travel opportunities were funded for 36 businesses, with budgets ranging from £400 to £18,200.

Lessons identified this year, and recommendations for the year ahead linked to this output

Key Challenges:
- While adding an extra bootcamp (bootcamp 0) in Cohort 4 allowed SPRING businesses to better refine their prototypes, they were also less likely to be specifically ‘girl-focused’ compared to earlier cohorts. Whilst prototypes that were less ‘girl-focused’ may have had the added benefit of being more widely accessible to other beneficiaries as well as girls, it is still worth noting in the context of this output, which focuses specifically on reaching girls.
- In a number of instances, delays in supplying prototype funding to SPRING businesses caused by administrative challenges (such as local banks not accepting international payments, holiday periods) resulted in subsequent delays to the launch of businesses’ prototypes.

Key lessons for future accelerator programmes:
- Ensure the timeline for support is adequate as nine months was a tight timeline for businesses to develop, launch and test prototypes. This will be heavily dependent on context, however existing accelerators in target countries or regions could provide a good starting point for designing an effective timescale.
- To maximise results with finite resources, apply a funding model that takes into account factors such as impact and growth potential, and evidence of commitment and viability. Ensure that criteria and process for awarding funding are clear to participants early on, so that the process is transparent.
- Promote tailored support for each business. The BAF proved to be a valuable programme feature, able to support activities that are important for the business and/or programme, and helped add value through supporting businesses to design and launch prototypes that reached girls.
- Businesses do not necessarily need to introduce new products, services or models to create impact for girls, they just need to be thoughtful about including them in their existing offer.
- Business can include girls in various ways, but it starts from listening to them to understand their needs, preferences and constraints, and considering their wider ecosystem.

Recommendation
The DFID SRO and programme manager should share the above lessons across DFID and other donors before the programme closes down.

Output Title	SPRING-supported businesses improve their investment readiness
Output number per LF		2	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Cumulative number (% in brackets) of SPRING-supported businesses who have improved their investment readiness	Target (August 2019): 27 / (22% in Cohort 1, 50% in Cohort 2, 37% in Cohort 3 and 35% in Cohort 4)	Exceeded expectations - 38 / (22% in Cohort 1, 50% in Cohort 2, 30% in Cohort 3 and 90% in Cohort 4)

Briefly describe the output and provide supporting narrative for the score

The target for this output has been exceeded by a clear margin: in Cohort 4, 18 out of 20 businesses received some level of investment readiness support, and all 18 improved their investment readiness. It is worth noting that not every SPRING business will seek external investment and only those businesses which have sought external investment are captured here. Evidence of improved investment readiness has been derived from baseline and endline assessments conducted by SPRING and verified by the independent M&E partner. SPRING developed an Investment Readiness Checklist which assessed businesses against ten standard metrics of investment readiness, with each metric awarded a score of 0 (low or not complete), 1 (medium or moderate/partway there) or 2 (high or strong). The metrics are:
1. Quality and completeness of founder experience and team
2. Demonstrated understanding of requirements/commitments in the capital raising process (including time and resources)
3. Clear valuation logic (if appropriate)/comparators (if available)
4. Company structure: is it investable, or does it need to be changed?
5. Defined share ownership and capital-raising structures
6. Established board and governance (or clear plan for establishing these)
7. Quality and completeness of financials (profit and loss, cash flow, scenarios) and other investment diligence documents
8. Pitch readiness (robust pitch deck and executive summary are in place)
9. Has a shortlist of potential investor types and rationale
10. Quality and volume of contacts with potential investors/meetings
Using these criteria, businesses were awarded a score between 0-20 that was used to track changes in their investment readiness over time.

However despite exceeding the target for this reporting period, the independent evaluation found that investment readiness support received the least positive feedback from SPRING businesses, with 11% reporting that they were ‘unsatisfied’ with support received (see figure 1, from End of Cohort 4 report), hence this output has been graded A+.

This year SPRING changed the programme’s support on investment readiness based on the learning from previous cohorts as the timeline for securing investment often stretched beyond the nine-month SPRING accelerator programme, and businesses needed highly tailored support. SPRING’s updated approach became flexible, with a stronger focus on local investment support delivered by regionally-based resources. SPRING also developed a tiered system to guide provision of SPRING’s investment support. This categorisation was separate from the business Investment Readiness score, and instead placed businesses into four categories based on their plans and timeline for raising capital. Businesses in Tier 1 were prioritised to receive the greatest level of support (see Table below). Not all businesses were seeking external investment.

Tier	Description of business stage	# of businesses	Support provided
1	Commercially sustainable ventures raising substantial capital in debt or equity, within SPRING timeframe, with high potential for scale and evidence of girl impact	8	Investment readiness activities such as preparing term sheets, pitch decks, valuations, or general help; dedicated capital raising advisory services, support to attend conferences, and introductions to investors
2	Similar profile to Tier 1, raising outside of SPRING timeframe or within timeframe but smaller capital need	21	Priority focus from investment readiness manager on activities listed above, BAF support for investment related activities, support to attend conferences, connections with investors within SPRING network
3	Raising mainly grants or smaller scope	13	Prompt, but lighter support from investment readiness manager and country manager; possible BAF support for fundraising activities (e.g. help with attending meetings with investors) on discretion
4	Not currently raising capital	19	General country manager support

The tiered ranking system, plus additional dedicated investment support provided by regional Investment Managers and additional funding made available beyond the accelerator through the Capital Raising Support (CRS), allowed SPRING to better match support with needs at the right time. CRS was specifically used to facilitate and support investment raising, through activities such as business planning, financial modelling, targeted marketing efforts and investment conference attendance. Separating this specific kind of support out meant SPRING supported more businesses in a more effective way, and ultimately led to better results. In Cohort 4, for example, 18 out of 20 businesses received some level of investment readiness support, and all 18 improved their investment readiness.

Case study: Build Up Nepal
Build Up Nepal empowers communities and local entrepreneurs, including single mothers and elderly women, to build high-quality earthquake resilient housing using local and environmentally friendly-materials. The company received support to work with a specialist contractor to refine their brick-making machine, a key element of their prototype, and further assistance was provided to help them to develop a professional pitch video to showcase to investors at the Asian Venture Philanthropy Network (AVPN) conference. These activities helped them to secure grant funding from the Volvo Development Foundation and SMW Investments to support 8 new women entrepreneurs and 15 new mason trainings.

SPRING also had a presence at most of the major global impact investing conferences. At these events support was provided to selected cohorts of investment-ready businesses to meet foundations, venture funds, and family office investors, carefully hand-picked by the SPRING Country Managers to be tailored to the businesses’ needs. For example, the CEO of Ubongo – a SPRING business that produces educational media – attended the DISCOP (film and television content producer and distributer in Africa) Abidjan Conference in Côte d’Ivoire, meeting with distributors, broadcasters and other key stakeholders in the media and television industry from across Africa. Ubongo’s CEO said:

‘The key outcome from attending this conference and TV market will be increased distribution of Ubongo Kids and Akili and Me content in Francophone Africa, leading to increased reach and impact for us as a company. Already Gulli Afrique has asked to license the rights to a third season of Ubongo Kids to dub into French, and numerous Francophone Distributors have given us distribution offers.’

Lessons identified this year, and recommendations for the year ahead linked to this output

Key challenges:
- Attracting investment is a resource-intensive activity requiring significant effort, even for small amounts. Businesses need time to capture data to demonstrate the business model, market fit, and impact case, and investment takes time to materialise. One approach some SPRING businesses found useful was to highlight the social returns on investment: investing in girls today can deliver returns on investment for future generations of women, stretching thirty or forty years into the future.
- Potential investors were not always familiar with girl impact-focussed businesses and needed to be primed and educated to invest in SPRING businesses. SPRING achieved this by developing a series of toolkits and sector briefs, highlighting market opportunities for investors, sector by sector.

Key lessons for future accelerator programmes:

SPRING has generated a number of lessons related to developing the investor readiness of businesses, in addition to a better understanding of investor landscapes.

- Programmes should allow for the provision of flexible (timing) and tailored (type) support by local individual investment managers who have a strong relationship with the businesses.
- Plan for additional time required beyond the end of the accelerator to strengthen the investment readiness of growth-stage businesses.
- To substantiate improved investment readiness, monitoring tools with clear definitions should be developed early in implementation. Businesses might need to be assessed multiple times with the endline evaluation occurring after all support has been received.
- As well as investment readiness (help firms present themselves in an attractive way to potential investor), accelerators should build investor readiness educate investors on what it means to invest in a given impact area, and provide relevant information and tools to support them.
- Small to medium-size enterprises in developing markets have diverse funding and support needs at different times, which should be matched accordingly
- Local knowledge and networks are crucial when it comes to selecting the right businesses, providing tailored business support and helping businesses to secure follow-on investment

Recommendation
The DFID SRO and programme manager should share the above lessons with donors and other accelerators before the programme closes down.

Output Title	SPRING-supported businesses benefit from human centred design and other forms of SPRING TA to improve business viability and develop products and services benefitting girls
Output number per LF		3	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Cumulative number (% in brackets) of supported businesses who report satisfaction with the HCD and other technical assistance provided through SPRING	Target (August 2019): 64 / (100% in Cohort 1, 78% in Cohort 2, 84% in Cohort 3 and 80% in Cohort 4)	Met expectations - 67 / (100% in Cohort 1, 78% in Cohort 2, 84% in Cohort 3 and 100% in Cohort 4)
3.2 Cumulative number (% in brackets) of SPRING-supported businesses who use HCD to refine their business model, product or service to meet the needs of target girls.	Target (August 2019): 64 / (89% in Cohort 1, 78% in Cohort 2, 100% in Cohort 3 and 75% in Cohort 4)	Met expectations - 68 / (89% in Cohort 1, 78% in Cohort 2, 100% in Cohort 3 and 95% in Cohort 4)

Provide supporting narrative for the score

In total, 68 businesses have met the requirements for the indicator, moderately exceeding the target of 64 and resulting in a score of A. Since revamping the accelerator design in Cohort 2, SPRING participant satisfaction improved with each Cohort, demonstrating the programme’s progress in selecting “best fit” businesses, aligning participant expectations with programme realities, and delivering effective support.

In the last year, scoring against output 3.1 (satisfaction with HCD and other technical assistance) found that 100% of participants who completed the accelerator indicated that they were ‘very satisfied’ or ‘satisfied’. Average satisfaction ratings varied by country; which was likely a reflection on the quality of country managers, who played a key role in supporting businesses.

The M&E partner found that numerous businesses reported finding human centred design useful, yet a very complex tool to use. Across all cohorts, technical support to apply HCD and develop a prototype was consistently among the highest-rated aspects of the accelerator. Human centred design was widely recognised by businesses as a value-adding methodology, and one that they would continue using within their business.

Reporting against output 3.2, (businesses use HCD to refine their business model), found that 19/20 businesses used HCD to refine products, services or business models to meet the needs of adolescent girls.

Case study: Pan Ka Lay, Myanmar
Pan Ka Lay was one of SPRING’s few idea-stage businesses at the start of the cohort. Its mission was to normalise menstruation in Myanmar and empower girls and women to manage theirs safely and confidently. The business planned to do this by selling reusable sanitary pads, accompanied by an educational campaign to combat prevalent misinformation and stigma. Through HCD research, Pan Ka Lay discovered that: 1) the price-point for its pads was far too high for target customers, and 2) even in rural areas, girls already had access to disposable sanitary pads, which they preferred to reusables.

Pan Ka Lay went on to test other menstrual management solutions with different target groups before pivoting away from the idea of selling products in mainstream markets. It decided to focus its prototype instead on an educational campaign (which research confirmed was needed and wanted) and on direct to business sales of reusable pads to relief organisations working in refugee camps. Pan Ka Lay’s educational campaign, 'So What?!', has reached over 716,000 unique viewers in Myanmar via Facebook videos, including nearly 150,000 adolescent girls.

Cohort 4 conducted research with end users and stakeholders following Bootcamp 1. The businesses used these findings to iterate prototype design at Bootcamp 2, five months later. The research process often helped to confirm hypotheses and assumptions, however in a few cases revealed critical flaws or lack of viability of early prototype concepts, resulting in major pivots (including Khalti, Jeeon, and Pan Ka Lay).Pan Ka Lay, for example, used HCD to test its idea of selling re-usable and organic sanitary pad in rural, urban and peri-urban areas, and realised that there was not a market for this. The focus then shifted to the ‘So What?!’ campaign for education on menstrual health, and the development of educational tools such as an educational comic book.

Lessons identified this year, and recommendations for the year ahead linked to this output

Key challenges:
- A number of businesses surveyed reported finding HCD a useful tool to help target their business, however felt that it was complex to use. During follow up, many were found to be using a ‘light touch’ version of HCD, and had not fully embedded the processes for considering adolescent girls.
- In the final year, SPRING developed a framework for assessing prototypes’ level of ‘girl focus’ across time. This data showed that prototypes on average had become less girl-focused, and that the prototypes of individual businesses had sometimes become less girl-focused following HCD research, as the research showed that an indirect path to girl impact would be more successful for the business.

Key lessons for future accelerator programmes:
As with previous outputs, the SPRING programme produced a number of valuable lessons on including HCD in programming. To help businesses assimilate HCD as a core business process, adopt an HCD curriculum that is practical/hands-on, and builds-in time for iteration. The curriculum may be best delivered by HCD and business strategy experts but should include local support for in-depth user research and prototyping (outside of bootcamps)
- Invest up front in selecting the right research partner and in building local capacity to ensure researchers have the requisite skills for in-depth HCD research
- Provide a mix of fixed and tailored support to ensure a common base across a cohort while also accounting for individual business needs
- Avoid force-fitting a new impact focus. Instead, start with understanding how the business’s existing impact model addresses different users’ needs, and then look for opportunities to enhance the impact potential or inclusiveness of the solution.

Recommendation
The DFID SRO and programme manager should share the above lessons across DFID and other donors before the programme closes down.

Output Title	Ecosystem stimulation for products and services benefitting adolescent girls
Output number per LF		4	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Cumulative number of communications products with evidence and/or lessons learned produced and disseminated by implementing partner	Target (August 2019): 46	Exceeded expectations - 60

Provide supporting narrative for the score

This output relates to work carried out in order to share the evidence and lessons generated through the SPRING programme with the wider development community (including donors, civil society, investors, and other accelerators). In total, SPRING produced 60 Knowledge Products (against a target of 46), including 29 in the programme’s final year. These knowledge products included reports, toolkits, blogs, videos, events, and panels, and were tailored to influence key target audiences (investors, donors, accelerators, and development practitioners) to apply SPRING’s learning to innovate for girl impact in emerging markets. All of SPRING’s knowledge products can be found on SPRING’s website (which will remain live for another year), USAID’s Development Experience Clearinghouse and will be uploaded to a dedicated page on a .gov.uk website. The output has exceeded targets for this year significantly and produced high quality products that have received good feedback, and has been awarded a score of A+ accordingly.

The last year of programme implementation focused on three separate knowledge tracks for sharing lessons learned:
- Track A focused on sharing SPRING’s unique model, primarily with donors/funders/foundations
- Track B focused on promoting the human centred design approach, focusing on businesses and funders of accelerators
- Track C focused on promoting girls as end users, and focused primarily on investors and donors

For example, SPRING made its curriculum available online for others to use at: https://www.springcurriculum.com/ (Track A); the ‘HCD brief: Scaling social businesses through design thinking’, aims to help businesses and potential funders of accelerators apply HCD in their work (Track B); and the SPRING interactive ‘Investor’s Toolkit’ shows private sector companies (multinational, national, including tech-oriented businesses) of the viability of girls/young women in their value chain or as end users (Track C). The latter was also linked to by the Gender Smart Investing Summit, demonstrating the quality and reputation of SPRING’s products.

In line with the increased focus on sharing lessons learned in this reporting period, SPRING also saw an increase in traffic to its website. Since June 2017, there were 44,044 unique visitors to the SPRING website, compared with 33,898 the previous reporting period. The most visited knowledge product was the draft Investor Toolkit, with 1,396 page visits (595 unique page visits).

Cutting across all three knowledge tracks, SPRING participated in panels, hosted satellite events, and held high-level meetings at several global and regional events and forums, including the Gender-Smart Investing Summit (London, November 2018), Skoll World Forum (Oxford, April 2019), Sankalp Africa (Nairobi, February 2019), the Asian Venture Philanthropy Network (AVPN) Conference (Singapore, June 2019), European Development Days (Brussels, June 2019) and Women Deliver (Vancouver, June 2019), SOCAP (San Francisco, October 2019).

In support of knowledge Track B, SPRING also collaborated directly with four other accelerators in Southern Africa and South Asia: MUVA in Mozambique, ACT in Zimbabwe, Maharashtra State Rural Livelihoods Mission (MSRLM) in India and VentureLab in Pakistan. Over the past year, MUVA and ACT leveraged key components of the SPRING model. Specifically the basic accelerator structure, HCD research approach and girl impact framework which have been adapted and refined to their own programme models As SPRING winds down, and ACT and MUVA prepare to graduate their first cohorts from these adapted accelerator programmes.

Lessons identified this year, and recommendations for the year ahead linked to this output

Key Challenges:
Communication and strategic alignment was not always as smooth as it could have been between SPRING staff and external accelerators with whom the programme collaborated. For example, not all of the accelerators SPRING worked with had a girl impact focus, so elements of SPRING’s lessons were not directly transferrable to them.

Recommendations for the year ahead:
- The SPRING M&E team should explore which aspects of the SPRING accelerator model were and were not easily transferable to other accelerators and why as part of the review of accelerator programmes. The findings should be documented in the Summative Report , which the SRO and PM can then disseminate within DFID and to other donors and funders of business accelerators.
- The DFID SRO and PM should draw up a dissemination plan for sharing lessons that emerge from the M&E phase of the programme, no later than 6 months after the annual review (June 2020). These lessons should be shared with other DFID teams leading programmes that engage with SMEs, or those with a specific sector focus covered by SPRING businesses.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The SPRING theory of change is presented below, there were no major changes from last year. The SPRING theory of change shows three concentric domains with multiple concurrent and complementary pathways through which the programme intends to precipitate positive changes leading to economic empowerment of adolescent girls.

Each year, the theory of change was refined through annual workshops with the implementing partner, M&E partner and donors, to integrate programme learning related to theory of change assumptions and causal links, and to reflect changes in programme design and implementation.

Over the past year, this reflection process has resulted in the following minor changes to the programme theory of change, represented in red on the next page:
1. At the enterprise outcome level, adding “Businesses continue to use HCD to refine solutions” as a separate pathway, because we have found that some businesses may not remain strictly committed to girl-focused solutions but nevertheless continue to apply HCD to their business, and as a by-product, may continue to reach girls.
2. At the enterprise impact/outcome level, adding a new arrow from “Girl Impact Evidence Base” (Impact level) up to “Businesses attract external investment,” as there is some evidence that when businesses are able to demonstrate social impact to investors, they are more likely to secure investment.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Now concluding its five-year tenure, SPRING has exceeded all expected outcomes in terms of girl reach and business performance, reaching over 2.5 million girls against a target of 200,000 and supporting businesses to raise £13.8m in investment, demonstrating the extent to which they have helped many to improve their investor readiness. As the implementation of SPRING has ended as of September 2019, its final outcome targets were set for this year, and will be fully discussed in the Programme Completion Report once the M&E phase has concluded.

	Target	Achieved
Outcome indicator 1: Cumulative number of SPRING-supported businesses securing external investment, aided by participation in SPRING	20	31
Outcome indicator 2: Cumulative number of adolescent girls reached with SPRING-supported businesses’ products, services or employment opportunities	200,000	2,534,214
Outcome indicator 3: Cumulative number of SPRING-supported businesses who have increased sales from products, services, or business models benefitting girls by 20% or more.	50	55

The programme has also (as described above, Outputs 1-4) demonstrated a strong, consistent application of its learning mandate both in programme adaptation and ecosystem stimulation. Nevertheless, it is important to highlight here two caveats of these successes:

- The exceptional girl reach has been largely influenced by a handful of businesses that use mass media to distribute their content (e.g., Ubongo with television and Pan Ka Lay with Facebook)
- This reach results from a broad spectrum of products and services with varying depths of impact or influence on girls’ lives. For some businesses, they might offer life-changing opportunities to only a few hundred girls; others might reach thousands but with potentially reduced impact.

This year, the M&E partner became the main supplier for SPRING as the implementation contract ended. M&E will continue for the next 2 years and we expect their forthcoming evaluations to judge the true impact of these wide-reaching interventions. This will give an evidence-based assessment of to what extent SPRING achieved its impact statement: “enterprises, investors and markets contribute to economic empowerment of adolescent girls”.

SPRING adapted from its original model and now measures the impact of various private sector products and services on economically empowering women and girls. Using a private sector development approach to deliver impact for adolescent girls is a novel approach. Rigorous monitoring and evaluation and adapting in response to evidence and learning as they have emerged, have been crucial to the success of this initiative. Emerging findings from the M&E component are beginning to show that SPRING’s central thesis was right, and that the girls reached by SPRING businesses had felt a lasting impact. For example, the Ubongo endline report found that:
By engaging with Ubongo Impact behaviour change content girls were exposed to information, tools, role models and encouragement which motivated them to practice what they learnt and seek out peers to support them. In doing so, girls have the potential to improve their life skills.

Similarly, the Paritran (Fightback) report found that: “There is clear evidence that girls who participate in Fightback Girls training feel safer as a result of it”. The evidence thus shows that SPRING’s innovative Theory of Change is likely to be proved right.

Explain major changes to the logframe in the past year

SPRING has exceeded all expected outcomes in terms of girl reach and business performance. Reporting against outputs 1 to 4 is now complete and they will no longer be tracked, as implementation of SPRING has ended, and the programme has now transitioned to the M&E phase. As part of this transition, two new output indicators were added to the logframe to reflect that DFID programme management would shift to ensuring accurate and thoughtful reporting from the M&E partner. The M&E partner will produce impact reports measuring the longer-term impact of SPRING supported businesses and their products on adolescent girls. The indicators added were:

- Output indicator 5.1: % of agreed milestones delivered on an annual basis as per the agreed timetable/work plan, reflecting agreed changes
- Output indicator 5.2: % of milestones delivered that are of a good quality, comments are addressed and reports are approved

A baseline of 80% of reports being delivered on time and to a good quality was set for each of the output indicators, and reporting on these is due to start in 2020. The DFID SRO and Coffey agreed that this was a reasonable target given that the timeliness of reports was dependent on the cooperation of the businesses and their availability for data collection and reporting. In the period covered by this annual review, one business that was lined up to be studied in an impact evaluation revealed at the last minute to the M&E partner that the they were no longer in operation. The M&E quickly had to select the next best available candidate, and amend their timescale to accommodate a new baseline. As future reports are also susceptible to external factors, a target of 100% was deemed unreasonable.

The quality of deliverables produced under output 5 will be independently verified by a USAID M&E expert. ‘Quality’ will be defined as deliverables being well-written, evidence-based, well-presented and of use to other actors in the field.

Describe any planned changes to the logframe as a result of this review (1/2 page)
There are no further changes planned to the logframe.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

SPRING’s main cost drivers are its programme activities, which account for 65.68% (£10.27m) of the spend to date. These figures relate to spend for the SPRING programme, and therefore include spending of funds from other donors. As businesses from earlier cohorts continued to develop, provision of more advanced support, such as capital raising support, was required more often increasing this cost. Programme costs were kept to a minimum through negotiating savings and free in-kind support. SPRING were incentivised to keep costs low through inclusion of a target figure in their logframe under output 4 (which they met).

The second largest cost driver was long- and short-term personnel fees, which has made up 34% (£5.37m) o the total spend to date, Costs for personnel were kept down by agreeing rates within DFID’s limits at the start of the programme, benchmarked with other similar programme fees. Changes in personnel were approved by the SRO, and based on a like for like exchange.

Economy (minimising input cost)
1. Contributions raised by SPRING through in-kind contributions (in GBP)	£1,118,974, this includes in-kind/pro bono support, negotiated savings and low-bono (i.e. below market rate) contributions and monetary contributions. This final figure includes savings from Economy Indicator 2 and Efficiency Indicator 3. / This is addressed under output indicator 4.2.
2.Cumulative cost savings (in GBP)	£119,566 increasing by £15,051.96 from August 2018 to August 2019 due to savings from Boot Camp 2, Cohort 4.
Efficiency (conversion of inputs to outputs)
1. Percentage (%) of milestone deliverables met on time	To date, the programme has delivered 100% of its milestones on time.
2. Management costs as % of total costs	6.63%, this continues a downward trend from last year (6.89%), 2017 (7.18%) and 2016 (9%). / SPRING has achieved this through active negotiation on rates (e.g. through a reduction in rental costs and negotiating market rates for all reimbursable procurements and economies of scale).
3. Cost (in GBP) for regional expenses for programme activity: Boot Camp (cost savings)	£13,208.14 is the cumulative total of all negotiated cost savings for the Boot Camps across all four cohorts.
Effectiveness (how well outputs produce outcomes)
1. Cost (in GBP) per business compared with value of services delivered per business	The HCD and bootcamp expertise costs were £21,842.74 per business supported to produce prototype, versus a counterfactual figure of £131,544 per business if the HCD expertise was sourced independently, based on market rate cost estimates. Therefore there is a saving of £109, 701, which is intended to demonstrate SPRING has used economies of scale to more effectively train businesses to be gender-sensitive. / This is a slightly higher cost per business than last year (£17,456) primarily due to higher cost for Boot Camps located in a different region.
2. Cost (in GBP) per girl reached	£6.82 including Ubongo / £45.81 excluding Ubongo / Last year’s annual review recommended that comparisons should be made between SPRING and similar programmes to give these figures context. However, the M&E partner reported that, given the specific and focussed nature of SPRING to target businesses to reach girls they struggled to find comparable data. While it is possible to provide a simple VfM figure of cost of reaching a single girl (and disaggregated by country), the M&E partner suggests that this data is not comparable to other accelerators or to other girl programmes.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

SPRING has achieved a continuous reduction in the cost per girl reached. This figure stood at £23.99 in 2018, £318 in 2017 and £542 in 2016. As such, the programme clearly demonstrates increasing value for money. The independent M&E reports show that SPRING has produced products and services that benefit girls in lasting ways, justifying this cost. For example, the endline evaluation report of Ubongo, the SPRING business with the biggest reach found that:
“the Ubongo Impact financial literacy episodes have shown that they have the potential to contribute to the well-being of girls by providing them with financial literacy-focused skills including budgeting, setting goals for saving, getting earning experience and providing encouragement and support to others to do the same.”

SPRING has also developed lasting contributions to the economic development sector, which have been made available as global public goods. This includes the HCD curriculum which can be used by other development actors to convince businesses of the benefits of targeting girls, and several other knowledge products that were discussed in section B.

Moreover, the implementing partner has demonstrated numerous examples of where they have been able to minimise overheads through innovative ways of leveraging pro bono support and negotiated savings, and have worked with businesses to ensure they are sustainable after SPRING’s involvement ends, and thus ensures the cost per beneficiary is low.

As the programme moves into the monitoring and evaluation phase, lessons drawn from the programme will be shared throughout DFID, other donors and other government departments where possible. This will add value to both this programme and future programmes in the sector. The programme must continue to complete the M&E phase to give a true reflection of the benefits and their impact for girls reached with products generated by SPRING.

A new way of measuring VFM will be established by DFID SRO with the SPRING M&E team to allow continued monitoring of VFM as the programme moves into its M&E phase, before March 2020, as per priority recommendation 4. Give the M&E contract is a payment by results model and has fixed costs and outputs, the process will be light-touch.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

SPRING has been a high-risk programme from its inception. The main risk over the reporting period has been that the handover from the implementing partner to the M&E partner would not be successful, damaging the effectiveness of the next phase of the programme (the M&E phase). This risk was mitigated against successfully and has not come to pass. The two implementing partners met regularly and dedicated several full day sessions to ensure effective handover of all SPRING data and technological assets and accounts. This risk, like many from the previous risk register, have now been closed as implementation is now finalised. The risk register was revised in the reporting period to reflect this.

Key risks remain security concerns in some countries of operation as businesses are still operating in fragile or conflict affected states and this could impact on the success of their products or their ability to report effectively to the M&E team. The M&E partner is cognizant of risks and undertakes regular security reviews of countries visited by its staff.

Another key risk that remains is the risk that the adolescent girls reached through the programme are not safeguarded well enough. DFID has discussed safeguarding with the M&E partner and is aware of Coffey’s strict code of conduct for its staff. Furthermore, locations for meeting girls for interviews are carefully considered and done at schools and/or with the permission of parents.

The full revised risk register for the next year can be found in Annex 1.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

SPRING’s implementing partner, Palladium, provided quality and timely narrative reporting and financial statements. They accurately tracked a complex arrangement of grant financing to several different businesses, and monitored spend to ensure it remained within budget line limits. All suppliers were aware of and followed DFID counter-fraud guidance.

Risks were discussed regularly and a programme risk register updated at each monthly meeting. Palladium completes annual risk assessments for each project, which cover financial and operational risks and processes. The last SPRING assessment took place in August 2019 and the findings did not highlight any serious risks.

Palladium provided regular progress reports on a quarterly basis (December, March, June, September) – the March and September reports have more substantial financial reporting. These were mostly submitted in good time in order for review. Palladium was able to flex its reporting to meet DFID’s requests, including providing extra detail for internal programme reviews at quarterly points, and adjusting its final report so that it provided enough information for a programme completion report in future years.

In line with DFID’s safeguarding standards, both Palladium and Coffey had Safeguarding policies and are aware of DFID reporting concerns email address. Safeguarding risks and mitigation strategies were discussed regularly with both partners over the reporting period.

Financial management and reporting

As of 10 December 2019, DFID had spent £14,205,657 of the total programme budget. In financial year 18/19 £3,122,567 was spent. From the start of this financial year to end November 2019, £721,106 has been spent, with a total of £839,076 forecast for 19/20 (£176,363 remaining). Palladium submitted a month to month forecast as the programme was demand led. They have achieved average variance of -1.35% over the year, which is well within DFID’s 5% tolerance for forecasting. The evaluation partner is on a payment by results contract, so forecasting is accurate based on when deliverables are due and costs are always fixed. Palladium had an established pattern of submitting invoices in good time in the middle of the month, and forecasts by the 23rd of each month to allow for accurate accruals. Coffey also submits accurate monthly forecast updates.

The final project audit took place in September 2019 and was submitted to DFID on 25 October 2019. It covered 1 December 2018 – 31 July 2019, which covered the bulk of the Palladium contract. The risks of not having an audit that covered the last two months of the project were considered minimal by DFID, as all grant funding to partner organisations would have been disbursed by these dates. The final audit found that Palladium’s financial reporting “fairly reflects, in all material aspects, the eligible expenditure of the project […] in accordance with generally accepted accounting principles and DFID’s requirements for finance reporting”. Risks of financial diversion in July and August were offset by increased spot-checks on the final two invoices. Palladium were able to provide detailed and organised receipts or timesheets for all requests.

SPRING implementing partner maintained a full asset register in London and all items were appropriately tagged and stored in secure locations.

Contract management

Palladium and Coffey are both key suppliers for DFID, and a strategic relationship management (SRM) scorecard was completed for both in this reporting period. Both partners adhere to the Supply Partner Code and are very responsive to DFID’s compliance requirements.

Palladium’s strategic relationship management (SRM) scorecard for the SPRING programme was completed in January 2019 and scored 74.50, putting at the top of the ‘good performance’ category, a reduction of 2 points from the July 2018 scorecard. Palladium sought feedback and have worked to improve in these areas: Communications with DFID programme team and Responsiveness to Feedback.

Coffey’s SRM for SPRING was completed in February 2019 and scored 72.00, placing it in the ‘good performance category. This is an improvement of 4.5 points on the 2018 scorecard. The lowest scoring area was adherence to schedule, where they scored a 4.0 (satisfactory) to reflect that, due to their reliance on the businesses to be available, there were often changes to the original workplan agreed with DFID. This reflects the highly adaptive nature of the programme, and both DFID and Coffey recognise this is a particular challenge of SPRING. Coffey scored 6.0 (exceeding performance) for their communication, demonstrating that they are very good at keeping DFID informed when changes to the schedule are needed.
Date of last narrative financial report(s)	September 2019 (final annual report)
Date of last audited annual statement (s)	16 October 2019

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

SPRING is an innovative accelerator programme, which aims to demonstrate the viability of adolescent girls as a target market for products and services. In order to demonstrate this viability, monitoring, evaluation and learning is a significant aspect of the programme.

During the last annual review phase, SPRING moved from the implementation phase to the M&E phase.

Monitoring (1/2 page)

SPRING have an internal team with further M&E provided by an independent M&E partner. Alongside SPRING’s continuous data collection, the independent M&E performs data spot checks to highlight performance, data gaps and recommendations. The reports delivered by the independent M&E partner have been delivered on time and to a high quality.

The SPRING Team (implementing partner) has been responsible for programme monitoring and contributes to the overall evaluation by collecting data from businesses, documenting process information, and advising on the selection of businesses for different evaluation components.

The programme’s M&E partner, produces independent reports focused on:
- Programme Performance Evaluations (PPE)
- Business Performance Evaluations (BPE)
- Girl Impact (IE)
- Reviews of data systems and Key Performance Indicators

As part of the transition to the evaluation-only phase of the programme, the SPRING implementing team has held a series of handover workshops with the independent M&E team to share data/information, answer questions, and discuss learning opportunities that could be pursued in the final years of the evaluation.

Evidence

In the past year, SPRING has produced reports linked to the evaluations mentioned above, which generally demonstrate that SPRING’s ToC will be proven correct. To date the M&E partner produced case studies on six Cohort 3 businesses and six Cohort 4 businesses, as well as endline reports for impact evaluations of:
- Totohealth (Cohort 1, Kenya: offers a free pregnancy and early childhood text-message service that helps reduce maternal and child mortality in Kenya by sending appointment reminders, surveys and announcements to parents to ensure they get the medical intervention they need, when they need it.)
- Shekina (Cohort 1, Rwanda: an agro-processing company that specialises in dry goods and is a pioneer firm in the dried cassava leaves market. Shekina has increased demand and price for the plant and its collection centres shorten travel for farmers and employ young women for sorting.))
- Fightback (Cohort 2, Nepal: offers mental, vocal and physical self-defence training to girls and young women to reduce and mitigate the risk of sexual violence. It also aims to change social norms by educating parents, teachers, boys and men on how to overcome gender stereotypes and how they can help protect girls.)
- Ubongo (Cohort 3, Tanzania: leverages the power of entertainment (television and radio) to deliver effective, localised and engaging multimedia content to families, caregivers and educators across Africa at low cost and massive scale )

The endline reports document the businesses’ involvement with the SPRING accelerator, in addition to recording challenges faced by each business, and analysing the overall impact of both the business itself and of SPRING on the business. For example, the Shekina end-line report revealed a sizeable deviation from the expected outcomes and generated a set of lessons from the Shekina experience, which can in turn be used by other businesses working with adolescent girls in agro-processing value chains.

The evaluations of Cohort 1 businesses Totohealth and Shekina showed some evidence of positive impact for girls’ well-being, but in both cases, outcomes were tempered by the fact that prototypes were not implemented as originally planned (which meant changes were required to the study design, and impact potential was diluted).

The Fightback evaluation showed particularly promising results, with improvement in girls’ knowledge, skills, confidence and overall well-being as a result of the training. Fightback was able to leverage the results to secure a grant from Grand Challenges Canada to scale their programme.

Selecting businesses for impact evaluations has proven challenging due to several factors:
1) the need to coordinate baseline data collection with timing of prototype rollout (to avoid contamination) 2) small sample sizes for some businesses (those reaching hundreds, rather than thousands of girls)
3) with some business models, there are challenges with tracking girls longitudinally (e.g. Maya Apa’s value proposition includes user anonymity) or establishing an appropriate comparison group
4) the difficulty predicting which prototypes will be commercially viable/sustainable

Learning

SPRING is a model of how an adaptive programme can improve its design over time, achieve results, and build knowledge in its field. With each cohort, SPRING collected feedback from businesses, consortium partners, M&E partners and donors. Together with ongoing analysis of programme results, this feedback gave an insight into how the programme could best meet the needs of businesses and achieve SPRING’s goals. The resulting adaptations made throughout the life of the programme indicate that SPRING has been able to capture lessons learned internally.

Over the past year, SPRING invested heavily in distilling and sharing lessons learned. Based on the prioritised knowledge tracks and audiences outlined with donors and key stakeholders, SPRING developed a number of reports and guides, presented at various conferences and events, and collaborated with other accelerator programmes to apply lessons from the programme.

In the final year of implementation, SPRING made use of existing professional relationships in order to disseminate lessons learned, receiving invitations to speak or hold workshops at a number of international events, including:

- Women Deliver
- European Development Days
- Asia Venture Philanthropy Network

In choosing to attend externally-organised events, as opposed to organising its own end of programme event, SPRING was able to reach a wider audience and achieve greater value for money. This allowed the programme to save on the cost of organising multiple, high-level events, yet still reach international audiences of donors, accelerator funders and businesses.

SPRING held a workshop for DFID staff and some external partners in June 2019 which received excellent feedback and focused on 1) lessons learned about SPRING as an early-stage investment vehicle 2) the programme’s approach to scaling inclusive businesses for girl impact 3) and understanding and strengthening innovation ecosystems. Furthermore, a closeout webinar was held in September 2019, which shared lessons from the SPRING experience on how businesses can be supported to drive impact for girls at scale in diverse and challenging markets.

As per priority recommendation 5, learning from SPRING will be shared as widely as possible over the remaining life of the programme.

Progress on recommendations from previous reviews

Overall progress on the 2018 annual review recommendations has been good, with most completed and justifications provided where the action was investigated but not carried forward.

2018 Recommendation	Response
SPRING’s Implementing Partner should develop a strategy to create an alumni network from each of the Cohort businesses within the next 6 months. Where there is a crossover between markets, users or products, SPRING’s Implementing Partner should consider forming collaborations within the Cohorts to strengthen the prototype sustainability and better share lessons learnt.	Completed. In each cohort, SPRING businesses set up WhatsApp groups to keep in touch with each other and the SPRING team. In addition, SPRING created a Facebook alumni group for businesses across cohorts to communicate, and recruited volunteer group administrators from each cohort to ensure that ownership of the group resides with the businesses. SPRING has also made explicit cross-cohort connections where relevant, for example, connecting health-focused businesses Maya Apa (Cohort 4, Bangladesh) and Babyl (Cohort 3, Rwanda) to discuss impact measurement, and connecting Build Up Nepal (Cohort 2, Nepal) and Earthenable (Cohort 1, Rwanda) to share learning.
As part of lesson learnt capturing, SPRING is hands-on resource intensive accelerator which in-part is also its strength. SPRING’s Implementing Partner should establish which SPRING activities are transformative to the girl impact and therefore mandatory and which are desirable.	Completed. Throughout the implementation phase, SPRING has used programme learning to refine its accelerator design and better support businesses to develop products or services with sustainable girl impact. As SPRING provided a mix of general and tailored support to each business, it would be difficult to discern which programme activities were universally most transformative for girl impact. That said, it is clear that introducing businesses to girls’ realities and contexts through a Bootcamp module, defining a girl impact theory of change and monitoring plan and undertaking HCD research with girls and key stakeholders were essential to helping businesses understand and respond to girls’ needs. In collaboration with other accelerators, SPRING have emphasised these three programme elements as being critical to the SPRING model.
SPRING’s M&E Partner should consider comparing SPRING to similar indicators from other accelerators to perform this assessment over the remaining programme lifetime.	Competed. The M&E Partner has added this as a small component of the summative PPE report and will address the issue as part of understanding the SPRING evolution, holistically. This was not identified as a key evaluation framework question, so limited data has been collected to enable this comparison. / Furthermore, the implementing partner attempted to compare SPRING’s performance with that of other accelerators using the Global Accelerator Learning Initiative (GALI) benchmarking tool. SPRING’s unique characteristics made it challenging to use the tool and draw meaningful comparisons, however. For example, most accelerators track overall revenue, while SPRING tracked prototype revenue for some businesses and overall revenue for others, depending on the prototype focus. In addition, the GALI benchmarking tool currently includes only one year of follow-up data.
As well as reviewing SPRING’s impact on the businesses and end users, SPRING’s M&E partner should review its wider impact on the ecosystems and markets which the businesses operate in. This should be included in the M&E strategy to be finalised this coming reporting year.	Considered, but not taken forward. The M&E Partner is not reviewing this. It is not part of the agreed M&E strategy and goes beyond the scope of our project. The M&E Partner will, however, look at external influences on the programme as part of the ongoing programme learning and adaptive approach.
Knowledge capture and dissemination will become increasingly pertinent to SPRING in the forthcoming period. SPRING’s Implementing Partner should develop a clear justification for the type of knowledge products produced, intended audience and expected impact with regards to resource availability and cost effectiveness within the coming reporting year.	Completed. The implementing partner has provided a clear justification to the donors in advance of developing each major Knowledge Product via a corresponding brief which describes the product’s content, resources required, timeline, intended audience, and expected impact. In the programme’s final year, the implementing partner also created an internal tool that outlines the audience, timeframe, level of effort, budget, an assessment of potential contribution to SPRING’s outcomes, and its value for money. This tool was used to inform decisions about whether to develop additional knowledge products.
SPRING’s Implementing Partner in collaboration with the M&E partner should seek to strengthen the businesses’ ability to collect and verify disaggregated data on the impact to adolescent girls- both in terms of direct and indirect impact.	Completed. Businesses’ interest and ability to collect impact data -- including age and gender disaggregated data on users -- varied widely. SPRING strengthened businesses’ ability to collect girl impact data through the M&E module, including working 1:1 with businesses on their individual Theories of Change, establishing customised KPIs based on each business’ impact model and collection ability, responding to ad-hoc support requests where possible, and making additional support available to qualified businesses through the Business Assistance Fund (BAF). For example, Resonate (Cohort 3) received BAF support to digitise and streamline their data collection processes, which will enable the business to disaggregate data more easily going forward. Still, for some businesses there was no commercial incentive to collect and verify data on direct and/or indirect impact to girls on a routine basis. / It is beyond the mandate of the M&E partner to work with the businesses in the sense of directly building their capacity, and might be interpreted as a compromise of the independence of the M&E partner. In performing verification spot checks, the M&E partner has occasionally made suggestions through the implementing partner to businesses, to improve or refine the methods businesses used to collect and report on data. / The M&E partner collects impact data with the cooperation of businesses. They collect some indirect impact, only with reference to businesses. There might be some impact data within families (mothers, aunts, brothers, fathers, etc), but this will be dependent on the selected businesses. They are fulfilling this obligation as far as they can within the limits of their relatively flexible evaluation framework.

Annex 1 – Risk Register

Risk Description	Risk Category	Gross Risk	Mitigation Strategy	Residual Risk
Security risks in countries of operation prevent programme from delivering objectives	Context	Major	Regular security reviews and training for staff and country managers for SPRING. DFID to regularly update team on changes to duty of care risk assessments. DFID has liaised with country office team and undertook enhanced due diligence for Burma.	Moderate
Poor safeguarding of girls - Activities to directly engage adolescent girls in the programme are not implemented in a safe and appropriate way	Safeguarding	Severe	Coffey International is bound by a strict code of conduct in addition to a set of minimum standards.	Moderate
Poor succession management and handovers with DFID staff turnover	Operational	Severe	DFID SRO will ensure the delivery plan is kept up to date and sufficiently detailed and the new programme manager is up to speed on the programme and all processes. JIG team leader and GRD corporate team to ensure timely recruitment process in the case of staff turnover.	Moderate
Criticism directed at the programme due to negative sentiment in UK on aid.	Reputational	Major	Quarterly review of all programme communications plans, agreed approvals matrix developed for all programme communication. Alignment with all donors on programme key messages.	Moderate
Lack of alignment between SPRING donors	Delivery	Major	This is a risk to manage particularly with the addition of a further donor to SPRING, so three donor organisations to coordinate across. The donors will aim to have a biannual call to align on programme objectives and theories of change and have a programme update call at minimum once a quarter with the SPRING team leader. Clear responsibility on major programme activities such as selection and knowledge products will also help to mitigate this risk.	Moderate
Lack of mentors for businesses – quality and quantity	Delivery	Moderate	SPRING is revisiting their mentoring strategy based on feedback from entrepreneurs and mentors on time commitments. They are looking into other approaches such as sector-specific coaches and mentoring being part of the pro-bono support delivered through corporate partnerships and through additional activities (Business Advisory Fund and Capital Raising Support).	Minor
Timeliness of delivery – delays in implementation	Delivery	Moderate	The programme is currently delivering to agreed timeframes as set out in programme ToRs. Timelines to be shared with all programme staff well in advance to facilitate planning. Any changes to the agreed schedule will be communicated to DFID by Coffey.	Minor
DFID lacks admin and FLD resources to manage SPRING effectively	Operational	Severe	SPRING is now entering its fourth year of delivery and the time commitment required for detailed programme management is substantially reduced compared to earlier years. The DFID team has completed recruitment of an additional Programme Manager and a Talent Entry Talent Programme candidate. The SRO will call on the WEE Policy Lead and Team Leader until the ETP candidate joins in January 2020.	Minor
Fraud or corruption within the Programme team	Fiduciary	Minor	Coffey International maintains a ‘zero-tolerance’ approach to corruption which will be contained in all staff contracts. Coffey International has robust procedures to tackle corruption, including clear procedures for whistle-blowing that safeguard staff who report malpractice. The programme will be subjected to internal and external audits.	Minor
Programme attracts criticism for poor value for money	Reputational	Moderate	Programme team and independent M&E team have developed a comprehensive framework for monitoring value for money. Agreed VFM indicators are reported in each SPRING annual review.	Minor
Programme is moving from delivery to monitoring phase.	Operational	Moderate	This phase will need to be carefully managed between DFID and programme staff. Regular team meetings are required, as well as pro-active anticipation of any issues that may arise.	Minor
Programme attracts criticism for grant financing to private sector.	Reputational	Minor	We have selected businesses using robust criteria to ensure work is additional and beneficial. We also have developed defensive lines if these activities receive criticism.	Minor

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided