Annual Review - Summary Sheet

Title: Humanitarian Assistance and Resilience in South Sudan Programme (HARISS) 2014-2020
Programme Value: during 2018, £119 million. Overall programme up to £565 million (cost extension in 2018)		Review Date: May 2018
Programme Code: 204019	Start Date: 13/03/2015	End Date: 31 May 2020 (no-cost extension in 2018).

Summary of Programme Performance
Year review conducted	2016	2017	2018	2019
Year assessing	2015	2016	2017	2018
Programme Score	A+	A	A	A+
Risk Rating	Major	Major	Major	Major

In the first half of 2018, the humanitarian situation in South Sudan continued to deteriorate and HARISS had to continue to flex in order to meet the needs of those affected by conflict, malnutrition and disease outbreaks. This review finds that it has done this extremely effectively, delivering humanitarian services at scale in some of the hardest-to-reach areas, in addition to laying the foundations for peace through its investments to strengthen resilience.

Delivering results in one of the world’s largest and most dangerous humanitarian crises is challenging and requires strong analysis and sound systems. While risk management, conflict sensitivity and value for money have continued to be prioritised, in 2018, HARISS has strengthened its contribution to assisting the humanitarian community to understand the depth and breadth of vulnerability as well as strengthening the accountability of the humanitarian system to those in need of assistance.

A. Summary and Overview

Context
In 2018, conflict in South Sudan continued, causing the destruction of homes, disrupting livelihoods and claiming lives. By the end of the year, nearly 1.9 million people were internally displaced and a further 2.3 million people had sought refuge in neighbouring countries.[1] While the signing of the Revitalised Agreement on the Resolution of the Conflict in South Sudan in September led to an overall reduction in hostilities, there was on-going disruption and violence continued in some areas of the country .[2]
[1] OCHA (2019) 2018 South Sudan Humanitarian Response in Review, March 2019.
[2] See Annex 1: Map 1 for an illustration of IDP and refugee populations in South Sudan and neighbouring countries.

Food security continued to decline with the Integrated Food Security Phase Classification (IPC) Analysis indicating that 6.1 million people were severely food insecure between July and August 2019[3] which included 1.7 million people on the edge of famine.[4] By the end of the year, it was estimated that cereal production had reduced by 25% from 2014-2017 leaving a deficit of almost 500,000 MT for 2018.[5] The continuing provision of food assistance played an essential role in offering a lifeline with significant efforts made to open more viable delivery routes including roads and rivers.
[3] It is noteworthy that this was higher than the same period in 2017 when 6 million people were in need.
[4] Ibid.
[5] FAO, 2018 in OCHA (2018) 2019 South Sudan Humanitarian Needs Overview, November 2018.

The economic crisis in the country continued to exacerbate the precarious situation of livelihoods in South Sudan; declining economic opportunities and continued high inflation have stretched meagre resources over time, negatively affecting communities affected by displacement or those without access to secure livelihoods. Disrupted trade flows, heavy reliance on oil, and skewed expenditure which has failed to prioritise poverty reduction, continue to expose many households to food insecurity and displacement.[6][7]
[6] World Bank, 2017.
[7] See Annex 1: Map 2 for an illustration of the severity of the needs across South Sudan in 2018.

Abuses of International Humanitarian law persisted, with widespread sexual violence and targeted killings, and destruction of livelihoods and property. Gender-based violence (GBV) has continued, with 2,300 cases documented by mid-2018.[8] The real extent of abuses is not known as a result of under-reporting caused by stigma, shame and low confidence in the rule of law, limited service availability and lack of access to formal systems of justice.[9] Attacks against humanitarian staff have also continued, with 15 aid workers killed in 2018 (increasing the total since 2013 to 112 deaths).[10]
[8] OCHA (2018) 2019 South Sudan Humanitarian Needs Overview, November 2018.
[9] The Gender-based violence sub-cluster Information Management System reported that 87% of reported survivors decline referrals to legal services (reported in 2019 South Sudan HNO).
[10] OCHA (2019) 2018 South Sudan Humanitarian Response in Review, March 2019.

At the close of 2018, it was estimated that 1.5 million people lived in areas facing high levels of access constraints,[11] and access incidents continued to affect the delivery of assistance.[12] Over 575 aid staff were relocated due to insecurity resulting in suspensions of aid delivery.[13] Operations in many parts of the country were also affected by interference by all parties as well as bureaucratic impediments. There were, however, some improvements in the operating environment as the year progressed, particularly after the Revitalised Agreement in September 2018.
[11] OCHA (2018) 2019 South Sudan Humanitarian Needs Overview, November 2018.
[12] See Annex 1, map 3 for an illustration of access in South Sudan in 2018.
[13] OCHA (2019) 2018 South Sudan Humanitarian Response in Review, March 2019.

South Sudan has continued to be affected by disease outbreaks which have required a scale-up in humanitarian response; 9 measles outbreak were declared and responded to in 2018 and preparedness activities were initiated in response to the Ebola Virus Disease (EVD) outbreak in Democratic Republic of the Congo as South Sudan is classified as very high risk of EVD disease transmition

Overall, the 2018 UN Humanitarian Response Plan (HRP) was well funded compared to other appeals with US$1.18 billion (68.8%)[14] received. Clusters with the most significant funding gaps included camp coordination and camp management, non-food items and emergency shelter and health.[15] The UK contribution to the HRP was approximately 14.3% of total funding, making the UK the second largest humanitarian donor.[16]
[14] https://fts.unocha.org/appeals/646/summary.
[15] Each of these sectors received were less than 30% funded against their HRP budget. See https://fts.unocha.org/appeals/646/summary.
[16] https://fts.unocha.org/appeals/646/donors?order=coverage_appeal&sort=desc.

Description of programme
HARISS is a large-scale, multi-year humanitarian programme (£565m 2014/15 – 2019/20) providing humanitarian assistance and resilience building activities across four components with 13 partners[17]:
[17] HARISS is delivered through 4 UN partner (UNICEF, WFP (including UNHAS and Logistics Cluster), FAO, IOM), 4 NGO partners (GOAL-led consortium, Oxfam-led consortium, IMC, Medair, HI and REACH), the ICRC, a pooled fund partner (SSHF) and a commercially-contracted monitoring and learning provider (ELFSS, run by IMC Worldwide). In additional, HARISS supports a number of technical secondment to the UN lead clusters (Standby Partners).
- Life-saving humanitarian assistance to reduce the vulnerability of people through: (i) the provision of food assistance and emergency livelihoods, nutrition, water, sanitation and hygiene (WASH), health, shelter and emergency non-food items (NFIs), camp management; (ii) making the humanitarian coordination system more effective and accountable.
- Resilience-building to help vulnerable populations prepare for, cope better with and recover from conflict and natural hazards that cause humanitarian disasters and stresses. The resilience approach focuses on food security and livelihoods, protection and reducing violence against women and girls, emergency preparedness and response and building the capacity of national NGOs.
- Monitoring, evaluation, accountability and learning (MEAL) to enable learning and adaptation.
- Internal Risk Facility (IRF) which offers the programme flexibility to respond rapidly to shocks and unforeseen needs across the country.[18]
  [18] For the purposes of this review, assistance to these components has been broken down further into sub-sectors to enable a proper analysis of support to each area, with grants made under the IRF included in the areas of the activities they funded.

During the 2018/19 financial year, HARISS spend was £119 million,[19] and included £758,149 under the IRF to UNICEF for Ebola preparedness activities (£606,367) and the Logistics Cluster to fund Ebola ambulances (£151,782). A cost extension for the programme was approved in May for an additional £122million across 18/19 and 19/20. This was largely programmed through existing partners, but two new partnerships where signed with HI (August) and REACH (November).
[19] In recognition of the dire humanitarian situation, a cost extension of up to £122 million was approved for the for the remaining two years of the programme to support the expansion of existing partnerships and a scaling up support on protection particularly in relation to disability and GBV.

HARISS was designed to shift from providing short-term assistance to meet immediate needs, to a more flexible, longer-term approach aimed at increasing the resilience of conflict affected people. These principles are now the cornerstone of the UK Humanitarian Reform (2017) agenda. As HARISS has evolved, it has aimed to integrate both the World Humanitarian Summit (WHS) Grand Bargain (GB) (2017) commitments as well as the UK Humanitarian Reform (2017) priorities in a number of ways:
- Piloting UN reform through in-country results compacts – up to 15% of HARISS funding to UN agencies is dependent on good performance against UK reform priorities.
- Piloting cash-based approaches where feasible.
- Strengthening accountability to Affected Populations (AAP) through encouraging HARISS partners to build two-way communication approaches with beneficiaries.
- Support to local and national responders through financing to national NGOs as downstream partners, including through the South Sudan Humanitarian Fund (SSHF) (in 2018, 39% of the SSHF funding went directly to national NGOs – up from 23% in 2017)[20]
  [20] South Sudan Humanitarian Fund (2019) SSHF Annual Report, 2018, April 2019.

Over 2018, there was greater stability within the DFID South Sudan Humanitarian and Livelihoods team which manage HARISS, which permitted a stronger partner focus with an emphasis placed on due diligence, risk management and conflict sensitivity. There was also significant high-level interest during the year, with visits from the joint FCO-DFID Minister of State for Africa, the DFID Permanent Secretary, the UK Secretary of State and the Minister of State for of Defence. South Sudan also participated in the review of the Independent Commission on Aid Impact’s Humanitarian Reform review.[21]
[21] See https://icai.independent.gov.uk/report/humanitarian-reform/.

This review covers the period of January 2018 to December 2018. It was conducted by an external reviewer with significant support and input from DFID HLT members. The review methodology is detailed at the end of the review. Due to the complexity of HARISS as a programme the standard DFID annual review process has been adapted to reflect the portfolio nature of the programme.

Recommendations
The table below provides a summary of recommendations against each pillar of the HARISS programme.

Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action.[22] Where necessary, these have been revised to account for changes in context. In total, 7 of the 19 recommendations made below have been brought forward from 2017.
[22] The 2017 review included a significant number of general recommendations (11 in total) in addition to recommendations that were specific to each pillar (39 in total). Many of these related to process issues that are either ongoing or have been addressed. Reflection from the 2017 AR process has led to a focus on a smaller number of recommendations.

Pillar	Recommendation
Emergency Food Assistance	There is a need for DFID partners to continue to explore and exploit opportunities to enhance access to food and to coordinate/integrate emergency food assistance and nutrition with support to food production. / WFP should continue to monitor the context, including market functionality, to ensure that cash programming is used, where effective and appropriate, with a view to replace, whenever possible, in-kind food distribution by cash-based food assistance.
Nutrition	Data about the extent to which nutrition services have been co-located and integrated with those of health, and benefit from WASH support is inconsistent. While progress has been made by HARISS partners in strengthening the continuity of care (SAM and MAM), there may be more that DFID can do to accelerate broader integration of services. / DFID’s programme portfolio includes investments in the Health Pooled Fund (HPF) and DFID also has links to the World Bank health programme. In the interests of consistency and maximising impact, there would be value in assessing the extent to which health facilities routinely provide nutrition services and how linkages can be strengthened in the future.
WASH	The slow pace of behaviour change linked to open defecation is a key threat to efforts to prepare for a potential EVD outbreak. HARISS WASH partners should be encouraged to broaden hygiene promotion to incorporate messages on the spread of the disease and how to prevent it.
Health	There is a need for stronger linkages to be made between the health, nutrition and WASH sectors, and better synergy between health services funded through HARISS, the HPF (major multi-donor, cross country health programme) and the World Bank to ensure complementarity and to support the sustainability of investments in strengthening health systems and addressing malnutrition.
Shelter/NFIs & Camp Management	It is now urgent that DFID and its partners strengthen the focus on resilience in areas of stability/return. This should include a greater focus on support for Housing Land and Property (HLP). / DFID should identify opportunities to support advocacy on durable returns where this is appropriate.
Food Security & Livelihoods	DFID’s engagement with REACH as a HARISS partner offers considerable scope for strengthening IPC analysis and predictive capacity which offers an opportunity to better understand food insecurity and to strengthen the relevance of responses. It will be important for DFID to use the partnership strategically in order to strengthen its own understanding of food security and inform its advocacy. / As DFID starts to plan the successor programme to HARISS, it should use the opportunity afforded by planned evaluations of Oxfam’s and GOAL’s resilience programmes (and potentially IMC’s IGA also) to identify good practice. More broadly, DFID should seek to look across its investments in HARISS and BRACE II with a view to determining the most efficient and effective models for strengthening resilience in South Sudan. / As the co-Chair of the Partnership for Resilience and Recovery (PFRR), DFID is well-placed to contribute technical advice to the emerging programme as well as ensuring that practical linkages are made between PFRR and DFID-funded resilience programmes.
Protection and GBV	DFID’s investment in the partnership with HI and IMC provides important resources to strengthen inclusion across HARISS partner programmes (including on data collection, reporting and programming). Efforts should be made to strengthen understanding among partners and to develop practical approaches to ensure they are inclusive / There continues to be scope for all partners to strengthen work on PSEA, ensuring adequate policies are in place and implemented, and a zero tolerance approach taken.
MEAL	DFID should facilitate strong relationships between ELFSS, HI, and the Conflict-Sensitivity Resource Facility, so as to optimise assessment of, and support to, strong, inclusive and conflict sensitive operations among all implementing partners in South Sudan.
Enabling Environment	While the approach taken by HARISS partners to community engagement has improved over time, there is still scope to better understand how responsive HARISS partners are to feedback. The development and roll-out of REACH’s community perceptions tracking mechanism will offer an additional resource to monitor and strengthen the relevance of partners’ programmes.
VfM and MYF	There is significant scope for DFID to better understand the value that UN agencies achieve through sub-contracting NGOs. The ELFSS synthesis revealed that the benefits of MYF are rarely passed across to partners including measures that may achieve VfM. This is an issue that has received dedicated attention from the HLT which offers important evidence of issues that DFID should seek to address in future. / The ICAI visit to South Sudan questioned whether DFID has sufficiently reliable information on management overheads throughout humanitarian delivery chains to determine whether they are justified. Better sight of these may offer the potential to strengthen VfM. / The HARISS programme has struggled to identify scalable resilience models, in large part because of the high cost and low transfer of value to beneficiaries. As the programme enters its final year, efforts should focus on a comparison of indicators, costs and value for money of different aspects of the programme.
Risk	The overall risk rating continues to be ‘major’ and at the ceiling of DFID’s risk appetite. While the approach of HARISS to risk management has been endorsed by DFID’s IAD, this will require continued prioritisation of the team.
Partnership performance and monitoring	During 2018, DFID has strengthened its knowledge and understanding of partnership practices between international organisations and local/national NGOs which will be further strengthened by ELFSS TPM synthesis studies on partnership and localisation. These inputs will complement DFID’s own analysis and offer an agenda to drive positive change in partnerships in the HARISS programme as well as in South Sudan more broadly. / Several of the HARISS partner reviews reported challenges with setting targets to measure progress against. This was particularly true for partners which deliver emergency response (e.g. MedAir) and for which quantitative response is largely predicated on the nature and scale of the emergencies that occur. While this review acknowledges the complexities of identifying indicators, in such cases, it may be more relevant to focus on issues of timeliness of response or the proportion of the population whose needs were met.

## B: THEORY OF CHANGE AND CONCLUSIONS

Summary supporting narrative for the overall score in this review
HARISS covers a range of humanitarian sectors and supports both life-saving emergency operations as well as interventions aiming to build resilience to shocks. The performance of each HARISS partner was scored individually against their logframe. These scores were then grouped by sector and aggregated into pillars (see below).[23] Overall, at a pillar level the programme scores an A+ although this includes both over and under performance by partners. This is an impressive achievement given the operating context.
[23] DFID has a standard approach for scoring performance in its Annual Reviews: A++ is over 137.5%, A+ is 112.5-137.5%, A is 87.5-112.5%, B is 62.5-87.5%, C is under 62.5%.

Pillar	Emergency Food Assistance	Nutrition	WASH	Health	Shelter/NFIs and Camp Management	Food Security and Livelihoods	Protection and GBV	MEAL	Enabling Environment
Weight[24]	32	7	10	12	7	14	7	1	8
Score	A++	A	A+	A	A	A	A	B	A+
[24] Pillars are weighted according to the budget allocated by HARISS to the particular sectors in 2017.

The HARISS programme has had to continue to flex in order to meet humanitarian needs in 2018, but it has achieved this well and so overall, this review considers HARISS continues to be an appropriate response to the context in South Sudan. It has been very effective in meeting the needs of those in crisis in addition to contributing to strengthening the resilience of people in more stable areas. It is this latter part of the programme that continues to perform less well due to a legacy of capacity issues, but also due to the complexity of partner interventions. While DFID has been proactive in seeking to address these challenges, they have impacted on performance.

Theory of change impact statement
Save lives, avert suffering, maintain dignity and reinforce coping capacities of those affected by conflict, disasters, shocks and conflicts in South Sudan

At an impact-level, HARISS has contributed to stabilising the situation in South Sudan, although it remains fragile and at significant risk of conflict, due to a range of factors which includes the fragility of the current situation, the limited access that communities have to resources, the protracted nature of displacement and the challenging economic and food security context. While the humanitarian components of HARISS were bolstered in 2018 to meet critical needs, and will continue to be essential, there is growing recognition among all actors of the need to place greater attention on strengthening livelihoods and local capacity where this is possible. This offers the potential for DFID to focus greater attention on resilience in 2019.

Theory of change outcome indicators
- Reduced vulnerability of people in need
- Improved capacity of the most vulnerable populations to withstand, adapt to, and recover from conflict, disasters and shocks
- Improved quality and impact of measurement of humanitarian action

At an Outcome level, 2018 saw a deepening of food insecurity and an increase in the numbers of people in crisis (IPC Phase 3), emergency (IPC Phase 4) and catastrophe (IPC Phase 5) compared with 2017 during the lean season between May and July, with a reduction by the end of the year to levels marginally lower than the same time in 2017.[25] The overall situation of acute malnutrition slightly improved in 2018 with no county reporting extreme critical levels (Global Acute Malnutrition above 30 per cent) of acute malnutrition.[26][27] For other HARISS outcome indicators, gaps in surveillance and the paucity of data confounds efforts to understand scale or identify trends in Crude Mortality Rates although reports suggest that the coverage of vaccine preventable diseases remains under 50%[28] which has played a role in the succession of disease outbreaks (particularly measles) which were declared and responded to in 2018.
[25] OCHA (2018) 2019 South Sudan Humanitarian Needs Overview, November 2018.
[26] OCHA (2018) 2019 South Sudan Humanitarian Needs Overview, November 2018.
[27] To put this into context, in 2018, 64 per cent of SMART surveys reported critical levels of acute malnutrition compared with 85 per cent during the same period in 2017
[28] OCHA (2018) 2019 South Sudan Humanitarian Needs Overview, November 2018.

While there were isolated parts of the country where communities were able to sustain improvements in their livelihoods and reduce vulnerability, these were not widespread, and gains were considered to be fragile. Efforts to strengthen resilience have been bolstered by the potential for peace but the piecemeal nature of these programmes has made it difficult to determine progress. This has prompted the launch of the Partnership for Recovery and Resilience in mid-2018 to strengthen coordination and accountability between partners.

Portfolio performance and cross-cutting issues
In terms of achieving an appropriate balance between humanitarian and resilience programming, the context in South Sudan has continued to tilt the HARISS programme towards humanitarian response, to a greater extent than was envisaged when the programme was designed. Despite this, DFID’s partners have performed well in scaling-up their programmes given the complexity and insecurity of the operating environment. DFID has supported programme expansion through three rounds of additional funding[29] which were consistent with the Humanitarian Response Plan (HRP) and humanitarian priorities:
[29] A fourth round of additional funding which had a focus on seasonal road repair was disbursed in February/March 2019.

- April/May 2018: Funding across a range of HARISS partners against priorities and gaps outlined in the 2018 Humanitarian Response Plan including multi-sectoral response (MedAir and ICRC), GBV (IMC), camp services (IOM), food and nutrition (WFP) and support to the SSHF.
- Aug/Sep 2018: Support to UN agencies (UNICEF, FAO, WFP) to militate commodity pipeline risks and frontline delivery gaps.
- Oct/Dec 2018: Additional funding for 2019 dry season prepositioning for health, early allocations to the SSHF, and support to Ebola preparedness (UNICEF, WFP, ICRC).

While HARISS comprises a complex mix of partners including UN, international NGOs, contractors and (downstream) national NGOs, coordination at the portfolio-level is an area that has improved with time. Reporting has also been strengthened, and DFID have worked with its partners to develop practical tools to address conflict sensitivity and to enhance due diligence and risk management. The use of ‘partner days’ by DFID Humanitarian and Livelihoods Team has permitted the sharing of analysis as well as learning on key issues which have included vulnerability, targeting and risk management

While this review is disaggregated by sector, many partners employ multi-sectoral approaches or work together to deliver results across sectors; collaboration between HARISS partners including in the WFP-led Integrated Rapid Response Mechanisms (WFP, UNICEF and FAO) and on issues of inter-operability between IOM and WFP. HI’s knowledge of inclusive programming has been used to benefit HARISS partners as well as the humanitarian community more broadly. Further strengthening integration between sectors and across partners will continue to be a priority for DFID in 2019.

HARISS has continued to provide contextualised support for humanitarian reforms and Grand Bargain (GB) priorities. ELFSS identified and analysed AAP plans and frameworks across HARISS partners and reports from its Third Party Monitors (TPM) identified practices which strengthened transparency and participation of communities in programme design and implementation.[30] DFID’s investment in its partnership with REACH at the end of 2018 is expected to make a significant contribution to filling the gap in understanding collective community perceptions of humanitarian assistance when it starts to report in 2019. HARISS has strengthened localisation through its contribution to the SSHF which, over the last three years, has shifted significantly towards funding NNGOs.[31] Throughout the year, DFID has also strengthened its analysis of the contribution made by HARISS to broader GB localisation commitments which will offer a platform to influence policies and practices in 2019. The use of cash for humanitarian response has continued to be prioritised by HARISS across a range of partners (WFP, FAO, GOAL and Oxfam) in addition to its use as a means of strengthening community resilience.
[30] ELFSS (2018) Accountability to affected populations, how is it being applied? December 2018.
[31] In 2018, 39% of the SSHF funding ($20.6m) was allocated to NNGOs. This represents a significant increase over time, from 12% in 2016 to 23% in 2017 to 39% in 2018 (South Sudan Humanitarian Fund (2019) SSHF Annual Report, 2018, April 2019.

The signing of the revitalised peace agreement has resulted in a decrease in violent conflict, however, in some areas, fighting continued, and in others, inter-communal violence erupted, highlighting the continuing importance of addressing the drivers of conflict, and ensuring that aid does not exacerbate tensions or lead to harm. With these challenges in mind, DFID has continued to promote conflict sensitive-approaches (CS) to humanitarian assistance. The CS minimum standards framework was used across all HARISS partners to assess capacities and performance, and is an area that DFID has opened up space for dialogue. Concern about CS was a key motivation for the creation of the South Sudan Donor Group which has advocated on factors that have constrained humanitarian effectiveness including protection of civilians, humanitarian access and taxes and fees levied by state and non-state actors on humanitarian agencies.

Gender and social inclusion across the HARISS portfolio continues to be mixed, with most partners routinely disaggregating data by gender; however, adequately assessing and taking account of the needs of people with disabilities remains a challenge.[32] The ambitions of the HARISS programme to strengthen these important cross-cutting issues have been set back as a consequence of the ELFSS contract revision and a Social Development Advisor gap in the DFID South Sudan team for the majority of 2018, but that said, there has continued to be a focus across the portfolio on promoting women’s participation in programming as well as ensuring that humanitarian assistance meets the specific needs of women (such as through the work of IMC) and people with disabilities (particularly from ICRC and IOM). In 2019, DFID’s support for inclusion will be strengthened through support for mainstreaming provided by HI.
[32] The 2017 AR noted that there are challenges in achieving disaggregated data for UN agencies due to limitations and agreements in overarching DFID MoUs negotiated by sector leads in DFID HQ. This has been raised to DFID HQ for consideration in the next renegotiation of the overarching framework agreements.

During the review period, projects delivered by Oxfam, GOAL and IOM all contributed to climate adaptation through the deployment of £8 million of international climate finance. The Oxfam and GOAL-led resilience projects delivered results against key performance indicator 1, with an estimated 211,490 people supported to better adapt to the effects of climate change. The IOM-led component reported against key performance indicator 9, installing 4 solar water pumps, a low carbon technology.

Data availability and analysis has continued to improve throughout the HARISS programme, in large part as a result of the support to TPM provided by ELFSS. The monitoring reports have provided an important complement to DFID’s own monitoring visits, particularly in less accessible areas. They have also played an important role in strengthening accountability for partner performance. For the broader humanitarian community, access to quality data for targeting and analysis continues to be variable and is an area which HARISS has the potential to strengthen in 2019 through its funding to REACH.

Key lessons
- Despite the potential for peace, the impact of the conflict, and vulnerability of South Sudanese people to food insecurity, disasters and disease outbreaks will necessitate continued need for significant humanitarian response for the foreseeable future.
- While large-scale IDP and refugee return and resettlement is yet to occur, it has the potential to create significant upheaval due to challenges associated with access to adequate services and livelihood opportunities, but also due to issues linked to housing, land and property. Achievement of durable solutions will require a general improvement of the security situation as well as assurances from government on safety.
- The current food production deficit in South Sudan (estimated to be 500,000 MT in 2018) is significant and will have a lasting legacy. Even the most optimistic predictions indicate that there will continue to be seasonal food shortages with potential spikes due to labour patterns and disease outbreaks between May/June and September each year. Wherever possible, efforts to address food insecurity should seek to narrow the gap in the long-term deficit by building long-term coping capacities in addition to meeting short-term food needs.
- A focus on meeting basic needs in such a volatile and insecure context has led to the prioritisation of rudimentary programming models. As access improves and scope for community engagement increases, it is essential that humanitarian partners seek to strengthen inclusion and equity as a means of ensuring that vulnerable members of communities are not left behind. This will be achieved by improving the collection and analysis of data in addition to assisting organisations to better understand vulnerability and how to comprehensively address it in their programmes. DFID’s support to REACH and HI have the potential to make an important contribution to these changes.
- Saving lives and supporting human development is poorly served by a siloed approach to meeting needs; while the humanitarian community organises itself sectorially, it is essential that planning is integrated in a way that can overcome sectorial boundaries in order to address the complex challenges posed by the breadth and depth of needs in South Sudan in a comprehensive way.
- While the international humanitarian community has provided much-needed assistance to South Sudan for many years, it has been less successful in strengthening local capacities. The long-term nature of the needs in the country, linked to GB commitments made by international actors to support localisation offer an important opportunity to address this gap.

## C: DETAILED SCORING

Pillar	Emergency Food Assistance	Pillar Score	A++
Risk:	Severe	Impact weighting (%):	32
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

Emergency food assistance accounted for 32% of HARISS funding in 2018. This is justified given the extent of food insecurity and associated malnutrition in South Sudan. This output captures food assistance delivered both in-kind and cash-based transfers and vouchers to food-insecure individuals and households.

The tables below show partner pillar scores and headline partner results which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)[33]	Output Performance
GOAL	Food insecure households access to humanitarian cash transfers to meet their immediate needs	2.2	C
Oxfam	Reduced immediate food gap and humanitarian need	1.2	B
WFP	Food, nutritional products, non-food items, cash transfers and vouchers distributed in sufficient quantity and quality and in a timely manner to targeted beneficiaries	88.4	A++
WFP	Development and implementation of a consultative framework to adapt food assistance modalities to contexts and needs, and enable timely shifts to various modalities	5.1	A
ICRC	Distribution of food commodities	3.3	B
[33] Pillar impact weightings are determined by the size and proportion of the partner budget which is utilised to support the particular sector – in this case food.

Headline results[34]	Partner	DFID Funded Milestone	DFID Funded Results Achieved
Number of people reached with food commodities	WFP / ICRC	222,716 / 59,292	221,540 / 51,317
Number of people reached with cash assistance	WFP / GOAL / Oxfam	151,238 / 12,130 HH / 500 HH	139,140 / 10,994 HH / 217 HH
[34] Headline results provide an indication of the most important results for the achievement of the output, rather than detailing all of the results. Results are usually annual but may on occasion be cumulative through HARISS.

Overall situation: Despite large-scale humanitarian assistance, the conflict pushed more people in South Sudan into hunger than ever before.[35] By September 2018, nearly 60% of the population faced severe food insecurity due to disrupted humanitarian assistance due to the conflict.[36]
[35] See https://www.unicef.org/press-releases/conflict-pushes-south-sudanese-hunger-more-6-million-people-face-desperate-food.
[36] OCHA (2017) 2018 Humanitarian Needs Overview, South Sudan, November 2017.

Partner performance:[37] WFP made the greatest contribution to this pillar which comprised a range of services including general food distributions, Integrated Rapid Response Mechanism (IRRM),[38] targeted food distribution and cash programming. Similar to 2017, WFP significantly over-achieved against their projected target which merited an output performance score of A++. The performance of ICRC was more modest albeit with a caveat that DFID does not set specific milestones, but contributes to a multi-donor appeal where ICRC sets its own targets which have a high degree of flexibility.
[37] Figures for partner performance for this pillar and subsequent pillars are taken from DFID’s implementing partner review. References for data obtained outside of these documents have been included in footnotes.
[38] IRRM is a delivery modality that allows small teams of WFP (and other staff) to reach populations in areas where WFP does not have a static presence over a short period of time.

WFP assisted over 2.2m people through general food distribution in 2018, with a DFID-attributable figure of 221,540 people. A significant proportion of this figure was achieved through WFP’s engagement in the IRRM which provides integrated assistance to communities in hard-to-reach areas, in partnership with UNICEF and FAO. An average of 26 IRRM missions were undertaken each month, which were estimated to have assisted over 1.2 million people. WFP has initiated a market monitoring process to determine the most appropriate modality with a view to identifying locations were cash is most appropriate; 12 reviews of food assistance modalities were undertaken in 2018 and the value of cash transfers was also regularly reviewed to ensure beneficiaries retained their purchasing power. Over the year, WFP’s cash programming reached 287,000 beneficiaries, of which 139,140 were DFID-attributable.

In 2018, DFID funded WFP biometric registration (including with additional funding provided through an uplift in April 2018) which has helped drive efficiency gains as it has reduced duplication of beneficiaries as well as offering significant benefits in tracking displacement. In the second half of 2018 alone, WFP estimated a reduction of $2 million in operational costs as a result of the beneficiary authentication process. Cost-savings were also achieved through a focus on expanding road and river transport, successful prepositioning and by the use of innovative transport solutions such as the deployment of Sherp all-terrain vehicles. These initiatives allowed WFP to reduce the number of locations served by air and integrate these into regular field office programme coverage.

Both GOAL and Oxfam have small-scale cash programmes within their resilience programmes which are focused on meeting immediate needs. For the second year, both organisations failed to meet all of their targets. GOAL changed its cash transfer strategy from unconditional to conditional cash transfers with the objective of leveraging these transfers as incentives to promote community assets that address risks and shocks, and it was this shift that led to delays and accounted for the reduced number of beneficiaries. Oxfam targeted a small number of people in Malakal and Twic East for asset construction but failed to achieve targets. Performance issues have been addressed with both organisations.

Gender and social inclusion: In 2018, WFP sought to promote gender equality by tailoring its assistance to the needs of women and girls and by encouraging female participation and leadership in decision-making and community engagement. To encourage women’s participation in decision-making, WFP introduced the standard that Project Management Committees (PMCs) should have corresponding male and female representatives in all posts. This has led to proactive and intentional community outreach and gender equality discussions with communities and, as a result, women made up 50% of the positions in PMCs across all areas of operation in 2018.

Risks and challenges: Updated risk matrices and delivery chain risk maps were prepared for all partners under this pillar; key risks outlined include variability in humanitarian access due to conflict, poor road conditions, inadequate human and financial resources, and insecurity to staff, partners and beneficiaries. The reduction in conflict significantly reduced the risk of looting and aid diversion, and WFPs roll-out of a formal complaints and feedback mechanism alongside community outreach, has strengthened its ability to monitor levels of satisfaction as well as respond to community concerns about the assistance provided. Focus Group Discussions with affected communities have informed WFP of common and consistent protection concerns faced by the community, including taxation of assistance by different actors, GBV (mostly during firewood collection) and threats and harassment by youth. Mitigation measures that WFP implemented included alterations to distribution sites, introduction of simultaneous distributions across various distribution points to address conflict over resources and introduction of GBV awareness, prevention and referral messaging.

Recommendations[39]
[39] Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action. In some cases, these have been updated to account for changes in context.
- There is a need for DFID partners to continue to explore and exploit opportunities to enhance access to food and to coordinate/integrate emergency food assistance and nutrition with support to food production.
- WFP should continue to monitor the context, including market functionality, to ensure that cash programming is used where effective and appropriate, with a view to replace, whenever possible, in-kind food distribution by cash-based food assistance

## C: DETAILED SCORING

Pillar	Nutrition	Pillar Score	A
Risk:	Major	Impact weighting (%):	7
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

HARISS funding for nutrition activities accounted for 7.5% of the total budget and activities broadly fell into two categories;
- Prevention of acute malnutrition comprising messaging on infant and young child feeding (IYCF) and blanket supplementary feeding programme (BSFP)
- Management of acute malnutrition comprising outpatient therapeutic programmes (OTP) for severe acute malnutrition (SAM) and targeted supplementary feeding programmes (TSFP)

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)[40]	Output Performance
WFP	Messaging and counselling on specialized nutritious foods and infant and young child feeding (IYCF) practices implemented effectively	21	A
UNICEF	Children with severe acute malnutrition access appropriate management of acute malnutrition	52	A
SSHF	Support to nutrition services	20	A
Medair	Children with severe acute malnutrition access appropriate management of acute malnutrition	7	A+
[40] Pillar impact weightings are determined by the size and proportion of the partner budget which is utilised to support the particular sector.

Headline results	Partner	DFID Funded Milestone	DFID Funded Results Achieved
Number of children (6-59 months) treated with severe or moderate acute malnutrition	UNICEF / SSHF / Medair	92,500 (SAM) / 114,000 / 24,352	100,641 / 114,000 / 26,717
Beneficiaries supported through blanket supplementary and/or therapeutic supplementary feeding programmes	WFP	41,753 / 82,123	36,197 / 72,243

Overall situation: In 2018, A convergence of factors, including severe food insecurity and inadequate health and water, sanitation and hygiene (WASH) services, has resulted in continued high malnutrition rates. Despite this, the number of people in need of emergency nutrition support decreased by 3% over the course of 2018 and the overall situation of acute malnutrition also slightly improved in 2018 with no county reporting extreme critical levels of acute malnutrition (Global Acute Malnutrition [GAM] above 30 per cent).[41] Moreover, IPC reports suggested a decrease in the number of counties classified with a critical nutrition situation from 43 in September 2017 to 31 during the same period in 2018.[42]
[41] OCHA (2018) 2019 Humanitarian Needs Overview, South Sudan, November 2018.
[42] Critical means GAM rates between 15 and 29.9 per cent. Reported in OCHA (2018) 2019 Humanitarian Needs Overview, South Sudan, November 2018.

Partner performance: UNICEF, WFP and the World Health Organisation strengthened their collaboration to provide continuity of care through referral mechanisms across the different treatment programmes for children with moderate and severe acute malnutrition.[43] This was formalised in September through a Letter of Understanding for collaboration on the treatment and prevention of malnutrition between UNICEF and WFP to strengthen their nutrition-sensitive activities. The two agencies also agreed to collaborate on the digitalization of nutrition programmes through the application SCOPE CODA (Conditional on-Demand Assistance), which aims to provide better quality care, real-time programme data and programme results, such as increase case management, coverage and reduce length of stay.[44]
[43] Ibid.
[44] World Food Programme (2019) South Sudan Annual Country Report 2018.

UNICEF achieved all indicators under this outcome and have met expectations. SAM treatment achievements are attributed to an 86% increase in the number of outpatient therapeutic programme treatment sites, from 462 in 2015 to 858 in 2018; increased partnership with civil society implementing partners; and active community case finding. Dry season prepositioning of essential nutrition supplies enabled continuity of service delivery.[45] UNICEF reported a significant over-achievement of its DFID-funded results for the number of children (6-59 months) treated with SAM or MAM with a total DFID-attributable reach of 100,641 children. WFP distributed prevention commodities in areas where GAM rates were higher than 15% including in some rural areas and Protection of Civilians Sites (POCs) during the lean season, and via IRRM responses linked to the provision of general food distributions. WFP achieved a DFID-attributable figure of 36,197 (from a grand total of 361,968) which was broadly in line with targets.
[45] UNICEF South Sudan (2019) UNICEF South Sudan annual report, 2018

Emergency response was supported by SSHF and MedAir; SSHF funding enabled partners to scale up the nutrition response in prioritized locations, expanding ongoing nutrition treatment services and outreach to children and pregnant and lactating women in hard-to-reach communities. Funding for rapid response activities supported response in locations with no ongoing services and in so doing filled essential gaps in service provision. In 2018, the SSHF targeted 600,000 people with a DFID-attributable figure of 114,000. MedAir performed well against their four objectives and moderately exceeded expectations overall with satisfactory discharge rates of 90% despite the potential for high default rates in areas where there are mobile populations. To mitigate the risk of defaulters, MedAir used networks of community nutrition workers who paid home visits to absentees and defaulters.

Risks and challenges: Risks for the nutrition programmes were similar to those of food security interventions; security risks (including staff safety), physical access constraints and bureaucratic impediments. During 2018, logistical constraints caused interruptions in the implementation of prevention programmes and there were also challenges posed by defaulters, particularly in areas affected by significant displacement. The nutrition sector was 57.3% funded against the 2018 HRP.[46]
[46] See https://fts.unocha.org/appeals/646/summary.

TPM monitoring raised concerns about the accuracy of data relating to numbers treated and treatment outcomes. Reports were received of programme interruptions due to conflict and poor record keeping due to low levels of literacy, at the same time as achieving cure rates of 93% which was inconsistent and suggested a need for greater scrutiny of reporting in the future.

Recommendations[47]
[47] Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action. In some cases, these have been updated to account for changes in context.
- Data about the extent to which nutrition services have been co-located and integrated with those of health, and benefit from WASH support is inconsistent. While progress has been made by HARISS partners in strengthening the continuity of care (SAM and MAM), there may be more that DFID can do to accelerate broader integration of services.
- DFID’s programme portfolio includes investments in the Health Pooled Fund (HPF) and DFID also has links to the World Bank health programme. In the interests of consistency and maximising impact, there would be value in assessing the extent to which health facilities routinely provide nutrition services and how linkages can be strengthened in the future.

## C: DETAILED SCORING

Pillar	WASH (Water, Sanitation and Hygiene)	Pillar Score	A+
Risk:	Major	Impact weighting (%):	10
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

WASH funding accounts for 10% of the HARISS budget. In 2018, HARISS supported WASH interventions through UNICEF, MedAir, Oxfam, IOM, SSHF and ICRC. These included:
- Drilling and rehabilitation of water sources (boreholes and wells) and establishing or restoration of surface water treatment systems
- Rehabilitation and construction of sanitation facilities within communities and in institutions;
- Promotion of improved hygiene practices through hygiene messaging
- Distribution of WASH non-food items like jerry cans and water treatment tablets

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)[48]	Output Performance
MedAir	Timely access to safe water, sanitation, and improved hygiene practices is provided to vulnerable populations in acute and chronic emergency situations	7	A++
UNICEF	Vulnerable populations in conflict-affected, and epidemic-prone communities in targeted counties have improved access to equitable and sustainable health, nutrition and WASH services.	19	A
IOM	Provide displaced populations and host communities with sustainable access to clean water and/or sanitation	32	A
Oxfam	Improved access to water and sanitation in remote areas	1	C
ICRC	Improved access to water, hygiene and sanitation facilities	21	A++
SSHF	Support to WASH services	20	A
[48] Pillar impact weightings are determined by the size and proportion of the partner budget which is utilised to support the particular sector.

Headline results	Partner	DFID Funded Milestone	DFID Funded Results Achieved
Number of beneficiaries with improved access to clean water and/or sanitation.	IOM / SSHF / MedAir / UNICEF / ICRC	145,228 (sanitation) / 10,000 HH (water) / 152,000 / 53 water sources / 115 latrines / 148,9000 (sanitation) / 245,473 (water) / 28,693	142,223 (sanitation) / 17,300 HH (water) / 152,000 / 82 water sources / 584 latrines / 89,891 (sanitation) / 247,879 (water) / 54,517 (water)

Overall situation: Available data suggests that only 29% of the population of South Sudan has access to a borehole, tap stand or water yard within a maximum 30-minute distance without facing protection concerns.[49] More than 90% of the population practices open defecation, either because they do not have access to, or are not accustomed to using a basic sanitation facility and only 13% of the population has access to WASH non-food items, such as jerry cans, soap and mosquito nets.[50]
[49] South Sudan Food Security and Nutrition Monitoring System, July- August 2018.
[50] Ibid.

Partner performance: IOM are responsible for providing water, sanitation and hygiene support in PoCs (Bentiu, Malakal and Wau), emergency WASH outside of PoCs and managing 50% of the WASH core pipeline. Outside of the camp as part of IOM WASH Emergency Preparedness and Response IOM has improved access for 86,500 individuals to safe water. 30% of the pillar impact weighting is attributable to IOM’s WASH programme which performed well against its output indicators in 2018.

The focus of ICRC, UNICEF and MedAir’s support are on IDP’s and communities affected by conflict; ICRC significantly over-achieved against its anticipated WASH outputs as did MedAir. The latter was due to the prioritisation of WASH interventions by the Inter-Cluster Working Group (ICWG) in response to conflict-related displacements. UNICEF struggled to achieve sanitation targets, but delivered stronger results in water treatment and distribution to conflict-affected people and institutions.

Funding from the SSHF enabled partners to respond to the needs of IDPs and host community members, improving access to safe water for drinking and domestic use, as well as improved hygiene to mitigate disease and infections. This included improving WASH in schools and health centres, as well as in households with malnourished children. Of the 0.84 million people targeted for WASH support, 0.83 million were reached,[51] giving a DFID-attributable figure of 152,000.
[51] South Sudan Humanitarian Fund (2019) SSHF Annual Report 2018, April 2019.

IOM’s policy of solarisation offers the greatest potential for strengthening the efficiency of water provision, however, progress across IOM’s sites was mixed with installation in the Malakal PoC significantly delayed.

Gender and social inclusion: IOM has conducted research into what factors impact women’s ability to actively participate in the provision of humanitarian WASH services in South Sudan and how can these factors be addressed in a practical, conflict-sensitive manner. SSHF partners engaged with communities about choices related to improvements in safe water and sanitation, providing opportunities for dialogue about sustainable service delivery and gender concerns which informed project design and implementation.

Risks and challenges: While WASH activities suffer the same security, access and conflict-related risks as other HARISS pillars, there are also a number which are specific to the sector with knowledge, attitudes and practices being a particularly important one; despite a significant focus on promoting the use of latrines and hygiene practices, a mix of entrenched practices linked to the high frequency of displacement has led to modest progress being made. With preparedness efforts now focusing on the potential for an EVD outbreak, it continues to be essential that progress can be made towards changing behaviours. The WASH sector was 37.3% funded against the 2018 HRP.[52]
[52] See https://fts.unocha.org/appeals/646/summary.

Recommendations[53]
[53] Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action. In some cases, these have been updated to account for changes in context.
The slow pace of behaviour change linked to open defecation is a key threat to efforts to prepare for a potential EVD outbreak. HARISS WASH partners should be encouraged to broaden hygiene promotion to incorporate messages on the spread of the disease and how to prevent it.

## C: DETAILED SCORING

Pillar	Health	Pillar Score	A
Risk:	Major	Impact weighting (%):	12
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

Health accounted for 12% of HARISS funding. Health interventions supported under HARISS included:
- Outbreak prevention and response;
- Primary health care especially maternal and child health including integrated management of childhood illnesses;
- Expanded programme of immunisation; and,
- Trauma treatment and rehabilitation, particularly of war wounded.

The tables below sets out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)[54]	Output Performance
MedAir	Increased access to quality preventative and curative health services for emergency affected populations	7	A+
UNICEF	Children and women in the target communities have increased and sustained access to community and facility level preventive and curative health services	33	A+
SSHF	Support to health services	42	A
ICRC	To help improve access to health and provision of surgical care	18	A
[54] Pillar impact weightings are determined by the size and proportion of the partner budget which is utilised to support the particular sector.

Headline results	Partner	DFID Funded Milestone	DFID Funded Results Achieved
Number of people vaccinated against preventable diseases	Medair / UNICEF	25,531 / 8,076 (Penta 3)	94,815 / 11,884 (Penta 3)
Number of people with increased access to preventive and curative health services	Medair	130,000	152,759
Number of people whose health needs were met (curative, preventive and vaccination) by SSHF funding	SSHF	380,000	380,000

Overall situation: Years of conflict have resulted in the destruction of health facilities, undermining healthcare and exacerbating risks of disease and mortality, with an estimated 4.8 million South Sudanese people in need of assistance to access health-care services in 2018.[55] Of the 1,893 health facilities, 419 (22%) are non-functional, and 955 (50%) are functioning at 10% of their capacity due to a combination of extensive looting and vandalization, critical loss of human resources, frequent stock outs of drugs and pharmaceuticals, and fiscal delays.[56]
[55] OCHA (2017) 2018 Humanitarian Needs Overview, South Sudan, November 2017.
[56] Ibid.

Partner performance: HARISS worked across a range of partners to address life-saving health needs as well as filling gaps in the health infrastructure. MedAir and ICRC sought to address immediate needs caused by conflict and displacement; ICRC focused both on supporting health centres in conflict-affected areas in addition to supporting to two surgical facilities. In 2018, MedAir complemented its emergency response activities in health with support to static health facilities in Aweil, Renk and Leer. Performance of both partners was considered strong, with MedAir over-achieving against three of its four outputs (including the total number of people benefitting from its health services). The mobile response was particularly effective in demonstrating flexibility and responsiveness in responding to a malaria outbreak in Ayod Country, a measles vaccination campaign in response to an outbreak near Rumbek and delivery of cholera vaccines following fighting in Unity.

The focus of UNICEF and the SSHF was in strengthening coverage of vaccination and improving access and responsiveness to health care needs of vulnerable populations by focusing on morbidity and mortality. UNICEF exceeded all of its output indicators, exceeding expectations for Penta 3 immunisation substantially (by almost 150%). With timely funding from the SSHF, cluster partners provided vital access to essential healthcare and preventive health services, and supported the detection of, and response to, disease outbreaks. Mass health education campaigns, as well as collaboration with WASH partners to improve conditions in health facilities, helped reduce risks of malaria, diarrhoea, pneumonia and other diseases.

HARISS successfully responded to a number of disease outbreaks in 2018; in response to 450 suspected measles cases, including five child deaths, UNICEF supported the Ministry of Health to conduct a countrywide measles follow-up campaign and local outbreak responses. Combined, these interventions accounted for the vaccination of 814,890 children aged 6 months to 15 years against measles in 2018 (84% of the target).[57][58] HARISS-funded partners also played a catalytic role in preparing for a potential EVD outbreak with MedAir conducting health and WASH assessments in Nimule to identify gaps in preparedness; and UNICEF received £606,367 from DFID’s IRF in December 2018 to support national-level preparedness activities for a period of 6 months.
[57] These figures are for the response as a whole rather than solely attributable to DFID.
[58] UNICEF South Sudan (2019) UNICEF South Sudan annual report, 2018.

Risks and challenges: In 2018, some 500 attacks on healthcare services were documented, including deaths of 115 healthcare workers,[59] with extensive looting and damage of health infrastructure. Additionally, there are widespread shortages of essential medicines in health centres. A time-bound challenge which impacted on the health sector in 2018 was a 4-month gap in World Bank funding for healthcare provision in Jonglei and Upper Nile; to address this, DFID provided £4,401,594 to UNICEF to provide primary healthcare in 212 sites over 4-months. The health sector was 29.4% funded against the 2018 HRP.[60]
[59] Surveillance System for Attacks on Health Care, 2017 and 2018.
[60] See https://fts.unocha.org/appeals/646/summary.

Recommendations[61]
[61] Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action. In some cases, these have been updated to account for changes in context.
There is a need for stronger linkages to be made between the health, nutrition and WASH sectors, and better synergy between health services funded through HARISS, the HPF (major multi-donor, cross country health programme) and the World Bank to ensure complementarity and to support the sustainability of investments in strengthening health systems and addressing malnutrition.

## C: DETAILED SCORING

Pillar	Shelter/NFIs and Camp Management	Pillar Score	A
Risk:	Moderate	Impact weighting (%):	7
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

Overall, S-NFI and CCCM sectors amounted to 7.4% HARISS overall budget. HARISS partners that work in this sector included IOM (S-NFI and camp management), Medair (S-NFI), and SSHF (S-NFI and CCCM).[62] The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.
[62] In addition, IMC provides NFIs, including dignity kits, to vulnerable women and girls in their project areas. See Protection pillar.

Partner	Output Description	Pillar Impact Weight (%)[63]	Output Performance
IOM	The dignity and living conditions of IDPs residing in PoCs is ensured through appropriate and timely service provision	19	A
IOM	Survival and self-sufficiency of IDPs is supported through timely and quality provision of S-NFI services	46	A
MedAir	Vulnerable populations affected by acute onset emergencies have timely access to quality lifesaving NFI services	7	A++
SSHF	Support to NFI/shelter	20	A
SSHF	Support to CCCM	7	B
[63] Pillar impact weightings are determined by the size and proportion of the partner budget which is utilised to support the particular sector.

Headline results	Partner	DFID Funded Milestone	DFID Funded Results Achieved
Number of people provided with shelter and/or non-food items (NFI)	IOM / SSHF / Medair	49,058 / 114,000 / 42,840	36,952 / 114,000 / 38,868

Overall situation: At the beginning of 2018, 1.7 million people required emergency shelter/NFI support in South Sudan (in addition to over 300,000 refugees living in neighbouring countries).[64] Included in this number were 827,000 people who required direct CCCM services. This comprised of nearly 300,000 IDPs of whom about 210,000 resided in UNMISS PoC sites, more than 27,700 in informal settlements, and more than 58,000 in collective centres. In addition to already recognised sites, CCCM also supported 527,000 IDPs and surrounding host communities in other camp-like settings across the country.[65]
[64] OCHA (2017) 2018 Humanitarian Needs Overview, South Sudan, November 2017.
[65] Ibid.

Partner performance: The focus of IOM was the provision of S-NFI services to populations primarily residing in PoCs; In doing this, IOM met expectations and in some areas exceeded the quantitative milestones such as in the provision of basic services and protection. The SSHF complemented the work of IOM by supporting efforts to strengthen site coordination and service delivery, with a particular focus on accountability and equity (see Gender and Social Inclusion below).

MedAir and SSHF’s shelter assistance was targeted at conflict-affected and IDP-hosting areas; funding from the SSHF focused on shelter solutions in hard-to-reach areas, with most support being channelled through national partners which were considered well-placed to enhance accountability to, and communication with, the affected population. MedAir distributed S-NFI items through its ERT and conducted twice the number of distributions than planned to displaced households identified through joint inter-cluster assessments (32 in total). Despite this, the number of people reached was only 91% of the target (38,868/42,840).

Gender and social inclusion: The SSHF funded cluster partners to work alongside IOM in the PoCs to improve accountability to the affected population, including the enhancement of communication and feedback mechanisms to promote equitable access to services. This included the creation of information desks, the establishment of feedback mechanisms, and strengthening the capacity of camp management committees.

IOM sought to strengthen equity by identifying and addressing the needs of women, youth and people with disabilities through a range of interventions; the DFID HARISS top-up enabled the extension of MHPSS services in Bentiu (PoC), Malakal (PoC and town) and Wau (PoC), targeting men, women, girls and boys across different sectors (general protection, child protection, sexual and GBV, education, health, WASH, CCCM), as well as key vulnerabilities (including child protection cases, GBV survivors, new arrivals, protection cases, people with disabilities, elderly, widows, and youth). The IOM MHPSS team also continued to work with camp management to ensure the provision of safe spaces for vulnerable people seeking psychosocial support.

Risks and challenges: The PoCs have a specific set of risks which are linked, in large part, to the forces that perpetuate their existence; these include threats to staff, bureaucratic impediments, community tensions and co-opting of the camp leadership. This has necessitated the development of participation and accountability mechanisms as a mitigating measure. IOM also have a conflict mediator in Bentiu PoC who facilitates community consultation, interactions with governance and leadership structures and pursues a strategy to mainstream conflict sensitivity. Outside the PoCs, the key risks are common with other HARISS pillars. The CCCM cluster was 21.5% funded against the 2018 HRP and the NFI-S shelter cluster received 29% of the funding requested.[66]
[66] See https://fts.unocha.org/appeals/646/summary.

Recommendations[67]
[67] Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action. In some cases, these have been updated to account for changes in context.
- It is now urgent that DFID and its partners strengthen the focus on resilience in areas of stability/return. This should include a greater focus on support for Housing Land and Property (HLP).
- DFID should identify opportunities to support advocacy on durable returns where this is appropriate.

## C: DETAILED SCORING

Pillar	Food Security and Livelihoods	Pillar Score	A
Risk:	Major	Impact weighting (%):	14
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

14% of the HARISS budget was allocated to the Food Security and Livelihoods (FSL) sector (excluding emergency food assistance). This was split between emergency livelihoods and resilience-building, delivered by 6 partners. FAO, ICRC and the SSHF are delivering in the area of emergency livelihoods (distribution of seeds and tools, fishing kits, vaccination of cattle). In some areas facing severe food insecurity where a static presence and longer-term activities were possible, two consortia have been selected (led by OXFAM and GOAL) to support communities to recover and increase their productive capacities, diversify their livelihoods and improve their resilience to shocks. Though its activities focused on GBV, IMC is also supporting income generating activities for women.

The tables below set out partner pillar scores and headline results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)[68]	Output Performance
GOAL	Beneficiary households' assets and livelihoods are strengthened and diversified	8	A
GOAL	Skills and knowledge for resilience are improved	5	A+
FAO	Emergency livelihood support provided to the most food insecure and vulnerable households	27	A
FAO	Production and availability of livelihood inputs supported in Greater Upper Nile	3	A
Oxfam	Increased local food production (staple crop, vegetable, livestock, fishing)	8	B
Oxfam	Improved markets functionality and access to incomes through support to microenterprises (IGA) and traders	5	B
Oxfam	Increased engagement of authorities, leaders and citizens, including marginalized groups (isolated groups, vulnerable women and youth), in addressing issues that are affecting their lives	2	A+
IMC	Women in Jonglei, Unity, Western Bahr El Ghazal and Upper Nile states engaged in feasible livelihood activities including Income Generating Activities (IGA)	4	B
ICRC	To respond to people’s most urgent needs and to help them build resilience, the ICRC, together with the South Sudan Red Cross (SSRC)	23	A+
SSHF	Support to food security and livelihoods	15	B
[68] Pillar impact weightings are determined by the size and proportion of the partner budget which is utilised to support the particular sector.

Headline results	Partner	DFID Funded Milestone	DFID Funded Results Achieved
Number of vulnerable households (HH) supported with emergency livelihoods kits (seeds & tools, fishing kits)	FAO / ICRC seeds / ICRC fishing	85,000 HH / 43,956 bens / 26,373 bens	83,859 HH / 47,882 bens / 29,842 bens
Number of vulnerable households supported to strengthen their resilience to shocks	GOAL / Oxfam / IMC	22,450 / 19,706 / 810 (IGA)	20,337 / 10,214 / 610 (IGA)
Number of livestock vaccinated and treated	FAO / ICRC	200,000 / 21,978	180,988 / 35,414

Overall situation: The food situation continued to deteriorate throughout 2018 with 5.4 million people projected to be food secure in the first quarter of the year.[69] The lean season began earlier and was worse than in 2017. During the year, conflict-affected, displaced households and returnees in Greater Upper Nile, Western Bahr El Ghazal and Greater Equatoria continued to face alarming food consumption gaps, asset depletion and malnutrition. While conflict has been the driver of food insecurity, other factors included poor infrastructure, disruption of livelihoods, poor economic conditions and inconsistent humanitarian access. The convergence of these multiple shocks resulted in high levels of chronic poverty, vulnerability, acute malnutrition and food insecurity, with communities resorting to the use of negative coping strategies such as going without food or selling their last female animal.
[69] OCHA (2017) 2018 Humanitarian Needs Overview, South Sudan, November 2017.

Partner performance: Partners providing support to emergency livelihoods have performed well, with ICRC distributing a range of livelihoods support (seeds and tools, fishing kits, livestock vaccination and livelihood support) which went beyond its output targets. FAO also performed well and ensured timely delivery through strong implementing partners with good links to communities. The increased use of seeds fairs were an important shift in approach as they have potential to secure more lasting benefits. Following an uplift in mid-2018, FAO’s targets for the dry season were revised and were not quite met, although they were within the accepted variance. ELFSS Third Party Monitoring continues to explore issues around quality, appropriateness and sustainability of emergency livelihoods intereventions, and is planning a TPM learning synthesis of FAO activities in the second quarter of 2019. However, noting that these intereventions are emergency in nature, and positioned as a better response than in-kind food distributions, so the level at which they can achieve sustainability objectives is limited.

The performance of the projects with a focus on supporting longer-term resilience activities (Goal, Oxfam, and the small livelihoods component of IMC’s wider protection programme) improved somewhat during 2018, although Oxfam and IMC still struggled to achieve targets due to a mix of organisational factors (high staff turnover, lengthy recruitments, limited technical capacity) and operational, and programmatic challenges. As a consequence of continuing concerns about quality gaps and management capacity, a decision was taken for the partnership with Oxfam to end after the growing season in September 2019. GOAL graduated from their Performance Improvement Plan and have achieved stronger results in 2018. Despite project sites being among the worst hit by food insecurity, results from the annual survey undertaken in June show significant improvements in household food consumption and reductions in the number of households having to use coping strategies. Despite the progress, concerns remain about the scalability of the programme given the comparatively high cost per beneficiary.

While modest in size, IMC’s women’s economic empowerment programme has delivered training on business management and leadership and provided seed money to support economic activities; while it fell short of some of its targets, it significantly over-achieved on issues of participation in skills-building activities, engaging over 20,000 women (against a target of 15,000) in 2018. We will continue to use ELFSS TPM to explore questions around the quality and impact of this kind of training in concert with other intereventions[70]. Both Oxfam and Goal, whose projects also involve a level of skills-building/training, will be undertaking end-line evaluations to evaluate impact. We will work with IMC to consider whether some kind of closure learning and/or evaluative exercise as they also wrap up and handover activities.
[70] DFID’s Best Buys guidance on livelihoods interventions based on global evidence indicates that business training alone is a low value, low impact intervention and that to have impact this needs to be paired with other sorts of supporting inventions, such as cash grants, capital etc.

This review echoes the findings of the 2017 AR that while the emergency livelihoods activities of this pillar (FAO, ICRC, SSHF), have achieved better results against targets, the lack of progress on resilience activities (GOAL and Oxfam) is due more to unsatisfactory performance and an extremely challenging operating environment than an inappropriateness of the response. It is important to note that elsewhere in the country, DFID South Sudan’s other resilience programme, Building Resilience through Asset Creation and Enhancement – Phase II (BRACE II), is successfully strengthening resilience (be it in more stable, less challenging locations), having learnt lessons from challenges during its earlier implementation period.

Gender and social inclusion: There were a number of initiatives taken by partners to promote gender equality and address broader issues of equity; the introduction, by Oxfam, of a Gender Action Learning Sets methodology to strengthen food production and income generation and a broader focus on promoting the participation of marginalised groups in programmes and governance-building activities made an important contribution. GOAL trained M&E staff on conducting the Core Humanitarian Standard self-assessment exercise[71] during the first quarter of 2018 which among other benefits, strengthened awareness among staff, partners and communities of responsibilities to improve the quality and accountability of its livelihoods support. IMC provided targeted support to train community leaders and women committee members on GBV prevention, achieving just short of the 1,800 planned beneficiaries.
[71] See https://www.chsalliance.org/self-assessment.

Risks and challenges: Delays in procurement and distribution are a key risk factor linked to FSL programmes although the emergency livelihoods partners achieved some measure of success in pre-positioning with no significant reports about timeliness. For the smaller-scale income generation and resilience programmes, staff recruitment and retention has been a constraint to the performance of projects, particularly for IMC (staff recruitment) and Oxfam (changes in staffing). For resilience programmes, challenges in establishing baselines and in the timely development and implementation of monitoring systems has adversely affected the ability of partners to report on changes over time.

Recommendations[72]
[72] Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action. In some cases, these have been updated to account for changes in context.
- DFID’s engagement with REACH as a HARISS partner offers considerable scope for strengthening IPC analysis and predictive capacity which offers an opportunity to better understand food insecurity and to strengthen the relevance of responses. It will be important for DFID to use the partnership strategically in order to strengthen its own understanding of food security and inform its advocacy.
- As DFID starts to plan the successor programme to HARISS, it should use the opportunity afforded by planned evaluations of Oxfam’s and GOAL’s resilience programmes (and potentially IMC’s IGA also) to identify good practice. More broadly, DFID should seek to look across its investments in HARISS and BRACE II with a view to determining the most efficient and effective models for strengthening resilience in South Sudan.
- As the co-Chair of the Partnership for Resilience and Recovery (PFRR), DFID is well-placed to contribute technical advice to the emerging programme as well as ensuring that practical linkages are made between PFRR and DFID-funded resilience programmes.

## C: DETAILED SCORING

Pillar	Protection and GBV	Pillar Score	A
Risk:	Major	Impact weighting (%):	7
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

Relative to other sectors in HARISS, the level of support to protection programming has been low, at 7.5% (albeit representing an increase of almost 50% on the proportion of the budget allocated to protection in 2017). There were four main HARISS partners which contributed to this pillar; IMC, ICRC, HI and SSHF, with HI project being in inception phase for most of the period of the review. Partner-supported activities included:
- GBV/protection prevention and response activities, including case management, psychosocial support, management of women and girls’ friendly spaces, and awareness raising.
- visits to detainees and restoration of family links as well as training combatants on IHL.
- integrated protection mobile responses (protection/GBV/child protection/mine action).

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)[73]	Output Performance
IMC	Sex and age appropriate case management services provided to survivors of GBV including individualized psychosocial support and safe referrals	8	A
IMC	Appropriate medical care, including prevention of HIV infection, is accessible for survivors of GBV in Jonglei, Upper Nile, Western Bahr El Ghazal and Unity states	8	A
IMC	Safety of women and girls in the community enhanced through GBV risks mitigation activities	8	A+
IMC	Capacity of community structures (community leaders, women's and youth's groups and others), IMC staff and implementing partners in Jonglei, Upper Nile, Western Bahr El Ghazal and Unity states enhanced to prevent GBV	8	B
IMC	Women and adolescent girls empowered with information, social networks and skill building opportunities	10	A+
IMC	Women and girls, men and boys affected by crisis are aware of their rights and entitlements, have access to information	3	B
SSHF	Support to protection services	9	A
ICRC	To help improve conditions for detainees	14	A
ICRC	to help reconnect family members separated by armed conflict and other violence	7	A
ICRC	To promote knowledge and respect for international humanitarian law (IHL) and international human rights law (IHRL)	7	A
HI	Vulnerable individuals (with and without disabilities), families, groups and communities exposed to violence and adversity are empowered with positive coping and solidarity mechanisms	2	C
HI	Improved quality of care, referral and coordination mechanisms in the MHPSS sector at local and national level	2	C
HI	Increased capacity of DFID HARISS team and other HARISS programme actors to mainstream disability within their strategic planning and operation and collect relevant data to measure disability inclusion within their programme in South Sudan	2	C
IOM	Conflict affected populations, especially persons with specific needs, have improved access to basic services and protection through inclusive and participatory approaches	11	A++
[73] Pillar impact weightings are determined by the size and proportion of the partner budget which is utilised to support the particular sector.

Headline results	Partner	DFID Funded Milestone	DFID Funded Results Achieved
Number of people trained on GBV prevention and response	IMC / IOM	1,800 / 300	1,739 / 3,484
Number of people reached with information on GBV, rights and services available	IMC	740,000	778,217
Visits to detainees and training of military and police personnel on International Humanitarian Law	ICRC	n/a	496
Number of people reached with protection interventions	SSHF	57,000	57,000
Number of people benefitting from awareness sessions on disability	HI	500	385

Overall situation: In the first half of 2018, some 2,300 cases of GBV were reported, a 72% increase in reporting of GBV compared to same period in 2017. During the same period, 97% of reported cases in South Sudan affected women and girls, and 21% of survivors were children, of which 79% were adolescent girls, consistent with previous years. Physical violence, commonly by an intimate partner or someone known by the survivor, continues to be the most common form of GBV, accounting for 42% of reported cases. Sexual violence constitutes 20% of reported cases.[74] Despite preventive actions by humanitarian actors, all forms of GBV continue to be reported in and near PoC sites as young men and armed elements acting with impunity often prey on, sexually assault, and loot from women and girls who venture to fetch firewood, cultivate crops or access markets.
[74] OCHA (2018) 2019 Humanitarian Needs Overview, South Sudan, November 2018.

Partner performance: IMC performed well against its core objectives and met or exceeded most of them including the provision of case management for GBV survivors, referrals for clinical management of rape, psychosocial support and community sensitisation on GBV prevention. This included an expansion of the programme as a result of an uplift of £1.774m in June 2018 which increased psychosocial support, women and girl friendly spaces and outreach activities. Performance was also affected by the need for a withdrawal from Akobo following months of tension and negotiation with local authorities.

HI has made a modest contribution in 2018 as a consequence of the partnership starting mid-way through the year (August 2018) and the subsequent slow start-up of its activities; by the end of the review period, the programme had only been operational for 5-months and was still in its inception phase. Despite this, some progress was made in awareness-raising of vulnerable individuals and communities about positive coping and solidarity mechanisms. HI also supported DFID during the HARISS partner day on vulnerability and targeting.[75] Linked to this, discussions were conducted between IMC and HI about the potential for strengthening coordination on disability inclusion.
[75] The partner day included presentations on understanding vulnerability (CSRF), targeting (ELFSS) and disability and vulnerability (HI).

ICRC’s protection focus remained on promotion of knowledge and respect for international humanitarian and human rights law.[76] In addition, ICRC facilitated contacts between family members separated by the conflict and supported family reunifications.
[76] Results are not due from ICRC until June 2019 when the ICRC 2018 Annual Report will be made available to its donors.

SSHF-funded activities targeted the most vulnerable people in need of protection, providing a range of services, including for GBV, child protection and mine action, through field-based partners, as well as through Juba-based ‘Integrated Protection Mobile Teams’ deployed to different locations as needed and in response fast-changing circumstances in order to undertake protection assessments and initiate response activities.

Gender and social inclusion: Equity and inclusion are central pillars of protection work, and partners reported that they have routinely sought to ensure inclusion of marginalised groups, including persons with disabilities and older persons. An example of this is the work of the IOM MHPSS team which has supported Camp Management to ensure the provision of safe spaces in the camp settings for vulnerable people seeking psychosocial support.

Risks and challenges: Constraints to humanitarian access hamper the delivery of protection to the most affected areas of the country and the identification of, and response to the needs of the most vulnerable. Furthermore, the need to respond to immediate life-threatening emergencies has reduced capacity to address other protection concerns such as those of incarcerated or exploited children, and women and girls exposed to harmful traditional practices, as well as housing, land and property concerns that hinder durable solutions for displaced persons. Gender-based violence is pervasive, yet grossly underreported throughout South Sudan due to fear of retaliation from perpetrators and social stigma, particularly for male survivors. Life-saving services and reporting mechanisms are not immediately available to survivors in many of the affected areas. While there is growing recognition of the importance of routinely addressing protection and GBV in programmes, given the context of patriarchal traditions linked to weak rule of law, addressing these deeply held attitudes is both a challenging and long term process.

The protection sector was comparatively well-funded in the 2018 HRP, receiving 55.2% of its budget. In saying this, it is important to acknowledge that this still left a funding gap of 44.8% of its budget ($55.2m).[77]
[77] See https://fts.unocha.org/appeals/646/summary.

Recommendations[78]
[78] Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action. In some cases, these have been updated to account for changes in context.
- DFID’s investment in the partnership with HI and IMC provides important resources to strengthen inclusion across HARISS partner programmes (including on data collection, reporting and programming). Efforts should be made to strengthen understanding among partners and to develop practical approaches to ensure they are inclusive
- There continues to be scope for all partners to strengthen work on PSEA, ensuring adequate policies are in place and implemented, and a zero tolerance approach taken.

## C: DETAILED SCORING

Pillar	MEAL	Pillar Score	B
Risk:	Moderate	Impact weighting (%):	1
Risk revised since last AR?	Y	Impact weighting % revised since last AR?	Y

Under this pillar HARISS has supported the Evidence and Learning Facility in South Sudan (ELFSS) with activities focusing on the provision of third party monitoring of the HARISS programme in addition to evidence generation on what is working (and what is not) in relation to a number of themes (AAP, resilience, multi-year humanitarian).

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)[79]	Output Performance
ELFSS	Third party monitoring	25	A
ELFSS	In-depth evidence papers	25	C
ELFSS	Support to implementing partners on their monitoring, accountability and learning	25	B
ELFSS	Provision of knowledge management services	25	C
[79] Pillar impact weightings are determined by the size and proportion of the partner budget which is utilised to support the particular sector.

Headline results	Partner	DFID Funded Milestone	DFID Funded Results Achieved
Third party monitoring of HARISS partner programmes	ELFSS	60 Fact Sheets[80]	61 Missions / 38 Fact Sheets
[80] Over the course of 2018 the contract for ELFSS was significantly re-negotiated. The target at the end of the contract negotiation, and subsequent contract amendment was 15 TPM fact sheets per quarter (i.e. 60 field missions resulting in 60 factsheets per year).

Overall situation: The ELFSS contract was designed in 2014-15 as a multi-year monitoring and evaluation system to enable iterative learning and generation of evidence for the HARISS programme. After a protracted inception phase, and the submission of the inception report in January 2018, it became evident that a change in outputs and associated contract amendment would be required. This was negotiated over the course of 2018, and was signed by DFID and IMC Worldwide on behalf of the consortium in January 2019. The contract amendment included significant changes to the scope of the services provided by ELFSS and included a reduction to the consortium shape/size. Reasons for the changes are complex, and include challenges internal to ELFSS, as well as to the DFID programme, the procurement process and commercial functions. The new programme fulfils the core needs of DFID, while also offering greater VfM.

Partner performance: The provision of evidence papers, support for MEAL and provision of knowledge management services were all put on hold while the revised contract was being negotiated and for this reason, little progress was made. The most significant contributions to these objectives were the publication of a Good practice Guide on AAP and the development of a prototype of the Knowledge Management Platform, but concerns were expressed about the added value and appropriateness of these products.

The provision of TPM services through ELFSS, however, has been a significant success, and the generation of high quality monitoring has strengthened the ability of DFID to understand progress against HARISS outputs and to hold its partners to account. The quality of TPM reports has been good, the team have been responsive to DFID requests about geographical and partner priorities, and in addition to fact sheets, in-person debriefs have provided valuable evidence to DFID. In 2018, ELFSS undertook TPM of all HARISS partners (excluding SSHF and ICRC) which included establishing new TPM relationships with WFP and IOM in addition to engaging with different types of programming (e.g. IRRM modalities).

Discussions with DFID staff highlighted a number of ways in which TPM reports and feedback have influenced decision-making which go far beyond the focus on project progress and partner performance. Examples of influencing have included TPM observations on the relevance of livelihoods packages, appropriateness of distributions, community perceptions of the value of cash-based interventions, and evidence about women’s empowerment. By the end of 2018, there was a significant volume of TPM reports which offered an important opportunity to draw out and synthesise cross-portfolio issues and contribute to learning, which was supplemented by DFID’s own field trips.[81]
[81] In 2018, members of DFID’s HLT undertook 21 field trips to Bor, Malakal, Bentiu, Rubkona, Wau, Renk, Rumbek, Ganyiel, Akobo and Juba.

Gender and social inclusion: Engagement between DFID and ELFSS has revealed the knowledge that TPMs have of local dynamics and power within communities. Monitoring reports underline this as TPM have assessed progress against issues of gender and social inclusion where these are explicit programme objectives, in addition to where they are cross-cutting.

Risks and challenges: For ELFSS the biggest challenge was the delays to full contractual implementation due to the protracted process of contract negotiation. After the suspension of non-core activities in January 2018, there was also risk of disruption to the delivery of TPM although significant delays were avoided.

For TPM specifically, the key risks were their access to and engagement with partners, their ability to gain access to monitor HARISS partner activities, and their ability to generate compelling evidence that could contribute to decision-making and prompt change. Engagement between DFID and ELFSS helped to strengthen understanding of how TPM engage with partners and beneficiaries and suggests that they possess a good understanding of conflict sensitivity and ethics. It also revealed the steps that have been put in place to reduce possible harm to researchers, enumerators, community members and interviewees.

Recommendations[82]
[82] Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action. In some cases, these have been updated to account for changes in context.
DFID should facilitate strong relationships between ELFSS, HI, and the Conflict-Sensitivity Resource Facility, so as to optimise assessment of, support to strong, inclusive and conflict sensitive operations among all implementing partners in South Sudan.

## C: DETAILED SCORING

Pillar	Enabling Environment	Pillar Score	A+
Risk:	Moderate	Impact weighting (%):	8
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

Under this pillar HARISS has supported the Logistics Cluster (LC), United Nations Humanitarian Air Service (UNHAS) and enabled the provision of specialist technical advice to key organisations (Standby Partnerships). Also included are the efforts by HARISS partners to strengthen monitoring and community engagement. Activities included:
- Providing logistical support to all humanitarian partners through the cluster system and safe air travel services for the humanitarian community
- Addressing key gaps in technical expertise within coordination and common service functions.
- Community engagement and monitoring by selected HARISS partners.

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)[83]	Output Performance
IOM	Conflict-affected populations benefit from better informed, more sustainable and locally-owned humanitarian response	11	A+
FAO	Evidence-based humanitarian response coordination, planning and monitoring	6	A
GOAL	RECOVER management is adaptive and informed by communities voices and feedbacks, and MEAL	3	A+
UNHAS	Efficient provision of common logistics services, including cargo transport, common storage capacity and coordination and information sharing	34	A+
UNHAS	UNHAS services provided to its users as planned, including passenger services, light cargo transportation and emergency relocations/evacuations	34	A
UNHAS	Synchronisation between LC & UNHAS improves the efficiency of the intervention for Rapid Response missions when both operations are called to respond within a short timeframe	3	A++
Standby partners	Support to surge and thematic humanitarian coordination and leadership capacity	4	A
SSHF	Education	7	A
[83] Pillar impact weightings are determined by the size and proportion of the partner budget which is utilised to support the particular sector.

Headline results	Partner	DFID Funded Milestone	DFID Funded Results Achieved
Percentage of priority and non-priority locations served	WFP UNHAS	90% and 60%	100% on both
Number of locations served	WFP UNHAS	55	57
Number of passengers transported per month	WFP UNHAS	6,840	8,221
Number of agencies and organisations using humanitarian air services	WFP UNHAS	285	297
Proportion of beneficiaries who know where to complain/provide feedback	GOAL	90%	87%

Overall situation: In addition to annual physical constraints created by rains and poor road conditions, active armed conflict, restrictions of movements, attacks against humanitarians and assets, and bureaucratic impediments continue to seriously curtail humanitarian access. At the beginning of the year, it was estimated that about 1.5 million people lived in areas facing high levels of access constraints – places where armed hostilities, violence against aid workers and assets, and other access impediments
render humanitarian activities severely restricted, or in some cases impossible.[84]
[84] OCHA (2018) 2019 Humanitarian Needs Overview, South Sudan, November 2018.

Partner performance: LC and UNHAS, both managed by WFP, performed well in 2017 and have achieved very strong results again, in 2018. The outputs were consistently delivered on time and outcome indicators were met or exceeded.

Over the course of the year, UNHAS flew an average of 8,221 passengers per month (120% of its target) from 297 (target 285) agencies to 57 locations (target 55). Importantly, given the context in South Sudan, it was able to respond to all of the requests made for security and medical evacuations. UNHAS made some changes to its fleet in 2018 and secured savings through longer-term aircraft contracts and improved fuel arrangements. The LC provided essential services to humanitarian agencies which included transportation of cargo, warehousing, operation information management and representation in key forums and successfully served all of the priority locations in South Sudan as well as the non-priority locations. Both LC and UNHAS operate with flexibility in order to best meet the needs of the humanitarian community; for example, the LC adapted its programming to increase road convoys and river transport which led to a reduction in the requirement for air transport which achieved significant cost-savings. In December 2018, DFID’s IRF approved £151,782 funding for the purchase of four ambulances to support EVD preparedness activities. Both the LC and UNHAS have also supported preparedness through other means which include the construction of treatment units, air lift of EVD-related materials and preparation of common storage facilities in priority areas.

Engagement with communities for the purpose of programme-design and monitoring is a key aspect of humanitarian accountability as well as a GB priority. DFID has emphasised the importance of mechanisms to engage community members across its programmes, but has funded specific initiatives for GOAL, FAO and IOM. While each of these is a work-in-progress, there is a growing evidence-base of their importance for ensuring the relevance of assistance, the delivery of inclusive programmes and avoiding the potential for violent conflict. For example, GOAL’s resilience programme works with customary institutions which contributes to conflict sensitive programming; working with these institutions builds on existing forms of social capital to address challenges and strengthen leadership to effectively resolve localised conflict and enhances a community’s capacity to mitigate and resolve conflict.

The final component of the ‘enabling environment’ pillar is DFID’s standby partners which played an important role in supporting the HARISS programme and wider humanitarian community in 2018. The focus of the support provided by the standby partnerships was supporting surge for the EVD preparedness work (three SBP across WHO and UNICEF) and the provision of specialist support to protection/GBV coordination (with UNHCR and UNFPA). DFID has also supported a HSOT Ebola Preparedness advisor within the British Embassy, who has played an instrumental role in driving cross-partner/system ebola preparedness with CDC.

While outside the scope of the 2018 review, DFID’s partnership with REACH, which commenced in Novermber 2018, has the potential to make an important contribution to the enabling environment pillar of the HARISS programme through its focus on real-time analysis and early warning of food insecurity, community perceptions of humanitarian assistance and the capacity of the humanitarian community to better understand displacement patterns.

Risks and challenges: The risks and challenges for LC and UNHAS projects are similar to other sectors: access constraints due to unfavourable weather or bureaucratic impediments, possibility of insufficient funding, unforeseen demand and insecurity. Likewise, the success of Standby Partnerships relies on the availability of quality secondees, which can be a challenge given the challenges of obtaining high quality human resourcing for South Sudan.

It is noteworthy that the focus of this pillar is on DFID’s efforts to mitigate the risks and challenges surrounding its programme and the broader achievement of peace and human security in South Sudan. This review considers that DFID’s efforts to address conflict sensitivity, promote risk management and strengthen community engagement were key strengths of its response. In addition to seeking to mainstream these approaches across HARISS partners, DFID used the evidence from HARISS to drive its policy and influencing with donor partners and the government of the Republic of South Sudan.

Recommendations[85]
[85] Recommendations from the 2018 review incorporate recommendations from the 2017 review that continue to have relevance and require action. In some cases, these have been updated to account for changes in context.
While the approach taken by HARISS partners to community engagement has improved over time, there is still scope to better understand how responsive HARISS partners are to feedback. The development and roll-out of REACH’s community perceptions tracking mechanism will offer an additional resource to monitor and strengthen the relevance of partners’ programmes.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Assess VfM compared to the proposition in the Business Case, based on the past year
Although this review offers significant evidence of initiatives to strengthen VfM, the aspirations outlined in the Business Case (BC) have not been realised, in large part because South Sudan has continued to be a country in conflict, rather than one benefitting from peace. As a consequence, the flex built into the programme to accommodate a move from short-term humanitarian programmes to longer-term resilience has not been used. Conversely, there has been a need for the programme to flex in the opposite direction, in order to permit it to address an increase in short-term, humanitarian need. This has had a significant impact on the proportion of activities targeted towards the humanitarian end of the spectrum where the mixture of conflict and poor infrastructure has meant that markets do not function adequately in many areas. This has limited the opportunities to use cash or market-based approaches which may have offered greater VfM.

The BC correctly identified the main cost drivers as the cost of supplies/inputs, transportation, bureaucratic impediments, exchange rate volatility, security and staffing which converge to make operating costs for humanitarian agencies and the delivery of programmes extremely high. Additionally, humanitarian organisations have lost significant volumes of aid to looting, raids on compounds, theft, and other instances of criminal capture, not to mention the costs associated with regularly relocation and evacuation of staff members because of any one of these factors.

Despite these challenges, HARISS partners have performed well in analysing and strengthening VfM which has been an area where there has been significant progress made in 2018. Key areas of improvement which are included in the table below are as follows:

- In a country with very few kilometres of tarmac road and a lengthy rainy season, despite its comparatively low cost, road transport can be extremely arduous. DFID have provided funding to WFP to fix roads which have reduced the need for more costly air transport. WFP, the main trainsporter of commodities across the country, in 2018 managed to reduce dispatches by aid from 29% to 19% (compared to 2017). WFP maintenance of the Juba-Rumbek road and exploration of new river routes reduced the need for air delivery, saving WFP an estimated $63 million[86].
  [86] WFP estimate in 2019 that a metric tonne of food cargo transported by road costs $257. This compares to $398 for a tonne transported by river and $2,950 by air. Transport costs are similarly 10 times more expensive by air compared to road transport.
- A focus on pre-positioning by road and river during the dry season has saved money as it costs less than using air transport which is necessary during the wet season. WFP have propositioned over 132,000Mt of food across 50 warehouse locations across the country (against a target of 140,000Mt). This is an extraordinary achievement. UNICEF also report that early HARISS funding in 2019 has enabled achievement of 100% of their DFID HARISS targets for WASH, health and nutrition. DFID’s MYF has provided the assurances of funding that are required for them to do this and has ensured that aid is in the right place at the right time.
- Significant investment in terms of beneficary registration and vertification in 2018 from IOM and WFP. This has helped reduce duplication and increased the potential for providing more targetted assistance. WFP estimate this has saved $2million in operational costs in the second half of 2018. In some locations authentication has led to a 14% reduction in the number of people.
- While still modest in scale, HARISS has prompted greater use of cash and vouchers among humanitarian agencies which can offer cost benefits when compared with food commodities as there are fewer logistics requirements. Cash also provides greater choice to recipients which increases the effectiveness of aid.With DFID support, WFP cash programming reached over 139,000 people.
- The focus by DFID on understanding and addressing bureacratic impediments such as taxation on aid has provided an enabling environment for assistance in addition to reducing costs.

DFID has also prompted partners to strengthen their own internal analysis of VfM; most partners have developed VfM matrixes which have been used to identify and drive VfM across the HARISS programme. During the year there was also support provided to partners by ELFSS to strengthen these matrices.

VfM measure	Approaches adopted	Partners
Economy	Transportation has been a cost which has seen considerable economies being achieved, largely as a result of a shift to cheaper forms of transport (from air to road or river transport) or through the use of innovative all-terrain vehicles which can travel on land and water. / There have been cases where transport, particularly air, has been shared by several agencies or where freight has been consolidated in order for capacity to be fully utilised. / Prepositioning of commodities offers significant VfM given that failure to achieve this before the rains necessitates costly air transport (estimated to be over 10 times higher per MT). / Several agencies have used their procurement systems and/or competitive tenders to drive down costs, particularly for high volume or value items such as food commodities or therapeutic foods.UNICEF estimate that this approach has saved them between 15-20% of the cost of similar supplies in the market for lower volume procurement. There was also evidence of Long-term Agreements increasing the timeliness of goods	ICRC / UNHAS / LC / Medair / UNICEF / WFP / IOM
Efficiency	Significant efficiencies have been achieved by co-locating SAM, MAM and health provision (UNICEF report a 90% co-location of SAM/MAM services with WFP). / Some agencies have switched from paper-based survey platforms to smart phone and tablet-based systems which has offered efficiencies in data transfer and in seamless analysis. / One agency has recruited and trained national staff based on a rigorous results-based framework which has increased efficiency as competent national staff based in Juba/field offices decrease reliance on international staff, increase response time (recruitment/deployment) and utilise fewer resources to reach outputs. / The use of solar pumps for water provision has reduced costs while still continuing to meet Sphere standards for the quantity of water. / The use of biometric registration offers efficiencies over a period of time as registration is transferrable which reduces the need for costly re-registration exercises. This means of registration also reduces the potential for duplications and in 2018 has achieved an impressive reduction in the number of ‘ghost’ beneficiaries.	Medair / WFP / UNICEF
Effectiveness	The production of local seeds has been supported alongside improving and tailoring agricultural kits to strengthen their effectiveness. / ELFSS TPM have noted the importance of strengthening training in order for farmers to achieve the best yields from seed varieties / Integrated programmes offers the potential to significantly improve the achievement of outcomes. While there is significant latitude to strengthen integration across programmes, linkages between SAM and MAM programming alongside health strengthen the effectiveness of efforts to treat malnutrition. / Targeting is an area that offers potential for strengthening the effectiveness of programmes through the use of inclusive vulnerability analysis. / In several cases, DFID’s decision-making to restrict the scope of services (ELFSS) or to reduce the duration of contracts for poor-performing partners (Oxfam) offers VfM as it reduces the risk of poor value spend. / Through WFP’s SCOPE CODA system, frontline workers can for example record information; track the nutrition and health status, of a young child or a pregnant woman; identify when someone has recovered; and indicate whether the treatment has been successful. / The IRRM strengthens the efficiency and effectiveness of humanitarian assistance through its use of integrated assistance.	FAO / ELFSS / UNICEF / WFP / HI / Oxfam
Equity	IOM’s data for the PoCs is disaggregated by age and gender and beneficiary data are collected and compiled in a timely manner for use in informing service provision. / The inclusion in programming of both host and displaced communities by several HARISS partners (including GOAL, FAO, IOM, IMC) has ensured greater equity as well as reducing the risk of conflict over resources.	IOM, IMC, FAO, GOAL

While all HARISS partners have worked with DFID on VfM, it is important to note that ICRC’s engagement can be a challenge due to the centralised nature of its management, which means that while it publishes some information on unit costs, it rarely provides additional information to DFID on VfM.

Different levels of unit cost information is available across the programme with some partners providing unit costs of inputs, some outputs and some at more an outcome level. The different depths of programming interventions (i.e. short-term emergency distributions vs. multi-sectoral resilience) makes cross programme comparision and synthesis of unit costs difficult. This was work that was originally planned with support from ELFSS within HARISS, but due to the scaling back of this contract did not progress beyond some intial engagement with partners on individual VfM frameworks. In the successor programme to HARISS, DFID should look to build a standardised framework with indicators which read across different projects and enables synthesis. This should include a focus cross programme key costs and key cost drivers (economy), as well as common measures of quality and timeliness (efficiency). Quantative VfM information is much weaker across UN partners, with the exception of WFP. This is in part linked to overall HQ level agreements on what can (and can’t) be shared locally in terms of financial information given overarching Memorandums of Understanding.

Recommendations:
- Partner VfM frameworks have been a useful tool at the project-level, but it remains a challenge to synthesise and draw together information across partners to provide a cross-portfiolio view on VfM. Originally the DFID team planned to work with ELFSS in knitting other VfM indicators and analysis across-portfolio, but with the significant revision of the ELFSS contract this has not been possible. Given this is the last year of HARISS, there will be limited scope for DFID to embedded a cross-portfolio approach. Thinking forward, DFID should prioritise the set up a VfM framework for the successor programme to HARISS (due to start in summer 2020).
- Incorporating equity in to partner VfM indicators was a priority for 2018. Progress has been made for a number of partners, but not all. Partners that are yet to include equity include WFP, FAO, and UNICEF.

Ongoing VfM of the programme
Despite South Sudan’s continuing reliance on humanitarian assistance, the progress that HARISS partners have made in identifying opportunities to strengthen VfM, linked to the important role played by HARISS in responding effectively to humanitarian need makes it essential that the programme continues to receive support from DFID.

In 2018, DFID’s Internal Audit Department’s assessment of DFID South Sudan noted that ‘DFID-SS has collaborated with partners to increase knowledge and capacity to achieve VFM on the programme such as hosting the partner training day’. The partner day referred to by IAD offered HARISS partners an important opportunity to better understand VfM and to use the opportunity to explore measures to strengthen VfM in their programmes.

As the HARISS programme enters its final year, a focus should be placed on proving and improving means of monitoring VfM and in strengthening analysis of VfM measures as a contribution to the design of the next iteration of the programme. It is anticipated that the ELFSS TPM synthesis on VfM will make a valuable contribution to this. A second important area for learning is on MYF, and it will be important that the evidence gathered by DFID’s advisors and ELFSS TPM is used to better understand the opportunities and limits for replicating this model in the HARISS successor programme (see table below).[87]
[87] The table was reproduced from ELFSS (2019) ELFSS Learnings from HARISS: Revisiting Assumptions of Multi-Year Funding, Synthesis Study 1. May 2019.

Assumed benefits of MYF	Evidence from the HARISS programme
Design and planning
More time to plan interventions leads to higher-quality project design	Among partners implementing projects that are exclusively funded by HARISS, the longer design phase helped shape which interventions were pursued and allowed for community engagement, which helped ensure relevance. Outside these HARISS-specific programmes, evidence that MYF supports better project design is limited.
Analyses & needs assessments / are of higher quality	While longer time frames allowed for more analysis and needs assessments in some cases, most are not as nuanced as expected due to general shortcomings in contextual analysis as well as standardised implementation norms.
Implementation
MYF leads to improved cost, / operational and administrative / efficiencies	The time frames of MYF allowed for more efficient procurement processes and lowered transaction costs. MYF could allow for better staff retention under the right institutional context (which is seen as enhancing programme quality), but current partners’ internal policies prevent this.
MYF can give flexibility and stability to an organisation	The ability for MYF to give stability to a partner’s overall programming is dependent on the proportion of the total budget that HARISS funding reflects. The ability to leverage resources and share costs across a partner’s portfolio is highly valued.
MYF supports higher order benefits (improved skills & relations)	MYF can allow the time to build the capacity of staff and stakeholders, as well as facilitate better community engagement.
Contingency funding & performance-based indicators / support flexibility & better results	In practice, mechanisms that enhance flexibility and the ability to mitigate risk within MYF, such as contingency funding, uplifts and the Results Compact, are not well linked to planning and, in some cases, may result in mixed incentives.
MEAL
MEAL systems & activities are / Strengthened under MYF	M&E systems tend not to change with MYF, but partners note that MYF time frames allow for greater emphasis on M&E. MYF may improve the ability to monitor programme impacts, but M&E systems do not systematically track the specific impact of MYF. HARISS has led to better accountability because it enables investment in feedback mechanisms and more time to respond to this. MYF facilitates opportunities for learning to some extent, but it must be actively encouraged within the organisation.
Partnerships
MYF enables stronger partnerships	All partners say that MYF facilitates better capacity building of downstream partners, but none are systematically tracking the extent to which any benefits of MYF are being passed on. Ultimately, a partners risk tolerance and a desire to maintain leverage play a large role in the duration of a sub-contract that they are willing to grant, and ultimately to number of MYF benefits that are translated to downstream partners.

While some assumptions about MYF have been realised by the HARISS programme, there are important benefits that have not been passed down to partners in practice and it is these aspects that DFID will need to address in the future.

Recommendations
- There is significant scope for DFID to better understand the value that UN agencies achieve through sub-contracting NGOs. The ELFSS synthesis revealed that the benefits of MYF are rarely passed across to partners including measures that may achieve VfM. This is an issue that has received dedicated attention from the HLT which offers important evidence of issues that DFID should seek to address in future.
- The ICAI visit to South Sudan questioned whether DFID has sufficiently reliable information on management overheads throughout humanitarian delivery chains to determine whether they are justified. Better sight of these may offer the potential to strengthen VfM.
- The HARISS programme has struggled to identify scalable resilience models, in large part because of the high cost and low transfer of value to beneficiaries. As the programme enters its final year, efforts should focus on a comparison of indicators, costs and value for money of different aspects of the programme.

Quality of financial management
The quality of financial management varies between partners although it has benefitted from regular scrutiny from DFID staff including as part of the partner review process.

In the underlying partner reviews, partner financial management was scored as follows[88]:
[88] Reach was not scored as the project only started in November 2018.

Partner	Financial Management
	A+ (Delivered 100% against their forecast, assets clearly monitored and accounted for, and audits covering all reasonable periods of project spend)
LC/UNHAS, IOM, FAO, ICRC, Medair, IMC	A (Delivered within 95-105% against their forecast, assets clearly monitored and accounted for, and audits covering all reasonable periods of project spend)
WFP, UNICEF, GOAL, IMC Worldwide	B (Either moderately did not deliver against their forecast (80-95% underspent or 105-120% overspent) and/or demonstrated poor asset management, and/or and audits only covering some periods of project spend)
Oxfam, HI	C (Underspent (or overspent) by 20% + for 2 or more consecutive quarters, and/or has no asset management in place, and/or has no audit cover in place)

In part this reflects the nature of projects and the difficulty of operating in the South Sudanese context, with new partners (HI) struggling to get up and running as quickly as anticipated and both resilience projects (GOAL and Oxfam) more prone to variations in forecast and spend due to the difficulties of implementing resilience projects. However, it also reflects the ability of partners to manage finances well, and to communicate that clearly to DFID. Central agreements with WFP at a headquarters level mean DFID receives only headline annual financial forecasts. Substantial variances occurred on some reports (UNICEF, Oxfam, HI) due to predictable reasons (eg using funds to pre-position stocks before the rainy season), and others failed take account of overspend/underspend in the next quarter’s forecast, with inevitable knock-on effects. There are indications that procurement is an area of weakness for come partners (Oxfam, HI), with associated impacts on VFM due to associated delays, poor financial planning, higher costs and the opportunity afforded for procurement fraud. Inaccurate financial information in reports and commercial documents (IMC Worldwide) was also a problem.

More positively, some partners have been very open and forthcoming in financial discussions (IOM), have proven accurate forecasting is possible (Medair), have trialed new approaches to improve accuracy (GOAL), and have been able to efficiently re-allocate budget following major unpredictable changes (IMC).Annual audited accounts (or copies of accounts) for 2017 have been received for all HARISS partners and in all cases were certified to be true, fair and unqualified by independent auditors.[89] DFID should continue to seel project level financial audits for partners where this is permissible within funding arrangements (i.e. NGO, private sector), and particularly were there have been concerns with the quality of financial reporting. DFID should also continue to review and scrutinise internal audits conducted in South Sudan. For programming 2018 we have received internal UN audits for UNICEF, UNDP (including SSHF) and WFP at the country-office level.
[89] Humanity and Inclusion’s and Reach’s programmes commenced in 2018 and therefore will not submit accounts at the end the financial year.

E: RISK

Overall risk rating: Major – HARISS overall

Overview of programme risk
The top 3 HARISS risks identified in the final quarter of 2018 were:[90]
[90] DFID HARISS Risk Matrix, Overall HARISS risks, November 2018.
1. Deterioration in context and increased humanitarian need leads to partners and DFID being unable to flex and respond appropriately to meet humanitarian need, putting lives at risk.
2. Insecurity leads to partners either being at harm or having to suspend activities and therefore not reaching beneficiaries and not being able to monitor activities.
3. Inadequate due diligence/controls (including of downstream partners) fails to identify/address risk of sexual exploitation and/or fraudulent activities.

Risk Management and Mitigation
Risk is managed on HARISS through an overall programme risk matrix which articulates HARISS programme risk appetite, including the appetite for different risk categories. This is updated on a quarterly basis, using information from partners' quarterly reports, risk matrices, delivery chain risk mapping and meetings. Light touch HARISS risk updates are also conducted on a monthly basis. 2018 has seen significantly more scrutiny from HLT on issues of risk and a greater focus on engaging with HARISS partners which has permitted a much better understanding of mitigation measures as well as strengthening transparency.

As referred to above, all HARISS partners are required to update their risk matrices on a quarterly basis and submit them with the narrative reports. These outline top delivery chain risks, mitigation measures and risk owners. They are analysed and discussed during partner meetings. These are then reported to the Programme Board and incorporated into office-wide risk assessments.

The DFID South Sudan team has also maintained a focus on communicating the importance of risk management to partners in addition to taking a lead on initiating discussions with HARISS partners on aid diversion including as the main topic for one of the Partner Days.[91] While the issue arose primarily as a consequence of the circulation of a paper analysing aid diversion,[92] DFID has subsequently played a catalytic role in creating space for discussion as well as providing clear guidance on tackling the conditions which perpetuate it with its partners. It has also convened a donor group to advocate on aid diversion.
[91] During the day, sessions were held on risk management and scenario planning in addition to a discussion about DFID’s risk register.
[92] United States Institute of Peace and Overseas Development Institute (2018) The Unintended Consequences of Humanitarian Action in South Sudan, Headline Findings, January 4th 2018.

In addition, DFID has continued to strengthen partner delivery risk maps and tracked due diligence actions. As part of this, a due diligence refresh was undertaken for several partners including FAO, IOM, WFP, and the SSHF between April and September 2018. There was also a safeguarding refresh for all DFID’s partners.

DFID’s Internal Audit Department visited in June 2018. Overall IAD found DFID South Sudan to have well designed controls and that controls were operating, and that the office had a mature control and risk awareness (with an upward trajectory). The HARISS programme represents approximately over 60% of DFID South Sudan’s spend. It is noteworthy that the 2018 audit report found controls on HARISS to be have been designed adequately, although a challenge given the operating environment to bring risk fully within appetite in practice. On financial management, the report identified areas of good practice around payment authorisation, and suggested increased scrutiny of exchange rates.[93]
[93] This was reported in the 2017 review and has been reproduced for reference purposes.

DFID South Sudan have implemented the majority of recommendations from the 2018 IAD visit. These were on addressing contract management challenges under ELFSS and enhancing it safeguarding assessments and controls. On exchange rate fluctuation challenges encountered by some partners, this is being progressed, but it is an ongoing issue given the operating environment. The audit also concluded that DFID South Sudan has made significant progress in its risk management and the upskilling its partners in this area.

Recommendation
The overall risk rating continues to be ‘major’ and at the ceiling of DFID’s risk appetite. While the approach of HARISS to risk management has been endorsed by DFID’s IAD, this will require continued prioritisation of the team.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery against the planned timeframe
There have been improvements in the timeliness of delivery in 2018 as evidenced in the results outlined in this review. This has been due, in large part, to successful pre-positioning which has received strong support from the Logistics Cluster and UNHAS. Where there have been concerns about the timely delivery or broader performance of HARISS-funded projects, DFID has taken a responsible approach to seeking solutions and engaging with partners.

Performance of partnerships
There are 13 direct ‘tier 1’ partners under HARISS, many of whom then have multiple downstream partners. These include the ICRC, a pooled fund (SSHF), a commercial partner delivering ELFSS and UN and NGO partners. While the performance of DFID’s partners has generally been satisfactory there are a number that have over-achieved and a smaller number that have under-achieved. Where this has been the case, DFID has, in the first instance, sought to provide support to address challenges, and in the event that performance does not improve, has initiated performance improvement plans (PIP). PIPs were agreed with two HARISS partners in 2018; one of the partners was successful in addressing the performance concerns and graduated out of the PIP mid-way through the year, while the other PIP ended early and the decision was taken to move to an early managed wind downDFID has been working with the partner to facilitate a responsible and conflict-sensitive exit. As discussed under the MEAL pillar, concerns about the performance of ELFSS was followed by a protracted process of contract negotiation which resulted in agreement on a reduction of services.

In addition to regular engagement (regular meetings, quarterly reports, field trips, use of TPM, etc) DFID have also been proactively incentivising performance improvements – both in delivery and in partner performance – through the use of Results Compacts with the UN organisations. At the time of writing results compacts for UN agencies were being assessed for 2018, and given this is the second year of implementation there is still substantive learning for DFID and partners.

Linked to partner performance, during 2018 DFID has sought to strengthen its understanding of the linkages between its ‘tier 1’ partners and their downstream partners, particularly local and national NGOs. This has been part of a broader set of discussions about how to strengthen localisation in South Sudan. From a practical perspective, there is now greater understanding of key capacity gaps, concerns and risks faced by local/national NGOs engaged in HARISS which provides an important agenda for change in addition to offering the potential to strengthen delivery capacity and contribute to progressing GB localisation commitments.

Recommendation
During 2018, DFID has strengthened its knowledge and understanding of partnership practices between international organisations and local/national NGOs which will be further strengthened by ELFSS TPM synthesis studies on partnership and localisation. These inputs will complement DFID’s own analysis and offer an agenda to drive positive change in partnerships in the HARISS programme as well as in South Sudan more broadly.

Asset monitoring and control
All partners maintain asset registers and have policies in place for asset management. For UN organisations (including SSHF, as funds are channelled through UNDP)[94] and ICRC, assets are managed in accordance with UN/ICRC policies and procedures and DFID-SS have little oversight of the details (although policies were assessed during due diligence assessments prior to funding).
[94] This arrangement will change at the end of 2019 as OCHA will take over Managing Agent responsibilities from the UNDP Multi-Partner Trust Fund.

For NGOs and commercial partners, DFID have undertaken periodic spot-checks including as part of the annual partner review process. While the majority of partners have been assessed as having adequate systems in place, there are a number of issues that were highlighted in the reviews and which will require follow-up. As projects close with the final year of HARISS, a key focus will be responsible project exit and the management/transfer of project assets.

Annual Review Process
This review was undertaken in two stages; an initial set of HARISS partner reviews was undertaken by members of the Humanitarian and Livelihoods Team with the support of cross-cutting advisors in DFID South Sudan. An external reviewer then used these inputs supplemented by other programme data, and interviews with DFID staff and partners to prepare the portfolio-level review. The draft portfolio-level review was quality assured and approved by the HARISS programme Senior Responsible Officer (SRO) and Head of Office.

The revised methodological approach for this review (i.e. a focus on partner performance and logframes assessed within a result framework) was agreed with the DFID Better Delivery Department.

The review here is intended to assess HARISS as a portfolio and its contribution to the wider humanitarian and resilience situation in South Sudan. It does not provide a summary of all the partner-reviews.

DFID field trips were limited by security constraints, but a number were carried out in the months leading up to the partner reviews and helped to inform them which included 21 visits including to Bor, Malakla, Bentiu, Rubkona, Wau, Renk, Rumbek, Ganyiel, Akobo and Juba. Additionally, the review has drawn on third-party monitoring reports from ELFSS, across multiple partners and locations. These routinely include beneficiary feedback on the contribution that programmes have made to meeting humanitarian needs and supporting recovery. Communities input from TPM reports was incorporated into each of the partner reviews which were reviewed to inform this AR.
ACRONYM LIST

AAP	Accountability to affected populations
AR	Annual Review
BSFP	Blanket supplementary feeding programme
CCCM	Camp Coordination and Camp Management
CS	Conflict sensitivity
DFID	Department for International Development
ELFSS	Evidence and Learning Facility in South Sudan
ERT	Emergency response team
EVD	Ebola Virus Disease
FAO	Food and Agriculture Organisation
FSL	Food security and livelihood
GAM	Global acute malnutrition
GB	Grand Bargain
GBV	Gender based violence
GUN	Greater Upper Nile
HARISS	Humanitarian and Resilience in South Sudan
HC	Humanitarian Coordinator
HCT	Humanitarian Country Team
HI	Humanitarian and Inclusion
HNO	Humanitarian Needs Overview
HPF	Health Pooled Fund
HRP	Humanitarian Response Plan
ICRC	International Committee of the Red Cross
ICWG	Inter Cluster Working Group
IYCF	Infant and young child feeding
IDP	Internally displaced person
IMC	International Medical Corps
IOM	International Organisation for Migration
IRF	Internal risk facility
IPC	Integrated Food Security Phase Classification
LC	Logistics Cluster
MAM	Moderate acute malnutrition
MEAL	Monitoring, evaluation and learning
MHPSS	Mental health and psychosocial support
MYF	Multi-year funding
NFI	Non-food item
NGO	Non-governmental organisation
OCHA	Office for the Coordination of Humanitarian Affairs
OTP	Outpatient Therapeutic Programme
PMC	Project Management Committees
PoC	Protection of Civilians
IRRM	Integrated rapid response mechanism
SAM	Severe acute malnutrition
SGBV	Sexual gender based violence
S-NFI	Shelter – Non-food item
SRO	Senior Responsible Officer
SSHF	South Sudan Humanitarian Fund
TPM	Third Party Monitoring
UNDP	United Nations Development Programme
UNHAS	United Nations Humanitarian Air Service
UNICEF	United Nations Children’s Emergency Fund
UNMISS	United Nations Mission in South Sudan
VfM	Value for Money
WASH	Water, sanitation and hygiene
WFP	World Food Programme

Annex 1: Humanitarian context maps

Map 1: Location and number of IDPs and refugees, South Sudan[95]
[95] OCHA (2017) South Sudan Humanitarian Response Plan 2018, November 2017.

This map below provides the Humanitarian Country Team’s shared understanding of the crisis in South Sudan, including the most pressing humanitarian need and the estimated number of people who need assistance. It represents a consolidated evidence base and a joint process of strategic response planning.[96]
[96] Note: The boundaries and names shown and the designations used on the South Sudan maps do not imply official endorsement or acceptance by the United Nations. Final boundary between the Republic of South Sudan and the Republic of Sudan has not yet been determined. Final status of Abyei region is not yet determined.

Map 2: Severity of need in South Sudan, 2018

This map presents an overview of where humanitarian needs are most severe across sectors. It is based on a variety of indicators for each county, including: the number of displaced people, food insecurity and malnutrition rates, number of violent incidents and casualties, number of children separated from their families, disease outbreaks, vaccination coverage, number of schools attacked, and access to safe water sources and improved sanitation.[97][98]
[97] OCHA (2017) South Sudan Humanitarian Needs Overview 2018, November 2017.
[98] Note: The boundaries and names shown and the designations used on the South Sudan maps do not imply official endorsement or acceptance by the United Nations. Final boundary between the Republic of South Sudan and the Republic of Sudan has not yet been determined. Final status of Abyei region is not yet determined.

The map in bottom left hand corner depicts the severity of need 12-months earlier in 2017. It uses the same indicators and thus provides a comparison of needs between the two years.

Map 3: Humanitarian access constraints in South Sudan in 2018[99][100]
[99] OCHA (2018) South Sudan Humanitarian Response Plan 2019, November 2018.
[100] Note: The boundaries and names shown and the designations used on the South Sudan maps do not imply official endorsement or acceptance by the United Nations. Final boundary between the Republic of South Sudan and the Republic of Sudan has not yet been determined. Final status of Abyei region is not yet determined.

Access constraints drive and magnify humanitarian needs by cutting people off much-needed assistance and protection. Tenuous access and a lack of safety assurances regularly prevent emergency assessment and response, as was the case in mid-2018 to an estimated 100,000 people in central Unity and 28,000 people in the greater Baggari area in Western Bahr el Ghazal.

Insecurity and violent acts against humanitarian staff and assets regularly obstruct access or force the relocation of staff and suspension of operations, as was the case in Maban in July 2018. Consistently, nearly half of reported access incidents are violent in nature and South Sudan continues to report the highest number of violent incidents against humanitarians globally, including casualties. The vast majority of these are against South Sudanese staff. Operational interference, restrictions of movement and bureaucratic impediments also persistently challenge and delay access to reach people in need. Consistent, safe and unhindered humanitarian access is critical to allow for close monitoring and provision of assistance in priority areas to prevent a further decline in humanitarian indicators.[101]
[101] OCHA (208) South Sudan Humanitarian Needs Overview 2019, November 2018.

Map 3: Comparative analysis of South Sudan IPC maps for January 2018 and September 2018[102]
[102] See https://reliefweb.int/sites/reliefweb.int/files/resources/South_Sudan_IPC_Analysis_Key_Messages_-_28_September_2018.pdf.