## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe. |  |  | April 2017 | April 2017-March 2018 | April 2019-March 2019 | April 2019-Oct 2020 | 2020-10-01
Smart Guide
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
Improved livelihood for Commonwealth citizens as a result of local economic development | National SDG reporting on Goals 8 and 16 | Planned | Commonwealth Countries sign up to agenda 2030 |  | 2.1 National reporting for Commonwealth countries against SDG indicators 8.3.1: Proportion of informal employment in non-agriculture employment, by sex and Indicator 16.6.2: 'Percentage of the population satisfied with their last experience of public services' (March 2019) | 3.1 Progress towards and review of Goal 8 and 16 at the UN High-level Political Forum (Nov 2019) | Progress in Commonwealth countries towards achieving SDGs 16 'ensure responsive, inclusive, participatory decision making at all level' and 'develop effective accountable and trasparent institions at all levels' esp. Indicator 16.6.2: 'Percentage of the population satisfied with their last experience of public services' (March 2021)
Achieved
Source
National reporting against the SDGs
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| The relevance of LED in value chain development, sustainable consumption and production, and market development for trade across the Commonwealth is better understood | Planned | No commissioned research | 1.1 Methodology developed for research (March 2018) | 2.1 Research commissioned (Dec 2019) | 3.1 Research completed and report drafted (Dec 2019) | CLGFreport/findings on relevance of LED to value chain, sustainable consumption and production and market development for trade across the Commonwealth is shared with the Commonwealth for example via Trade Ministers (March 2021)
Achieved
Source
ILO/ National Government reporting
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
Economic development, investment, and increased job opportunities in local communties in target countries | LED results in improved environment for doing business locally | Planned | Local business environment in the target councils unassessed | 1.1 Priority areas for improvement to support doing business locally identified in 10 councils (March 2018) | 2.1 local councils are providing LED services to improve doing business locally (March 2019) | 3.1 Data collection from Local business forums/associations (representing formal and informal traders)/ chambers of commerce etc in four council areas underway (Oct 2019) | Local business forums/associations (representing formal and informal traders)/ chambers of commerce etc in four council areas report improved environment for doing business as a result of LED (March 2021) | 1. Change of government does not significantly affect national commitment to LED 2. Sufficient political commitment to policy change 3. Resources are availlable for local governments to implement LED 4. Significant shocks such as natural disasters, epidemics or conflict do not affect any of the participating countries. 5. There are no major global or national financial crises resulting in recession in any of the participating countries 6. Changes at national or Commonwealth level do not result in the withdrawal of member states from the Commonwealth 7. Three years is a realistic timeframe for such change to be effected
|  | Achieved |  | Target met: 26 councils have identified prioirty areas of support to doing buisness | Target met: at least 13 LED strategies in place and being implemented | Target met: data collection on buisness satistaction with coucnil LED suport is underway in atleast 4 councils
Source
Commonwealth reporting, CLGF reporting
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Jobs created in local communities as a result of LED | Planned | No data on job creation to date | 1.1 CLGF develops a strategy for M&E of job created as a result of this project (March 2017) | 2.1 CLGF tests M&E to measure job creation in 3 pilot councils (March 2018) | 3.1 Assessment of job creation in all target councils underway (July 2019) | At least 1,500 jobs created, positively impactng over 5,000 lives (March 2021)
|  | Achieved |  | Target met: CLGF has included jobs creaed as one of the M&E elements in each national work plan (OP1, 2 & 3) councils have identified prioirty areas of support to doing buisness | Target met: Job creation included as factor in local economic assessmets (LEA) implemented in 8 councils | Target met: councils monitoring job creation as part of LEA in all core pilot councils
Source
Local statistics, CLGF reporting
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
National/ provincial LED strategies designed and being rolled out (Botswana, Zambia and Sri Lanka) | Number of countries that have adopted the CLGF approach to LED and are rolling out national LED strategies which are designed to be (1) pro poor, (2) gender sensitive, (3) enable local participation, (4) locally responsive | Planned | At least two countries have expressed interest in developing a LED strategy or implementing an existing LED strategy | 1.1 At least two LED strategies and/or implementation strategies under development (Dec 2017) | 2.1 Implementation strategy and M&E framework being rolled out (July 2018) | 3.1 On-going implementation of roll out. 3.2 Postive reporting of progress against agreed implementation plan and M&E framework (Oct 2019) | National/ provincial LED strategies designed and rolled out in at least 2 countries (March 2021) | 1. Low staff turnover/ sufficient institutional memory. 2. Limited impact of council elections or government change 3. Successful identification of good models and policy lessons to strengthen design, implementation and monitoring . 4. Councils are committed to changing their practice over the long-term 5. Three years is a realistic timeframe for such change to be effected. 6. That COVID 19 does not impact negatively on the ability of local governments to leverage funds against bankable projects.
|  | Achieved |  | Target met. Partners in Botswana, Sri Lanka, Zambia have agreed work plans. | Target met. Partners in Botswana, S.Lanka, Zambia are implementing agreed work. M&E framework in place and being used. | Target met. Partners in Botswana, Sri Lanka & Zambia implementing agreed work plans. Good progress being reported.
Source
National LED stategy documents implimentations plans/ annual reports
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Percent of citizens surveyed in areas implementing LED report improvement with the council’s economic development services (disaggregated by gender) | Planned | Insufficient data available at the local level on citizen satisfaction with LED services | 1.1 Mapping of citizen interface/engagement underway in 12 target councils (Nov 2017) 1.2 Consultations with local stakeholds (citizen groups, business associations for formal and informal traders etc) undertaken in 12 target councils (March 2018) | 2.1 KAP survey developed (July 2018) 2.2 Piloting KAP survey in three countries (Nov 2018) 2.3 Revise KAP survey method (Feb 2019) | 3.1 Commission KAP survey (May 2019) 3.2 KAP survey completed (Feb 2020) | 75% percent of citizens surveyed in areas implementing LED report improvement in the council’s economic development services, disaggregated by gender (March 2021)
|  | Achieved |  | Target met: 26 councils identified and developing LED strategies and plans. | Target met: KAP surveys developed and piloted, and methodology revised. | Target 3.1 met. KAP surveys have been commissioned with all local councils.
Source
Knowledge Attitude and Practices (KAP) survey; CLGF reports
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
50 | Target councils demonstrate increased capacity to develop bankable projects and successfully leverage investment | Planned | Limited evidence of successful and bankable projects developed by target councils | 1.1 At least 8 councils (2/3rds) have increased capcity to target potential LED investors (Dec 2017) 1.2 LED strategies adopted by at least 8 (2/3rds) of the target councils (March 2018) | 2.1 At least 8 (2/3rds) of target councils identify and start to develop business plans for at least one bankable project (Nov 2018) | 3.1 At least 4 (1/3rd) are in dialogue with potential investors (July 2019) | 8 (2/3) of target councils from OA 1 and/or OA2 develop bankable projects and successfully leverage funding of up to £1.5m for implementation of LED priorities (March 2021)
|  | Achieved |  | Target exceeded. 14 councils developed LED strategies. | Target exceeded. 13 councils have developed bankable plans aligned to their LED strategies and are in dialogue with potential investors. | Target exceeded. 13 councils have developed bankable plans aligned to their LED strategies and are in dialogue with potential investors.
|  | Source | [5 empty] | RISK RATING
Project docs/ annual report council minutes/business plans; CLGF reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
Increased capacity to roll out LED in selected countries (Ghana, South Africa and Swaziland) | Number of countries embedding the CLGF approach to LED, where appropriate, in national policy, legal, regulatory and capacity development frameworks for LED | Planned | National level policy, legal and regulatory frameworks in place but limited capacity to roll out | 1.1 Assessment of barriers to successful national roll out of LED policy undertaken in three countries (Oct 2017) 1.2 LED implementation strategies developed in at least two countries (March 2018) | 2.1 Policy review/amendments started where required, responding to assessment findings (July 2018) 2.2 Dialogue underway with stakeholders needed for ensuring buy-in for roll out (March 2019) | 3.3 Positive progress reported against targets set out in implementation strategy for roll out (July 2019) | Two countries have increased capacity and are rolling out their LED strategy (March 2021) | 1. Change of government does not significantly affect national commitment to LED 2. Low staff turnover/ sufficient institutional memory. 3. Changes represent genuine improvements and impacts 4. Three years is a realistic timeframe for such change to be effected
|  | Achieved |  | Target met. Assessments of national LED environment undertaken in 3 focal countries. LED strategies developed in Swaziland and South Africa. | Target met. Constructive relationships in place between CLGF and its partners in support of LED rollout. | Target met. All three countries making progress against agreed targets in their roll-out strategies.
Source
Commonwealth Local Government Handbook 2015-16, 2019/20 - CLGF reports and local reporting
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Capacity of technical staff and political leaders to deliver LED services increased (councils and ministries) | Planned | Three country governments have identified capacity gaps affecting roll out of LED nationally and have requested CLGF support to addess these gaps | 1.1 Detailed assessment of capacity gaps complete in three countries (Oct 2017) 1.2 Capacity development activity planning underway (March 2018 | 2.1 At least 80 technical staff and political leaders trained to deliver LED services (July 2018) 2.2 Evidence of increased capacity demonstrated via a sample of stakeholders participating in key practitioner tracking (March 2019) | 3.1 120 technical staff and political leaders are actively participating in the national roll out (July 2019) | Increased capacity of 200 technical staff and political leaders to deliver LED services demonstrated (March 2021)
|  | Achieved |  | Target met. Assessment of capacity gaps completed and integrated into targeted work plans. | Target met. Stakeholder tracking demonstrating increased LED capacity built. | Target exceeded: 140 technical staff and political leaders actively participating in national roll-outs.
Source
Key practitioner tracking; CLGF reporting
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
20 | Improved economic opportunites for citizens in areas implementing LED | Planned | Insufficiant data available at the local level on economic opportunities for citizens | 1.1 Assessment of data availability and data gaps indentified in 6 target councils (Nov 2017) 1.2 Consultations with local stakeholders (citizen groups, business associations for formal and informal traders etc) undertaken in 12 target councils (March 2018) | 2.1 KAP survey developed and piloted in three councils (July 2018) 2.2 Piloting KAP survey in three countries (Nov 2018) 2.3 Revise KAP survey methodology (Feb 2019) | 3.1 Commission KAP survey (May 2019) 3.2 KAP survey completed (Feb 2020) | 60% of surveyed citizens who have used council LED services report improved economic opportunites (March 2021)
|  | Achieved |  | Target met. Assessment of data availability and gaps undertaken for 10 Councils in Swaziland, 3 Councils in Ghana and 1 district in South Africa. | Target met. KAP surveys developed and piloted in all three countries. | Target met. KAP survey data is supporting councils in their LED work and will support citizen satisfaction assessment at end of project.
|  | Source | [5 empty] | RISK RATING
Knowledge, Attitudes and Practice Survey (KAP); CLGF reports
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
Increased awareness of LED potential in selected countries with some fragility (drawn from Bangladesh, Cameroon, Lesotho, India, Pakistan, Sierra Leone, Zimbabwe) | National actors (ie Ministry of LG, LGA, business fora) use lessons from demonstration projects and national/regional exchange to inform enabling policy and LED practice to empower local governments to deliver LED | Planned | LED not being implemented, or being implemented in an ad hoc manner | 1.1 Awareness on potential of LED raised with national actors (Dec 2018) | 2.1 National actors in at least four countries are working towards improving policy and practice in LED (July 2019) | 3.1 At least two LGAs have developed policy recommendations supporting LED adoption (July 2019) | National actors in at least two countries use lessons from demonstration projects, national and regional exchange and learning, to inform policy development (March 2021) | 1. Low staff turnover/ sufficient institutional memory. 2. Limited impact of council elections: need to assess where and in what proportion of countries this is likely to be an issue. 3. Successful identification of good models and policy lessons to strengthen design, implementation and monitoring 4. Councils are committed to changing their practice over the long-term 5. Political and financial support for LED delivery is maintained. 6. Three years is a realistic timeframe for such change to be effected
|  | Achieved |  | Target ongoing. Awareness being raised with technical staff, local leaders and national and state decision makers. | Target partially met and ongoing. Working with national actors in three countries (India, Sierra Leone, Zimbabwe) towards improving policy and practice on LED. Work in a fourth country paused due to political situation. | Target met and ongoing. Work in India, Sierra Leone and Zimbabwe has supported development of LED policy recommendations.
Source
CLGF reporting, reports by national actors, policy papers/statements, media reports
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| LED demonstrated as an approach to integrated local development | Planned | LED not being implemented, or being implemented in an ad hoc manner | 1.1 Development of LED strategies initiated in 6 councils (March 2018) | 2.1 LED strategies adopted and being implemented by 6 councils (March 2019) | 3.1 At least 4 councils are undertaking LED activity (July 2019) | 4 councils have demonstrated the LED approach through the development and implementation of LED strategies (March 2021)
|  | Achieved |  | Target met. 9 LED strategies developed/being developed. | Target met. LED strategies have been developed or are being developed in 14 councils. | Target met. 8 Councils undertaking LED activities.
Source
LED strategies, CLGF/local reporting
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
15 | Improved economic opportunites for citizens in areas implementing LED |  | Insufficient data available at the local level on citizen satisfaction with LED services | 1.1 Mapping of citizen interface/engagement underway in 12 target councils (Nov 2017) 1.2 Consultations with local stakeholds (citizen groups, business associations for formal and informal traders etc) undertaken in 12 target councils (March 2018) | 2.1 KAP survey developed (July 2018) 2.2 Piloting KAP survey in three countries (Nov 2018) 2.3 Revise KAP survey method (Feb 2019) | 3.1 Commission KAP survey (May 2019) 3.2 KAP survey completed (Feb 2020) | 50% percent of citizens surveyed in areas implementing LED report improvement in the council’s economic development services (disaggregated by gender) (March 2021)
|  | Achieved |  | Target met. Mapping of citizen engagement completed in 13 targeted councils. Consultations with local stakeholders in 12 target councils. | Target met: Surveys developed and commissioned to assess impact on populations. | Target 3.1 met: Surveys developed and commissioned to assess impact on populations.
|  | Source | [5 empty] | RISK RATING
Local survey reports, CLGF reporting, local media reporting, KAP suvey
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
CLGF acknowledged as a Commonwealth centre of LED learning and good practice | Regional and global policy events highlight the effectiveness of LED as a means of achieving sustainable development | Planned | Some limited recognition of the role of LED in achieving sustainable development within regional and global policy | 1.1 Strategy developed for targeting key policy events (July 2017) 1.2 One regional and/or global policy event highlights the effectiveness of LED as a means of achieving sustainable development (March 2018) | 2.1 Awareness of the role of local government in LED raised at the Commonwealth Summit (April 2018) | 3.1 One regional and/or global policy event highlights the effectiveness of LED as a means of achieving sustainable development (Dec 2019) | Three regional and/or global policy events highlight the effectiveness of LED as a means of achieving sustainable development (March 2021) | 1. Ability to source good quality materials and resources on LED 2. Other agencies are keen to work together with CLGF and its partners on LED and invest in LED initiatives at the local level 3. Political and financial support for improved policy on local government service delivery continues. 4 CLGF's ability to leverage funding is maintained
|  | Achieved |  | Target exceeded. CLGF developed strategy for key policy events. 2 global events held highlighting effectiveness of LED for sustainable development. | Target met. CLGF an active participant at CHOGM 2018 with LED highlighted in the Forums and in presentation to Foreign Ministers. | Target on track. CLGF has participated in several global and regional events to highlight LED. CLGF Southern Africa conference in June 2019 attended by 100 participants from 11 SADC countries supported ongoing exchange of good practice.
Source
Meeting outcome statements, CLGF reports
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| National actors capitalise on the Commonwealth's shared systems, structures, language and governance to successfully implement LED | Planned | Limited data on how CLGF's resources and good practice on LED are being used across the Commonwealth | 1.1 CLGF Member survey on use and expected future need for resources and good practice on LED (Dec 2017) 1.2 Dedicated knowledge management strategy on resources and good practice on LED (March 2018) | 2.1 Knowledge management strategy on resources and good practice on LED being implemented (Dec 2018) | 3.1 Number of quality materials and resources available through the CLGF knowledge hub increased (May 2019) 3.2 Member survey completed on impact of CLGF resources on understanding of LED among members (Dec 2019) | CLGF members in three countries not participating in output areas 1,2 and 3 use CLGF resources and good practice on LED to inform policy and practice (March 2021)
|  | Achieved |  | Target met. Survey developed and circulated to all members. Results included in knowledge management strategy. | Target met. CLGF is implementing its knoweldge management strategy. | Target 3.1 met: CLGF continue to identify and add material to be held on their knowledge management hub.
Source
Member survey; CLGF reports
| Output Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3
| CLGF’s knowledge hub has a sustained increase of quality LED-focused resources, reviewed on an annual basis with annual increases in the number of visitors to the knowledge hub on the CLGF website. | Planned | Knowledge Hub live with a focus area on Local Economic Development | 1.1 Visitors to the Knowledge Hub on the CLGF website increased by 10% on previous year (March 2018) | 2.1 Dedicated knowledge management strategy on resources and good practice on LED (July 2018) 2.1 10% increase on the previous year's visitors to Knowledge Hub (March 2019) | 3.1 Peer review of LED-focused resources in CLGF Knowledge Hub commissioned (July 2019) 3.2 10% increase on the previous year's visitors to the Knowledge Hub (March 2020) | Peer review of LED-focused resources confirms good quality resources in the Knowledge Hub and number of vistors has increased by at least 10% per annum (March 2021)
|  | Achieved |  | Target met. 25.5% increase in visitors to knowledge hub in August 2017 - July 2018 period compared to previous year. | Target met. 96% growth in visitors to the hub over (Aug 2018 - July 2019) compared to the previous year. | Target 3.1 met. CLGF has commissioned a peer review of LED-focused resources on the knowledge hub.
|  | Source | [5 empty] | RISK RATING
CLGF reports/knowledge management strategy reporting/website statistics
IMPACT WEIGHTING (%) | Output Indicator 4.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3
15 | % of funding leverage against DFID contribution | Planned | Last programme secured 35% (financial and in-kind) | 10% of the DFID contribution leveraged (March 2018) | 25% of the DFID contribution leveraged (March 2019) | 40% of the DFID contribution leveraged (Dec 2019) | 65% of the DFID contribution leveraged (March 2021)
|  | Achieved |  | Target exceeded. Plus 40% of DFID contribution leveraged. | Target exceeded. Plus 40% of DFID contribution leveraged. | Target exceeded. CLGF has leveraged £3.7m for project work in the 3 regions (SA, West Af, South Asia)
Source
Financial acquittals and CLGF reporting
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.