Annual Review - Summary Sheet

Title: Increasing coverage of Long Lasting Insecticidal Nets (LLINs) in Uganda.
Programme Value: £19,900,000		Review Date: November 2015
Programme Code: 203671	Start Date: 13 December 2012	End Date: 31 December 2016

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	A	A+	A
Risk Rating	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

In August 2014, Uganda marked the end of the universal net distribution campaign, the largest universal net coverage campaign anywhere in the world. Over 21 million Long Lasting Insecticidal Nets (LLINs) were distributed across the country with the aim being to get at least one net into each household, and on average one net for every 1.8 people in the country (Uganda’s definition of universal coverage). 4.45 million nets were procured for the campaign with UK funds. A further 1.6 million have been procured for routine distribution targeted to pregnant women and under 5s from now on. In addition, DFID funded the distribution of 12.1 million nets funded by other development partners including the Global Fund.

By the end of the campaign, it was estimated that 93% of people that registered for a net had received one. However, the population estimates used to calculate the number of nets required for the campaign were lower than the population turned out to be, resulting in fewer nets than were required distributed in Kampala and Wakiso districts. (DFID support to Uganda’s census will improve the planning of such programmes in future.) In addition, there were challenges with data management for the universal net campaign.

Behaviour change communication (BCC) activities were conducted to raise awareness on the benefits and care of LLINs. This included mass media campaigns on bill boards, radio spots and talk shows. While mass media campaigns are a good channel for raising awareness, interpersonal communication (IPC) to promote behaviour change, necessary for the utilisation and care of the LLINs could have been strengthened.

Summary of recommendations for the next year

As the contract with the implementing partner on this programme has ended, all outstanding funds on this programme should be integrated into the larger DFID-USAID malaria programme.

Establish the current gap in funding for the next LLIN campaign (2016/17) and review the possibility of DFID support to the procurement of LLINs.

Ensure effective evaluation of the campaign, using data from the UK-funded Malaria Indicator Survey.

A. Introduction and Context

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

Reducing the high levels of morbidity and mortality associated with malaria in Uganda will require sustained delivery of proven prevention and treatment strategies at scale. The three primary interventions recommended by WHO’s Global Malaria Project to tackle malaria are: a) distribution of insecticide-treated nets, more specifically Long Lasting Insecticide Treated nets (LLINs), to achieve universal coverage; b) indoor residual spraying (IRS) of houses to reduce and eliminate malaria transmission; and, c) diagnosis of malaria cases and treatment with effective medicines. Uganda’s inability in the past to take these proven anti-malarial interventions to scale means that malaria prevalence and malaria related deaths have remained high. DFID Uganda is funding all three interventions.

With support from partners, Uganda has prioritised universal LLIN coverage as a prevention strategy to decrease malaria related morbidity and mortality. By achieving universal LLIN coverage, Uganda will not only be able to protect the large number of people sleeping under these nets but may also be able to protect other households in the vicinity not using nets. Universal coverage and high use of LLINs would be likely to significantly reduce the burden of malaria in Uganda which in turn would lead to wider socio-economic benefits through increased educational performance, reduced absenteeism from work and school, savings in healthcare spending and lives saved. To carry out this initiative, Uganda needed at least 21 million LLINs for an estimated population of 34 million. The Global Fund to fight AIDS, Tuberculosis and Malaria (GFATM) committed to providing 15 million LLINs; Government of Uganda (GoU) requested DFID support for the procurement and distribution of an additional 5 million LLINs while World Vision International committed to provide 500,000 LLINs.

DFID provided £19.9 million through a delegated cooperation arrangement with the United States Agency for International Development (USAID) to support procurement and distribution of five million LLINs, distribution of LLINs procured by the GFATM, as well as a behaviour change communication campaign designed to increase rational use of LLINs; and an evaluation that will seek to understand the impact of the campaign and what aspects worked well, to help other countries implement similar approaches. The original DFID budget at approval of the project in November 2012 was £17 million; however following a request from Ministry of Health in late 2013 to cover a gap in the distribution budget, an additional investment of £2.9 million was approved on 20 November 2013. This cost extension was to enable DFID to support distribution of an additional 4.5 million LLINs, procured by the GFATM. The programme was implemented through two USAID partners; the Stop Malaria Project (SMP) and DELIVER (a private contractor) – various subcontractors, including the Malaria Consortium, were involved in distribution and behaviour change communication (BCC) activities.

The universal coverage campaign was launched on 10 May 2013 in Soroti district at an event presided over by His Excellency the President of the Republic of Uganda. Fifteen months after its launch, the end of the campaign was officially marked at a ceremony presided over by the President of Uganda. It is a major initiative of the National Malaria Control Programme (NMCP) of the Government of Uganda (GoU) and its partners, to achieve universal coverage of LLINs in Uganda. As per the World Health Organization (WHO) recommendations, LLINs were distributed at no cost to all Ugandan households through a one-off mass distribution campaign, and routinely thereafter to all pregnant women and mothers of infants during ante-natal and immunisation visits.

Working through USAID, DFID provided funding to conduct: i) a process evaluation that sought to establish the extent to which the campaign had been implemented according to agreed guidelines ii) an impact evaluation to establish the overall effectiveness of the campaign.

## PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The two main outcomes for this programme are: proportion of children under five who slept under a LLIN/ITN the previous night; proportion of pregnant women who slept under a LLIN/ITN the previous night. Results from the Malaria Indicator Survey (MIS) indicate that 74.2% of children under five and 75.4% of pregnant women had slept under an LLIN the previous night indicating excellent progress towards the outcomes as shown below:

Outcome 1: Increased use of LLINs among pregnant women and children under 5.
Indicator	Baseline	Milestone 2015	Progress
Proportion of children under five who slept under a LLIN/ITN the previous night	42% (2011)	75%	74.2%
Proportion of pregnant women who slept under a LLIN/ITN the previous night	47% (2011)	75%	75.4%

Overall output score and description: A

Based on the progress to date, the programme met expectation.
Achievements
Over 21 million nets were distributed in the universal LLIN distribution campaign, the largest attempt to achieve universal coverage with nets anywhere in the world. By the end of the campaign, it was estimated that 93% of people that registered for a net had received one. The national coordination of the campaign was impressive with strong leadership from the GoU and the involvement of key stakeholders including the Armed Forces that provided security during the distribution exercises. At the district level, district leaders were highly engaged through the district task forces which contributed to the success of the campaign. Over 110,520 Village Health Teams (VHTs) participated in the registration and distribution of the nets, sensitising communities on the benefits of the LLINs.
Challenges
The major challenge was the delay in net delivery and distribution. The former was caused by an upsurge in global net orders, with the result that net manufacturers could not deliver according to earlier estimated timelines. Delays in distribution were a result of delays in finalising the net distribution schedule and micro planning among major malaria stakeholders in the country. In some parts of the country, bad weather and a poor road network contributed to delays in the arrival of nets to final distribution points. In addition, there were challenges managing the large volumes of data generated in a timely manner. Lastly, the population estimates used to calculate the number of nets required for the campaign were lower than the population turned out to be resulting in fewer nets than were required distributed in Kampala and Wakiso districts. DFID support to Uganda’s census will improve the planning of such programmes in future, resulting in more efficient use of funds right across Uganda’s public service delivery.

The programme has been extended twice to allow collection of data relevant to assessment of the effectiveness of the programme. This includes data from the MIS and a DFID funded evaluation currently underway. The findings of the MIS were disseminated on the 6/11/2015 and it is anticipated that the evaluation of the programme will be finalised by May 2016.

Key lessons

The DFID/PMI joint programme on malaria has been an important avenue to strengthen donor harmonisation and effectiveness on influencing policy and malaria programming in Uganda. This was demonstrated by the role of DFID and PMI on the National Coordination Committee.

Recent data from the 2014 MIS on malaria progress shows considerable reductions in malaria parasite prevalence (from 42% to 19% nationwide, and from 63% to 20% in the northern region) alongside dramatic scale-ups in the coverage of malaria interventions and reductions in child mortality. The results demonstrate the effectiveness of the key interventions supported by this project – LLINs. In addition, it indicates that the key assumption underpinning the project (that the scale up of malaria prevention and case management will lead to drops in malaria prevalence and then to reductions in mortality and morbidity) remains valid.

The ongoing malaria epidemic in previously sprayed parts of northern Uganda also points to the importance of coupling the distribution of LLINs with behavioural change communication post the distribution exercise. This serves to enhance net utilisation.

Key actions

Emerging evidence from the outbreak region shows that net utilisation after the withdrawal of the IRS was not optimal. To ensure utilisation and proper care of LLINs, there is need for concerted efforts in post distribution behaviour change communication with a big focus on interpersonal communication.

In anticipation of the next universal campaign in 2016/17, due consideration must be given to the set-up of an automated system linked to the data base created during the just concluded campaign. This will improve data management during the campaign reducing delays between quantification and distribution of the LLINs.

Discuss and agree DFIDs contribution (bilateral or through the GFATM) to the next universal coverage campaign.

Has the log frame been updated since the last review?

Yes. A time extension to allow for completion of the evaluation of the LLIN campaign was granted in 2015. The programme is now expected to close by December 2016.

## C: DETAILED OUTPUT SCORING

Output Title	Increased ownership of LLINs
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	80%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress	Status
1.1 Proportion of households with at least one LLIN.	85%	90%	Met expectation / A
1.2 Number of LLINs procured and delivered through DFID support	0	0	Met expectation / A

Key Points
Ownership of at least one insecticide treated net (ITN) is higher in rural areas (92%) than urban areas (84%). By region, ownership of at least one ITN ranges from 81% in Central 1 to 97% in North East and South Western. Ownership of at least one ITN varies by wealth quintile with more households in the lower wealth quantiles owning at least one ITN compared with households in the higher wealth quintiles. On average households own 2.5 ITNs.

A total of 1,412,000 LLINs procured with funding through this programme are yet to be distributed through a new USAID mechanism being set up. The distribution of additional LLINs procured with funding from this programme was done through a mechanism established under DFIDs wider support to the control of malaria. Therefore no milestones were included in this logframe to avoid double counting. While there has been significant progress on distribution mechanisms, it appears that there is need to improve harmonisation in the routine distribution of LLINs for pregnant women and child by different stakeholders including the GFATM. This is because there are at least three major stakeholders procuring LLINs for distribution in health facilities. There have been cases of clinics receiving LLINs from two providers which results in clinics overstocked with LLINs which are often bulky thus consuming limited space at health facilities.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation: To ensure the most in need receive the 1,600,000 DFID funded LLINs that arrived in November 2014, it will be important to have a clear distribution plan that targets the poorest and most vulnerable.
A clear distribution plan was established targeting distribution to the most at need including in the districts affected by the malaria outbreak.

Recommendations

1. The NMCP through the Integrated Vector Management technical working group should spearhead efforts to improve the coordination of routine distribution of LLINs for pregnant women and children. This must be done with the support of the key stakeholders PMI, DFID and GFATM.
2. It will be important to include any LLINs that will not be distributed through the routine distribution channels for pregnant women and children in the current quantification exercise for the next UCC.

## C: DETAILED OUTPUT SCORING

Output Title	Increased awareness of the importance of using LLINs
Output number per LF		2	Output Score	B
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress	Status
2.1 Awareness among women age 15 to 49 years about the benefits of using LLINs	85%	94%	Moderately exceeded expectation / A+
2.2 Percentage of villages covered through community sensitisation drive during mass LLIN campaign	85%	33.8%	Substantially did not meet expectation / C

Key Points
A crucial element in the fight to eliminate malaria is the ability to reach the population with information and educational materials. To assess the coverage of communication programmes, women interviewed in the 2014-15 MIS were asked if they had seen or heard any message about malaria prevention in the six months preceding the survey. Women who had heard or seen malaria prevention messages were then asked to report the source of the message. Overall 63.8% of women had been exposed to a malaria message in the preceding six months, the majority of whom (82%) had heard the message on radio. Fewer women reported having been exposed to a message through a community event (16.9%) and community health worker (33.8%). This low level of dissemination of information through interpersonal communication (IPC) is a reflection of a poorly implemented post distribution BCC campaign which largely focused on mass media communication. Indeed, a weak BCC campaign has been cited as one of the possible causes of the re-emergence of malaria in the 10 districts following the withdrawal of IRS.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation: To ensure utilisation and proper care of LLINs there is need for concerted efforts in post distribution behaviour change communication.

Partners implementing IPC activities at the community level using tools developed by Communication for Healthy Communities (CHC) should remain accountable to CHC, providing information on population reached with messages on LLIN use.

Support for behavioural change communication (BCC) is being implemented through the USAID programme CHC. Through a DFID led effort to revive malaria technical working groups, a BCC working group was established to improve and coordinate both mass media and IPC activities on the prevention and control of malaria. This has improved accountability on reach of materials developed by CHC and improved post LLIN distribution messaging on utilisation of LLINs.

Recommendations

Under the leadership of the NMCP, partners including DFID, PMI and GFATM need to agree on what additional efforts must be taken to further strengthen and document best practices on IPC to increase LLIN utilisation. The results of the evaluation will provide insights on the link between IPC and LLIN utilisation following the last universal coverage campaign.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The main cost driver was the cost of the distribution of the LLINs mostly because of poor planning. Given that all the procurements had been completed, there were only a few activities- specifically the evaluation undertaken during this reporting period. The remaining LLINs after the universal campaign have continued to be distributed through routine antenatal and immunisation clinics. USAID is in the process of awarding a new contract to an Implementing Partner to speed up the distribution of the remaining LLINs in the next year.

VfM performance compared to the original VfM proposition in the business case
Savings on the unit cost of the LLINs from $3 to $2.79 resulted in the procurement of an additional 1,600,000 LLINs. These nets will be channelled through routine distribution at antenatal and immunisation clinics and possibly during the next universal net campaign in 2016/17 resulting in additional lives saved. These savings were made possible because of bulk procurement through USAID’s procurement partner DELIVER. Logistics costs including the cost of distribution rose slightly due to poor planning in the early stages of the programme and also the additional number of nets distributed by DFID.

Assessment of whether the programme continues to represent value for money
Pooled procurement of LLINs by DELIVER has been a key cost saver for the programme. Data from the Malaria Indicator Survey shows that there has been a significant increase in ownership and utilisation of LLINs following the universal campaign. The inputs to the programme have been exceptional value for money as demonstrated above by the drop in LLIN prices below the business case benchmark for nets, in spite of unprecedented global demand.

Quality of financial management
All funding for this programme has been disbursed to USAID. USAID has adhered to quarterly narrative and financial reports. However there is approximately a balance of £671,808 that will be utilised before the end of the project; £250,000 will be spent on Monitoring and Evaluation, and £421,808 will be spent on LLIN distribution.

Date of last narrative financial report	01 September 2015
Date of last audited annual statement	N/A. USAID does not provide audited statements as audits are conducted for the whole USAID portfolio and are not specific to Uganda. Only financial reports are shared. However in the event that the audit picked up an issue relevant to the DFID programme, this would be shared with DFID.

E: RISK

Overall risk rating: Medium

Overview of programme risk
There have been significant delays in finalising the evaluation of the net distribution campaign, a component funded by DFID that have resulted in the programme being extended a second time to enable finalization of the evaluation. This in part was attributed to delays in the dissemination of the MIS report that forms a critical part of the evaluation. However as the evaluation is now underway following the dissemination of the MIS results on 6/11/2015 and it is expected that the final evaluation report will be disseminated in May 2016. Lastly, with approximately 1,412,000 LLINs yet to be distributed, there are risks around how these nets are distributed in a harmonised manner with other partners to ensure that there is no duplication of efforts resulting in some facilities receiving more nets than are required. In addition it will be important to critically assess the distribution channels to ensure that the most cost efficient mechanism is used.

Outstanding actions from risk assessment
1. DFID to maintain strong oversight of the evaluation of the campaign to ensure timely completion.
2. DFID to follow up on distribution of the remaining LLINs and work with other partners to ensure a harmonised approach to national distribution of LLINs for pregnant women and children.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The LLIN distribution covering the entire country was completed in 15 months, three months more than the originally planned 12 months, due to unanticipated delays in arrival of the required LLINs and the long clearing process at the National Drug Authority (NDA). One of the reasons for the delay of net delivery was a fire at the manufacturing plant of one of the suppliers. DELIVER also indicated delays due to vastly increased demand for nets globally, which made lead times volatile and unpredictable.
The evaluation of the campaign is yet to be completed. Following the recent release of the results of the MIS it is expected that the evaluation will be concluded by May 2016.

Performance of partnership (s)
The DFID/USAID partnership played a key role in the universal campaign through the National Coordination Committee. Both DFID and USAID provided technical guidance and oversight instrumental in the implementation of the campaign. The partnership has produced efficiency gains in procurement of the LLINs resulting in a cost saving worth 1,600,000 LLINs.

Asset monitoring and control
Three laptops were procured with DFID funding: 2 by the Stop Malaria Project for the LLIN Programme Specialist and the LLIN Finance and Compliance Specialist; and 1 by Malaria Consortium for the LLIN Programme Coordinator. These assets are tracked in the partner’s inventory list. Each of the laptop users signed for the laptop on receipt and is responsible for the asset. When leaving the organisation, the user has to be cleared after handing over the asset(s) in their possession to the office before their final payment. USAID disposes off assets using their internal procedures. There is a high level of confidence in the management of programme assets by USAID.
G: CONDITIONALITY

Update on partnership principles

Not relevant as while the programme contributes to GoU policies and plans, the funding is not part of the MTEF.

H: MONITORING & EVALUATION

Evidence and evaluation

DFID in partnership with USAID/PMI funded the MIS that provided high quality data that is influencing decision making. Recent data on malaria progress shows considerable reductions in malaria parasite prevalence (from 42% to 19% nationwide, and from 63% to 20% in the northern region) alongside dramatic scale-ups in the coverage of malaria interventions and reductions in child mortality. The results demonstrate the effectiveness of the key interventions supported by this project – LLINs, IRS and case management. In addition, it indicates that the key assumption underpinning the project (that the scale up of malaria prevention and case management will lead to drops in malaria prevalence and then to reductions in mortality and morbidity) remains valid.

In addition, it is expected that data from the evaluation of the campaign will provide useful information on the implementation and impact of the campaign that will be useful for informing the implementation of the next campaign in 2016/17.

Monitoring progress throughout the review period
Quarterly meetings were held between DFID and PMI/USAID to discuss issues relevant to the programme. Reports were submitted by USAID as stipulated by the MoU to provide an update on progress. In addition, through quarterly meeting with the Ministry of health, updates were provided to the national malaria control programme on progress to date and to ensure all activities conducted under the programme were in line with the national malaria reduction strategic plan (2016-2020).

DFID Annual review: 16th November – 20th November 2015

The review was conducted by the Human Development Team. It was based on a desk review of the business case, logframe and monitoring and reporting documents as well as key stakeholder meetings.