Annual Review – Report Summary Sheet

Title: Somali Health and Nutrition Programme (SHINE)
Programme Value £ (full life): 89.6 million		Review Date: November 2019
Programme Code: 204903	Start Date: November 2015	End Date: March 2021

Summary of Programme Performance
Year	2016	2017	2018	2019
Programme Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204903/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204903/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)
The Somali Health and Nutrition Programme (SHINE) is entering its fifth and final full year. It continues to address the high levels of preventable maternal and child deaths among Somali women and children and demonstrates DFID’s continued commitment to improving the health status of Somalis. SHINE has delivered strong results but been hampered by a staggered implementation and complex design. These and other lessons will be incorporated into the new programme currently under design. The five-year (2016-2021) programme with a total budget of £89.6m uses a mixed delivery approach to deliver across three core areas (Note. An acronym list is included at Annex 1).

1. Health service delivery: Provision of the essential package of health services (EPHS) aligned to the Somalia National Health Sector Strategic Plans (HSSP).
2. Health system strengthening: Supporting the Somali Health Authorities (SHAs) lead, regulate and oversee basic service provision and by building core elements of a functional health system (supply chain, information systems etc).
3. Demand creation: Empowering vulnerable populations, especially women and children, to overcome barriers to accessing services and make healthy choices.

Somalia Health and Nutrition Programme (SHINE) programme structure
SHINE (2016-2021) £89m

        Service delivery and health system strengthening
SAHAN: Design of demand creation and behaviour change interventions and piloting with service delivery partners across locations.
MESH: Cross cutting support to monitoring and evaluation and third-party monitoring
UNICEF Commodity Security Programme

Locations: SHINE Supply Sites

UNICEF and UNFPA supply chain strengthening support.

SHINE SUPPLY
EPHS Service Delivery and district/regional health systems strengthening

Locations: Awdal &Toghdeer, Somaliland; Galgaduud, Galmadug and Banadir

Additional system strengthening work at the national level and in Federal Member States.
UNICEF
EPHS Service
Delivery and district/regional health systems strengthening

Locations: Awdal,Toghdeer, Erigavo, Somaliland; Galgaduud & Mudug, Galmadug and Banadir

CHANGE
EPHS Service Delivery and district/regional health systems strengthening

Locations: Sahil, Somaliland
Karkaar, Puntland
Gedo, Jubaland

The earlier Annual Reviews document SHINE’s slow roll out and the staggered start of components but also the strategic use of ‘bridge’ funding to UNICEF to ensure services were maintained and the programme delivered. This Annual Review finds SHINE in a strong position, in full implementation and poised to deliver its greatest impact during the remaining period.

The status of each component is outlined in brief below:

- The Community Health and Nutrition through Governance and Empowerment (CHANGE) programme led by Population Services International has managed a consortium of international NGOs to support delivery of essential services in 3 regions since 2016 (Trocaire in Gedo, Jubbaland; Health Poverty Action in Sahil, Somaliland; and Save the Children in Karkaar, Puntland). In the last year they have achieved key service delivery targets providing care to over half a million people, accelerated work on quality improvement and use of data and actively shared lessons with the other service delivery components.
- The SHINE Supply Programme led by Mott Macdonald began in July 2018 after protracted procurement. In the last year locations and partners were selected and delivery of services initiated in 16 districts supported by NGO partners (Action Against Hunger led consortium in Banadir; Mercy USA in Galgaduud and HPA in Awdal and Togdheer in Somaliland). Strong leadership and a results-driven approach has seen the programme reach key service delivery targets and influence others in the sector. Health systems strengthening support to human resources, information and coordination, district level management and supply chain is poised to start properly.
- The Commodity Security Programme (CSP) provides supplies to SHINE Supply partners and carries out broader supply chain strengthening activities. Lessons from inception led to a revision of UNICEF and UNFPA’s roles with UNICEF taking sole responsibility for procurement and distribution and leading on work to improve forecasting and quantification. Without a formal working relationship between UNICEF and SHINE Supply (Mott Macdonald) and both components set up to separately report to DFID there have been challenges in developing the partnership needed for effective delivery. Considerable effort is still needed to ensure reliable provision of supplies. UNFPA are now focused on supporting front-line staff to provide family planning services.
- The UNICEF Service delivery programme succeeded the earlier UNICEF bridge programme (ending December 2018) which continued basic services in locations previously supported under the Joint Health and Nutrition Programme (2011-2016) during contracting of SHINE Supply. Under the bridging UNICEF achieved impressive reach albeit with a limited number of services supported at only higher-level facilities. A revised partnership with UNICEF was finalized in November 2018 to support essential services in line with the other SHINE service delivery components. After final agreement of locations, selection and contracting of partners services largely began between July and August 2019 with Mercy USA supporting delivery in 2 Banadir districts; and 1 each in Mudug and Galgaduud; an HPA led consortium with Mercy in 3 districts in Toghdeer and Awdal; and the Somali Red Crescent Society in Erigavo. Contracting delays have affected achievement of service delivery targets.
- The SAHAN (Somali Advocates for Health and Nutrition) demand creation and behaviour change programme began in 2016 with an extended inception phase carrying out formative research and agreeing the approach. From January 2018 the focus has been on designing interventions. The 2018 Annual Review recommended accelerating partnerships with SHINE service delivery partners to pilot these interventions and generate evidence. In April a failure to do this triggered a rapid review of the programme. Since then considerable progress has been made, with all 12 prioritised prototypes on track to be in the field by the end of December, and early indication of their impact.

Summary supporting narrative for the overall score in this review (1/2 page)

This year has seen a step change in the overall status of the programme with all components now in implementation, delivery increasing over the period and this trend poised to continue. Each component scores A giving an overall score also of A.

Output 1 on the delivery of essential health services scores A as a result of strong continued delivery through the CHANGE programme and despite some challenges with supplies through the Commodity Security Programme, very positive trends under SHINE Supply. UNICEF service delivery only began in the last quarter but experienced partners with pre-existing presence in the locations should pick up delivery quickly. Overall utilisation of core maternal and child health services (skilled birth attendance, treatment of common childhood illnesses, immunisation, preventative nutrition services) is good. Late presentation for antenatal care means the recommended 4 visits are rarely delivered and birth spacing remains sensitive and will receive greater investment in the final year of SHINE. Integration of treatment for severe acutely malnourished children has faced challenges coordinating with the largely humanitarian approach to managing this through UNICEF but is improving through concerted effort from the DFID team.

Work under Output 2 on government oversight and health system strengthening has grown over the last year with progress largely in line with targets giving an A score. Health systems investments will continue to increase over the next period with work led by different partners designed to provide cross-cutting support across SHINE. CHANGE is now piloting a tool to help improve quality of care through a digital approach to supervising health facility staff, a tool for government to better analyse and present district health management information data (DHIS II) for decision making, and an approach to working with the private sector to deliver essential services. Work under the Commodity Security Programme to provide supplies to SHINE Supply partners has experienced challenges in establishing working relations between Mott Macdonald and UNICEF, and in partners capability to move to forecasting supply needs. This has impacted the timely delivery of appropriate supplies. Intensive work is going on to improve this through development of a detailed joint work plan and link it to wider investment in the supply chain by UNICEF to improve forecasting and quantification of supplies. UNFPA work with health care providers to clarify values around the sensitive issue of family planning and improve their ability to offer these services has begun. SHINE Supply met their deliverables on planning their health systems investments and the emphasis is now on accelerating implementation. Work on health workforce management in particular will be important in informing future support with the World Bank.

Output 3 focuses on the SAHAN programme and demand creation. Having struggled to move from a focus on research and a lengthy intervention design process, a rapid review conducted in April provided the stimulus to accelerate progress. The programme now has 5 prototypes aimed at increasing uptake of services in the field, with early evidence of their impact available and service delivery partners already recognising their value. For example, Trocaire in their work under CHANGE in Gedo has documented a significant increase in demand for service through their pilot work with the Hooyo ku Hooyo prototype educating and referring women from the community level.

In the last year SHINE partners have shown considerable influence in the wider health sector captured under Output 4. For example, PSI’s private sector pilot work has generated significant interest from Government, and their community level work is feeding into a Government and World Bank process to update the community health strategy. SHINE partners are also influencing each other, as illustrated by UNICEF’s replication of SHINE Supply’s competitive process to contract NGO implementing partners. This should only grow as they become more established in their implementation, and regular meetings and exchanges are encouraged to facilitate this.

Quarterly SHINE partner meetings in Mogadishu and Hargeisa have been critical in improving data analysis and discussion of trends in service delivery, coordination on health systems work and sharing of lessons and experience. These will continue to ensure partners maximise the remaining time to deliver for vulnerable Somali women and children with even greater scale and impact.

An assessment of the overall risk of this programme at this Annual Review, building on the Internal Audit Review which took place in June, upgrades the level from Moderate to Major. This is in recognition of the continued insecure and volatile operating environment, the specific objective to work with and build Government capacity and an effort to better calibrate risk ratings across the DFID Somalia portfolio.

Summary of recommendations
1. Ensure lessons from the design, set up and implementation of the SHINE programme inform the future DFID health programme.
2. Focus on drawing the links between the different SHINE components via regular coordination meetings and joint work-streams to maximise impact.
3. Strengthen the working relationship between SHINE Supply (Mott Macdonald) and the Commodity Security Programme (UNICEF) and ensure enhanced performance management of UNICEF and linking to work under the Somalia Humanitarian and Resilience Programme (SHARP).
4. Increase the focus on use of data to drive performance and strengthen work on inclusion.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Improve the standardisation, coverage and quality of Essential Package of Health Services (EPHS)
Output number per LF		1	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Overall Results
Indicator(s)[1]		CHANGE[2]	SUPPLY[3]	UNICEF[4]	Score
Output Indicator 1.1					A
1.1a) % of EPHS facilities offering integrated modern birth spacing (health centre, referral health centre, hospital)	EXPXP	80%	70%	40%
	ACH	86% (24 of 28 facilities)	96% (65 of 68 facilities)	50% (23 of 46 facilities)	A
1.1b) % or # of supported health facilities offering nutrition specific intervention package in the course of routine health service delivery (primary health unit, health centre, referral health centre and hospital)	EXP	100%	90%	60%
	ACH	94 (93 of 99 facilities)	95% (110 of 116 facilities)	50% (56 of 113 facilities)	A
Output Indicator 1.2					A
1.2) # of women receiving modern birth spacing methods (total users)	EXP	3681	3228	920
	ACH	4,043	1386	245	B
Output Indicator 1.3					A
1.3) # of women delivering with the help of a skilled birth attendant at a health facility	EXP	17,044	48,884	7,433
	ACH	18,943	44,064	2,516	A
Output Indicator 1.4					A
1.4) # of U1 children vaccinated with pentavalent 3 doses	EXP	30,456	38,520	7,015
	ACH	29,713	59,311	3,436	A
Output Indicator 1.5[5]
1.5ai) # of children aged 6-59 months receiving a package of nutrition specific interventions	EXP	269,259	116,790	30,692
	ACH	268,667	41,801	8,689	A
1.5aii) # of pregnant women receiving a package of nutrition specific interventions	EXP	74,297	53,958	12,602
	ACH	87,889	60,004	9,175	A
1.5aiii) # of lactating women receiving a package of nutrition specific interventions	EXP	Working on disaggregating (currently included with pregnant women)	Working on disaggregating (currently included with pregnant women)	12,602
	ACH			2,964	B
1.5bi) # of under-fives on SAM treatment (number)	EXP	8775	TBD	3,750
	ACH	6314	3791	1,016	B
Output Indicator 1.6
# of women attending 4+ ante-natal visits (note this was 2+ visits for 2016 AR, and 3+ for 2017/18)	EXP	6,023	17,424	5,846
	ACH	7,799	17,448	2,371	A
Output Indicator 1.7					A
Total # of outpatient visits	EXP	508,939	439712	83,102
	ACH	508,069	456,395	64,686	A
1.7ai) Total # of male out-patient visits (0-59 months)	EXP	Target only set for total outpatient visits (508,939)	107,873	12,276
	ACH	107,392	101,510	13,241	A
1.7aii) Total # of male out-patient visits (5 years and older)	EXP	Target only set for total outpatient visits (508,939)	63,315	29,230
	ACH	127,462	70,127	13,744	A
1.7bi) Total # of female out-patient visits (0-59 months)	EXP	Target only set for total outpatient visits (508,939)	120,183	12,276
	ACH	121,136	111,555	15,102	A
1.7bii) Total # of female out-patient visits (5 years and older)	EXP	Target only set for total outpatient visits (508,939)	188,697	29,230
	ACH	200,932	173,203	22,599	A
[1] See Annex 2 for reconciliation of output 1 results from UNICEF bridge funding reported under earlier Annual Reviews.
[2] CHANGE figures include results for Oct 2018 to Sep 2019 – targets were set for the year.
[3] SHINE Supply figures include results for April-Sep – targets were set for the end of September.
[4] UNICEF’s figures include results for July-Sep – targets are also for a single quarter.
[5] Work going is going on to update the DFID Somalia nutrition methodology note for reporting against DFID SDP targets, these numbers (and 1.1b) represent best current estimates but may be slightly revised when this process is complete.

Briefly describe the output and provide supporting narrative for the score
This output captures the essential service delivery through CHANGE, SHINE Supply and UNICEF Service delivery and represents the core of the SHINE programme. The overall score is assessed as A.
Under the CHANGE programme, work has continued at scale to reach over half a million people with essential services. Targets for core maternal and child health services (output 1.3 skilled birth attendance, output 1.5 preventative nutrition, output 1.6 antenatal care and output 1.7 outpatient care for common illnesses) have all been met. Birth spacing is well integrated, with Trocaire who were previously lagging behind, now making good progress under outputs 1.1a and 1.2. Issues with nutrition supplies and termination of USAID funding to outreach temporarily affected delivery on nutrition treatment (output 1.5bi) and immunisation (output 1.4). However, inclusion of outreach in the revised DFID budget, and work by DFID to facilitate Change partners to access nutrition supplies from UNICEF have already seen trends in service delivery increase again. Areas for improvement found by third party monitoring, particularly around the quality of services available at lower level facilities, have been fed back to partners and are being worked on.
After a competitive contracting of partners and short set up period SHINE Supply began delivery in early 2019. Despite some issues with supplies provided by UNICEF under the commodity security programme (see output 2) partners have met or nearly met core maternal and child health targets (see outputs 1.3 skilled birth attendance, 1.4 immunisation, 1.6 antenatal care, 1.5 preventative nutrition and 1.7 outpatient care) with particularly impressive performance on immunisation. Trends in utilisation are still increasing and this is attributed to strengthening of the referral network through ambulances, partnerships with SAHAN and the work of outreach teams. Progress on birth spacing under output 1.2 has represented a greater challenge. While services are increasingly available the sensitivity of this work means that uptake requires additional support. This will be provided through partnerships with UNFPA (see output 2 and SAHAN (see output 3). Nutrition treatment under output 1.5bi has also faced challenges. UNICEF chose to allocate nutrition supplies from the humanitarian pipeline to SHINE Supply partners but the administrative process to enable this was neglected leading to delays in their delivery. Issues accessing historical data also inhibited development of meaningful milestones. These problems have now been fixed and meanwhile facilities continued to offer important preventative nutrition services.
Delivery under UNICEF service delivery programme is at an earlier stage due to time taken to finalise locations and NGO partnerships for delivery. A similar competitive process with Government closely engaged in the partner selection was replicated from SHINE Supply. Services began to roll out from July 2019 and are yet to start in Buhoodle. Better progress has been made in providing outpatient services (output 1.7), including antenatal care (output 1.6) and nutritional support to pregnant women (output 1.5aii); while birth spacing (output 1.2), delivery care (output 1.3), immunisation (output 1.4) and nutrition services for children (output 1.5ai &1.5bi) are further behind and services are still being set up. Locations include those with historically low vaccination rates and work is going on to strengthen the cold chain using GAVI funds. Nutrition integration should not be problematic given UNICEF’s management of the severe acute malnutrition treatment pipeline. Even with annual milestones given pro-rata for the quarter July-Sep, achievement of targets is lagging across outputs. UNICEF have flagged concerns with the over-ambition of targets based on district populations targets pushed for by Ministries of Health and these are being revisited. UNICEF issues are assessed as lying primarily with delays in contracting partners rather than performance in delivery; and trends look positive with utilisation figures expected to pick up as partners fully establish implementation.
Challenges and Risks
The three main challenges for service delivery have been:
1. The late initiation of services under the UNICEF service delivery programme affecting service delivery results with milestones not amended to accommodate the delays. However, there is positive indication that full implementation will soon be reached, and milestones are being revisited to ensure they are realistic for the next year.
2. The inconsistent provision of equipment and supplies by UNICEF under the CSP to SHINE Supply partners. Partners have made positive progress despite this, but delivery will be further improved with strengthening of working arrangements between Mott Macdonald and UNICEF.
3. The selection of a single implementing partner, HPA, under three fund management agents – PSI, UNICEF and Mott MacDonald. This has stretched the partner’s capacity and concentrated risk in a single partner. Measures are being put in place to help support HPA to deliver across the programmes.

Lessons and recommendations:
Ensure realism on time taken to initiate service delivery: Experiences from set up of SHINE Supply and the UNICEF Service Delivery programme (agreement on delivery locations with Government, negotiation of partner contracts and preparation of facilities for service delivery) provide clear lessons for a future programme on both the importance of realistic timelines and the significant investment of time, resources and energy needed to manage this process effectively.
Recommendation: In designing future support realistically estimate the investment and time taken to navigate the set-up phase of any service delivery work and do not over-estimate expected results during this period.
In partner selection consider ability to deliver multiple components: The processes to select partners under both SHINE Supply and UNICEF Service Delivery did not look at the ability of individual partners to deliver across multiple components. This has seen the same NGO awarded multiple contracts, which has the advantage of simplifying the delivery chain, but has caused concerns about their capacity.

Recommendation: Ensure agreed monthly meetings take place to enable a harmonised approach to managing HPA by PSI (CHANGE), Mott Macdonald (SHINE Supply) and UNICEF and ensure issues with capacity are jointly addressed.

Carefully consider partner working arrangements and UNICEF performance: The SHINE design includes the provision of commodities by UNICEF through the CSP to SHINE Supply partners managed by Mott Macdonald but with both partners ultimately reporting and accountable to DFID. The lack of an established mode of operation between the two organisations and some resistance to working closely, along with institutional issues has caused difficulties in ensuring a consistent supply chain to SHINE Supply NGO partners.

Recommendation: By December 2019 enhance performance management of UNICEF (linking to work under the Somalia Humanitarian and Resilience Programme) and agree a shared Mott Macdonald – UNICEF joint work plan with clear roles and responsibilities until the end of the programme. Carefully consider the ability and modality for UN and private organisations to work closely in any future programme.

Facilitate coordination and communication between partners: Experience managing the multiple SHINE components, in particular the 4 which have some role in service delivery, has highlighted the importance of ensuring communication, coordination and learning between partners to ensure a coherent approach. Specific opportunities for synergy exist with UNICEF and SHINE Supply supporting districts in the same regions, and partnerships with SAHAN to promote utilisation of services.
Recommendation: Ensure quarterly SHINE partner meetings take place in Hargeisa and Mogadishu with the Ministry of Health; and encourage regular engagement between PSI, UNICEF and Mott Macdonald as management agents to ensure lessons are shared and approaches harmonised.
Strengthen data-driven approach: A greater focus on data analysis, particularly as part of quarterly reports and review meetings has improved discussion on performance. This should be based on a continued harmonisation of reporting across partners to enable comparison.

Recommendation: Continue work with MESH to finetune the log frame and finalise the SHINE dashboard by December 2019 to facilitate improved analysis of partner data and strengthen the quality of discussion and decision making.

Focus on gender and social inclusion. A strategy was developed under SHINE Supply and shared with other partners, but a greater focus needs to be placed on implementation and addressing the supply and demand side barriers to access.

Recommendation: Work with partners and MESH to incorporate better monitoring and addressing of social exclusion issues in service delivery work by first quarter of 2020.

Output Title	Strengthen government oversight of service provision (monitoring and data use; supply chain systems; health information systems; human resources for health)
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Overall Results
Indicator(s)		CHANGE	SHINE SUPPLY	Score
Output Indicator 2.1				A
Monitoring, supervision & health information use 2.1a) % or # of regions/districts conducting 4 quarterly “integrated” supportive supervision visits per year	EXP	100%	100%
	ACH	85% / HPA 2 districts (100%); SCI (3 of 5 districts (60%); Trocaire 4 districts (100%)	85% / (2 quarters April to Sep)	B
Monitoring, supervision & health informal use 2.1b) % of follow up recommendations from integrated supportive supervision visits actioned	EXP	50%	25%
	ACH	HPA (6 of 7); SCI (25 of 31); Trocaire (6 of 9). / Total: 78%	25% / (2 quarters April to Sep)	A
Monitoring, supervision and health information use 2.1c) Number of tangible examples of data and evidence being used for decision making and service improvement involving government.	EXP	3	3 examples
	ACH	+3 / (e.g. inclusion of TB case detection in outreach Gedo as a result of low case load).	7	A
Output Indicator 2.2		CHANGE	UNICEF CSP (providing supplies to SHINE Supply)	B
Strengthened supply chain 2.2a) Lead time - average number of days from order being submitted to supplies arriving at partner warehouse in country	EXP	180 days	100 days
	ACH	20 – 120 days	Jan-March: 40 days / April-June: <120 days / July-Aug: >120 days	B
Strengthened supply chain 2.2b) % of regions/districts /facilities reaching key milestones for moving to forecasting and quantification of essential drugs and commodities	EXP	Primary health units: 30% Health Centres: 40% Hospitals: 50%	Primary health units: 30% Health Centres: 40% Hospitals: 50%
	ACH	100% (Trocaire) / 70% (SCI) / TBC (HPA)	Not achieved	C
Strengthened supply chain 2.2c) tangible examples of a more streamlined and efficient supply chain	EXP	1 example	1 example
	ACH	Example provided from HPA on improvements in Berbera hospital.	2 (Evidence of increased use of LMIS; / plan in place for national quantification and forecasting exercise in FGS).	A
Output Indicator 2.3		SHINE Supply		A
Strengthening Performance of District Health Management Teams (DHMTs)	EXP	THET first visit to Somaliland and Somalia and consultation with MOH officials completed and report with findings. AR input with lessons learned.
	ACH	Achieved		A
Health Workforce Management Strengthening	EXP	CGA WP and budget completed. CGA first visit to Somaliland and Somalia and consultation with MOH completed and report with findings.
	ACH	Achieved		A
Supply Chain Management Strengthening	EXP	IPA attended HSS consultation meeting and conducted first consultation visit to Somaliland and Somalia. Report with key findings. Review TOR and focus for IPA support. Strengthen interaction with UNICEF. AR input with lessons learned.
	ACH	Achieved		A
Strengthening of operational planning process, data analysis and use, and health sector coordination	EXP	TOR for approach completed. WP and Budget completed. Data collection on coordination structures and processes started and reported upon. WB consultation meeting started. First consultation meeting to Mogadishu.
	ACH	Achieved		A

Briefly describe the output and provide supporting narrative for the score
This output captures work with Government on strengthening the health system in Somalia across CHANGE, SHINE Supply and the Commodity Security Programme. The overall score is assessed as A.
Under CHANGE with service delivery well established, partners have successfully introduced a focus on quality improvement and use of data (output 2.1). To support the former, quarterly supportive supervision by Government are well institutionalised and the focus is now on piloting a digital tool the ‘Health Network Quality Improvement System (HNQiS) to make the system more efficient and help ensure recommendations are implemented. PSI has also shared the tool widely and will work to encourage uptake by other SHINE partners. Under their drive to improve use of data for decision making (Data 2 Action framework) PSI are also working with Government at a range of levels to help them analyse and make better make use of DHIS II data in CHANGE regions. PSI has also made good progress in their work with the private sector supporting a network of providers to collect and report data into the DHIS II in Somaliland and provide quality and affordable services in line with the EPHS. Case studies are being documented and lessons collated into a protocol for working with the private sector. The focus of the next year is to accelerate the work across quality, data use and working with the private sector and demonstrate tangible impact.
Output 2.2 was introduced after the last Annual Review to better capture progress under the Commodity Security Programme (CSP) as it entered full implementation. This programme has two main functions: 1) To procure and distribute supplies to partners under SHINE Supply (and allow them to deliver under output 1); and 2) To make investments to improve management of supplies more broadly.
The inception phase was jointly implemented by UNICEF and UNFPA (August 2017- December 2018) with a new simplified modality agreed at the end. This saw UNICEF take responsibility for all procurement and distribution of commodities to SHINE Supply partners and lead on building institutional supply chain management capacity. A more specific role was agreed for UNFPA to work with health care providers and support them in offering family planning services in recognition of the sensitivity of these services in Somalia.
Output 2.2a looks primarily at UNICEF’s effectiveness in timely procurement and distribution of supplies to partners under SHINE Supply with the intention of moving gradually from a ‘push’ kits-based system to a ‘pull’ system based on request for particular items from partners. To date January-June supplies were quantified by UNICEF (with partner input) based on kits. Data on lead time presented is from UNICEF but Mott Macdonald analysis shows a different picture as well as issues with provisions received not matching orders. An analysis to triangulate information is currently being finalised. Efforts to have partners quantify and forecast supplies for July-December revealed issues with capacity to do this and led to delays in these orders being placed and therefore received. Additionally, there were issues establishing an approach for partners to access UNICEF’s humanitarian nutrition supply chain which is handled separately from health commodities. A detailed work plan is now being developed to ensure the working arrangements improve. For these reasons, despite the CHANGE programme’s progress, this indicator scores B.
Output 2.2b looks specifically at the shift to a ‘pull system’ through improved forecasting and quantification in SHINE supply areas and this has not been achieved. Some supporting activities have taken place e.g. updating of LMIS tools based on experience using them, but progress on this is top priority for the next year. Output 2.2c captures UNICEF’s wider supply chain management work building on that under the inception. Positive achievements include nationally some improvement in inputting of data into the logistic management information system (LMIS), and ability to use this to track and plan; and establishment of Commodity Security Technical working groups (TWG) in Mogadishu and Hargeisa and agreement in FGS to conduct a national forecasting and quantification process for 2020 across the sector.
Between October and December 2018 UNFPA worked with UNICEF to wrap up some of the inception phase activities and transition these to UNICEF and develop their plans to work on family planning uptake. This will involve introduction of the injectable contraceptive DMPA-SC to Somalia (secured through the central DFID UNFPA supplies programme) to improve the method mix; and selection and initial training of MoH and SHINE Supply staff on values clarification and use of modern contraceptive methods to enable cascading to health care providers. This work will ultimately be reflected in progress under output 1.2 on family planning uptake but in the recommended update of the log frame an indicator will also be added under output 2.
The SHINE Supply programme has a dedicated health systems component working with Government through four consortium partners each with a specific lead (output 2.3). Tropical Health and Education Trust (THET) on district health management training; Charlie Goldsmith Associates (CGA) on health workforce management; International Procurement Agency (IPA) on supply chain; and Mott Macdonald International Health leading on operational planning, data analysis and health sector coordination. These partners have all met their milestones for this Annual Review which focused on consultation and work plan development with the Ministries of Health. There is now an urgent need to accelerate this work and maximise impact in the limited time remaining. A balance will be struck between investments to improve delivery under SHINE and work to help inform a future programme in collaboration with the World Bank. For example, given the health worker salary top ups represent a significant cost-driver of health sector support CGA will carry out an analysis of current practices and make recommendations for the future; THET’s support to district health management teams should yield improvements in oversight of services within SHINE; and IPA will work closely with UNICEF under the CSP to improve supply chain management.
Challenges and Risks
The three main challenges for the work on government oversight and health systems strengthening are:
1. The separation of support between multiple different components. Work should support standardisation of approaches and building of systems across the programme and sector, but the multiple channels of support makes this challenging. Efforts will continue to ensure these regular SHINE partner meetings have helped facilitate this.
2. The limited time remaining in the SHINE programme (service delivery ends December 2020). This means support needs to be correctly balanced between investments in the system at large and lay the foundation for a future programme and those that will directly support delivery under SHINE.
3. The low-base level of capacity amongst partners to move to a ‘pull’ supply system. Support to broader supply chain strengthening will help improve this but realistic targets need to be set, particularly in roll out of the logistic management information system.

Lessons and recommendations
Lessons highlighted under output 1 on the importance of strengthening Mott Macdonald and UNICEF’s working relationship to ensure consistent provision of supplies to SHINE Supply partners (Recommendation 3) and the importance of coordination between all SHINE components via regular partner meetings in Mogadishu and Hargeisa (Recommendation 4) will also underpin progress under output 2 to make long term improvements in the Somali health system.
Additionally:
Importance of coordination on key system issues: Higher-level partner coordination is not sufficient to address detailed technical issues and specific groups are needed to progress issues in particular areas. The Commodity Security Technical Working Group meetings have provided an invaluable platform to bring together health sector partners, including those not part of SHINE to discuss challenges facing procurement and distribution of commodities and health system strengthening of Supply Chain Management.

Recommendation: DFID to support quarterly TWG meetings in both FGS and Somaliland while ensuring key leadership from the MoH / MoHD. It will also explore with the Government the need for additional technical groups potentially around information management.

Strengthening log frame indicators and milestones: The indicators under Output 2 do not capture all of the activities going on (e.g. UNFPA work) and are insufficient to promote accountability on the CSP which enables SHINE Supply’s delivery under Output 1. Milestones also need to be re-visited to focus delivery in the limited remaining time, and the total number of indicators is too many. The opportunity will be taken after the Annual Review to revisit these.

Recommendation: DFID to convene a partner meeting to discuss and finalise all log frame indicators, with a focus on output 2 and the aim of reducing the total number, by the end of December 2019.

Integration of health and nutrition: The CSP experience has highlighted the divisions between UNICEF’s health and nutrition sections, and the very separate processes used to manage the respective supplies. This has caused major issues for provision of commodities to SHINE Supply partners who were contracted to deliver an integrated programme.

Recommendation: DFID will continue to advocate to UNICEF through both SHINE and SHARP support, to improve the integration of support to health and nutrition.

Shift from push to pull supply chain management system. This requires considerable changes in ways of working and investment in key skills. A pragmatic approach needs to be taken which builds gradually to full operationalisation of an LMIS system, while maximising impact on current service delivery under SHINE. Support to SHINE service delivery locations represent a good testing ground for changes in supplies management and need to be prioritised to have demonstrable impact on the ground.

Recommendation: By December 2019 revisit UNICEF’s approach to LMIS roll out and ensure it is practical and realistic for the current Somalia context. Agreement of the essential medicines list is a necessary pre-requisite to improving supply chain management.

Quality of District Health Management Information System (DHIS II) data. Issues exist with the indicators included in the DHIS and the quality of data inputted.

Recommendation: DFID and SHINE partners to provide experiences and lessons into the ongoing UNICEF led DHIS II indicator review. MESH to carry out a rapid data quality review of the DHIS II in SHINE districts by December 2019.

Output Title	Develop and support scale up of proven behaviour change interventions (healthy behaviours include health service utilisation)
Output number per LF		3	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Overall Results
Indicator(s)		Milestone 3 (Annual Review 4 2019)	Score
		SAHAN
Output Indicator 3.1
3.1 a Number of interventions designed and tested	EXP	35 prototypes designed 24 prototypes tested
	ACH	47 prototypes designed 29 prototypes tested 5 prototypes piloting	A+
3.1b Number of interventions in pilot	EXP	5 prototypes in pilot in the field (12 prototypes on track for pilot by Dec 2019)
	ACH	5 prototypes in the field and good progress against the others.	A
3.1 c Number of evidence generation and synthesis products and processes used in prototype development	EXP	15 quality evidence generation or synthesis products (cumulative – 9 reported at last AR)
	ACH	44 evidence generation and synthesis products: Innovation labs reports (4), Discovery day reports (7) - MOH, HPA, MERCY, ACF, BRICiS, Somali Justice league, Perspective media. Insight generation activity reports (4), Prototype Testing reports (29)	A+

Briefly describe the output and provide supporting narrative for the score
The 2018 Annual Review highlighted the SAHAN programme’s struggle to move from designing interventions to generating evidence and piloting these in the field with SHINE service delivery partners. In April 2019 a decision was made to conduct a rapid review of the programme through MESH (Monitoring and Evaluation of the Somalia Humanitarian Programme). The review confirmed that the programme had been too fixated on the lengthy design process and recommended prioritising a list of 12 prototypes to have in the field by the end of December 2019. SAHAN has since made good progress meeting the target of 5 by the end of September. Given the remedial actions needed to get SAHAN on track the programme scores an A rather than A+ but is showing a positive trajectory. Lessons from discontinued prototypes will also be captured and shared.
The following 5 prototypes are now in pilot:
1. Hooyo ku Hooyo (HkH): This prototype supports home visits by respected women in the community to discuss maternal and child health topics including antenatal care, facility delivery, postnatal care and birth spacing and child health and refer those in need of services. Evidence to date shows high uptake amongst those referred.
2. Birth Preparedness Class (BPC): These classes alleviate provide vital information to prepare for birth, alleviate fears and familiarise women with the health facility. It responds to the low uptake of delivery care and HkH will refer women in the community to the classes. Pilot has recently begun with class participants place of delivery tracked to monitor impact.
3. Values Clarification and Attitude Transformation (VCAT): This work recognises the sensitivity of providing family planning in Somalia and the need to start by addressing basic values and therefore attitudes to delivering care amongst providers. Champions trained under this intervention will then be used by UNFPA in their work (described under output 2). A curriculum has been developed and training begun.
4. Family Planning Method Mix: This prototype builds on the preference of many for accessing family planning services through the private sector. It will look like a gradual reduction of a subsidy to investigate if a self-sustaining cost-recovery model can be created for this.
5. Men’s Club: This focuses on improving men’s understanding and knowledge about the needs of women and children given their role as gatekeepers for women to access services. Discussions will take place in areas where men gather, and the impact on service utilisation amongst their families tracked.
The prototypes are being piloted with SHINE service delivery partners and as mentioned in output 1 the impact on uptake of services is already being realised. Evidence for the impact of each prototype will be collated and shared with health sector stakeholders. Additional prototypes are preparing for pilot in the next quarter. These include social media prototypes that will amplify specific messages including; testimonies from men role-modelling positive health behaviour and promotion of traditional nutritious foods; work with ‘super sheikhs’ to promote messages through media talks, debates and Friday prayers; updating infant and young feeding counselling tools based on SAHAN formative research and latest evidence from behavioural science; and use of an interactive voice response (IVR) to provide health education and prompt for health appointments through a partnership with a mobile provider.
SAHAN cites a range of evidence generation products under output 3.1c. Some of these are standard documents associated with the programme while others have been designed to serve as guidance and models for other partners. The latter are more aligned with the intention of this indicator but even focusing on these the milestone is met.
Challenges and Risks
The primary challenge faced by SAHAN has been shifting its operating model from a focus on new prototype design to the piloting of prototypes in the field and demonstration of their impact. The conducting of the Rapid Review helped manage this risk and provided the needed catalyst for PSI to accelerate the partnerships with SHINE delivery partners in the field and start piloting.
Lessons and Recommendations
Challenges of implementing a new approach to demand creation in Somalia. The SAHAN programme took an ambitious new approach to working on demand creation in Somalia using human centred design to generate new interventions. The complexity and capacity required to make a success of this approach was underestimated. After many challenges the programme is now on a positive trajectory and needs to keep up momentum for the remaining period.

Recommendation: DFID to closely monitor the programme using the established GANTT chart, other rapid review recommendations and regular monthly updates to ensure SAHAN remains on track.

The importance of partnering and influencing others. The nature of the programme requires PSI to partner with service delivery partners to pilot prototypes and influence other key stakeholders to institutionalise the interventions in the Somali health sector.

Recommendation: PSI to continue working closely with SHINE service delivery partners and other key stakeholders (UNICEF, UNFPA, Save the Children etc) to implement prototypes and share lessons and evidence. Establishing their interventions in other non-DFID funded programmes will be an important indicator of success (see output 4).

Monitoring and evaluation approach. A proportional approach to M&E has been agreed in order to provide robust evidence of impact without unnecessary complexity and cost. For each prototype an M&E plan is developed. An approach to consolidating and sharing this evidence needs to be finalised.

Recommendation: PSI to work with DFID and MESH to agree the approach to collating and sharing evidence by the end of December 2019.

Output Title	Promotion of a learning culture in SHINE to inform the wider health sector
Output number per LF		4	Output Score	A+
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Overall Results
Indicator(s)		Milestone 3 (Annual Review 4 2019)					Score
Output Indicator 4.1: Practical examples of SHINE partners sharing knowledge and best practices leading to a new activity/initiative by another stakeholder.					A
			CHANGE	SHINE Supply	SAHAN	UNICEF	CSP	Total
EXP	At least 10 examples where SHINE partners/others shared knowledge/best practices in ways that led to a new activity/initiative.		3	3	3	1	3	10
ACH	Numerous examples provided across partners, most of which have practical links to new activities and initiatives that will further SHINE objectives.		4	4	3	1	1	13	A

Briefly describe the output and provide supporting narrative for the score
Partners across all components have carried out a range of initiatives which have led to new activities or initiatives outside routine delivery under outputs 1 and 2. The collective achievements score A.
Under CHANGE examples include the below, although all are not all fully realised, they show positive engagements and influence.
Work to develop disability adjusted life year estimates for the impact of EPHS service provision under CHANGE stimulating interest from both SHINE partners and Ministries at recent meetings and discussion about how this approach can be extended to other regions.
- One output of the private sector work will be a protocol for engaging the private sector and productive discussions are ongoing with the Somaliland and Somalia Ministries on adoption of this.
- Work on the HNQiS tool has included engagement with GAVI/UNICEF on use of it to monitor immunisation services and agreement to include an immunisation check list. PSI has also reached out to other SHINE partners to explore opportunities for them to use it.
- CHANGE has developed a number of useful tools that SHINE supply who are considering picking up for their own use. These include a tool to define minimum EPHS standards, tools to conduct data quality assessments, a simple stock record tool and a story of change tool to capture beneficiary interviews.

Several examples of the SHINE SUPPLY teams work on others exist.
- Their focus on data analysis has seen both UNICEF and PSI improve their presentation of data at quarterly meetings.
- Their investment in using data directly from the DHIS II has pushed others to do the same, and therefore invest in the quality of data in the national system.
- Their closer engagement and collaborative approach with the Ministry of Health has eased decision making in their own programme, but also encouraged others to take a similar approach;
- UNICEF followed SHINE Supply’s approach to competitively select partners and engage FGS and SL MoHs in the final selection.
SAHAN has extended beyond partnerships with SHINE service delivery partners under DFID funds to influence the core programmes of key partners. This has included:
- Detailed discussions with both UNICEF and UNFPA who are interested in adopting some of the prototypes. Close follow up is ongoing. As prototypes have entered the field and begun to generate evidence PSI have also received significant interest from a wider range of stakeholders interested in hearing more about the interventions.
- Invited to define the birth spacing story line in an EU funded radio show ‘Sahanka Nalosha’ implemented by Perspective Media.
- Invitation from the Federal Government and World Bank to participate in work to re-define the community health strategy and learn from the Hooyo ku Hooyo and other prototypes.
UNICEF service delivery is at an earlier stage, but it aims to link with other SHINE components and share lessons and approaches. For example, they have already initiated work to look at quality of care through a proxy indicator on correct treatment of acute respiratory infections, this was presented at a recent partner meeting and generated interest from the Ministries of Health and other partners. Activities under the Commodity Security Programme are currently largely captured under Output 2. A better disaggregation of milestones for output 4 will be looked at as a recommendation of this Annual Review but work under the CSP TWG involving all sector partners, is a good example of influencing others and working to change their approach to managing supplies. UNICEF have also reached out to other SHINE partners as critical stakeholders to inform the ongoing DHIS II review funded by the Global Fund.
Challenges and Risks

The main challenge is ensuring partners place enough emphasis on this output, compared with the more tangible quantitative outputs; and value this wider influencing work to maximise their overall impact.

Lessons and recommendations

Emphasise the importance of learning and influencing. It is important partners recognise the value of influencing others to ensure the long-term impact of their work.

Recommendation: DFID to more explicitly follow this output through quarterly reviews and partner meetings to ensure sufficient effort is dedicated to it. This will be incorporated into review of the log frame and finalisation of the SHINE Dashboard with MESH by the end of December 2019.

Maximise learnings from CHANGE given its longer implementation and wide-ranging support, including in working with the private sector. Given its long history including with the predecessor programme the Health Consortium for the Somali people, it is vital lessons from this programme are shared and replicated.

Recommendation: Ensure a platform is given to CHANGE at SHINE quarterly partner meetings and PSI and partners are encouraged to actively engage with other SHINE components on a regular basis; and with the World Bank as they develop their new health project.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

The programme’s theory of change in the business case rested on 4 basic assumptions:

1. Investment through a mix of interventions and mechanisms allows for increased geographical reach, empowerment of both government and communities, combined with spreading of risks. A mixed delivery will enable organisations to focus on their areas of comparative advantage and encourage competition on efficiency and effectiveness.

As highlighted in previous Annual Reviews assumption 1 has proved more difficult in practice than in theory. While different organisations do have comparative advantages to a degree it is not clear that the focus on supposed comparative advantage justifies the resulting highly complex set of partners and coordination issues. This has been exacerbated by the staggered start of different SHINE components. The programme is now in full implementation however, with regular SHINE partner meetings ongoing, improved communication between partners and links being built between components (e.g. SAHAN partnering with service delivery partners, health systems work under different components extending across wider SHINE locations). This is mitigating the risks of the complex design and improving efficiency.

2: Improved quality and standardization of EPHS increases access to services. A focus on breadth (including nutrition and family planning) and quality could be first trialled through ‘an embedded EPHS’ model in the Change programme.

Evidence on the optimal package of services to maximise value for money and impact is still being generated. UNICEF bridge funding demonstrated the limitations of only supporting higher level facilities and neglecting the lower level, but there remain questions about the relative impact of all the interventions included in the EPHS package. Work on reviewing and prioritising the EPHS package will take place in partnership with the World Bank to inform future support.

3: Tackling key barriers to access will increase demand for health services. A greater focus on demand side barriers and wider social determinants will both prevent ill health and increase use of services when needed. Piloting and building evidence for new approaches, with a focus on the community level will improve the cost-effectiveness of demand side interventions.

The shift of SAHAN to piloting interventions in the field has begun to generate evidence to back up this assumption. Early indications show positive trends in service utilisation where partners are piloting SAHAN interventions. Evidence will continue to be collated and shared.

4: Improved supply and demand of proven health interventions will increase utilization of quality care and reduce morbidity, disability and mortality.

This assumption remains valid and is backed up by substantial global evidence and experience under SHINE to date. The early impact of SAHAN on utilisation of services is an important reminder of the importance of complementary investments in the supply and demand side. It is vital that people are influenced to use services, but unethical to raise demand if the supply side is unable to cope with the increased numbers. As further data is generated over a longer period of full supply and demand component implementation this question of optimal balance will be returned to with the support of MESH.

The theory of change for SHINE is therefore in essence that provision of quality services (Change, SHINE Supply, UNICEF); accompanied by demand creation and behaviour change interventions (ongoing activities and partnerships with SAHAN to trial new approaches); and additional systems investments will increase utilisation of quality health services (outcome level) and ultimately improve health status (impact level). Despite the complexity of the programme design the interventions are aligned to the theory of change. As a recommendation of the last Annual Review a strong focus has been placed on linkages and coherence of approach to maximise impact of the interventions through different components across SHINE, and this will continue.

Service utilisation is at the heart of the outcome level indicators in the SHINE log frame and has been reported on by CHANGE from the start. Under CHANGE utilisation has increased over the life of the programme, stabilised, and then spiked with drought or other specific increases in demand. SHINE supply shows an increasing trend in utilisation, largely due to the gradual rehabilitation of some facilities, and strengthening of community level referrals. UNICEF have observed immediately high utilisation rates of outpatient services, a reflection they believe of high needs due to recurrent drought, but they have not yet formally reported outcome data. Getting accurate population denominator figures remains a major issue however, and this data needs to be triangulated by also looking at trends in absolute numbers under output 1.

After the 2018 Annual Review additional outcome indicators were added on stock outs, uptake of services as a result of SAHAN interventions, quality of care and government leadership. It took some time to agree these and partners have subsequently been working on reporting tools. Under SHINE Supply some stockouts have been reported and work is going on to triangulate these with UNICEF reporting under the CSP and understand how this can be avoided in the future. Under SAHAN, data tracking of service utilisation amongst those receiving the Hooyo ku Hooyo intervention has begun, once piloting with all partners has been completed a composite figure will become available but trends are very positive of around 70% taking up a referral for services. The impact of each prototype on utilisation will be measured so this body of evidence will grow rapidly. The next year will see a concerted focus on measuring the agreed outcome indicators across programmes.

Outcome indicators		CHANGE	SUPPLY
Supply stock outs - % of EPHS supported facilities without stockouts of key tracer commodities in a 1-month period	EXP	70%	70%
	ACH	99% (only stock out of RDT supported in single facility in Gedo)	Stockouts reported in July-Sep quarter. Details being confirmed.
Quality of care - % reaching defined standards and & of beneficiaries reporting positive experiences	EXP	80%	Develop approach for reporting
	ACH	Tool developed to initiate reporting HNQiS	Reviewing CHANGE tools for possible use
Quality of care - % of interviewees comprising health facility users having positive attitudes about essential health and nutrition service	EXP	TBD	Develop approach for reporting
	ACH	HPA: 99% in survey of 60 users (survey across all partners planned for Dec2019)	Reviewing CHANGE tools for possible use
Supply Health Facility Utilisation Rates Numerator -Total new curative visits in a year; Denominator - Total catchment population	EXP	More than 0.7 outpatient visits per person per year	Not set
	ACH	0.74	0.1
Government leadership – Tangible examples of concrete government leadership	EXP	3	3
	ACH	3 (shift to mobile salary payment in Sahil; Government led view of Save the Children Karkaar programme July 2019; planning of Maternity wing in Dollow hospital)	5 (review of health worker salary lists in Somaliland; setting criteria for recruiting additional staff; leading on supportive supervision visits; calling for and leading coordination meetings; HSS preparatory meetings and planning)
		SAHAN
Demand Health facility utilisation Rates Numerator – Total health facility visits amongst those receiving intervention Denominator - Total number receiving a given behaviour change intervention during pilot period	EXP	20%
	ACH	Hooyo ku Hooyo 70%+

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year
Key costs and cost drivers
The SHINE programme is focuses on delivery of high impact essential interventions and is aligned with the Best Buys. The VfM approach set out in the Business Case focuses on increasing service delivery efficiencies by continuing to shift away from simple input and economy measures to focus more explicitly on the cost drivers and also track data on unit costs of EPHS delivery.

An analysis conducted by DFID with the Health Consortium for the Somali People (HCS) – now the Change Programme - in 2014 showed the costs of EPHS delivery in Somalia to be USD 5.88 per capita which is comparable to similar fragile countries of Afghanistan (USD 5.50), DRC, South Sudan, and even Ethiopia, Kenya, and Rwanda (which range between USD 5-12). Change partners have worked out their budget by output which has enabled better tracking of spend to results and monitoring of variable costs (see below). Work is going on to replicate this under SHINE Supply and UNICEF Service Delivery. Across service delivery components staff and supplies are key cost drivers. While the former has been difficult to reduce given resistance from government on increasing their contribution, harmonization with government pay scales has helped and work on improving this continues. Under CHANGE progress has been made on more efficiently competitively procuring supplies, and under the Commodity Security Programme, work on moving from kits to itemized orders to reduce wastage.

The complexity of the design, multiple agreements increases the management costs and reduces the efficiency of the programme. However, efforts are being made to strengthen linkages and avoid duplication. For example, under SAHAN a shift from designing demand creation prototypes to piloting them with service delivery partners has seen this component’s value for money increase, as evidenced by the increased utilisation of services in SHINE pilot areas.

Annex 3 shows the value for money framework agreed across SHINE components which includes service delivery unit costs, amongst other measures of economy, efficiency, effectiveness and equity. As shown below Change have begun to report against this template and other components are being encouraged to follow this model so that performance can be compared across programmes and for data to be used more actively for decision making.
Economy
For CHANGE partners there is considerable variance across partners reported input costs (per diem, consultancy, supplies) as illustrated by the per diem rates above. This is in part due to different levels of insecurity and ease of access but better justification and standardisation where applicable would be helpful, along with a breakdown of prices for specific commodities.
CHANGE / Economy VfM Indicator	PSI Change Partner	Average Unit Cost Oct 2018 - Mar 2019	Total Cost
Per Diem Rates	HPA	£11.37
	TRO	£20.00
	SCI	£40.00
	PSI	£12.00
	AVERAGE:	£ 20.84
	AVERAGE:	3.50	-£ 0.81

SHINE Supply and UNICEF service delivery have not yet reported comparable costs but this is being worked on to enable future comparison. For SHINE Supply analysis shows that the proportion of management fees to total costs has naturally decreased with the move to implementation and introduction of contracts to implementing partners. Some specific examples of include the reduction of accommodation costs in MIA, Mogadishu; and a framework agreement with an agent to reduce travel costs. For UNICEF the competitive process used to contract, caused some delays in timing but also enabled greater negotiation of costs. They have also been able to leverage on support through GAVI and Global Fund to provide complementary support to HIV, malaria and vaccination; and economies of scale provided by central pool procurement of supplies. Under SAHAN the use of costly external consulting firms has been kept to a minimum and in-house skills developed to help contain costs.
Efficiency
Across CHANGE partners unit costs for delivery of key EPHS services vary with Save the Children consistently most expensive, this is also reflected in the indicator on ratio of total budget to number reached. HPA has managed to reduce this ratio over the last year and this needs further investigation to see how cost-savings were achieved. It is likely due to economies of scale with multiple grants. Analysis of trends and differences in efficiency indicators are being explored with PSI to actively inform decision making.
CHANGE / Efficiency VfM Indicators	PSI Change Partner	Average Unit Cost	Change, earliest to latest reporting
Unit cost of delivery with a skilled birth attendant	HPA	£ 13.91	£ 2.16
	TRO	£ 8.47	£ 2.00
	SCI	£ 19.22	-£ 3.80
	AVERAGE:	£ 11.91	£ 0.20
Unit cost of OPD visit	HPA	£ 1.02	£ 0.30
	TRO	£ 1.16	£ 2.00
	SCI	£ 6.46	-£ 2.91
	AVERAGE:	£ 2.88	-£ 0.20
Ratio admin costs/total other costs	HPA	8%	£ -
	TRO	8%	£ -
	SCI	6%	£ -
	PSI	10%	£ -
	AVERAGE:	8%	£ -
Ratio total budget to number reached	HPA	£ 3.58	-£ 4.31
	TRO	£ 4.28	£ 0 .67
	SCI	£ 6.13	-£ 0.61
	PSI	£ -	£ -
	AVERAGE:	3.50	-£ 0.81

SHINE Supply has not yet reported on the unit costs associated with key services, as done by CHANGE, although data being collected will enable this in the future. The table below however shows a useful breakdown of direct (by output) and indirect costs, with the indirect/admin proportion higher than that under CHANGE (although precise definitions of categories requires further investigation). The table rightly shows the greatest spend against output 1 focused on delivering services and with the most direct impact on health outcomes. Future reports should include the ratio the ratio between direct and indirect costs and total numbers of people served.
SHINE SUPPLY Efficiency indicator / Ratio admin costs/total other costs	Total Spent	% of Annual Budget	% of Total Programme Budget (until March 2021)
Output 1: Support for the Essential Package of Health Services (EPHS)	2,608,187	61%	13%
Output 2: Health Systems Strengthening (HSS): assessment and roll-out	489,389	11%	2%
Output 4: Promotion of a Learning Culture in SHINE to inform the wider health sector	338,618	8%	2%
Subtotal:	3,436,194	80%	17%
Management (Mott Macdonald management team costs)	583,553	14%	3%
Security/Duty of Care	265,237	6%	1%

UNICEF are also collecting data to enable calculation of service unit costs; and under the Commodity Security Programme the implementation of national forecasting and a supplies management system will help reduce waste. SAHAN is collecting data during the current pilot phase which will allow a unit cost per prototype to be generated.
Historic data from the life-time of SHINE will be used to generate an updated average unit cost for delivery of EPHS and inform the next phase of programming with the World Bank.
Effectiveness
The CHANGE programme has demonstrated effectiveness through maintaining strong service utilisation, avoiding stock outs of key supplies that would limit service delivery ability (outcome level), and by demonstrating evidence of government leadership (output 2). PSI has also used their health impact calculator http://impactcalculator.psi.org/calculator/311 to estimate disability adjusted life years and deaths averted in the last year, which total 120,875 and 1433 respectively. SHINE Supply has also shown positive trends in utilisation and government leadership, although issues remain with stock outs which need resolving to ensure effectiveness. There are positive signs that utilisation of services will also pick up in UNICEF service delivery districts; and that the addition of SAHAN to help generate demand across SHINE service delivery areas will have a positive impact on the overall effectiveness of the programme. The impact of individual protypes on utilisation of services will be measured.

Equity
Equity was a very important consideration in the choice of locations for service delivery under both SHINE Supply and UNICEF service delivery. As far as data allowed, population size, health needs and the level of other financing were all criteria. Outpatient service delivery data is disaggregated by sex under all programmes and current trends unusually show lower numbers of boys. Early exploration implies this is due to data input error rather than an actual trend. All programmes are working to improve social inclusion, including of the disabled; and existing SAHAN prototypes have a specific focus on reaching those that have not historically had contact with health services.

Lessons & Recommendations
1. Use MESH to support better harmonisation of VfM reporting across SHINE components in line with the agreed framework to enable comparison (some of these are already integrated into the log frame e.g. utilisation, stock outs). Partner meeting with MESH on VfM to take place in December 2019.
2. Ensure UNICEF provides a VfM update in their next 6-montly report due in January 2020.
3. By the end of December 2019 further explore the variations between Change partners across key economy and efficiency indicators and opportunities to improve these

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
Overall risk rating: Major

Overview of programme risk
After an assessment of programme risk for this Annual Review the overall residual risk rating for the programme has been increased to major going forward. This is in recognition of the ongoing challenges of Somalia as an operating environment due to the weak government, high insecurity and recurrent risks of climatic shocks. The management burden of a complex programme delivery structure and set of partners. The objective to work closely with government and build their role despite their low capacity and the very limited domestic resources. And a comparison with other programmes in the DFID Somalia portfolio. This rating places the programme still within the overall DFID Somalia risk appetite.

As described earlier the initiation of the five SHINE components has been staggered over the life of the programme and a variety of delivery mechanisms are being used. Each partner maintains their own component specific Risk Register for regular risk monitoring and risks are reported quarterly to feed into the overall SHINE Risk Matrix.

Operational risks
The operational context and volatility in the security situation especially in Southern Somalia means it remains a high-risk environment. SHINE work ranges from support to more stable areas in Somaliland and Puntland to more insecure areas of Jubaland, Galmadug and Banadir. Partners working in the less stable areas are highly experienced in more humanitarian style delivery, while elsewhere work with the Government is much closer. While the risk of deterioration in security and access creating an unacceptable safety risk for implementing partners is possible in some places, the experience of partners and range of delivery channels means we are in a strong position to maintain service delivery under all but the most serious of circumstances. The team compensates for the inability to directly verify activities outside of Somaliland by use of third-party monitoring (TPM). Under LAMPS every site under the CHANGE programme was visited. This support has now transitioned to MESH and a TPM strategy including field visits and use of the call centre is being finalised.

The politics remains complex and represents an important contextual risk. While the FGS has committed to strengthening governance structures to incentivise peace and stability, relations with the FMS remain turbulent. The inclusion of Somaliland adds a further complicating factor in managing government involvement in the governance of SHINE and management of these relationships to ensure their leadership and engagement in the programme requires substantial effort and time. As noted by IAD partner coordination is an important risk, particularly when the challenges of working with Government are combined with the large number of partners working across the components. To mitigate this regular quarterly partner meetings are now carried out in both Mogadishu and Hargeisa, with all partners coming together annually in Nairobi.

Climate is also an important influence on the operating environment. Extreme events, particularly drought, are responsible for significant internal movement of people which can lead to spikes in demand for services and makes management of supplies more complex. To mitigate this IRF funds from SHARP have been allocated to SHINE partners e.g. PSI (CHANGE) and UNICEF. This has helped complement regular programme funds with humanitarian funds, in particular to support nutrition treatment.

The following risk management improvements are also being taken forward with the aim of completion by March 2020[6]:
[6] DFID Internal Audit Department visited DFID Somalia in June 2019; the report is not yet published but some initial recommendations are already being taken forward.
Risk appetite – A clear risk appetite statement for the programme will be developed, building on that from DFID Somalia as a whole.
- Risk register –The risk register is being updated and informed by the ongoing delivery chain risk mapping exercise for each component to provide a more holistic assessment of risk levels in the register.
- Risk coverage – A detailed delivery chain risk mapping exercise will look at the flow of funds to highlighting those that could materially impact the programme for escalation to the programmes risk register, to ensure adequate mitigating actions are in place to manage this risk within appetite. Risk assessments will be done on a regular basis to ensure risks materialising outside of programme appetite are escalated to office level to ensure the HoO is aware and the team can benefit from cross-office support.
- Assurance plan –The TPM strategy being developed with MESH will combine a risk focused allocation of resources with a randomised element for balance.
- Downstream assurance –The team are following up on the due diligence of downstream partners and will update risk registers accordingly.

Delivery risks
IAD flagged sustainability and value for money as delivery risks. While there are intractable issues with domestic resource mobilisation in Somalia fundamentally affecting the sustainability of interventions without external support, efforts are being made to build systems and capacity to enable greater local ownership. The value for money section outlines in more detail efforts to ensure we are maximising the return on our investments across components.

Other specific issues exist around the management of valuable medical and nutrition supplies through UNICEF and significant work is going on to improve performance management. In a similar vein issues with PSI’s delivery under SAHAN have been mitigated through an external review, close management of progress and enhanced reporting requirements.

Fiduciary risks
The SHINE programme team continues to work with our partners to strengthen risk management by ensuring strict mitigating measures are in place around aid diversion and financial management. Due diligence assessments (DDA) of all first-tier partners has been completed (Mott, UNICEF, UNFPA, PSI) with an enhanced due diligence on UNFPA, UNICEF and PSI conducted this year. The enhanced DDAs confirmed that they have fiduciary safeguards in place as per their rules and procedures to enable the thorough management of downstream partners, with stringent expenditure reporting processes which provide information of funds utilised and any balances held so far. The team is working to mitigate against the loss of valuable medical supplies across partners and ensure systems are strengthened and any incidents immediately investigated. To date audit statements have been received from UNICEF and PSI and they give no indication that funds have been spent inappropriately. We expect audit statements from UNFPA and Mott by Dec 2019.

The team is also working on strengthening the following areas:
- Resource accounting –The programme team has moved to resource accounting across all components and is working with partners to strengthen this. This includes working very closely with partners on forecasts to minimise the risk of pressure to reach unrealistically large targets
- Performance –The team will aim to incorporate financial reporting analysis into VFM and performance analysis to provide assurance funding is being spent to deliver results as intended.
- Asset management – The team will look at options for providing assurance over programme assets held in partner offices (e.g. use of TPM) bearing our inability to go to many field locations and coordinate the approach across the wider office.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Delivery against planned timeframe

Performance in delivering to planned timeframes has varied across components. This is the fourth SHINE Annual Review and the first in which all 5 components are in implementation.

The delivery of each components/ partner is assessed through progress against milestones in the logframe and regularly assessed through monthly/ quarterly progress meetings on individual programmes and SHINE wide meetings in Hargeisa and Mogadishu.

The CHANGE programme started in 2016 continuing seamlessly from its predecessor the Health Consortium for the Somali people. The budget has been realigned in order to allow for more support to quality improvement and use of data (the chosen HSS priorities under output 2) and also to allow important outreach services previously supported by USAID to continue. Quarterly reports are received and review meetings held. The programme is on track.

The SAHAN programme had a slow inception and in implementation struggled to move into partnerships with implementing partners to pilot the agreed demand creation interventions in the field. Following the decision to reduce their budget to £8m (September 2018), the programme underwent a rapid review in June 2019 (facilitated by MESH) to help prioritise and focus the remaining implementation period. The pace has accelerated and to maintain this DFID has agreed a detailed GANTT chart to track progress on a monthly basis and continues to engage support from MESH. The programme is now on track but will require close monitoring to ensure this is maintained.

The SHINE Supply Component implemented by Mott Macdonald rapidly took off after the contract was signed in July 2018. The component successfully completed the 9 months inception phase meeting all agreed deliverables in the work plan and in April 2019 and was given the go ahead to move to implementation phase. Mott MacDonald submits monthly and quarterly reports with a quarterly performance management framework agreed to assess both programmatic and technical key performance indicators in the implementation phase. Mott has consistently met its deliverables and have had a good SRM score. The programme is on track.

The Commodity Security component inception was extended due to the delays in the SHINE Supply procurement and its intrinsic link to this via its role to provide supplies to SHINE Supply partners. In January 2019 it entered implementation with agreement that UNICEF would lead on the procurement and distribution and supplies and UNFPA take a more focused role on family planning. There have been challenges with working relations between Mott Macdonald and UNICEF. To manage this the DFID team has initiated regular face-to-face meetings. DFID is also developing key performance indicators which will be used to better monitor UNICEF performance on a quarterly basis and improve the quality of programme delivery.

UNICEF Service Delivery component has been a bit slow to start due to the time taken to contract downstream partners. Although it took time to complete, the transparent competitive process with MoH involvement was considered a positive development from previous practice. After agreement on locations and signing of the MoU in December contracting took place in March/April and services started from July. The component is picking up pace but has required and will continue to need, DFID support to ensure meaningful progress during the increasingly short implementation period. UNICEF has brought on board additional staff to help in managing the programme and improvements are expected.

The Monitoring, Evaluation and Learning (MEL) element of the programme is being taken forward by MESH II programme (under the Somalia Humanitarian and Resilience Programme). So far MESH has supported SHINE in reviewing the programme log-frame indicators; conducted a rapid review of SAHAN; and has supported the writing of this annual review by reviewing the result per output, the VfM and challenges reported by partners. Alongside that, MESH is working on a TPM framework for SHINE; doing a review of the quality of data reported through the district health information system (DHIS II) and has began work on the SHINE Dashboard. Going forward SHINE will continue to work with MESH to maximise programme impact.

Performance of partnership (s)

SHINE is implemented through a mix of delivery channels aimed at leveraging the comparative advantage of NGOs, the UNs and a Private Management Agent and the flexibility this range of partners brings. This implementation mechanism has presented a platform for lesson learning but the complexity of partnership arrangements (in particular the relationship between the UNICEF led CSP and Mott Macdonald led SHINE Supply programmes) and number of partners has proved challenging in terms of management work load and ensuring coherence of approach and linkages between components.

In managing SHINE DFID has maintained good relationships with all partners. To enhance coordination, sharing of lessons and drive performance DFID holds quarterly partner meetings led by the Ministries of Health in both Mogadishu and Hargeisa and annual meetings for all in Nairobi. DFID also holds monthly/quarterly meetings with the partners to review progress and the performance of the component and partners.

Specific investment is being made in the relationship between Mott Macdonald and UNICEF to ensure improved provision of supplies to SHINE Supply downstream partners. It has also been necessary to closely manage the SAHAN programme following last year’s ‘B’ score in the annual review and the rapid review findings and DFID has put in place mechanism to continue to do this.

Given the centrality to SHINE of building Government ownership of the health sector the management of relations with Ministries of Health at all levels requires a major investment of time. The bigger politics continued to complicate things with Somaliland consistently pushing for separation of support, and to be treated on par with the Federal Government. Work is going on with the World Bank, GAVI and the Global Fund to agree a shared approach to governance of health support.

Asset monitoring and control

The partners each manage a DFID specific asset register for all equipment procured for use within the health facilities, the Ministry of Health offices and for programme operations. All projects are expected to update DFID on the asset registers during their quarterly reporting, where the lead partners of the various components conduct spot checks of the assets procured and reported by their downstream partners and cascade the findings to DFID in the quarterly report. The SHINE partners reporting cycle is in line with DFID’s YR cycle. MESH has been engaged to provide TPM support with obtaining assurance over programme assets location and status – in line with IAD recommendations.

Quality of financial management

DFID fully funds all five on-going components (CHANGE, SAHAN, SHINE Supply, Commodity Security, and UNICEF Service Delivery) of the SHINE programme. CHANGE and SAHAN are Accountable Grant Arrangements, while the UNICEF Service Delivery and Commodity Security Programmes are MoUs to the UN and the SHINE Supply component a contract with Mott Macdonald.

SHINE programme budget for the FY 19/20 is £21.9m (broken down as below), slightly up from £21.8m spent in 2018/19.

So far, SHINE has disbursed/ spent £52.5m by end Sept 2019 and will have disbursed/ spent £66.27m (74%) of total SHINE budget) by the end of this FY. The balance of £23m (26% of SHINE budget) is SHINE’s projected budget 2020/21.

In this FY, to better manage the overall SHINE budget, there was a slight reallocation within the components where £4m was reallocated from the Commodity Security component and distributed as follows:
- £1.2M – has been allocated to CHANGE component to allow for continuity of health service provision until Dec 2020
- £1.2M – has been allocated to UNICEF – Commodity Security Programme for the procurement of additional nutrition commodities
- £1.6M – has been allocated to UNICEF (£1.2m) and UNFPA (£0.4m) for Health Systems Strengthening support under the Commodity Security Programme.

Total Budget: SHINE Component Breakdown in 2018 & 2019 and spend to date

SHINE	Programme Name	Budget end Sep 2018 £m	SHINE Budget to end Sep 2019 £m	Component budgets in the 2019/20 FY	Total SHINE spend up to end Sep 2019
1. Supply
	UNICEF EPHS Bridge (ended Sept 2018)	8	8	0	£8m disbursed
	UNICEF Service Delivery	11.488	11.488	5.15	£5m disbursed
	SHINE Supply (Mott Macdonald)	20	20	8.42	£5,607,832 disbursed
	Commodity Security Programme (UNICEF/UNFPA)	15	13.8	0.4	£11m disbursed
	CHANGE (PSI managed)	27	28.2	5.47	£18,838,850 disbursed
2. Demand	Sahan demand creation (PSI managed)	8	8	2.5	£3,894,835
TOTAL		£89.610	£89.610	21.95	£52.341

Partners’ financial performance continues to vary within SHINE. The shift to resource accounting this financial year has also required additional support to partners and reprofiling and budget monitoring. SAHAN is being continually monitored to ensure it can fully utilise its remaining budget in view of previous challenges in contracting downstream partners and meeting its forecasts. On the service delivery side components (CHANGE, SHINE Supply and UNICEF), the programme team will continue to work closely with partners to regularly monitor forecasts and to mitigate against pre-payments to the UN which were flagged in the recent IAD report. The team will also endeavour to flag any changes in forecast that could impact on the overall programme spend to allow the SRO to make the necessary decisions to fully utilise the budget.

Date of last narrative financial report(s)	PSI (SAHAN and CHANGE)15th Nov; Mott Macdonald 1st Nov; UNICEF Service Delivery Report Oct 19; UNICEF/ UNFPA commodities Oct 19.
Date of last audited annual statement (s)	PSI Oct 19; UNICEF July 2018; Mott (expected Dec 2019) / Audit recommendations are being tracked at the quarterly partner meetings and updated on the SHINE delivery plan.

MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
Partners’ quarterly reports from the CHANGE, SAHAN, SHINE Supply, UNICEF Service delivery and UNICEF/UNFPA Commodity Security Programme were used to inform drafting of this Annual Review.

During the reporting period, two partner site visits, one in March to PSI/HPA managed facilities in Berbera and one in July to facilities in Hargeisa were conducted. These visits significantly contributed to triangulation of the data provided within the CHANGE partner reports. Key action points derived from the visits, particularly addressing partner gaps in service delivery have been used to develop corrective action plans that will enhance support by the three fund management agents.

Quarterly SHINE partner review meetings are conducted in Hargeisa and Mogadishu to analyse and discuss trends in service delivery, ensure the health systems support under individual programmes is taken advantage of across SHINE, and share lessons and challenges.

The Learning and Monitoring Programme Somalia (LAMPS) third party monitoring (TPM) activities for the CHANGE programme ended in June 2019. TPM across all SHINE components will now be conducted through MESH. LAMPS provided a learning report summarising findings from their monitoring which will inform MESH support. Positive findings were sited on health facility governance, HMIS reporting, availability of facility equipment and provision of ANC and nutrition services.

Work has also gone on with MESH to develop a SHINE dashboard to help present and analyse partner data, and future support will help improve VfM reporting across programmes and a rapid review of the quality of data reported through the DHIS II, and potentially the Somalia Health and Demographic survey data (SHDS).

Evidence (1/2 page)

As reflected in the theory of change strong evidence underpins the design of SHINE and its focus on delivery of services, building systems and government oversight and generating demand for services. In turn through the indicators in the log frame SHINE is contributing to the evidence base for investments in each of these key areas and ongoing learning is fed back into programme implementation and shared with other stakeholders. The partnership with MESH continues to strengthen both the use of evidence – e.g. through analysis of relevant data sources such as the upcoming SHDS; and the generation of evidence e.g. through rapid reviews and evaluations such as that conducted for the SAHAN programme. The SHINE dashboard will provide a platform for analysis of data and trends in programme performance.

Learning (1/2 page)

Output 4 in the log frame focuses on learning. DFID will continue to support partners to learn from each other during the implementation of each SHINE component. Lessons are being documented and will inform the design of the next Business Case.

Progress on recommendations from previous reviews (1/2 page)

Recommendations for the previous Annual Review have been achieved as follows:

1. CHANGE programme: The Data 2 Action and HNQIs tools for data collection and assessment of quality of care have been finalized. Roll out of these to public and private sector facilities in Somaliland, with a view to scale up in other regions is ongoing.
2. SHINE Supply: Contracting of service delivery partners was finalized in January 2019 with service delivery started between February and March 2019. Consortium Partners (CPs) for the delivery of the health systems strengthening work were contracted.
3. Commodity Security Programme: Timely and effective quantification, procurement and delivery of health and nutrition supplies for SHINE supply supported districts is an ongoing process, with initial supplies having been distributed to partners in January and March 2019. Distribution of Q3 and Q4 supplies is underway while quantification and forecasting of the 2020 supplies (including buffer stocks) has been finalized. Establishment of a good working relationship between UNICEF and Mott MacDonald requires further work for which measures have been put in place as detailed in the output sections above.
4. UNICEF service delivery: The service delivery support package was finalized, contracting was slow but partnerships are now in place with service delivery starting gradually from July 2018. Areas still pending are Erigavo Hospital in Sanaag and Bohoodle district in Togdheer but these should begin soon as partner contracts are already in place with UNICEF.
5. SAHAN testing and piloting: PSI has now moved to contracting partners to engage in SAHAN activities following the programme review in June that provided direction on how the programme needs to proceed. Impact of SAHAN demand creation activities has already been felt in Gedo and Sahil regions through significant uptake in utilization of service delivery.
6. Linkages between SHINE components: This is slowly picking up with regards to service delivery approach, health systems support and integration of demand creation activities. Ongoing SHINE partner review / coordination meetings will be used as platforms to access progress on linkages as well as mitigate challenges.
7. Monitoring and evaluation: the SHINE logical framework was successfully finalized and has been used to inform results for the drafting of this Annual Review. MESH is working with the DFID SHINE Team to ensure M&E includes a coherent approach to value for money and enables comparison of different approaches to inform future health programming.
8. Linkages with humanitarian programme: there has been significant collaboration ensured between the SHINE and Building Resilience Communities in Somalia II (BRCiS II) programme. Joint programme activities conducted include; the finalization of the BRCiS Logical framework and engaging to realize a streamlined approach to procurement and distribution of nutrition supplies. BRCiS II partners also regularly attend SHINE and CSP TWG meetings.
9. Financial management: There has been considerable traction in improving the accuracy of financial forecasting of partners, including with PSI.
ANNEX 1. ACRONYMS

Community Health and Nutrition through Local Government Empowerment	CHANGE

District Health Information System	DHIS

Essential Package of Health Services	EPHS

Federal Government of Somalia	FGS

Federal Member States	FMS

Global Alliance for Vaccines and Immunisations	GAVI

Global Evaluation Framework Agreement	GEFA

Global Fund to Fight AIDS, TB & Malaria	Global Fund

Human-centred Design	HCD

Health Consortium for the Somali People	HCS

Health Monitoring Information System	HMIS

Health System Strengthening	HSS

Internally Displaced People	IDPs

Integrated Supportive Supervision visits	ISS

Joint Health and Nutrition Programme	JHNP

Learning and Monitoring Programme Somalia	LAMPS

Management Agent	MA

Memorandum of Understanding	MoU

Ministry of Health	MoH

Monitoring and Evaluation of the Somali Humanitarian Programme	MESH

Ministry of Health and Development MoHD

Monitoring and Learning	M&L

Mott Macdonald	MM

Non-Governmental Organisation	NGO

Official Journal of the European Union	OJEU

Population Services International	PSI

Procurement and Commercial Department	PCD

Severe Acute Malnutrition	SAM

Somali Health Authorities	SHAs

Somalia Humanitarian and Resilience Programme	SHARP

Somali Health and Nutrition Programme	SHINE

Somalia Humanitarian, Health and Resilience Team	SHHARE

Terms of Reference	ToR

Tropical Health Education Trust	THET

United Nations	UN

United Nations Fund for Children	UNICEF

Value for Money	VfM

ANNEX 2.

The table below outlines the additional women reached under the 2017 and 2018 UNICEF bridge funding under SHINE. Results presented for the Annual Review differed from those in the end of calendar year results and the balance is captured here.

Output 1	2017 BRIDGING		2018 BRIDGING		Reconciliation (balance)
	UNICEF bridging Jan-Sep 2017 (for AR)	UNICEF calendar year Jan-Dec 2017 (final report)	UNICEF bridging Jan-Aug 2018 and Oct-Dec 2017 (for AR)	UNICEF calendar year Jan-Sep 2018 (final report)	Due to change in UNICEF results reported at AR versus end of calendar year
# of women delivering with the help of a skilled birth attendant	48651	100904	95304	70988	27937 additional women not reported in earlier ARs
# of children vaccinated with pentavalent	95058	202535	162132	132,400	77745 additional children not reported in earlier ARs
# of U5 children and # of pregnant women receiving nutrition specific interventions	81317	762975 / CU5 264678 / PLW 498297	466515 / CU5 not included / PLW 466515	630,502 / CU5 207336 / PLW 423166	845645 additional women and children not reported in earlier ARs

ANNEX 3. SHINE Value for Money framework

4 Es	Key indicators	Monitoring
Economy / (Lowest price for Inputs of required quality)	- Consultant rates / - Per Diem rates / - Cost of key commodities	Quarterly budget reporting / Quarterly budget reporting / Reported annually (at Annual Review)
Efficiency / (Inputs produce Outputs of required quality for lowest cost)	- Unit cost for EPHS (breakdown by service) / - Ratio admin costs/total other costs and/or total budget to number reached. / - Lead time for commodities (planning to arrival in country) / - Unit cost per prototype	Report bi-annually (end Sep, end March) / Quarterly reporting / Quarterly reporting (log frame indicator) / Quarterly prototype tracker review
Effectiveness / (Outputs achieve Outcomes)	- Stock outs (monthly at facility level -focusing on key tracer drugs) / - Government leadership and ownership / - Unit cost per DALY averted / - Health service utilisation rates	Quarterly reporting (log frame indicator) / Quarterly reporting (log frame indicator) / Report bi-annually (end Sep, end March) / Report annually (CHANGE) / Quarterly reporting (log frame indicator)
Equity (fair distribution of benefits)	- Disaggregated service use data / - Choice of implementing areas / - Prototype behaviour change power	Quarterly reporting (log frame indicator) / Determined in inception phase. / Quarterly prototype tracker