Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Research for Development (R4D) Portal (Contract Title: Research for Development: Management and Maintenance of Research Database and Website)
Programme Value: £4,368,342 (since 2007)		Review Date: December 2015
Programme Code: 112152	Start Date: 1st January 2015	End Date: 31st December 2015

Summary of Programme Performance
Year	2008	2009	2010	2011	2012	2013	2014
Programme Score	1	1	70.00	83.75	A	A	A
Risk Rating	Low	Low	Low	Low	Medium	Low	Low

The above programme performance scores for previous years for the R4D programme are provided but it should be noted that they reflect previous DFID annual review reporting criteria and structure etc

Summary of progress and lessons learnt since last review

Progress has been as expected and R4D’s services are being maintained and updated, with no major issues or downtime on accessing the R4D platforms. Usage of the website and database remains consistent and R4D remains a valuable research resource for researchers, development professionals and DFID staff. Work on the “clean up” of the database and document types in preparation for handover and migration to a new R4D service has had an added benefit of DFID staff being able to learn from the CABI editorial team.

Three out of the four recommendations from the previous annual review have been actioned and completed as specified under the appropriate output and/or section. The remaining recommendation
(that the R4D programme team should work with DFIDs learning group to make sure that R4D content is accessible to DFIDs internal systems in a way that makes it combinable with other data sources) is still ongoing as highlighted under Output 1.

Summary of recommendations for the next year

The annual review team recommend that:

- Recommendation 1: the RSS feeds should be refreshed to ensure that they continue to be robust for the remainder of the programme (to ensure that they are accurate and manage risks to DFIDs reputation). In making this decision the R4D programme team should take into account any costs involved and/or the length of time any such refresh of the RSS feeds will take in light of the development of a new R4D on .Gov.UK .
- Recommendation 2: the DFID programme team continues the enhancements to the accuracy and content of the R4D database (as timing of the new R4D development permits). They may wish to concentrate in the short term on content in the database with no documents attached and/or only urls
- Recommendation 3: regular meetings with CABI editorial continue to ensure that the work required on making the R4D database ready for handover and migration are completed to time and to enable CABI to continue to share knowledge and information with the DFID programme team on the content of the R4D database

A. Introduction and Context

DevTracker Link to Business Case:	Quest No: 4910406
DevTracker Link to Log frame:	Quest No: 4910412

Outline of the programme

The UK is providing up to £335,696.00 from 1st April 2015 to 31st September 2016. CABI are the existing partner and supplier and have been managing R4D since 2007.

The R4D programme assists DFID, along with other online services such as .Gov.uk and the Development Tracker, in improving the openness and transparency of DFID funded research.
To enable it to achieve its goal and expected impact R4D has the following two key components:

1. R4D website and database
2. R4D Open Data: Linked Development and Data.gov.uk

R4D is freely accessible and open to all. Its content is searchable via major search engines such as Google. The R4D website enables visitors to access, browse and search the database of DFID funded research programmes, projects, outputs and contacts. It has both simple and advanced searches, and offers browse by Country, Region, Theme and Research Contact, as well as a system which enables users to submit and upload content via a web form and/or spreadsheet. It provides links to the DFID Research section on .Gov.uk, DFID systematic reviews, R4D Open data and an R4D usage dashboard.

R4D Open Data makes available publications metadata for other organisations and individuals to use, reuse, re-distribute, extend or build on. It enables others to use R4D publication information in other websites and databases and/or create other applications. Linked Development currently enables the Development Tracker to link to DFID funded research information and outputs held in the R4D Database. CABI are responsible for managing the content of R4D and its database.

R4D is a valuable research tool for researchers, policy makers and development practitioners. There is no other existing online system or website which provides this information. The R4D database holds nearly 50,000 programme, project and document records from the 1990s to the present day. In 2015, (from January to November) the R4D website had 1,687,593 visits and 1,259,486 downloads of DFID funded research from the R4D database[1].
[1] Figures taken from the R4D usage Dashboard http://r4d.dfid.gov.uk/UsageDashboard.aspx. (data for September 2015 was lost so August usage data was used to estimate September figures)

The planned outputs and deliverables under the existing contract (Amendment 10) are listed below. The main activities involved are for maintenance of and support to the R4D sites, platforms and data, including the updating and uploading new DFID funded research outputs and programme/project information to the R4D database by CABI staff. In addition, CABI will provide a managed handover (when required) of all R4D data and outputs, as well as the structured closure of all existing sites, platforms etc once a new R4D solutions has been built on .gov.uk

To support and maintain, on a day to day basis, the R4D website, platforms, their material and/or applications to ensure that all services and material/data on them are accessible to all R4D users.

To support and maintain, on a day to day basis, the updating and uploading of DFID funded inputs and outputs.

To support, update and maintain R4D Open Data (including the API for the DFID Development Tracker).

To manage the handover and migration of R4D content and data to DFID and/or its consultants and/or a new R4D service

To contribute to the GDS process for the development and build of the new R4D service on .Gov.uk (as required and requested by DFID).

The Discovery Phase for a new R4D was completed in October 2014. Following the Discovery Phase Research and Evidence Division (RED), Business Solutions Division (BSD) and the Government Digital Service (GDS) have made decisions on the way forward for R4D and in early 2015 a Business Case for a new R4D service on .Gov.uk was approved. RED and BSD are currently in procurement for suppliers to develop and build a new R4D on .Gov.uk. The new R4D is expected to go live prior to the end of September 2016.

During 2015 the DFID programme team and CABI prioritised work on the R4D database to ensure that R4D content is ready for migration (and risks around migration are managed) and to action outcomes from the Discovery Phase. The first stage and major part of the work on the R4D content was completed at the end of December 2015 and centred on streamlining what CABI added to the database (to core document types only), and the retagging and deleting of content as specified by DFID (to make migration easier).The DFID programme team and CABI expect to continue with minor cleaning up of the database into 2016 (or until a date for migration is agreed.

As this is the final Annual Review for the R4D Programme (the programme ends in September 2016) and as DFID has already agreed a way forward for R4D the review team will take this into account when making recommendations for this programme.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The programme is on track and meeting the agreed deadlines. CABI staff are experienced in the management and maintenance of R4D and have the skills and experience required.

As the Outputs suggest CABI have kept R4D and its services maintained, available and updated. The majority of activity during this period for both CABI and DFID has been on Output 2 (content delivery). Work on content was mainly prioritised to manage risks around migrating content to a new R4D and to focus on core research outputs from DFID programmes and projects. All document types were reviewed and a list of core document types for harvesting and retagging agreed with CABI. CABI ran 14 reports and from these updated around 8000 items. All content of core document types were retagged and where necessary CABI have updated, retagged and/or deleted content in the database manually. Clean up is expected to continue into the next period and up to the end of the contract and/or migration to the new service on .Gov.uk.

Work on the “clean up” of the database and document types has had an added benefit with DFID staff being able to learn from the CABI editorial team.

The only work which has not been completed is the handover and migration of the R4D database as DFID is currently in procurement for a provider to develop a new service on .Gov.uk.

Overall output score and description

Overall score is A. The programme is meeting expectations.

Key lessons

- The regular editorial meetings have been successful in agreeing and moving forward the work required for migration of the database as they have enabled DFID and CABI to agree work and deadlines to achieve them.
- The regular editorial meetings have enabled the CABI Editorial Team to share their vast knowledge and experience of the database and its content with the DFID R4D programme team. It is expected that the current R4D Programme Team will manage the new R4D when it is built and this knowledge transfer has given them a better and deeper understanding of DFIDs research outputs on R4D
- Purdah restrictions which stopped all social media and most communications activity during the 2015 General Election impacted on the numbers of users directed to R4D and usage dropped significantly for a short period by 28k in visits (from March to April 2015) to R4D (in the same period last year visitor numbers rose by around 3,500 from March to April 2014).

Key actions
- Review R4D’s RSS feeds to see if they can be updated (within timeframes for development of new R4D and to ensure value for money)
- Continue with minor content clean-up of the R4D database (until migration is confirmed) now that the major work has been completed.

Continue regular meetings with CABI editorial to ensure that the clean-up work is on track

Has the logframe been updated since the last review?

Yes.

The Logframe has been amended to reflect the recommendations from the previous annual review to adjust the risks for Outputs 1 and 2 to Low as well as, updating Output 3 to include migration of the R4D database to the new R4D on .Gov.uk and the closure of all existing platforms.

## C: DETAILED OUTPUT SCORING

Output Title	Content Accessibility: R4D website and database content is accessed/used. Content is accessible to users in a range of forms and formats
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

*the existing contract has break clauses every 2 months from the 31 Mar 16 until end of contract 31 Sept 16
Indicator(s)	Milestones*	Progress
Output Indicator 1.1: Content is accessed and used	Target March 2016 - Increase in monthly visits, unique visitors and downloads	Slightly missed target. Metrics do not reflect the total usage of R4D and its services due to loss of data in September and usage for August has been used to estimate September usage of R4D. As in previous years there was also the usual drop off in usage due to the summer but in addition in 2015 there was also a short, sharp drop in usage during Purdah (as DFID in accordance with policy did not use Twitter to promote R4D content). Despite this loss of data and Purdah fluctuations usage remains substantial – average monthly visits to the website 152,807, unique visitors 79,800 and downloads 125,681.
Output Indicator 1.2: Content is accessed and used by users in the north and south (developing countries)	Target March 2016 – Maintained and/or increased global reach/number of developing/emerging countries in top 10	Exceeded target. Six developing and emerging countries are in the top 10 when ranking by visitors –India, China, Ethiopia, South Africa, Nigeria and Philippines. This is an increase of 2 countries since the last review.
Output Indicator 1.3: Content is accessible via key search engines/reference services and through feeds	Target September 2016 – RSS Feeds accessible and metatags maintained	See below

Key Points

Usage during this period is substantial and remains steady but is down for some indicators since the last annual review. The monthly averages changed by 3,252 visits to the website (2% increase), 6,200 unique visitors (7.2% drop) and 17,652 downloads (12.3% drop) (2014 the average number of monthly visits were 149,555, unique visitors 86,000 and downloads 143,333).
- The reason for the drop in downloads and unique visitors is not know. Usage during 2015 has, as in previous years, been impacted by seasonal fluctuations over the summer, loss of usage data in September and additionally dropped for a short period as a result of Purdah restrictions by 28k in visits (from March to April 2015) .
- Developing/emerging country usage of R4D content has slightly increased this year. In general developing country usage is increasing at approximately the same rate as the site in general.
- Website content site maps are released to key search engines on a daily basis. Metatags optimised for Google Scholar are released on a daily basis as part of standard operating procedures. Scholar updating procedures have been updated to force re-crawling of pdf documents where they have been replaced or edited so that Google Scholar also updates R4D pdf document details.
- Subscriptions to Key Theme and Country Feeds have slightly declined during 2015. It should be noted that the technology on which the feeds run is now becoming quite old and has therefore experienced some minor issues during this reporting period.

DFID R4D programme staff regularly tweeted new outputs (except during Purdah) which were added to R4D, including outputs from small projects like the Policy Research Fund which are often not published elsewhere on the internet and not tweeted by other organisations

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations from last Annual Review: The previous review recommended that the Logframe risk rating for this Output should be updated and reduced to low. This has been actioned. It also recommended that the R4D programme team should work with DFIDs learning group to make sure that R4D content is accessible to DFIDs internal systems in a way that makes it combinable with other data sources. The R4D programme team is currently working with BSD regarding joined up search (BSD are taking forward some aspects of the learning groups work) - Stage 1 is due to complete March 2016 and includes further research into research/search tools to prepare for Stage 2, quick wins and encouraging better use of existing search tools. Stage 2 (a new project to acquire and implement improved search tools) is currently expected to move forward once another IT project is completed in spring 2016.

Recommendations

Recommendation 1: the RSS feeds should be refreshed to ensure that they continue to be robust for the remainder of the programme (to ensure that they are accurate and manage risks to DFIDs reputation). In making this decision the R4D programme team should take into account any costs involved and/or the length of time any such refresh of the RSS feeds will take in light of the development of a new R4D on .Gov.UK .

Output Title	Content Delivery: Content in the R4D database is updated and maintained
Output number per LF		2	Output Score	A+
Risk:		Low	Impact weighting (%):	30
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

*the existing contract has break clauses every 2 months from 31 Mar 16 until end of contract 31 Sept 16
Indicator(s)	Milestones*	Progress
Output Indicator 2.1:Content updated and added to the R4D database	Target September 2016 - Records/content added/updated to R4D database in timely fashion	Day to day updating etc. is ongoing. A breakdown of the overall numbers of material added during the review period is given in the table below. CABI action requests from DFID for outputs/projects to be added as well as actively search for DFID research outputs on the internet. The priority work throughout the review period was to undertake clean-up of content and document types which completed end December 2015
Output Indicator 2.2:Content maintained, up to date and accurate	Target September 2016 - Records/content maintained and amended in a timely fashion	Work on this indicator is ongoing and also included on clean up. During this period CABI editors continued the rolling programme of updating projects and outputs. CABI also action ad hoc requests from the DFID R4D programme team and/or DFID staff normally within 24 hours. Monthly search engine optimisation reporting allowed for prompt correction of broken links. The clean-up work throughout this period has also assisted in making the database more accurate and up to date
Output Indicator 2.3:Document types, Metatags/metadata cleaned, updated and maintained to improve accuracy of content	Target September 2016 – regular and ongoing update of data and tags	Minor cleaning up of metadata tags has been ongoing as required. During the majority of this period CABI have been working on the “clean up” of the document records and types with the R4D programme team. CABI have met the agreed deadlines for the clean-up of document types.

Key Points

- This period has seen CABI and the DFID programme team concentrate on the work required to prepare the R4D database for migration and handover. CABI editorial team have engaged fully in this process with DFID. Their understanding of DFID requirements and their experience have assisted this work and meeting deadlines.
- The clean-up work has been significant to ensure that the R4D content can be easily migrated and to focus content added on core research outputs. All document types have been reviewed and a list of core document types for harvesting and retagging agreed with CABI. CABI ran 14 reports for DFIDs review and actioned updates to 12 reports (estimated update of over 8000 items). All content of core document types were retagged (to do this their editorial and IT established an automated process). Also where necessary CABI have updated retagged and/or deleted content in the database manually (as the numbers were small).

Doc Types	No of items in Spreadsheet
Documents	1420
Drafts	308
Flyers	241
Blogs	44
Training events	272
Events	71
Web content	897
Meeting reports	567
Computer software	63
Manuals	505
Training materials	167
Research papers	3659
Discussion papers	453
Visits	3
Total Documents	8670

Whilst undertaking the priority clean-up work, CABI have also continued the day to day work of keeping the database up to date and current. During this period CABI confirmed that there were no significant backlogs of material to add to the database.
The table below[2] shows the month by month breakdown of the total numbers of projects, outputs and organisations in the database, up to and including November 2015 (statistics for December are not available until mid-January 2016). The table clearly shows the fluctuations and impact on the R4D database and its content of the “cleansing” work undertaken in 2015 (work concentrated on outputs so organisation and project record numbers were not as significantly impacted). The bulk of the clean-up work was done during September – November 2015. Projects and outputs were still added during this period for example the individual projects under the Policy Research Fund (PRF) and the Humanitarian Innovation and Evidence Programme (HIEP) – which is the reason for the increase in the number of projects added.
[2] Figures taken from the R4D usage Dashboard http://r4d.dfid.gov.uk/UsageDashboard.aspx. (data for September 2015 was lost so August data was used to estimate September figures)

Date	No of Projects	No of Outputs	No of Organisations
Jan-15	5,660	38,347	4,266
Feb-15	5,732	38,602	4,299
Mar-15	5,760	38,888	4,310
Apr-15	5,784	39,055	4,325
May-15	5,807	39,171	4,326
Jun-15	5,814	39,297	4,329
Jul-15	5,818	39,492	4,331
Aug-15	5,850	39,064	4,340
Sep-15	5,850	39,064	4,340
Oct-15	5,869	38,317	4,341
Nov-15	5,874	38,468	4,342

- Indexing and metadata quality continue to improve in response to cleaning up of document types and links, updating of authority files and controlled vocabularies[3].
  [3] Authority files and controlled vocabularies can be added to documents to assist users with finding materials and make tagging/keywording of documents in databases consistent.
- DFID R4D Programme team are assisted in identifying new projects to be added to R4D by working closely with the RED Research Teams but also by using the DFID Development Tracker and DFID Transparency data.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation from last Annual Review: Last review recommended that Logframe risk rating for this Output should be updated and reduced to low. This has been actioned. As highlighted above CABI and the DFID programme team have also completed the other recommendation of reviewing and agreeing document types for harvesting.

Recommendations

Now that the major work on document types has been completed the review team recommends that the DFID programme team continues the enhancement to the accuracy and content of the R4D database (as timing of the new R4D development permits) to ready the database content for migration. They may wish to concentrate in the short term on content in the database with no documents attached and/or only urls (to ensure that the database is as “clean” as possible).

Output Title	Maintenance, Handover & Migration (inc closure of all platforms): Website, database, search and open applications maintained and accessible to all users; handover of R4D and involvement in GDS process for the new R4D undertaken and completed as specified by DFID.
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	30
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

*the existing contract has break clauses every 2 months from 31 Mar 16 until end contract 31 Sept 16
Indicator(s)	Milestones	Progress
Output Indicator 3.1: Website, database and search maintained and accessible	Target March 2016 - website, database and search accessible and all bugs, accessibility issues fixed and/or resolved. All platforms maintained	Work on this indicator is ongoing - although there have been some issues (see indicator 3.2) platforms and services have been maintained and CABI have provided a good steady service.
Output Indicator 3.2: Open data and applications (API) maintained and available through R4D	Target September 2016 - Open data accessible and any issues, bugs resolved and/or fixed. Platforms maintained	Work on this indicator is ongoing. Open data platforms have been maintained with only minimal loss of service to the end user. Issues which did arise during this period were promptly detected and rectified. These platforms have been used to facilitate data exchanges with DFID partners.
Output Indicator 3.3: managed handover & migration of R4D content and data with specified DFID timeframe. Includes closure of all platforms and sites as and when specified by DFID	Target March 2016 – Handover, migration and closure undertaken and completed.	See below
Output Indicator 3.4:Contribute to the GDS process for the new R4D on .Gov.uk (as required and specified by DFID)	TBC	See below

Key Points

- The Linked Development platform is listed as having 5 star open data[4] status in data.gov.uk, the government service design manual specifies that data published should aim to reach at least the 3 star open data level[5].
  [4] 5 star rating scheme http://5stardata.info/en/
  [5] Government Services Design Manual – Open Data https://www.gov.uk/service-manual/technology/open-data.html
- DFID remains fully briefed by CABI on any server/platform downtime and/or issues which include any identified potential and anticipated security issues as they arise.
- All site code continues to be made available to DFID on GitHub with updated code released there as a result of any bug fixes made at code release points.
- As per previous reviews statistics taken from data.gov.uk site analytics shows that for “all months” R4D Open Data is in the top 5 of DFID data usage with 508 views and 93 downloads of data registered[6]. R4D is fourth this year one place higher than last year.
  [6] https://data.gov.uk/data/site-usage/dataset?month=&publisher=department-for-international-development

DFID Dataset	Views	Visits	Downloads
Full information/data on DFID aid projects	1326	211	862
Spend over £500 in the Department for International Development	1226	447	1324
Organogram and staff pay data for Department for International Development	900	394	380
Research for Development - R4D open data	508	136	93
DFID Annual Report 2011-2012	483	314	496
Provisional UK Official Development Assistance as a Proportion of Gross National Income	425	216	184
Spend over £25,000 in the Department for International Development	395	162	103
DFID Workforce Management Information - Public body	371	70	182
DFID Statistics on International Development 2011	362	170	49
DFID Government e-payments framework transactions	352	113	62

Indicators 3.3 and 3.4 have not been assessed as DFID is currently in procurement for suppliers to build a new R4D solution on .gov.uk. This work is now not expected to place until 2016. Handover of R4D is written into the current contract with CABI and DFID has agreed to keep CABI updated on details of their expected involvement once a supplier is in place. As highlighted by the previous annual review CABI made a good contribution to the Discovery Phase and worked well with external providers who were delivering it. DFID anticipates an equally professional approach and response from CABI during handover and migration of R4D.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were no issues raised under this output in previous annual review

Recommendations

The annual review team did not identify any recommendations under this output. It noted the way forward for R4D has already been agreed and DFID is in procurement for suppliers to build a new solution on .Gov.uk. This is the final Annual Review and the R4D programme will end on or prior to 31st September 2016 (depending on the go live date of the new R4D service).

Output Title	Project Management: Excellence in project management in accord with best practice
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

*the existing contract has break points every 2 months from 31 Mar 16 to end of contract 31 Sept 16
Indicator(s)	Milestones	Progress
Output Indicator 4.1: Project is managed to time and budget (with deviates managed and report via monthly meetings and/or agreed updates to workplan and forecasting and maintenance and update reports). Handover managed and completed within specified DFID timeframe	Target March 2016 – Workplan and budget forecasts met. Delivery of maintenance and update reports. Handover, migration and closure managed and completed (if applicable) –	The handover of R4D has not yet taken place as the new R4D solution has not been built. CABI submit invoices on a monthly basis along with a revised budget forecast for future spend (if appropriate). During this period meetings mainly concentrated on the work required to make the database ready for migration.
Output Indicator 4.2: Staff and programme work streams managed effectively to ensure deliverables and service standards. Staff have appropriate skills and training	Target March 2016 - CABI outline progress – part of maintenance and update reports. Reviewed formally AR/PCR (whichever appropriate	A new Content Editor was hired to manage the project together with the existing team of editorial staff who have the relevant experience in content editing and managing R4D. Programme, project and team managers are trained and accredited in Prince 2 and Agile methodologies for project management.
Output Indicator 4.3: Project managed to PRINCE 2 and manage IT maintenance via AGILE	Target September 2016 – review formally at AR/PCR. Sprint cycle number and number of completed stories	CABI have an AGILE approach to project management and all staff involved in the project have regular “scrum” meetings. CABI co-ordinate fortnightly reviews and planning sessions with bi-monthly testing and release schedules. DFID programme team also have access to the CABI Storytracker.
Output Indicator 4.4:Manage and oversee CABI involvement and contributions to GDS process for new R4D on .Gov.uk (as specified by DFID)	TBC	See below

Key Points

- R4D is a mature service and the CABI programme team have the necessary skills and experience to manage the service and platforms (and when appropriate the handover of R4D). CABI also ensured that the new content editor was properly inducted to ensure a smooth transition without interruption to CABI/DFID working and to the service as a whole.
- During this period it was agreed that DFID and CABI management meetings would be scheduled to coincide with key programme milestones. The regular monthly meetings continued but were focused on ongoing maintenance and preparing the R4D database for migration.
- The regular meetings between the DFID programme team and CABI editorial has enabled CABI to pass on their experience and knowledge of managing R4D content
- Indicators 4.4 have not been assessed as DFID is currently in procurement for suppliers to build a new R4D solution on .gov.uk. This work is now not expected to place until 2016.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were no issues raised under this output in previous annual review

Recommendations

The DFID R4D programme team should continue to have regular meetings with CABI editorial to ensure that the work required on making the R4D database ready for handover and migration can continue as well as the sharing of knowledge.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

As highlighted in the previous Annual Review the primary cost driver is the CABI staff costs. These costs, under the existing contract are over 80% of the total budget. They are split between the CABI programme and administrative staff, editorial team and the IT support and maintenance.

The other costs for the programme are the direct costs for hosting of sites, platforms and expenses as well as CABI consultant costs who provide support to CABI mainly in the areas of web analytics and statistics. Under the existing contract and forecasting CABI have spent 63% of the contract value to March 2016.

As DFID is currently in procurement for suppliers for the new R4D the handover work budgeted for in the existing contract is now not expected to be undertaken until 2016, the existing programme therefore has a slight underspend. The underspend total at December 2015 is £8,719 (minus VAT).

VfM performance compared to the original VfM proposition in the business case

There has been no change. The three cost lines, CABI staff costs, direct costs and consultant’s costs are contractual, with CABI staff costs being the key costs in the existing business case for the current contract (amendment 10) and previous business cases.

Assessment of whether the programme continues to represent value for money

The existing R4D programme is “proprietary” and managed by an external supplier and does not therefore represent best value for money. DFID has approved and is in procurement for a new R4D service on .Gov.uk (which will be managed in house by DFID staff) and will represent better Value for Money. However the current programme does represent value for money in the preservation and effective handover of the existing archive to the new in-house system.

In accordance with the recommendations made in the previous Annual Review the contract extension to September 2016 was enhanced to improve value for money. The existing contract has been “reduced” to ensure only core activities and work is undertaken whilst a new R4D service is developed and built. CABI worked hard to ensure that DFID had value for money and at the same time ensured that the R4D service could still be maintained to a good standard. Areas which were reduced for contract amendment 10 include travel and expenses, CABI IT staff time and a reduction in the types of documents harvested by the CABI editorial team.

To further ensure value for money of the R4D programme, until a new R4D service is built and live on .Gov.uk, the existing contract to September 2016 has 3 break points where the existing supplier will require formal approval from DFID prior to proceed (31st March 2016, 31st May 2016 and 31st July 2016).

Quality of financial management

CABI, as per the contract, submit monthly invoices in arears for work undertaken. They provide monthly forecasts of spend. If appropriate after discussions between CABI and the DFID programme team forecasts maybe amended to reflect work undertaken and/or about to be undertaken.

Expenditure is monitored by the DFID programme team. Invoices are checked each month and they are also compared to the forecasts provided by CABI. Once checked and if appropriate any queries the DFID programme team have are clarified with CABI and saved to Quest. Only once clarification is received and/or discussed are invoices approved for payment.

CABI have policies and procedures to deal with bribery, fraud, whistleblowing and corruption as well as guidelines on procurement. As part of the process for the current contract to September 2016 (contract amendment 10) DFIDs Procurement and Commercial Department undertook a due diligence on CABI.

Date of last narrative financial report	CABI Financial Statement 2014 (most recent published on CABI website)
Date of last audited annual statement	CABI Annual Review 2014 (most recent published on CABI website)

E: RISK

Overall risk rating: Low

This has not changed from the last review

Overview of programme risk

The risk is Low as R4D is a mature service and CABI are experienced in delivering it. Processes are in place to ensure that updating continues, all services are maintained and accessible and that the database and its content is as accurate as possible.

The major work on the “clean up” of the database has been completed, this work has not only increased the accuracy of R4D document records, it has also contributed to the ongoing management of risks around the migration of the existing content to a new R4D by ensuring that research outputs are easily identified and as “clean” as possible for transfer.

Outstanding actions from risk assessment

There are no outstanding actions

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is on track. The contract is for core maintenance and update only. The adjustments and rationalisation of the document types has been completed and general editorial and IT work is ongoing until the end of the contract and/or up to the relevant break point (which ever is appropriate).

Performance of partnership(s)

No applicable

Asset monitoring and control

Assets identified in the previous Annual Review are the existing “DFID server(s)”. Due to their age the value of these assets is regarded as minimal. When the new R4D solution is built and live on .Gov.uk these server(s) will be decommissioned.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable as this is a UK-based programme, which makes DFID research outputs globally available online.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The R4D Dashboard analytics are the major source of evidence on usage of the R4D website and database. R4D is a significant and important resource for ensuring that the research funded by DFID is accessible and open to all. In total R4D contains 48,684 records 38,468 research outputs, 5,874 projects and 4,342 organisations. During this review period monthly usage of R4D shows: average visits to the website 153, 417 and downloads 114,498.[7] It should be noted that all these statistics reflect not only the fluctuations brought about by the clean-up work on the R4D database, the failure of the statistics usage software to record usage data during September 2015 and the restrictions during purdah.
[7] Figures taken from the R4D usage Dashboard http://r4d.dfid.gov.uk/UsageDashboard.aspx. (data for September 2015 was lost so August usage data was used to estimate September figures), usage statistics are up to and including November 2015

As DFID has already undertaken a Discovery of R4D in October 2014 and are now in procurement to build a new R4D on.Gov.uk the R4D Programme did not undertake any further assessments of R4D and its services in 2015. However, from time to time DFID does receive feedback via Twitter on R4D:
“Useful resource @DFID_UK #R4D Research for Development searchable database of evidence r4d.gov.uk…[Editor in Chief BMJ Open, 10 December 2015]

“Research for Development #R4D is a very handy resource for managing and translating knowledge into action…”[public health and development practitioner, Pakistan, 20 September 2015]

As highlighted in the previous review DFID were due to undertake an evaluation of DFID evidence portals (which included R4D). This evaluation was delayed but started during this period. CABI have provided requested data and feedback to the evaluation team from Mott MacDonald. The final report from this evaluation is now expected March 2016.

Monitoring progress throughout the review period

CABI and the DFID programme team met monthly from January to March 2015. These meetings were to review progress with agreed actions and follow up (if appropriate). Prior to these meetings CABI provided editorial and IT technical overview of sprints completed and planned work for next sprint which were agreed by DFID.

From April 2015 it was agreed with CABI that meetings would focus primarily on the editorial work to ensure that the R4D database was ready for migration to the new service on .Gov.uk. Actions and delivery times are agreed at meetings and where appropriate followed up by the DFID project officer who is leading on the clean-up of the R4D database prior to the handover of the R4D service.

As per the terms of reference CABI also provide 6 monthly Management and Maintenance Reports which provide an overview of progress against the outcomes in the logframe for the period/contract. The final report under contract amendment 9 was delivered in March 2015 [Quest no. 4954728] CABI have also delivered the first report up to September 2015 under this existing contract amendment 10 [Quest no. 5264216].

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process