FLAG B

Evaluation of the impact of the Free Health Care Initiative on maternal and child mortality in Sierra Leone

Business Case

14 December 2011

Contents	Page
Acronyms	3
Project Summary	4
1. Strategic Case
A Context and need for DFID intervention	6
B Impact and Outcome	11
2. Appraisal Case
A Feasible options	13
B Strength of the evidence	14
C Costs and benefits	15
D Assessing Value for Money	17
E Value for Money statement for the preferred option	17
3. Commercial case
A Procurement/commercial requirements	18
B Use of competition to drive commercial advantage	18
C Response of market place	18
D Key cost elements	18
E Procurement process	18
F Contract and supplier performance management	19
4. Financial Case
A Project cost	19
B How the project will be funded	20
C How funds will be paid out	20
D Assessment of financial risk and fraud	20
E How expenditure will be monitored, reported and accounted for	20
5. Management Case
A Management arrangements	20
B Risks and their management	21
D Monitoring, measuring and evaluating progress and results	22
6. References	23
ANNEXES
Annex 1 : Logical Framework
Annex 2 : Service Provider Terms of Reference
Annex 3 : Key results of the Free Health Care Initiative, year one
Annex 4 : Theory of change and service provider assumptions

AfDB	African Development Bank
AfDF	African Development Fund
AIDS	Acquired Immunodeficiency Syndrome
ANC	Ante Natal Care
BPEHS	Basic Package of Essential Health Services
BEmOC	Basic Emergency Obstetric and Care
CEmOC	Comprehensive Emergency Obstetric and Care
CMR / CSC / CSO / DFID	Child Mortality Rate / Critical Success Criteria / Civil Society Organisation / Department for International Development
DHS	Demographic and Health Survey
E4A / FHCI	Evidence for Action to reduce maternal and Neonatal Mortality in Africa / Free Health Care Initiative
GoSL	Government of Sierra Leone
HMIS / IHP+ / JPWF / M&E / MNCH	Health Management Information System / International Health Partnership Plus / Joint Programme of Work and Funding / Monitoring and Evaluation / Maternal, Newborn and Child Health
MDGNA	Millennium Development Goals Needs Assessment
MDGs	Millennium Development Goals
MICS	Multi-Cluster Indicator Survey
MMR	Maternal Mortality Ratio
MoHS	Ministry of Health and Sanitation
PMDUP / PRSP	Prevention of Maternal Deaths from Unwanted Pregnancy / Poverty Reduction Strategy Paper
RMCH / SLDHS	Reproductive, Maternal, Child Health / Sierra Leone Demographic Health Survey
SP / SSL	Service Provider / Statistics Sierra Leone
STI	Sexually Transmitted Infection
ToRs / UNAIDS	Terms of Reference / United Nations AIDS
UNICEF / UNFPA	United Nations Children’s Fund / United Nations Population Fund

Business Case and Intervention Summary

Intervention Summary

Title: Evaluation of the impact of the Free Health Care Initiative on maternal and child mortality in Sierra Leone

What support will the UK provide?
How much funding does the UK expect to provide? / The UK will provide up to £1 million for the independent evaluation of the Free Health Care Initiative (FHCI) for pregnant and nursing women and children under five years old in Sierra Leone / Period of funding / 4 years (2012/13 – 2015/16).

Why is UK support required?
What need are we trying to address? / The overarching challenge for government and partners is to determine programme efficacy and effectiveness and whether the funds being invested in the FHCI will result in the reduction of maternal and child mortality. The FHCI programme was designed as an emergency response to the dire maternal and child mortality statistics and was implemented within a very short time; as a result the mechanisms for an impact evaluation were not put in place at the start. This programme will also provide an improved level of transparency on the use of resources that has not been available to date. / DFID Sierra Leone and the Government of Sierra Leone (and particularly the Ministry of Health and Sanitation – MoHS) also want to determine whether the processes that were undertaken and the systems that were put in place to enable the FHCI to be launched in April 2010 were effective or need to be improved upon, demonstrate value for money, and can be institutionalised to ensure the longer term delivery of quality health care services. The findings of the evaluation will therefore inform annual reviews of the FHCI where programme design for effective delivery will be assessed. It will also inform decisions by both DFID and the wider donor community regarding whether investments should be maintained, increased or held back if the FHCI is not achieving the desired outcomes. / What will we do to tackle this problem ie why is evaluation of the Free Health Care Initiative important? / DFID Sierra Leone will commission an independent evaluation of the FHCI programme. The evaluation will look both at the processes that were adopted for delivery and how well these were able to deliver the desired results as well as putting in place clear baselines so that outcomes can be monitored every year going forward, and the impact can be evaluated at the end of the project. It will also assess the extent of any unintended consequences, and should also consider a counterfactual ie what would have happened without the additional funding that has already been received and is planned. / Whilst a number of countries in Africa and Asia have offered free health care packages to vulnerable populations there appears to be no evaluation of the impact on health outcomes and mortality as a result of a comprehensive scheme such as the FHCI in Sierra Leone, and only one evaluation of a scheme targeting young children in Ghana where the results were mixed. The evaluation will therefore offer the opportunity to undertake a robust and credible assessment of the relationship between free of charge health care at the point of service delivery and health outcomes/mortality for the target beneficiaries, and will provide important information and lessons that will be useful to Sierra Leone and elsewhere. / Who will be implementing the support we provide? / The proposed best option for the implementation of this project is to secure an independent service provider via an international competitive tendering process. This will ensure that the evaluators are independent of FHCI programme implementation. The findings of this project will be widely disseminated as part of the annual joint review of the health sector that the MoHS intends to establish from June 2012, and will be used to inform policy development and programme design going forward. The findings may also be published in reputable international journals to facilitate learning on a global basis.

What are the expected results?
What will change as a result of our support? / An assessment and creation of an evidence base of whether and how the FHCI is achieving the expected health outcomes and is resulting in the impact of reduced maternal, newborn and child mortality. During the inception phase a baseline against which progress can be measured will be established, as will the counterfactual that demonstrates what would have happened to maternal and child mortality in the event the FHCI had not been launched. / Improved utilisation of information and data to inform the effective management of the FHCI within the context of delivery of the National Health Sector Strategic Plan (NHSSP). / Improved transparency and accountability between the state and its citizens, and between the state and its financing partners. / What are the planned outputs attributable to UK support? / An independent evaluation undertaken and lessons generated to improve understanding of the impact of and operational effectiveness of the FHCI. / Improved understanding of the socio-cultural considerations of the uptake of health care amongst the FHCI target group in Sierra Leone. / How will we determine whether the expected results have been achieved? / The service provider will be bound by an output-based contract with terms of reference (ToR – see Annex 2) that outline the expectations and quality of the deliverables. These will be reviewed after the five-month inception period, and as part of the project annual review process. A midterm review to assess progress will also be carried out at the end of Year Two with a final evaluation at the end of the project.

Business Case

Strategic Case

A. Context and need for a DFID intervention / Background to the FHCI / Maternal and child mortality rates in Sierra Leone continue to be amongst the worst in the world. The 2008 estimates of a maternal mortality ratio (MMR) of 857/100 000 live births and a child mortality rate (CMR) of 140/1 000 live births indicate that attainment of the Millennium Development Goals (MDG) for an MMR of 660/100,000 live births and a CMR of 95/1,000 live births is unlikely (Sierra Leone DHS 2008). / In recognition of the severity of the situation maternal, newborn and child morbidity and mortality was prioritised in the President’s Agenda for Change (PRSP 2) and subsequent National Health Sector Strategic Plan 2010 – 2015 (NHSSP) which underpins the implementation of the Basic Package of Essential Health Services (BPEHS). / The FHCI was launched in April 2010 as a response to the recognition that the cost, and/or perceived cost, of accessing care was the most significant reason in preventing the actual uptake of health services particularly by the most vulnerable: pregnant and nursing women and children under the age of 5. The 2008 National Service Delivery Perception Survey in Sierra Leone showed that 88% of respondents saw the lack of finance as a barrier to accessing care, the second most significant barrier was distance and a lack of transport however this was listed at only 6% as a barrier[1]. Table one below shows this information as a graph. These findings are consistent with other studies which highlight the role of user fees as a barrier to access for example lack of funds has been cited by 92.4% of respondents in Burundi , 75.8% in DRC, 83% in Chad and 65.2% Mali[2],[3] / Table one: source National Service Delivery Perception Survey, 2008 / The importance of cost as a barrier is reinforced by a 2005 survey which found that 71% of surveyed households with a sick family member were not seeking care outside of the home due to the lack of finance[4]. The same survey estimated the actual average cost of health care in Sierra Leone at US$3.30/person/episode of illness; the equivalent of 26 days of work. There is no specific evidence on the socio-cultural considerations around the uptake of health care within the FHCI’s target group, or their influencers, or since its introduction. / The Initiative provides for free health care and consultations for the aforementioned target groups and is supported by six complementary priority interventions aimed at ensuring: / continuous availability of equipment, drugs, and other essential commodities; / adequate number of qualified health workers; / strengthened and effective oversight and management arrangements / information, education and communication to stimulate demand for free quality health services; / monitoring and evaluation; / adequate infrastructure[5]. / The cost for funding the FHCI for the first year, as detailed in the MoHS report of the first 12 months of implementation of the FHCI[6], was $35.84 million. This was provided by the Government of Sierra Leone (GoSL), DFID, Africa Development Bank (AfDB), World Bank, UNFPA, UNICEF and Global Fund. DFID was the single largest contributor (42%), while the share of GoSL was about 12%[7]. Financing was primarily for payment of health workers salaries (52%); drugs and consumables (40%); and service delivery related activities (8%). / Currently there is no independent evaluation of the FHCI however utilisation data from the first year of the Initiative, as drawn from the HMIS, shows some promising results (see Annex 3) including: / 2,926,431 under 5 consultations, a tripling compared to the year before; / 1.288,828 million of these young children received life saving treatment for malaria; / 126,477 women delivered their babies in a health facility, 39,100 more women than the year before; / 20,135 maternity complications were managed in health facilities with a 60% drop in the fatality rate in these cases; / 140% increase in the number of new users of modern family planning. / Need for an evaluation of FHCI / Many of the key indicators show positive behavioural changes since the introduction of the FHCI, but despite the indication that substantial progress is being made in improving the access and uptake of maternal and child health services, there is much still to be achieved. The FHCI is a potentially valuable intervention and one against which future plans for investment are being made (in terms of the GoSL planned second phase of universally free of charge health care and the plans of funders such as DFID). However the relationships between the changes in uptake of services and the FHCI have not yet been fully researched or evidenced. Further there is no concrete evidence that the initiative is leading the anticipated health outcomes or having an impact on reducing maternal, newborn and child mortality; nor how changes have been achieved if this is found to be the case. The recent FHCI-focused MoHS Health Information Bulletin published in April 2011[8] also raised a number of challenges associated with the first year of implementation but to date it has not been feasible to formally and independently review the operational processes required to deliver the FHCI (many of which have been acknowledged as challenges for implementation). Nor has it been feasible to look at the quality of care provided during the first year. / There is a strong strategic case for supporting an evaluation which will scrutinise the relationship between free of charge health care and mortality to demonstrate if the desired health outcomes have been achieved and if there has been an impact on mortality. In addition, the evaluation will determine whether the FHCI demonstrate good value for money for achieving the desired health outcomes, and will review cost-effectiveness and appropriateness of the implementation of the FHCI to help ensure that ongoing decision making is informed by robust evidence. / There are many strategic advantages for DFID to sponsor the evaluation which include: / DFID is the single largest contributor to the FHCI[9], even more than the GoSL, and there is a need to determine the results from resources committed so far; / to uncover any or all forms of bottlenecks (in process as well as in service delivery) impacting on results; / to learn lessons and mitigate any negative effects and amplify potential synergies; and, / to initiate a well established process of regular, independent evaluation. / Health context / As outlined above Sierra Leone continues to have some of the worst MNCH indicators in the world. The FHCI has been selected by the GoSL, within the context of the National Health Strategic Plan, to help improve the uptake of services and, by assumption, the health of the target group. The FHCI aims at providing services for approximately 230,000 pregnant women, 230,000 lactating women and nearly 1 million infants every year. The existing HMIS and Monitoring and Evaluation (M&E) systems are improving to a level where over 80% of districts are now regularly submitting data and it is therefore possible to monitor and analyse the use of services with increasing levels of confidence. The proposed evaluation will fill an important gap in providing evidence of the impact the FHCI is having on mortality. / Policy context / National: As noted the FHCI forms an important and integral part of the President’s and the GoSL commitment to decreasing maternal, newborn and child mortality. The FHCI is seen as an opportunity to “fundamentally alter prospects for women and children”[10]. There is a high level of political support for not only attaining the desired outcomes but also for ensuring that the selected strategy (FHCI) is as effective as possible. The proposed evaluation is supported by the GoSL as a method for validating both impact and the strategy of removing user fees. There remains an ongoing global academic debate about the value of removing user fees and the MoHS are keen to ensure that the impact and operational effectiveness of the FHCI are fully understood and that the value of this approach continues to be well considered. In addition the proposed intervention is welcomed as an opportunity to further improve transparency and accountability and is seen as complementing the aims and outcomes of the National Results Framework and National Monitoring and Evaluation Plan (currently being finalised). / In order to improve aid effectiveness, reduce the high level of fragmentation in the health sector and work in a more coordinated, effective and resource-efficient manner, in May 2010 Sierra Leone signed up to the International Health Partnership Plus global agreement (IHP+). Working together with its partners, a Sierra Leonean version has since been developed providing the governance framework for the implementation of the NHSSP. / A Joint Programme of Work and Funding (JPWF)[11] is also being developed in order to operationalise the NHSSP in a more coordinated and effective manner from 2012. The 3-year costed JPWF will provide a comprehensive framework for aligning interventions to sector priorities, as well as planning, monitoring and budgeting processes. The Sierra Leonean IHP+ Compact therefore provides the governance framework which government and its partners will work within to deliver the JPWF. Underpinning the JPWF is the need for regular and quality data and information demonstrating that the interventions and activities being delivered are the right ones and are delivering the desired results; and that investment decisions are regularly being informed by concrete evidence. / National elections planned for 2012 and whilst it is not possible to speculate on any change in policy, should there be a change in government, there is a high level of expectation that the commitment to the FHCI will continue as it is perceived to be successful, has shown significant utilisation results so far, appears to be well received by constituents and is one of few truly national interventions which provides it with political capital. / Global: The proposed evaluation and the aims of creating a credible evidence base with which to assess the impact of the FHCI on mortality is congruent with several high level commitments made by the UK and Sierra Leonean governments, including the landmark agreement in 2009 in the UN Human Rights Council Resolution on maternal health[12], the 2010 UN launch of the global strategy on maternal health[13] and its related Commission on Information and Accountability for Women and Children’s Health[14]. / UK government and DFID priorities: The proposed evaluation’s terms of reference are informed by “Choices for Women: planned pregnancies, safe births and healthy newborns”, the DFID framework for results for improving reproductive, maternal and newborn health in the developing world. DFID Sierra Leone’s Operational Plan (2011 – 2015) includes the reduction of maternal and child mortality as one of two MDG health pillar outcomes and support for the provision of free, essential health care for 460 000 pregnant and lactating women and 1 million children every year[15]. The proposed evaluation will provide evidence that the targets are being met in the most effective manner and also that in doing so the FHCI is contributing to the strategic priority of reduced maternal and child mortality. / Other interventions / There are no other planned evaluations of the impact and operational effectiveness of the FHCI on a national scale. The national MoHS HMIS and M&E functions have seen significant investment and improvement and perform a valuable role in monitoring (particularly the uptake of services) and learning, but currently there is not a mechanism for independent evaluation of the impact of the FHCI. / The proposed intervention will work closely with other planned sub-sector evaluations being carried out by partners and national departments such as the household perception surveys, Improving Health Services Delivery Through Community Monitoring and Awards Competition, and Benefit-Incidence Analysis studies. It will also work closely with DFID-funded research programmes such as the recently launched REBUILD programme[16] and the Evidence for Action to reduce maternal and neonatal mortality in Africa project (E4A). It will also work closely with the bi-regional prevention of maternal death from unwanted pregnancy programme (PMDUP). / The MoHS envisages that over the four years, the proposed intervention will progressively become the main platform to harmonise multiple partner supported sub-sector evaluations and reviews leading to a more efficient single joint annual review and evaluation platform. / Evidence / The evidence base in Sierra Leone is defined as comparatively weak (DFID Sierra Leone Operational Plan 2011-2015), reflecting the destruction and disruption caused to the management and delivery of basic services across the board including health care provision. The FHCI is recognised as an innovative response to the crisis of unacceptably high maternal and child mortality rates and “therefore does not have a strong local evidence base”[17]. / A number of countries have introduced schemes to reduce the impact of cost on health seeking behaviours, particularly by vulnerable groups, including exemption schemes, the removal of fees and revised pricing systems. Evaluations of such schemes have been undertaken in other countries however there appears to be limited evidence of the impact of such schemes on health outcomes and mortality. / There is one known evaluation in the region which has attempted to do this, however it draws its evidence from a small sample in rural Ghana (2,600 in a population of nearly 24.5 million) and focuses only on children under five years of age, and on malaria outcomes[18]. In this instance the evaluation concluded that “the removal of out of pocket payments for health care changed health care-seeking behaviour but not health outcomes for children”. It was not however able to say whether other critical factors such as indirect costs were more of a barrier than the direct costs of paying for treatment. Other examples are the evaluations of the Ghana health scheme which introduced free deliveries in 2004. These have made observations and recommendations around issues such as equity of access, cost-effectiveness, quality of care and the importance of monitoring and evaluation[19] or focused on economic evaluation[20] and institutional deaths[21] but did not include the broader impact on mortality. Similarly evaluations in Burkina Faso[22], Senegal[23], Uganda[24] and Mali[25] have focused on process, cost and utilisation. / These evaluations offer valuable learning for Sierra Leone and in some instances the unexpected findings of the evaluations (for example that the Ghanaian health scheme’s design meant that wealthier women were benefitting more than their poorer peers[26], and that non-financial barriers were of significance in Burkina Faso[27]) confirm the value of evaluation for learning and also the need to understand what, if any, other barriers to access may be evident. / The proposed evaluation offers the opportunity to set a precedent in undertaking a robust and credible assessment of the relationship between free of charge health care at the point of service delivery and health outcomes/mortality for pregnant and nursing women and children under five years old. / A2. Feasibility of intervening / DFID Sierra Leone’s investment in supporting the FHCI has been significant and has included the provision of drugs and medical supplies, provision of VSO doctors to fill critical gaps in hospitals, as well as focused technical assistance to the MoHS to address a range of systemic issues including developing national M&E systems, cleaning up the payroll and removing ghost workers, and developing a national human resources strategy and long-term workforce plan. A commitment of up to £63.4 million for reproductive, maternal, neonatal and child health has been made, further underpinning the need for evidence of impact. / Although this evaluation has not been undertaken before, the main methodologies that are likely to be utilised, such as large scale national surveys, have been successfully used in Sierra Leone with good results. The proposed intervention falls within DFID’s remit, as outlined in the policy context above, is fully supported by the GoSL (see FLAG A of the submission), and is a low cost intervention with disproportionally large potential benefits. / The experience accumulated by and expertise within DFID leaves it well placed to propose this intervention which is entirely feasible but unlikely to be undertaken without DFID funding and which offers significant benefits in understanding the value of the investment in the FHCI to date which will help inform future policy and investments. / A3. Consequences of not intervening / As outlined the proposed evaluation offers a number of substantial and strategic benefits. It is unlikely that this intervention will be undertaken if not funded by DFID and therefore the main consequence of not intervening is the missed opportunity to capitalise on these benefits. / In addition, failing to undertake the intervention is associated with relatively high risk as the pace of the FHCI’s implementation coupled with the macroeconomic constraints of Sierra Leone and uncertainty of donors support means that FHCI implementation remains a high risk intervention. In this instance the lack of robust evidence of impact of the FHCI and confidence in its key processes (as a result of evaluating them) risks the failure to identify unintended negative impacts or processes along with learning that can be shared globally. Alongside the lack evidence of impact and the missed opportunities to adjust as required and to learn, there is potential for the cost effectiveness and value for money of the intervention to be compromised. / Ultimately the failure to fully understand and manage the impact of the FHCI may have far reaching implications beyond the investment made to date. For example unidentified challenges may be preventing the FHCI reaching its full potential and contributing to further decreases in deaths. Additionally as a fragile state Sierra Leone’s investment in health care systems is particularly important (given the known relationship between healthcare services and state building[28]) and evidence to verify that the investment is effective is critical in helping to ensure the best returns in terms of addressing poverty, supporting development and preventing a return to conflict. / Further the failure to achieve outputs such as developing a baseline against which to measure progress will compromise the ability of the GoSL to be truly accountable to its citizens, funders and the global audience. For the MoHS to ensure the limited resources available are used to deliver essential health care in a well-targeted, resource-efficient and evidenced-based manner, evidence of the impact of interventions is essential over and above the outputs regarding increased utilisation of services and will inform the annual reviews and planning stages of the JPWF.
B. Impact and Outcome that we expect to achieve / Impact: Evidence of improved maternal, newborn and child health in Sierra Leone. / Outcome: Evidence of the role of the FHCI in decreasing maternal, newborn and child morbidity and mortality. / Outputs: / Improved understanding of the impact and operational effectiveness of the FHCI / Key activities will include the determining of a baseline and evaluation of the progress made in implementing the FHCI. It will also look at the results achieved, the level of the quality of care provided, the impact on health outcomes including deaths, and the contribution towards state building by the FHCI. The scope of the evaluation is more fully defined in the service provider ToR (see Annex 2). During year one it is anticipated that methodologies will be developed and therefore included in the annual evaluations from year 2. / Effective and participative annual evaluation process that remains within budget / The project will develop, test and implement an annual evaluation process that meets the evaluation objectives as described in the service provider TOR and ensures that all stakeholders, including harder to access and vulnerable populations, are represented and involved in the evaluation. In addition the project will advocate for the annual evaluation to be incorporated within the JPWF, and develop an effective strategy for communicating and disseminating results to all stakeholders, thereby increasing transparency, accountability and an improved citizen engagement in health services management. / 3. Improved understanding of the socio-cultural considerations of the uptake of free health care amongst the FHCI target group / The project will design, test and utilise appropriate methodologies to access and secure the opinion of the target group to establish the existence and impact of socio-cultural determinants of health seeking behaviours. The annual evaluation process will become part of the MoHS’s JPWF which will help to institutionalise the process and also the discussion and use of the findings. / Social Impact / The proposed intervention is aligned with the aspiration of the FHCI to “fundamentally alter prospects for women and children” and to ensuring that the needs of the poor and most vulnerable, particularly women and children, are met. As outlined in the theory of change (see Annex 4) the evaluation will test the assumption that the FHCI is having impact on health outcomes and on reducing the number of deaths amongst the target group and will also test that there is no disparity of benefit for any user or potential user group. The findings of the evaluation has the potential to help ensure that the FHCI is socially appropriate and for any potential issues to be addressed. / The implementation of the evaluation and the design of the ongoing evaluation process will be a participative one and seek input from relevant experts and authorities to ensure that the methodologies are socially and culturally appropriate and that there is full representation of civil society including harder to access and vulnerable populations. / The project also includes research which will focus on the socio-cultural aspects of health seeking behaviour amongst the FHCI target group and their influencers. The tendency to date has been to focus on financial barriers which have been identified as the most significant barrier (see section A). This research will provide additional information on the social impact of the FHCI and will complement and contextualise the findings of the proposed evaluation. The need to ensure consideration of the broader socio-cultural context in relation to the efficacy of the FHCI is seen as crucial and has been identified as a critical success criterion for the proposed intervention. / Political Impact / The Government of Sierra Leone has made a strong commitment to improving maternal, newborn and child health and the FHCI, which is a key policy within the NHSSP, is a core pillar of this commitment. The results of the FHCI to date, measured in terms of the utilisation of services, show some promising increases and also some unexplained plateaux for some services. The FHCI is a national programme with a perceived high level of political capital and a better understanding of its performance, and any potential issues, will be advantageous to policy makers. The Director of Reproductive Health at the MoHS recently expressed concern that the rate of population growth will negatively influence the provision of services including the FHCI; lending weight to the argument for the need to ensure that the efficacy of the FHCI is fully understood and maximised[29]. / Institutional impact / This project will promote the culture of focus on results and through the process and working closely with other DFID interventions (see page 9) will build institutional capacity to accurately measure, record, report and use health data. / Fiduciary impact / Fiduciary impact is minimal given that the evaluation services will be contracted out through a robust international tendering process and payment will be made upon delivery of the agreed outputs. / Sustainability / The project will run for four years with set milestones and expectations of progress throughout that period. It is anticipated that during the first year any gaps in data and information will be identified and that an initial baseline will be determined. This will form the basis for subsequent analysis of performance and impact and will therefore be a substantial contribution to the long term sustainability of the FHCI. Similarly the information generated by the evaluation will provide a precedent and allow the strategic benefits outlined in Section A – Context and Need, to be realised on an ongoing basis. The principle outcome, and associated benefits, will be the ability to generate bespoke and meaningful information that will not only support the effective implementation of the FHCI but also to provide data and information for future decision making. The annual evaluation process will become part of the MoHS’s JPWF which will help to institutionalise the process, secure funding beyond that provided by this project, and ensure regular discussion and use of the findings through the planned annual joint reviews and planning processes for the health sector.
[1] National Service Delivery Perception Survey, GoSL, 2008
[2] Ponsar, K Tayler-Smith, M Philips, SGerard, M Van Herp, T Reid, R Zachariah. No cash, no care: how user fees endanger health—lessons learnt regarding financial barriers to healthcare services in Burundi, Sierra Leone, Democratic Republic of Congo, Chad, Haiti and Mali
[3] For an overview see Yates, R. 2006, International Experiences in Removing User Fees for Health Services – Implications for Mozambique. DFID Health Resource Centre
[4] ibid International Health 3 (2011) 91– 100
[5] For further information see: Government of Sierra Leone, 2009, Free healthcare services for pregnant and lactating women and young children in Sierra Leone.
[6] Government of Sierra Leone. Ministry of Health & Sanitation Health Information Bulletin. Volume 2, Number 3. FHC Edition (April 2010 – Mar 2011).
[7] Government of Sierra Leone. Ministry of Health & Sanitation Health Information Bulletin. Volume 2, Number 3. FHC Edition (April 2010 – Mar 2011).
[8] Government of Sierra Leone. Ministry of Health & Sanitation Health Information Bulletin. Volume 2, Number 3. FHC Edition (April 2010 – Mar 2011).
[9] Government of Sierra Leone, Ministry of Health & Sanitation. Health Information Bulletin. Vol.2, No.3. April 2010-March 2011).
[10] Government of Sierra Leone, 2009, Free healthcare services for pregnant and lactating women and young children in Sierra Leone.
[11] The JPWF is currently being finalised and is due to be implemented from January 2012.
[12] http://righttomaternalhealth.org/hrc-resolution
[13] http://www.everywomaneverychild.org/
[14] ibid
[15] As per the FHCI Framework 2009
[16] Working in Cambodia, Zimbabwe, Uganda and Sierra Leone, this research project aims to get a better understanding of the changes in health financing policy and poor households’ expenditure on health and to explore how policy and practice can be strengthened in relation to health financing and staffing. For more information visit http://www.rebuildconsortium.com
[17] DFID SL Operational Plan 2011-2015. February 2011
[18] Ansah EK, Narh-Bana S, Asiamah S, Dzordzordzi V, Biantey K, et al (2009) Effect of removing direct payment for health care on utilisation and health outcomes in Ghanaian children: a randomised controlled trial. PLoS Med 6(1): e1000007. doi:10.1371/journal.pmed.1000007
[19] # Sophie Witter, Sam Adjei, Margaret Armar-Klemesu and Wendy Graham. Providing free maternal health care: ten lessons from an evaluation of the national delivery exemption policy in Ghana Global Health Action, Vol 2 (2009)
[20] Armar-Klemesu M, Graham W, Arhinful D, Hussein J, Asante F, Witter S, et al. An evaluation of Ghana's policy of universal fee exemption for delivery care. Aberdeen and Accra : IMMPACT; 2006.
[21] Bosu W, Bell J, Armar-Klemesu M, Tornui J. Effect of delivery care user fee exemption policy on institutional maternal deaths in the Central and Volta Regions of Ghana. Ghana Med J 2007; 41: 118–24.
[22] Ridde, Yaogo, Kafando, Kadio, Ouedraogo, Bicaba, Haddad.Targeting the worst-off for free health care: A process evaluation in Burkina Faso, Evaluation and Program Planning 34 (2011) 333–342
[23] Sophie Witter, Thierno Dieng, Daouda Mbengue, Isabelle Moreira and Vincent De Brouwere. The national free delivery and caesarean policy in Senegal: evaluating process and outcomes Health Policy and Planning Volume25, Issue5 Pp. 384-392
[24] Nabyonga J et al (2005) Abolition of cost sharing is pro-poor: evidence from Uganda Health Policy and Planning 20(2), p187-195
[25] Marianne El-Khoury, Timothee Gandaho, Aneesa Arur, Binta Keita, and Lisa Nichols. April 2011. Improving Access to Life-saving Maternal Health Services: The Effects of Removing User Fees for Caesareans inMali. Bethesda, MD: Health Systems 20/20, Abt Associates Inc.
[26] Armar-Klemesu et al 2006
[27] Ridde et al 2011
[28] See Eldon, Waddington and Hadi. Health System Reconstruction: Can it Contribute to State-building? October 2008 HLSP Institute
[29] Statement made at the launch of the "Everyone campaign" in Freetown 26 July 2011, Reported in the New Vision 27 July 2011

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The logic behind the proposed intervention is to test the assumption that the FHCI with its six complementary interventions are not only improving the uptake of health services amongst target populations but that they are having impact on health outcomes and mortality rates (see Annex 4 for the FHCI theory of change). The FHCI is a high value, high risk and potentially high achieving initiative however there is currently no provision for evaluating its impact or the efficacy of its implementation. This means that the opportunities for learning and for recognising negative aspects and potential for improvements (and increased impact) are being lost. / The methodologies for the proposed evaluation will be designed to meet the objectives outlined in Section B – Impact and Outcome, and detailed in the service provider TOR (see Annex 2). Consequently the evaluation will straddle both the systems-processes domain and the performance-service delivery domain. The final methodology for the intervention, from defining the base line, establishing the counterfactual, and undertaking the evaluation and developing the annual evaluation process will be determined in discussion with the service provider. This is building on the original scoping of the proposed intervention which was carried out by technical assistance provided by the World Bank with inputs from DFID’s Evaluation Department (UK). / The findings from the evaluation, and the processes used in its design and implementation, together with the findings of the research into health seeking behaviours, will inform the development of the ongoing evaluation process which is intended to ensure that (positive) changes resulting from the FHCI are maintained and evidenced. Three viable options for the delivery of the intervention have been identified and appraised: / Option Title Description / 1 Government-led Government-led evaluation and development of an ongoing evaluation process / 2 Independent Evaluation and development of an ongoing evaluation process led by an independent organisation /consortium / 3 Do nothing (counterfactual) DFID provides no technical or financial support for an impact evaluation or ongoing evaluation process of the FHCI. / Option 1: Government-led / What it will consist of: / This option will consist of the GoSL, predominantly the MoHS and Statistics Sierra Leone, designing and implementing the evaluation and ongoing process as per the terms of reference. It is anticipated that the main implementing agency (MoHS/Statistics Sierra Leone) will work in partnership with other governmental departments and external partners including NGOs and CSOs to provide additional capacity as required. / How it will work: / It is anticipated that during year one the initial evaluation will be designed, tested and executed. The findings will be analysed and presented as an early stage evaluation of the impact of the FHCI; a communication strategy will be developed to ensure that the findings are disseminated in an accessible and appropriate manner. The process of the evaluation will, after review, inform the design of the annual evaluation process which will also include the additional areas of impact on poverty, equity of access and financial viability; the methodologies for assessing these three areas will be developed during the initial year. There will be a need to develop a process by which the impact (if any) of the findings of the research into the socio-cultural determinants of health seeking behaviours and assumptions made in the delivery of the FHCI are considered. / As a participative process the development of capacity for the sustaining of the annual evaluation will be integral from the start of the implementation, however a formal development plan for the full project period will be developed at the start of the project. The focus of years 2, 3 and 4 will be on continued capacity and process development, undertaking the annual evaluation, and appropriate dissemination of the findings. / Evidence: / There is limited evidence to support this option as there is no precedent of a national evaluation of impact within the health sector undertaken by the GoSL. / Option 2: Independent / What it will consist of: / This option will consist of an independent organisation being appointed (through due procurement processes) to design and implement the evaluation and to develop the ongoing annual process as per the TOR. It is anticipated that the main implementing agency will work in partnership with external partners, such as NGOs and CSOs, involving government bodies (eg MoHS, Statistics Sierra Leone) in particular points of the process (see below). / How it will work: / The implementation of the project will be as outlined in option 1 however implementation will be led by an independent agency who will work with a Steering Committee comprising a mix of membership (development partners, civil society and relevant government departments), who will play an oversight role with regards selection of methodology, reviewing reports for factual inaccuracies and ensuring wide dissemination of the results. / Evidence: / There have been a number of large surveys and evaluations undertaken within Sierra Leone, including the DHS and MICs and those outlined in the “other interventions” section above. Many of these follow internationally accepted methodologies and some have focused on evaluating the impact of free healthcare initiatives. However as outlined above there is no precedent, nationally or globally, for independently evaluating the impact of free health care on mortality. / Option 3: Do nothing (counterfactual) / What it will consist of / Under this option, no DFID resources would be allocated for an impact evaluation of the FHCI. This would allow the allocated funds to be used for a different purpose. / How it will work: / The current focus and mode of health care service delivery of the FHCI would continue unaltered due to a lack of evidence demonstrating the need to do otherwise.
B. Assessing the strength of the evidence base for each feasible option / Quality of evidence: / Option Evidence rating / 1. Government-led Limited / 2. Independent Medium / 3. Do nothing (counterfactual) N/A / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impact Climate change and environment opportunities / 1. Government-led C C / 2. Independent C C / 3. Do nothing (counterfactual) n/a n/a / This intervention is unlikely to have any significant impact on the environment or climate change: the main potential negative impact is the use of transport within Sierra Leone to undertake field visits, and the possibility of international flights associated with the provision of technical expertise. In both instances the implementing agency will be expected to do all possible to reduce the carbon footprint. This will include ensuring that all travel is validated against agreed TOR, that consideration is given to ensuring that unnecessary travel is avoided, and that the logistics of essential travel maximise the outputs from the journey. The use of local capacity for data collection where appropriate will reduce the level of international support required in-country (and therefore international flights). / The evaluation has the potential to impact positively if additional areas for increased operational effectiveness are identified (many of the recognised challenges of implementing the FHCI require travel to resolve them). Of course any increased effectiveness of the FHCI (that may result from the intervention) may also lead to an increase in the overall population as death rates further decrease and this is likely to have an impact on the environment; however both the GoSL and DFID have made strong commitments to improving family planning services and utilisation which will help to offset this impact. / There is very little difference in potential impact between the first 2 options. It is possible that the second option may attract international bids and therefore international travel will be higher than option 1. However should option 1 be preferred it is anticipated that there will still be a need for international technical assistance, given the limited capacity in-country to carry out such an evaluation, and therefore international travel. / There is limited evidence for all three options as most research to date has looked at the relationship between environment/climate change and health outcomes rather than evaluation processes. It is not possible to ascertain evidence for the counterfactual option as the number of influential variables is high and complex. It is possible to argue that without the evaluation there will be no travel, and resulting impact, however it is also possible to argue that without evaluation the opportunities for improved efficiency and the opportunities to ensure the most effective contribution to development, state building and poverty reduction are lost and the subsequent opportunities to reduce the associated environmental damage are compromised.
C. What are the costs and benefits of each feasible option? / Option 1: Government-led implementation. / Costs: The main costs associated with the project will include the design, testing and implementation of the initial evaluation (which will form the basis for developing a framework and processes for the annual evaluations) and the subsequent annual evaluation. These will have to be contracted in given the lack of capacity in either the MoHS or Statistics Sierra Leone to carry out such a large-scale, independent exercise. It is anticipated that the costs incurred in year one will be higher than those incurred in subsequent years, reflecting the plan of work. The exact costs will be defined when the final methodologies are proposed. The provision of up to £1 million is considered adequate to cover the requirements of this intervention. / Benefits: The main benefit of this option will be the direct involvement of GoSL via the MoHS and Statistics Sierra Leone in particular. It is anticipated that this will help to ensure that critical political buy-in and administrative support at provincial, district and health facility level will be met. / Risks: The main risk associated with this option is that the intended independent nature desired of the evaluation may be compromised, politically or otherwise. Additionally there is a lack of capacity in the MoHS and Statistics Sierra Leone to manage a project of this nature; the MoHS department for M&E currently has only 4 members of staff and there is a valid risk that taking on the management of this project may compromise the outcome of this intervention and also other work being undertaken such as ongoing efforts and investments to strengthen of the HMIS. Statistics Sierra Leone also faces critical staffing gaps and undertaking this work will have a similar negative impact to those outlined for the MoHS. / Option 2: Independent evaluation / Costs: The costs for this option will be defined as outlined above (option 1). It is reasonable to assume that the costs for this option may be higher if the project is managed by an international agency, however there is an expectation of cost savings associated with utilising project managers with specific experience in this area (specifically in areas such as risk reduction, errors and faster turn around times). The provision of up to £1 million is considered adequate to cover the requirements of this intervention. / Benefits: The main benefit of this option is that the evaluation will be undertaken by an independent organisation which will add to the credibility of the findings and improved confidence in the development of the framework for the annual evaluation process. In addition this option will include a robust international competitive tender process, against the TOR, which should ensure that the selected service provider has the right mix of experience and technical expertise in impact evaluations which should lead to a quality outcome and help to ensure the best return on this investment. Although the MoHS have been considered as a realistic alternative option there is a high level of support from the MoHS for this option, particularly in light of the lack of capacity in the MoHS and this options independent and objective nature. / Risks: There is a risk that the service provider (whether national or international) will not be able to ensure critical political buy-in and administrative support at provincial, district and health facility level and access to information in the same way that it is assumed that a government-led implementation would be able to. However this is not seen as a significant risk as the TOR for this intervention has been developed in close collaboration with MoHS who are supportive of this intervention and will have an oversight role in its development and delivery. The service provider will therefore be expected to develop effective relationships with all key stakeholders including MoHS. / Option 3: Do nothing / Costs: There will be no financial costs associated with this option, however as noted in the strategic case, there are significant opportunity costs associated with not evaluating the FHCI and with not supporting a sustained approach to annual evaluation. / Benefits: The benefit of not undertaking this intervention will be the ability to utilise the funds elsewhere. / Risks: The risks of this option are high and as outlined in Section A above (the consequences of not doing anything). Notably the opportunity to fully understand the impact of the removal of user fees on health outcomes and on mortality will be lost as will the opportunity to ensure that the effectiveness of the FHCI is scrutinised, learned from and that amendments are made to its implementation as required. The FHCI is central to the GoSL’s commitment to and strategy for the reduction of maternal, newborn and child health and DFID has made substantial investments to date in the initiative. Inevitably many of DFID plans for further support to the health sector (outlined in the MDG Pillar of DFID Sierra Leone’s Operational Plan) assumes that the FHCI will continue, that it is having impact, and that it is operationally effective. This has not been tested.
D. What measures can be used to assess Value for Money for the intervention? / Over the next four years, investment by GoSL and donors in national, fee-free, MDG 4 & 5 focused health programmes is expected to total some £150 million of which DFID will contribute £70 million (47%)[30]. This represents a total per capita spendfor the target beneficiaries of £25 each year of which DFID will provide approximately half at £11.75/capita. / MDG 4 & 5 health care budgets / Period 2012/13 – 2015/16 / Programme Health inc RMNCH Malaria Total / DFID £63,400,000 £7,000,000 £70,400,000 47% / Total £132,700,000 £17,000,000 £149,700,000 100% / Whilst this represents a significant improvement for Sierra Leone in terms of health investment, £25/$40 per capita is below the WHO minimum required to provide basic curative services of $44 in 2009, which WHO recommends should rise to a minimum of $60 (£37) by 2015 if the MDG goals are to be achieved[31] It is therefore increasingly important to determine what is being achieved by the FHCI, and whether it represents good value for money. / The impact evaluation project promises a cost-effective means by which all FHCI stakeholders will be able to progressively assess the FHCI impact. In particular, the project will evidence the degree to which the FHCI’s free-of-charge services and six complimentary interventions are contributing to increased service-uptake, improved health outcomes and reduced maternal, newborn and child mortality. / The programme will also evaluate the total actual cost of FHCI inputs – from all sources – spent in producing the evident results/impacts. By combining assessments of results and costs, the project will enable stakeholders to assess the degree to which the FHCI’s has had an impact on health outcomes and whether this demonstrates good value for money. DFID will also be able to ascertain whether its investments remain within DFID’s fragile-state, value-for-money parameters. It will create efficiency gains as implementers at all levels will be conscious that there is independent assessment of processes, costs and results. Lessons will be learnt as to whether the FHCI is an approach that delivers results at a better value for money compared with other interventions in the Sierra Leonean context. Assessment of value for money issues will be included in the TOR for the service provider. / At £1 million, the requested budget will represent 0.75% of total[32] FHCI investment focused on improved MDG 4 & 5 outcomes over the next four years. As this falls well below DFID’s generally accepted practice of ensuring evaluation costs do not exceed 5% of total programme budgets, this essential intervention is cost-effective and represents very good value for money. Project costs will also be closely scrutinised at regular intervals by DFID to ensure actual costs stay within project parameters and outputs are useful to FHCI management and oversight.
E. Summary Value for Money Statement for the preferred option / On consideration of the benefits and risks (which are seen as low and easily mitigated), the preferred option is the second one: an independent organisation. The independent nature of the implementation is a particularly valued aspect of the selected option. / It is recognised that this option may require more funding than option one but should still fall within the £1 million for which approval is sought; which itself is a small investment given the potential outcome and the scale of DFID’s and GoSL’s investments. The benefits of having experienced technical experts involved and the anticipated resulting high quality of outputs will make a larger and sustained contribution to both the overall outcome of: / Evidence of the role of the FHCI in decreasing maternal, newborn and child morbidity and mortality. / and to the overall impact of: / Evidence of improved maternal, newborn and child health in Sierra Leone.
[30] Health Results Framework 2011-14 (DFID-SL, 2011)
[31] Ke Xu, Priyanka Saksena, Matthew Jowett, Chandika Indikadahena, Joe Kutzin and David B. Evan, Exploring the thresholds of health expenditure for protection against financial risk, World Health Report (2010), Background Paper, 19
[32] 0.014% of total DFID contribution to Sierra Leone’s health sector.

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / The preferred option for delivering the initial impact evaluation of the FHCI and developing the processes and capacity for annual evaluations will be through direct procurement of an external contractor, who may sub-contract to other service providers with particular expertise and/or experience. / Procurement of these services will be through international competitive tendering according to OJEU procedures, and selection will be carried out by a panel involving DFID Sierra Leone, DFID Evaluation Department and the Department of Planning and Information, MoHS.
B. How does the intervention design use competition to drive commercial advantage for DFID? / DFID competition procedures for contracts relating to services will be followed. The judgement of bids against agreed evaluation criteria will be based primarily on the ability to deliver the services specified in the TOR whilst offering the best value for money. The ToR for the service provider will promote flexibility and innovative approaches ensuring that the project retains a best value approach throughout its duration. The budget proposed by bidders will be seen alongside quality and past performance and experience to ensure maximum value for money.
C. How do we expect the market place will respond to this opportunity? / There is an expectation that there will be a number of high quality responses to this opportunity, as a result of the international tendering process, from organisations which have relevant and appropriate prior experience of both designing and implementing impact evaluations of this nature. / The use of Sierra Leonean-based organisations will be explored during the procurement process including possible partnerships between organisations in Sierra Leone and elsewhere. Potential benefits of using Sierra Leonean organisations include greater knowledge of the FHCI and the environment within which it is implemented, strengthening of local capacity, and reduced costs.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The proposed £1 million represents exceptional value for money for the breadth of outcome from this project. The main cost drivers will be associated with the practicalities of undertaking the evaluation including survey costs such as sample size, the scope of work which will involve extensive travel to and around Sierra Leone, the number and type of expertise required, and the time involved across the lifespan of this four year project. The level of confidence in the outcomes of the evaluation and the learning captured regarding free health care in practice are substantial added value.
E. What is the intended Procurement Process to support contract award? / DFID’s international competitive tendering process will be used. This will enable the identification of service providers which are best able to deliver the required outcomes at the best cost. The selection panel will consider criteria including: / The bidder’s understanding of the ToR and strength of technical response including proposed methodology / Relevance and strength of track record in the area / Knowledge and understanding of the health sector in Sierra Leone / The strength of the mix of personnel involved / The financial proposal versus value for money considerations
F. How will contract & supplier performance be managed through the life of the intervention? / The contract and performance of the appointed service provider will be managed by DFID Sierra Leone primarily through an output based contract which will be linked to the attached TOR and milestones outlined in the logframe (and any subsequent DFID approved amendments made after the inception period). The payment of invoices will be made upon satisfactory attainment of these deliverables. / The first five months will constitute the inception period when an inception report will be due to access service provider performance and progress against the agreed deliverables. DFID reserves the right to terminate the contract at this stage if satisfactory progress had not been made. A midterm review of this project will be undertaken and continuation of the contract for the remaining two years will be dependent on the findings of the midterm review being in line with stated expectations.

Indirect procurement – not applicable

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The project will require up to £1 million over a four year period (2012/13 – 2015/16). The following table provides an overview of the anticipated annual breakdown (by financial year). Budgeted expenditure in the first year is higher than subsequent years as it reflects the initial set-up costs and higher level of technical assistance from the service provider. Year four is also relatively high reflecting the cost of the end of project review including activities to carry out a successful impact evaluation. / Projected budget (100% DFID) by financial year / 2012-2013 2013-2014 2014-2015 2015-2016 Total budget (48 months) / Apr -Mar Apr-Mar Apr-Mar Apr - Mar / Total £350,000 £200,000 £200,000 £250,000 £1,000,000 / Forecasting will be completed ahead of the beginning of each financial year. Regular monitoring of forecasts will be carried out through the DFID health quarterly progress meetings where all service providers provide quarterly progress reports against results and expenditure and assess and review forecasts for the remainder of the financial year.
B. How will it be funded: capital/programme/admin? / The programme will be funded from programme resources and has been budgeted for in the DFID Sierra Leone Operational Plan. A payment plan will be set based on the milestones to be agreed during the inception phase.
C. How will funds be paid out? / DFID will make payment to the service provider against quarterly itemised invoices and financial and narrative reports which will be subject to the successful delivery of agreed milestones.
D. What is the assessment of financial risk and fraud? / In general there is a high financial and fraud risk in Sierra Leone. The option identified for delivering this project will reduce these risks by channelling resources through a service provider that has been selected based on a rigorous international procurement process, and can demonstrate robust fiduciary controls. The option of channelling funds through the MoHS is rated as high risk as found in the recent DFID Fiduciary Risk Assessment[33] as a result of weak financial management and procurement systems. This risk is unlikely to reduce in the period leading up to the national elections in November 2012. / The MoHS is supportive of this project, recognising the invaluable information it will provide for policy-making, budget allocation and programme design. The MoHS will also play an oversight role as part of the Steering Committee that will oversee the design and delivery of the project and is satisfied that the project will meet its evaluation requirements as detailed in the jointly developed service provider TOR.
E. How will expenditure be monitored, reported, and accounted for? / All expenditure will be subject to rigorous quarterly monitoring using standard DFID procedures for inspecting invoices to ensure Value for Money and compliance with agreed fees and budget allocations. In line with the DFID Blue Book the ToR for the service provider will outline expectations of financial statements and reporting requirements including: / quarterly narrative and financial reports which can be reconciled to the financial schedule; / presentation of key results, expenditure and forecasts at the DFID health quarterly progress meetings; / annual narrative and financial reports. This information will be shared with MoHS and partners as part of the joint review process the Ministry is introducing from 2012 to monitor and track performance of the JPWF; / Midterm review of programme progress and expenditure at the end of Year Two; / certified annual audit statements showing funds received and expended which should occur concurrently with the annual project review; / A final evaluation report three months after the end of the programme which accounts for all funds received.
[33] Carole Pretorius. Sierra Leone Fiduciary Risk Assessment : Education, Health and Water Sectors, October 2011

Management Case

A. What are the Management Arrangements for implementing the intervention? / Within DFID the project will be managed by the DFID Sierra Leone MDG Team. Technical oversight will be provided by DFID’s Health Adviser whilst day to day issues regarding reporting requirements will be provided by the MDG Assistant Programme Manager. Any contractual issues will be dealt with by the DFID Contracts Officer. / In order to ensure robustness of methodology and quality of reports produced (particularly ensuring factual correct information), a Steering Committee will be established which meets quarterly. Members will be drawn from DFID Sierra Leone under the Health Adviser’s leadership (to include representation from DFID’s Aid Effectiveness, Value for Money and Evaluation Departments), MoHS’s Department of Planning and Information who lead on monitoring and evaluation for the Ministry, and other relevant external stakeholders. / The Steering Committee will ensure that the project is aligned with the management framework for the Health sector as articulated in the IHP+ Compact for Sierra Leone. The project will be incorporated into Sierra Leone’s 3 year rolling JPWF which will provide for sustained financing of the project beyond the life of DFID’s current funding, and report to the Health Sector Steering Group through participation in its multi-stakeholder Integrated Service Delivery and Monitoring and Evaluation working groups.
B. What are the risks and how these will be managed? / Probability & Impact Score (1-5): 1=low 5=high / Risk Prob-ability Impact Mitigation Residual / Probability Residual / Impact / Miss-use of disbursed funds by service provider and its subcontractors. 1 4 The robust contractual arrangements and management of these by DFID will reduce this risk. 1 3 / Service provider fails to maintain a team in-country with sufficient technical or managerial capacity to implement project effectively. 2 5 DFID oversees timely reporting by service provider and facilitates early solutions to identified problems, including termination of contract for persistent poor performance if needed. 2 4 / Sub-contracted partners fail to add required capacity to service provider operations. 3 3 Service provider closely monitors performance of sub-contracted partners and facilitates early solutions to identified weaknesses/problems. 2 2 / Service provider fails to develop process to objectively evaluate impact of FHCI against maternal, newborn and child mortality by end of project. 1 5 DFID oversees timely reporting by service provider and facilitates early solutions to identified weaknesses/problems, including termination of contract for persistent poor performance if needed. 1 5 / National process to evaluate delivery, uptake and impact of FHCI against change in the rate of maternal, newborn and child mortality not fully established by end of project. 1 4 DFID oversees timely reporting of progress by service provider and facilitates early solutions to identified weaknesses/problems in methodology or other barriers preventing effective impact evaluation. 2 4 / Pre and post Election (late 2012) insecurity reduces geographic access. 4 3 Service provider develops alternative strategies during inception phase to counter possible periods of insecurity. 3 2 / Access to GoSL process data delayed or manipulated. 2 4 DFID and service provider maintain supportive relations with key ministries and parastatal institutions to ensure the evaluation process remains objective and is verifiable. 1 4
C. What conditions apply (for financial aid only)? Not applicable
D. How will progress and results be monitored, measured and evaluated? / DFID will agree with the service provider a four-year workplan with key performance indicators in line with the finalised logframe at the end of the five month inception period. The service provider will submit quarterly narrative and financial reports, and present a quarterly progress report against results/deliverables and expenditure at the DFID health quarterly progress meetings. Their performance will also be assessed as part of the annual review process. In line with results-based-management principles, the annual reports will highlight in particular outcomes where progress to date is above or below target to an unexpected degree. Strategies to build on strengths and address weaknesses will then be identified / At the end of year two, a midterm review to assess performance against the contract deliverables and logframe will be carried out by DFID where the decision to contract the service provider for a further two years will be made. A final report is then expected three months after the end of the programme and before expiry of the contract detailing both progress against the deliverables and expenditure of all programme funds. Dependent on the decision at the midterm review, this final report will be produced either at the end of the first two years if the contract is not extended otherwise at the end of the four years.
Logframe / Quest No of logframe for this intervention: 3305237