## Sheet1
PROJECT NAME | Improved Public Financial Management and Accountability
IMPACT | Impact Indicator 1 |  | Baseline (2010) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016) | Assumption
Improvements in the delivery of basic public services, particularly at the sub-national level | Population with access to basic health services | Planned | 78.8% |  |  | 90% | 90% | 1. Government commitment to policy reforms is maintained despite changes in ruling coalition and a new Constitution. 2. Polarization among political parties does not cause programme delays.
Achieved
Source
MDG progress reports, Nepal Health and Demographic Survey
| Impact Indicator 2 |  | Baseline (2010) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
| Adult literacy rate | Planned | 56% |  |  | 60% | 60%
Achieved
Source
Nepal Human Development Report
OUTCOME | Outcome Indicator 1 |  | Baseline (2011/12) | Milestone 1 (2012/13) | Milestone 2 (2013/14) | Target (2015) | Cost Extension Target (2016) | Assumptions
Enhanced efficiency, transparency, and integrity of public finances at the national, sectoral and sub-national level | Proportion of audit observation and unaudited funds of MOFALD by Auditor General of Nepal | Planned | Observations for MoFALD (50th Audit Report ): NPR 3,541,200,000 =10.1% | Proportion of audit observations 9.1% of total audit amount | Proportion of audit observations 8.2% of total audit amount | Proportion of audit observations 7.5% of total audit amount | Proportion ofaudit observations 9.0% of total audit amount (see notes sheet | 1. Strong citizens’ demand for public goods and services puts pressure on government to deliver on reforms. 2. Institutional mechanisms and capacity enhanced and are able to enforce audits.
|  | Achieved |  |  | 12.5% | 10.7%
Source
Office of the Auditor General (OAG) reports
| Outcome Indicator 2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
| Percentage of District Development Committees (DDCs) annual audit reports published electronically | Planned | 0 |  | Website developed | 25% of DDCs publish annual audit reports electronically | 100% of DDCs publish annual audit reports electronically
|  | Achieved |  |  | 80% | 100%
Source
MOFALD Reports
| Outcome Indicator 3 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
| Number of targeted government procurement entities that use the e-GP system | Planned | 0 |  | E-GP software developed | 25% of targeted government procurement entities use the e-GP system | 500 government procurement entities using e-GP system
|  | Achieved |  |  |  | 371 entities using e-GP system in 2015.
Source
PPMO Reports
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016) | Assumptions
Improved local budget and fiscal management | Number of Village Development Committee (VDC) accounting software packages rolled-out to selected VDCs | Planned | 0 | Accounting software developed | Accounting software rolled-out to 500 VDCs | Accounting software rolled out to1000 VDCs | 1500 | 1. Effective coordination among multilateral and bilateral donors in PFM reforms. 2. Changes in government structure due to a new constitution will not cause delays and disruptions in implementation.
|  | Achieved |  |  | 250 | 1196
Source
MOFALD Reports
| Output Indicator 1.2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
| Number of Village Development Committees (VDCs) where performance measures' indicators and guidelines are applied for allocating block grants | Planned | 0 | Performance measures' indicators and guidelines developed | Piloting of Performance measures' indicators piloted in 25 VDCs | Performance measures' indicators rolled-out to 100 VDCs | Performance measure indicators rolled out to 75 VDCs
|  | Achieved |  |  | 50 | 50
|  | Source |  |  | MoFALD
Local Bodies Fiscal Commission and MOFALD Reports
| Output Indicator 1.3 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
| A medium-term budget framework at the national level for MoFALD developed | Planned | 0 | - | - | medium-term budget framework at the national level for MoFALD developed | MTBF framework for MoFALD adopted
|  | Achieved |  |  |  | Drafted but not adopted
Source
Local Bodies Fiscal Commission and MOFALD Reports
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
20 | Implementation status of municipal administration and revenue system. | Planned | 0 | 0 | Municipal administration and revenue system developed | Municipal administration and revenue system developed piloted in Kathmandu municipality | Municipal administration and revenue system developed piloted in Kathmandu municipality
|  | Achieved |  |  |  | Piloting ongoing. Delayed.
|  | Source | [5 empty] | RISK RATING
|  | Local Bodies Fiscal Commission and MOFALD Reports | [5 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | ADB (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016) | Assumptions
Strengthened fiduciary risk management at the sub-national level | Proportion of community-level projects selected through the ward citizen forums and community awareness centers | Planned | 47% | 55% | 65% | 75% | 60% | 1. Effective coordination among multilateral and bilateral donors in PFM reforms. 2. Changes in government structure due to a new constitution will not cause delays and disruptions in implementation.
|  | Achieved |  |  | 49.8% | 47%
Source
MOFALD Reports
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
15 | Number of Village Development Committees (VDCs) subject to internal audit in compliance with revised internal audit guidelines. | Planned | 0 | 0 | Revision of internal audit guidelines. | 100 VDCs subject to internal audit in compliance with revised internal audit guidelines. | IA guidelines developed and agreed with MOFALD
|  | Achieved |  |  |  | IA guidelines not developed
|  | Source | [5 empty] | RISK RATING
|  | MOFALD Reports | [5 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | ADB (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016) | Assumption
Enhanced public procurement system | Number of ministries and districts in which relevant procurement officials trained in public procurement. | Planned | no training conducted | Training on public procurement developed | Procurement officials in 2 ministries, 3 districts trained | Procurement officials of 8 ministries 35 districts trained | Procurement official of 15 Ministries and 60 Districts trained | 1. Effective coordination among multilateral and bilateral donors in PFM reforms. 2. Changes in government structure due to a new constitution will not cause delays and disruptions in implementation.
|  | Achieved |  |  | 2 Ministires, 3 Districts | 11 Ministires and 45 Districts
Source
PPMO reports
Output Indicator 3.2
| 1 Stage 2 Envelope module of e-governmet procurement system developed | Planned |  | NA | NA | NA | 1S2E module developed and piloted in 2 procurement entities
Achieved
Source
PPMO reports
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
15 | Number of procurement plans prepared for DDCs and municipalities | Planned | 0 | 0 | 10 | 15 | 75 DDCs + 55 (old) Municipalities
|  | Achieved |  |  | 62 (DDCs) + 55 (Municipalities) | 72 (DDCs) and 54 (Municipalities)
|  | Source | [5 empty] | RISK RATING
|  | PPMO reports, MOFALD reports | [5 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | ADB (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | [7 empty] | Assumptions
Strengthened institutions of oversight and accountability | Output Indicator 4.1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016) | 1. Effective coordination among multilateral and bilateral donors in PFM reforms. 2. Changes in government structure due to a new constitution will not cause delays and disruptions in implementation.
| Compliance of Corruption Act and related regulations with United Nations Convention Against Corruption (UNCAC) | Planned | Not compliant | - | Amendment to Corruption Act and related regulations for compliance with UNCAC developed | Amendment to Corruption Act and related regulations for compliance with UNCA submitted to cabinet | Technical advice provided to CIAA and NVC for revision of Corruption Act for compliance with UNCAC and new Constitution
|  | Achieved |  |  |  | Securing legislative amendment beyond scope of programme and implementing agencies.
Source
CIAA and Government of Nepal reports
| Output Indicator 4.2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
| Status of complaints response system of National Vigilance Centre (NVC) | Planned | None | - | - | Complaints response system of NVC established and operatioal | Complaints repsonse system settling 50% of complaints received in-year
Source
NVC reports
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Target (2015) | Cost Extension Target (2016)
10 | Training provided to relevant staff of NVC and CIAA | Planned | No training provided | - | - | Basic and advanced level training in fraud audit and investigation competencies for relevant staff of NVC and CIAA provided. | Training delivered to 50 CIAA staff and 50 cross-government staff (NVC, OPMCM)
|  | Source | [5 empty] | RISK RATING
|  | NVC and CIAA reports | [5 empty] | High
INPUTS (£) (Output 1-4) | DFID (£) |  | Govt (£) | ADB (£) | Total (£) | DFID SHARE (%)
| 4200000 |  |  | 13652000 | 17852000 | 23.53%
INPUTS (HR) (Output 1-4) | DFID (FTEs)
0.2 PFM Adviser, 0.2 PFM PM
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2012) | Milestone 1 (10.2013) | Milestone 2 (10.2014) | Target (05.2016) | Cost Extension Target (2016) | Assumptions
Improve public financial management and accountability in key sectors of Nepal | Number of Fiduciary Risk Assessments (FRA) and Annual Statements of Progress (ASPs) | Planned | 0 | 1 FRA | 6 ASPs | 6 ASPs; 6 FRAs | 13 FRAs; 7 ASPs | 1. GoN remains committed on PFM reforms 2. GoN counterparts are willing and available to implement PFM reform 3. Analytical work is used effectively 4. GoN and DPs approve and endorse ToRs for PEFA Secretariat positions
|  | Achieved |  |  | 4 FRAs, 1 ASP | 9 FRAs, 3 ASPs
Source
Supplier's Progress Reports; Number of FRA and ASP reports received by DFID Nepal
| Output Indicator 5.2 |  | Baseline (2012) | Milestone 1 (10.2013) | Milestone 2 (10.2014) | Target (05.2016) | Cost Extension Target (2016)
| Number of sectors with simplified financial monitoring reports produced within 45 days after the end of the trimester with GoN official and endorsed by Development Partners (DPs) | Planned | 0 | 0 | 2 sectors producing simplified FMRs in three consecutive trimesters on time and endorsed by DPs. | 3 sectors producing simplified FMRs in three consecutive trimesters on time and endorsed by DPs. | 4 sectors (Health, local govt, climate change, women and children)
|  | Achieved |  |  | 3 sectors(Forestry, Health, Local Govt) | 3 sectors (Forestry, climatechange, local govt)
Source
Supplier's Progress Reports; FMRs received by DFID Sector Advisors (forestry, local governance and health)
| Output Indicator 5.3 |  | Baseline (2012) | Milestone 1 (10.2013) | Milestone 2 (10.2014) | Target (05.2016) | Cost Extension Target (2016)
| Number of key sectors with new or revised PFM reform action plans developed and shared with the PEFA Secretariat. | Planned | None | 0 | 2 | 2 | 3
|  | Achieved |  |  | 2 | 3
Source
Supplier's Progress Reports
| Output Indicator 5.4 |  | Baseline (2012) | Milestone 1 (10.2013) | Milestone 2 (10.2014) | Target (05.2016) | Cost Extension Target (2016)
| Number of priority actions under key sector PFM reform action plans implemented in conjunction with government with a view to improved PFM processes. | Planned | None | 0 | Activities implemented under 2 pre-developed action plans. Number to be determined | Activities implemented under 2 pre-developed action plans. Number to be determined | 6 priority actions (under Women and Children, Health, Local Govt)
|  | Achieved |  |  | 2 | 2
Source
Supplier's Progress Reports
| Output Indicator 5.5 |  | Baseline (2012) | Milestone 1 (10.2013) | Milestone 2 (10.2014) | Target (05.2016) | Cost Extension Target (2016)
| Number of demand-led analytical assessments completed to inform and improve DFID sector programmes | Planned | None | 3 analytical assessments completed | 4 analytical assessments completed | 4 analytical assessments completed | 5 (PEFA Sec, Health, Local Govt)
|  | Achieved |  |  | 7 | 5
Source
Supplier's Progress Reports; Analytical reports submitted to DFID
IMPACT WEIGHTING (%) | Output Indicator 5.6 |  | Baseline (2012) | Milestone 1 (10.2013) | Milestone 2 (10.2014) | Target (05.2016) | Cost Extension Target (2016) | RISK RATING
40 | Number of long-term technical advisors recruited to support capacity development of the PEFA Secretariat, particularly to enhance sector PFM initatives. | Planned | None | 0 | 2 | 2 | 2 | Low
|  | Achieved |  |  | 0 | 2
Source
Supplier's Progress Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 3000000 |  |  |  |  | 100%
INPUTS (HR) | DFID (FTEs)
0.2 PFM Adviser, 0.2 PFM PM

## Notes
Outcome Indiactor 1: Audit clearance has never fallen below 10.7%. Revised milestone represents realistic stretch for GoN.
Outcome Indicator 2: Online publication of audit reports now mandatory
Outcome Indicator 3: Changed 'percentage' to 'number' as total number of targeted procurement entities never defined.
PFMA Business Case was extended to 31 December 2016 to respond to delays in implementation (related to earthquake and adminstrative delays). As a result, the following output indicators have been extended during the cost extension period:
Output Indicator 1.3
Output Indicator 1.4
Output Indicator 2.2

## Sheet2
OAG 50th report
| NRS | GBP
Capital expenditure | 3599300000 | 22495625
recurrent expenditure | 31535600000 | 197097500
total expenses for MOFALD | 35134900000 | 219593125
audit observations for MOFALD | 3541200000 | 22132500
audit observation % | 10.08%

## Sheet3
[8 empty] | 2012-12-01 | FY 12/13
2013-01-01
2013-02-01
2013-03-01
[8 empty] | 2013-04-01 | FY 13/14
| FY 12/13 | FY 13/14 | FY 14/15 | FY 15/16 | Current OP Total in this BC | Total Additional Requested for future OP | Total in this BC | 2013-05-01
| (current OP period) | (current OP period) | (current OP period) | (next OP period) |  |  |  | 2013-06-01
Funding to the ADB managed SPM Programme | 2.2 | 0 | 2 | 0.8 | 4.2 | 0.8 | 5 | 2013-07-01
Funding to a bilateral contractor for analysis and additional sector support | 0.75 | 0.75 | 0.75 | 0.75 | 2.25 | 0.75 | 3 | 2013-08-01
Total | 2.95 | 0.75 | 2.75 | 1.55 | 6.45 | 1.55 | 8 | 2013-09-01
All figures in million Pounds | [7 empty] | 2013-10-01
[5 empty] | 2.15 |  |  | 2013-11-01
2013-12-01
2014-01-01
2014-02-01
2014-03-01
[8 empty] | 2014-04-01 | FY 14/15
2014-05-01
2014-06-01
2014-07-01
2014-08-01
2014-09-01
2014-10-01
2014-11-01
2014-12-01
2015-01-01
2015-02-01
2015-03-01