    Amendment Letter No. 3
Contribution to 2019 Humanitarian Operations in North East Nigeria under WFP Country Strategic Plan (SO1 and SO3)
DFID Project No. 300432-109 and 300432-112

I refer to the Memorandum of Understanding between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Department for International Development (“DFID”) and World Food Programme (‘WFP’) signed on 17 October 2018.

Following recent discussions and correspondences with WFP on its increased caseload and funding gaps in light of the deteriorating food security situation in the north east of Nigeria, DFID proposes to contribute an additional £10,000,000 (Ten Million Pounds only) to the World Food Programme’s Strategic Outcome 1 under its Country Strategic Plan towards financial year 2020.

DFID therefore proposes that the figures and words £44,500,000 (Forty-Four Million, Five Hundred Thousand Pounds only) in paragraph 3 of the Amendment Letter 2 be replaced with the figures and words £54,500,000 (Fifty-Four Million, Five Hundred Thousand Pounds only).

DFID proposes the contribution will be transferred in accordance with the following schedule

Strategic Outcome	Payment Due Date	UK£/Amount
SO1	17 October 2018	£15,000,000
SO1	15 May 2019	£15,000,000
SO1	15 September 2019	£10,000,000
SO1	15 December 2019	£10,000,000
SO3	15 May 2019	£1,500,000
SO3	5 August 2019	£1,500,000
SO3	5 November 2019	£1,500,000

DFID proposes that the end date of 31 March 2020 in paragraph 5 of the Amendment Letter 2 be replaced with 31 March 2021 for SO1. The end date of March 2020 remains the same for SO3.

DFID proposes that the title in paragraph 7 of the Amendment Letter 6, “Contribution to 2019 Humanitarian Operations in North East Nigeria under WFP Country Strategic Plan (SO1 and SO3)” be amended to ‘Contribution to Humanitarian Operations in North East Nigeria under WFP Country Strategic Plan (SO1 and SO3)’.

1. In accordance with Paragraph 11 of the Framework Agreement, WFP Nigeria shall provide DFID with the following reports:
  1. Progress Report every six (6) months, updating DFID on the status of the SO1 project together with latest available approved budget within six (6) weeks after the end of the relevant period.
  2. WFP Annual Country Report (ACR) – which WFP will submit, not later than 31 March of each year; an annual financial report in WFP’s Annual Country Report (ACR) format or, where relevant, standard trust fund reports, as of 31 December every year, certified in accordance with the WFP’s standard procedures for certification.
  3. Provisional Reports – within three (1) months following the date of completion or termination of the respective Contribution Agreement, the relevant WFP country office (or regional or Headquarters unit in the case of, respectively, regional and global projects) will submit a provisional narrative report summarising the project performance and results as well as provisional financial data in WFP’s ACR or trust fund report format, as the case ay require.
  4. Final Reports: Upon completion of the WFP programme/project, WFP shall submit, no later than 30 June of the year following its financial closure, a final financial statement in WFP’s ACR format certified in accordance with WFP’s standard procedures for certification.

WFP Nigeria shall also continue to provide DFID with a light-touch quarterly narrative progress report that gives an update on activities under SO3, followed by quarterly review meeting.

All other terms of the Framework Arrangement and Memorandum of Understanding will apply.

This letter of amendment will place on record our common understanding of the above changes and will come into operation on the date you sign the confirmation below. This note will be known as Amendment No. 3/2019.

Please sign both copies of this letter; return one to me and retain the other for your own records.

Signed on behalf of DFID:
Name:
Position:
Address/Contact Details:
Date:

Signed on behalf of the Partner:
Name:
Position:
Address/Contact Details:
Date: