Annual Review - Summary Sheet
To note that this document is made up of two components – the General PPA Annual Review (TI-S) and the CHASE PPA Annual Review (TI-UK)

Transparency International Secretariat (TI-S) PPA Annual Report for 2014/15
Programme Value: £16,871,720 over 5 years		Review Date: 1 July 2015
Programme Code: 202515	Start Date: 1 April 2011	End Date: 31 March 2016

Summary of Programme Performance
Year	2011/12	2012/13	2013/14	2014/15
Programme Score	A	A+	A+	A+
Risk Rating	Low	Low	Low	Low

Annual Review Process
This report is based on TI-S’ self-assessment of progress and performance against the PPA log frame during this fourth year of PPA funding. DFID has reviewed TI-S’ assessment and provided a DFID specific response within each section of the report. DFID’s responses are based on the narrative provided, known evidence and subsequent discussion with TI-S. All recommendations have been agreed by both TI-S and DFID.

TI-S Summary of progress and lessons learnt since last review
In terms of advocacy, we have had some major successes in year 4 such as the adoption of anti-corruption principles by the G20 and the inclusion of a governance goal within the draft Sustainable Development Goals. There is a clear momentum for anti-corruption action at the international level (also at the G7 and EU levels), but substantial efforts are needed to capitalise on it. The programme continues to prove its value in changing policies and practices, and our direct support to victims and witnesses of corruption has allowed us to collect more and more stories showing our impact on people’s lives. More than 60 chapters work on such cases and often mainstream this approach into their activity. We will however need to closely monitor civil society space and attacks on activists and whistleblowers, which were prominent issues in year 4. We have increased our reach through website, blog and social media alike, and the 2014 Corruption Perceptions Index received huge media attention and visibility. Partnerships with other NGOs also helped us broaden our audiences. Nationally, chapters have made efforts to reach out to more and more citizens, for example in the Middle East and North Africa, where networks of women leaders have been set up. We continued to strengthen our evidence base on corruption with 10 new publications, ranging from the Exporting Corruption Report on foreign bribery to the Transparency in Corporate Reporting report, which boosted private companies’ engagement with TI and their commitment to improve their behaviour. Finally, the TI secretariat supported chapters to develop their capacity, especially in the field of leadership, risk management, advocacy and communications. For this purpose, horizontal learning and chapter-to-chapter exchanges have proven very useful.

Summary of recommendations for the next year
- Develop a new 5-year strategy to be implemented from early 2016.
- An organisational audit of the secretariat will be performed to examine TI-S’ processes and systems and see how TI-S can further improve its value for money.
- Expand TI-S’ supporter base, for example through TI-S’ Global Unmask the Corrupt campaign and a new responsive website.
- Deepen TI-S’ analysis of National Integrity System Assessment impact data.
- Strengthening synergies between research and knowledge products.
- Secure further partnerships to carry out regional surveys for the Global Corruption Barometer.
- Increase understanding of what works, what does not, and why in anti-corruption work.
- Continue strengthening the management and resolution of cases of corruption.
- Strengthen the TI secretariat’s value-added as a ‘broker’ and ‘facilitator’ within the TI movement.

DFID Response: / DFID welcomes the progress that TI-S has outlined in this section, providing strong evidence of TI’s global influencing, securing significant advances in the G20 and SDGs, for example; the adoption of anti-corruption principles by the G20 and the inclusion of a governance goal within the draft Sustainable Development Goals (SDGs). DFID is aware that there is no other organisation in the corruption sphere that has such a broad spread of reach, this is important for partners like DFID where making the connection between the different levels is key. / It would have been good to see the link made clear in this section between PPA funding and what has been achieved, although this is explained further on in the report. / TI-S has included ambitious and robust activities for the next reporting year. DFID looks forward to seeing the outcome of these, particularly the finalised new 5 year strategy.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	DFID to input
DevTracker Link to Log frame:	DFID to input

TI’s strategy 2015 remains the overarching guiding document for the TI secretariat and chapters. Continued PPA support allows us to take the implementation of our key strategic priorities to the next level. The adoption of TI’s strategy 2015 was a landmark moment for the TI movement. This document sought to bring more common focus to the work of the TI movement while supporting its diversity. Based on the strategy, the secretariat developed a five-year implementation plan. It is for the continued and deepened implementation of this five year plan and for the specific role of the secretariat within the TI movement that PPA support is used. The PPA logframe reflects a few of the key strategic roles of the secretariat, such as global influencing (outcome 1, output 3), support to chapters in undertaking national level work (outcome 1, output 4) and development of evidence and recommendations on anti-corruption policy and practice (output 1). Output 2 reflects the increased focus on people engagement in the TI movement. It is important to note that, although the PPA does not necessarily directly fund national-level changes in policy and practice mentioned in the report, it has been indispensable to allow the secretariat to fulfil its roles, such as providing technical assistance to chapters and supporting them in developing policy advice based on existing standards. The PPA has provided the backbone that enables TI to be present in over 100 countries through its network of chapters, and to work towards change as an international coalition. The intervention logic of the PPA is based on the assumption that improved anti-corruption understanding, policy and practice by public, non-state actors and citizens all over the world (Outcome) contributes to a reduction in corruption at all levels and across all sectors of society (Impact). The four result areas are consequently interconnected. A better understanding of corruption and how it manifests itself enables citizens to be better informed when demanding accountability. Equally, information about corruption will allow TI to undertake evidence-based advocacy aiming to improve policy and practice of public and other institutions. While leading governmental and business institutions have the potential to influence the way corruption occurs within societies, public pressure can be used to ensure greater responsiveness by these institutions. Meanwhile, laws and their effective enforcement can provide the framework for operations and value-based leadership can help shape behaviours. Ultimately, working better together as a movement will enable us to become better at diagnosing corruption and will allow the various constituents of the movement to learn from each other’s interventions in citizen mobilisation, advocacy, coalition building.

The UN Sustainable Development Goals will frame the future of the development agenda and TI, also in partnership with the UK government, has been actively engaged in shaping these. TI’s strong belief that corruption must be ended in order to end poverty was amplified by a joint statement signed by 70 organisations and companies, and is reflected in a call made by more than seven million people from 194 countries who said that “an honest and responsive government” was among their top four concerns. In 2014 global news were increasingly marked by corruption scandals, often made public by whistleblowers. Large-scale tax evasion, money laundering and corruption schemes are being unveiled, pointing to the need for integrity in the business and public sectors. We continue seeing the space for civil society action shrink in many countries. This trend, combined with ever stronger push-back from vested interest, makes it even more essential to scale up our support for anti-corruption activists and whistleblowers.

While maintaining our evidence-based and constructive approach and capitalise on our expertise and strengths, the election of a new Chair and Vice-Chair of TI’s international Board of Directors has given the TI movement new momentum and energy. Building on our traditional and effective ways of working, we will increasingly use cases to identify systemic weaknesses and campaigning for change.

DFID Response: / TI-S have used this section to provide a clear, concise outline of how the PPA supports the work of TI-S which is reflected in the outcomes and outputs in the logframe and in the narrative throughout the report. / DFID notes the election of a new Chair and Vice-Chair of TI’s international Board of Directors is being credited for a new drive and energy throughout the TI movement.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The programme is on track and we expect to achieve the outcome by the end of year 5. In this reporting year, three of the targets were achieved, while on one indicator (1.3) we are slightly below target.

Indicator 1.1: TI contributed to 57 changes in policy and practice, including:
- The creation, following allegations of embezzlement, of an independent trust in Honduras to oversee the purchase and distribution of pharmaceuticals by state-run hospitals
- The request by the Kenyan government that our chapter becomes an observer on the national implementation entity committee, to take part in the Task Force on Anti-Corruption for REDD[1], to give training on anti-corruption, and to develop a code of conduct for the National Environmental Management Authority committee.
  [1] Reducing Emissions from Deforestation and forest Degradation
- The setting up of a complaints desk by the Department of Lands in Papua New Guinea which was launched in August 2014. Our Chapter advocated for a complaints desk following the analysis of citizens’ corruption-related grievances reported to the chapter since 2009, which revealed that they mostly related to the land sector. TI PNG collaborated with the government by providing technical guidance. The chapter now continues to follow up and monitor the complaints received and the Land Department’s progress in addressing them.
- Changes regarding the transparency of lobbying in several European countries

Indicator 1.2: 34 TI secretariat recommendations were adopted, including the following:
- The G20 adopted anti-corruption principles. TI conducted intense advocacy on countries seen as blocking, including China, as well as supporting (Australia) the adoption of these principles. TI also authored an op-ed for Open Democracy 50:50 on the G20, corruption and gender which was listed in their "Highlights of 2014".
- The UN SDGs: The UN Working Group adopted a governance goal recommendation (using TI’s wording), an anti-corruption target and a target related to accountable and transparent institutions. TI worked hard to get government and company support for this goal. TI organised a high-level meeting with UK Prime Minister Cameron and the President of Ghana where Mr. Cameron used TI facts, figures and key messages on development. We also published a sign-on letter calling on governments to back a governance goal. The letter had more than 70 sign-ons from over 20 countries, including companies such as Safaricom and Ericson and NGOs like Oxfam International. In addition, TI leads up work on supportive states within our role on the executive committee of Beyond2015, which oversees the strategic management of the platform of over 1,300 CSOs worldwide.

Indicator 1.3: The number of unique visitors on our website increased (+6.4%), but not as much as targeted (10%). This is due to an increased focus on our social media which in turn has led to an increase of social media supporters by 50% to 100% depending on the platform. Also worth noting is the huge increase in backlinks to the TI website which have grown from 290,000 to 1.75 million from end 2013 to end 2014. Our flagship Corruption Perceptions Index is a huge opportunity to increase our reach, and we succeeded in attracting media attention, for example through an embeddable map of the results that was viewed on hundreds of external websites and is becoming the single most viewed piece of content we have ever produced – 3.2 million views in a single month. For International Women’s Day, through a special website feature, blog posts and social media, we successfully showcased how corruption affects women and the achievements women have had against corruption, including several interviews with female chapter staff from all regions. The content proved highly popular and one social media graphic received around 10,000 likes and 800 shares on Facebook, making it one the most popular posts for us.

Outcome indicator 1.4: 33.9% of the cases taken on by our chapters were solved since the new cases database was started in 2011 (target: 30%). TI’s impact on people’s lives is reflected in the human interest stories that we collect from the many cases of corruption reported to our chapters. A recent example is the case of a raped child in Zimbabwe, where the accused bribed the police to try to drop the investigations, but was eventually prosecuted thanks to TI’s support and legal advice. This shows the importance of giving people an avenue to speak up against corruption. This area of work was strengthened by the development of an online Corruption Reporting Tool setup wizard, which assists chapters in the deployment of their own tool in order to allow people to report corruption grievances on a much larger scale, to enhance monitoring of corruption and visualise it on a map.

Overall output score and description
To develop evidence on corruption issues: A+
To support citizens to address corruption and promote integrity: A+
To reach out to and influence external stakeholders: A
To strengthen the capacity of the TI movement: A++

Key lessons
- There is a clear momentum for anti-corruption at the international level (G20, G7, EU, UN Sustainable development goals), but substantial efforts are needed to capitalise on it. Meanwhile at the national level however, there have been increased insecurity and attacks on civil society last year, such as in Sri Lanka, and supporting anti-corruption activists and whistleblowers has become even more essential.
- Work with witnesses and victims of corruption is more and more mainstreamed into the activity of chapters, and taking different forms.
- An increasing number of visitors are coming to the TI website using a tablet or phone. We started extensive work to make our website responsive (i.e. adapted to mobile devices).
- Partners can really help us amplify our message and reach new and larger audiences. The partnership with Global Witness and ONE for our G20-related work is an example.
- Partnerships with existing regional survey networks seems to offer a sustainable long-term model for our Global Corruption Barometer, our flagship survey of citizens’ experience and views of corruption.
- Chapter-to-chapter exchanges proved very useful for learning.

Key actions
- 2015 will be an important year for TI as the movement is developing a new 5-year strategy that is expected to be implemented from early 2016.
- An organisational audit of the secretariat will be performed to examine our processes and systems and see how we can further improve our efficiency and value for money.
- We aim to expand our supporter base, for example through our global Unmask the Corrupt campaign, through a new responsive website that attracts more visitors and through technical assistance to our chapters on fundraising from the public.
- Regarding our research work, our priorities will be the Global Corruption Barometer, deepening our analysis of the impact of National Integrity assessments, and strengthening synergies between research and knowledge products.

Has the logframe been updated since the last review? The logframe was updated following DFID feedback to be more ambitious in our targets. The final updated logframe was approved by DFID and is reported on here.
DFID Response: / DFID is pleased to learn of the progress made by TI-S this year and notes that even though indicator 1.3 is slightly below target, TI-S are confident that the programme is on track and that it will achieve all outcomes by March 2016. / We note TI-S’ achievements under each outcome indicator, particularly interesting as mentioned earlier, is the excellent work on the G20 and the SDGs. / The work and activities undertaken by TI-S for International Women's Day on how corruption affects women and the achievements women have had against corruption, is interesting and important. We are pleased to note the impact this had on social media with a particular graphic being one of the most popular ever posts for TI. / We are pleased to see TI-S are using learning to improve and develop, for example working with partners to help reach new and larger audiences. TI-S’ partnership with Global Witness and ONE for its G20-related work is a good example of this. / The overall output score of ‘A+’ reflects TI-S’ sound progress in the first year of the extension.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	To develop evidence on corruption issues
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number and Description of TI-S research publications	10	10
No and descriptions of TI National Chapter research publications supported by TI-S	30	39

Evidence based advocacy is an essential part of TI’s approach to fighting corruption. It allows us to identify and formulate recommendations and solutions based on evidence, thus bringing credibility and access to opinion makers and policy makers. In line with this year’s target, we published 10 reports on topics ranging from corporate integrity to poverty and foreign bribery. TI’s evidence and research outputs focused on issues that were high on the agenda, e.g. sustainable development/ climate change (and the link to corruption) as well as on its long-standing flagship reports, such as the Corruption Perceptions Index, Foreign Bribery Monitoring (OECD Progress Report) and Transparency in Corporate Reporting assessments of the world’s largest multinational companies.

TI’s assessments of the various climate change-related funds and mechanisms have contributed to a number of advocacy gains, such as increased disclosure by UN REDD programme and a review of the Global Environmental Facility’s engagement policy with civil society. In a similar vein, the follow-up advocacy by TI chapters on TI’s Exporting Corruption Report, which assesses OECD member states’ compliance with the Foreign Bribery Convention, has been an important factor in helping move governments towards relevant legislative changes and particularly better enforcement. Here, Canada and New Zealand (classified in 2013 under “limited” or “little” enforcement, respectively) are particularly noteworthy as, for the first time, relevant investigations of foreign bribery are under way.

The Corruption Perceptions Index (CPI) has reached a wide and global audience with more than 250,000 downloads of CPI material in the months after the launch, and 3 million clicks on the CPI interactive map. It also continues to be used widely by policy-makers and the business community. A recent survey shows that 3 out of 4 compliance officers of major companies use the CPI information as a primary source for their country risk analysis. TI’s Transparency in Corporate Reporting report is expanding its recognition and impact, as more and more companies (80 this year) engage with TI to discuss their ranking and how to foster corporate transparency.

TI chapters received substantial support from the secretariat (development of methodologies and training on their use; technical assistance and quality assurance; editing and review of reports) to build their own evidence base in their countries. The 39 national reports published are an integral part of larger evidence-based advocacy efforts by TI chapters to improve anti-corruption efforts in their countries. This combination of strong evidence, the engagement of key stakeholders in the process and subsequent constructive advocacy is a hallmark of TI’s approach to fighting corruption. The National Integrity Systems assessments, which provide a comprehensive sector-by-sector analysis of national anti-corruption efforts as well as concrete recommendations to stamp out corruption, are a good example. While impact resulting from the 14 assessments published this year is too early to establish, such reports provide a roadmap for change, and we already have evidence of how much they have enabled chapters to influence governments and trigger reforms. An example of earlier change comes from Georgia, where the party and campaign finance law was amended following a campaign by a civil society coalition formed by TI Georgia, thereby improving transparency and the protection of voters against intimidation. This was a direct result of the study, which gave credibility to the advocacy work.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
- securing partnerships to carry out regional surveys for the Global Corruption Barometer, which gathers citizens’ views from all over the world
- deepening our analysis of the impact of our National Integrity System assessments
- strengthening synergies between TI’s research and knowledge products
- increase understanding of what works, what does not, and why in anti-corruption work.
- strengthen empirical research towards greater case based advocacy and campaigning.

DFID Response: / DFID notes that evidence based advocacy is an essential part of TI-S’ approach to fighting corruption, therefore, we are pleased to see that TI-S has made strong progress against this output, meeting the target for indicator 1.1 and exceeding the target for indicator 1.2 by 30%. The strong results reflect the progress being made by TI-S in the area of research and evidence. / There is strong evidence of TI-S’ reach and influence in the political arena. TI-S’ mapping of OECD countries’ performance on anti-bribery is judged to be a catalyst for other countries to revitalise their approach to their companies’ bribing overseas as TI-S’ analysis showed only four ‘active enforcers’ of the OECD convention (UK is one of these). For example, France is now about to run a large international conference next year focused on its companies’ bribery; signalling the scrutiny has had an effect. / Scoring: A+ - Outputs moderately exceeded expectation.

Output Title	To support citizens to address corruption and promote integrity
Output number per LF		2	Output Score	A+
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of corruption grievances reported to ALACs	3500	4688
Number of case studies published of people successfully resisting corruption	40	40

By end of March 2015, 62 chapters were supporting victims and witnesses of corruption through a total of 102 offices. 4,688 corruption grievances were reported, well over the target of 3,500. The number includes 2,180 complaints from men and 815 from women (gender information is not known for the rest of the cases). The data is received from the online database with which TI is collecting information on corruption cases. As of March 2015, 46 countries had access to this online database, although 6 of them had not yet used it. The TI secretariat has been managing the database since its inception and has helped chapters use it and improve the quality of the data. It also provided tools (a case management handbook and an online reporting tool setup wizard), and fostered learning and knowledge sharing.

A total of 40 case studies were published during the reporting period. These include:
- 16 true stories, viewed more than 23,000 times on the website.
- 7 video stories profiling citizens in Africa who successfully spoke out against corruption with the help of our legal advice centres.
- Video profiles of social entrepreneurs whose initiatives are leading to significant gains against corruption.
- A photo story on migrant workers in the Maldives. Selected by the editorial panel of the platform Exposure as one of the week’s top stories, the story was viewed 5,887 times.
The latter example provides particularly interesting lessons:
- The storytelling output does not only give an account of TI’s successes in helping citizens solve their grievances; it also increases our visibility. For example, the Facebook post on this Maldives story attracted 6,939 likes – one of the most-liked posts of the year.
- The attention raised by such stories helps chapters to speak out more effectively at the national level: the photo story prompted a national TV news service to invite the chapter to talk about their work as well as two print stories, allowing the chapter to increase public awareness of this under-discussed issue. Stories also support fundraising efforts at a global and national level.
- It is also an example of a chapter mainstreaming the support to victims and witnesses of corruption in its work. A lot of grievances came from migrant workers, and the chapter decided to reach out to them, advise them on their rights, and eventually advocate for new legislation on migrants’ rights. Citizens’ demand for support thus allows identifying specific issues where our work can have impact on people’s lives, but also on policy and practice.

An online story database now provides the Transparency International movement with a fully searchable selection of 60+ human interest stories (sortable according to location or topic). It will allow chapters to easily source the right success case study to be used in their fundraising or public communications.
Summary of responses to issues raised in previous annual reviews (where relevant)
We have updated our ALAC data following the problems that we encountered in 2013. The data is attached to the report.

Recommendations
- TI-S will continue to strengthen the management and resolution of cases of corruption by professionalising its systems and approaches and by expanding this work nationally and globally.
- To achieve this, it is essential to strengthen the use of data for advocacy and technology for reporting corruption cases, and to support TI chapters to use social sanctions and civic actions to solve relevant cases.
- TI-S will work with the TI movement to mainstream case work into as many areas as possible, be it procurement, election monitoring, corruption in the private sector, etc.
- TI-S will increase its fundraising efforts to support case work by Chapters.

DFID Response: / TI-S has exceeded the target for indicator 2.1 and met the target for indicator 2.2. / DFID is pleased to learn that the number of corruption grievances reported to ALAC's has been exceeded by 34% with 62 chapters supporting victims and witnesses of corruption through a total of 102 offices. We would have liked to see more information here on what happens after the corruption grievances are reported. / DFID appreciates that TI-S are attempting to disaggregate the data on this indicator. We look forward to seeing more disaggregation of data where possible, in future reporting. / The total of 40 case studies published in the reporting period is impressive, we note the examples TI-S has provided of the snowballing effect of these, for example increasing TI-S’ visibility and supporting fundraising efforts at both the global and national level. / DFID notes that TI-S has updated its ALAC data following issues with this in 2013. / Scoring: A+ - Outputs moderately exceeded expectation.

Output Title	To reach out to and influence external stakeholders
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of page views of the TI Space for Transparency Blog	499,572 (i.e. 10% increase)	479,008 (i.e. 5.5% increase)
Number and description of TI documents with recommendations on Anti-Corruption practise and policy annually	30	41

During the reporting period, with PPA support, there was a greater focus on reaching larger audiences through outreach to our website and social media channels, which explains why we are under target for the first indicator (which measure the readership of our blog only), while substantially overachieving on the second one. In total, we published 109 blog posts in 2014 with slightly more than 50% focused on TI chapter activities. We produce this content in collaboration with the chapters, either interviewing them, editing text they send, or drafting based on raw materials they have sent. These efforts help to raise the profile of their national work to the international level. We accompanied the 2014 Corruption Perceptions Index launch with a series of blog posts analysing the results for various regions. The L.A. Times published an article drawing on many of the blog posts.

Our chapter in Haiti and staff at the TI secretariat worked on a blog post describing the long process of anti-corruption legislation which was guided by TI’s work. On 8 April 2014 Prime Minister Laurent Lamothe both linked to the blog on his Facebook page (which has 89,000+ likes) and tweeted it to his 46,000 followers.

There have been increased efforts to reach out to women and communicate on the relationship between gender and corruption:
- In the Middle East and North Africa, an initiative was launched to create opportunities for women to play a role in the fight against corruption. In 6 countries, chapters and partners began targeting women in their outreach work for the first time in the region. National networks of women leaders (450 as of October 2014) from the private, public and academic sectors have been established and we plan to continue working with them on advocacy activities in 2015.
- Our chapter in Guatemala carried out a study to assess if women have as much access to public information as men and if and how their level of access influences their economic development. The chapter is now planning to work with the government to develop and implement public policies for improved economic welfare of women.
- For International Women’s Day, through a special website feature, blog posts and social media, we successfully showcased how corruption affects women and the achievements women have had against corruption, including several interviews with female chapter staff from all regions. The content proved highly popular and one social media graphic received around 10,000 likes and 800 shares on Facebook, making it one the most popular posts for us: http://blog.transparency.org/tag/womenagainstcorruption/

Summary of responses to issues raised in previous annual reviews (where relevant)
Regarding further details on the widening of TI’s audience, especially in the Arab world, we have expanded our presence by formalising a partnership with a Jordanian NGO, and continued to strengthen our collaboration with I Watch, our chapter in Tunisia. The broadening of our audience in Tunisia is particularly evidenced by the chapter’s outreach to the youth (e.g. summer school) and an initiative to create opportunities for women to play a role in the fight against corruption (see above).

Recommendations
- Shaping and developing a supporter base will top TI-S’ list of ambitions for next year. TI-S aim to shape a digital environment that truly engages and inspires its supporters.
- Launch a new responsive homepage (i.e. suitable for mobile devices) that aims to attract more visitors.
- The continued successful rollout of the global Unmask the Corrupt campaign remains a priority. TI-S also see this campaign as an important driver for engagement, capacity building, and impact.

DFID Response: / DFID notes that although TI-S has exceeded the target for indicator 3.2 by 37% it has not quite met the target for indicator 3.1. We accept that this is largely due to TI-S deciding to focus on reaching a larger audience through its website and social media channels rather than through readership of the TI Space for Transparency Blog. However, it would have been helpful had TI-S contacted DFID once this decision had been made and we could have discussed revising the target figure on the logframe. This is something TI-S should bear in mind for future reporting. / We are pleased to learn that TI-S, in collaboration with the Chapters, published a total of 109 blog posts in the reporting year, which in turn has led to increased awareness at an international level of the work of the Chapters throughout the TI movement. That fact that the then Prime Minister of Haiti linked to a blog post relating to anti-corruption legislation which had been produced by TI-S and the Haiti Chapter is a further example of TI-S’ reach and influence. / Scoring: A - Outputs met expectation.

Output Title	To strengthen the capacity of the TI movement
Output number per LF		4	Output Score	A++
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of capacity development activities implemented by TI Chapters with Secretariat support	30	39
Number of trainings organised by TI-S for TI National Chapters	30	50

The TI secretariat continued to provide ongoing support to TI chapters and to carry out activities aimed at strengthening the capacity of the global TI movement. Efforts to facilitate horizontal learning as an effective approach to capacity development were further intensified. Below are more details on three of this year’s priority areas:
Leadership Development: Building on the success of an initial ‘leadership development’ pilot project initiated in September 2013, a model for induction of Executive Directors in TI Chapters was piloted in the Asia Pacific region. The model is framed around a set of key leadership behaviours, and combines experiential learning in a workshop setting with personal leadership development plans supported by ‘learning buddies’ and senior mentors from the region. Secondly, a group of 5 senior chapter executives met in April 2014 to explore strategic leadership challenges, and benefited from a 10-day ‘study tour’ to Bangladesh to deepen their understanding of ‘inclusive leadership’. The pilot identified the combination of training, horizontal learning, experiential learning (incl. out of the classroom) and coaching provided by a senior leadership development consultant as a key success factor.
Risk management capacity: The TI secretariat developed a “risk management health check” to help TI chapters evaluate their current level of risk preparedness and to develop practical action plans to address any critical gaps faced, in turn allowing them to do better advocacy. The tool was piloted by TI Argentina in December 2014, and is now available in Arabic, English, French, Russian and Spanish. Dialogue was initiated with chapters in Cambodia, Georgia, Romania, the UK and Vanuatu with a view to implement the tool in 2015. The secretariat supported chapters in Palestine and Tunisia in developing security action plans, and representatives from 10 countries took part in security-related capacity building activities in 2014. Training on risk management has already significantly enhanced the capacity of a number of participating chapters. For example, the Chapter in Yemen has now finalised a written security and safety policy, and has begun holding monthly meetings to discuss the security situation and safety of staff, participants and supporters. Chapters that faced concrete safety threats (Palestine, Sri Lanka, Maldives, Yemen) were supported by the TI secretariat security helpdesk in developing immediate risk response capacities.
Advocacy and communications capacity: Building the capacity of TI Chapters to establish, nurture and sustain effective relationships with key external stakeholders is critical to achieving sustainable anti-corruption impact. Often, this capacity is built through project-related training that allows Chapters to directly put into practice any newly acquired advocacy, campaign and communication skills. For example, Chapters that participated in the “Lifting the Lid on Lobbying” project individually and collectively developed capacity to advocate against legal gaps and the lack of transparency in lobbying practices in 17 European countries and the EU in Brussels, culminating in the launch of a regional report scheduled for April 2015. At other times, Chapters received individual, tailor-made training. For example, TI Italy demonstrated enhanced advocacy capacity following such training by launching a domestic media campaign on occasion of the G20 Anti-Corruption Working Group meeting, and actively engaging in TI’s global ‘Unmask the Corrupt’ campaign. To support this capacity development priority, we also developed a ‘communications hub’ that serves as a resource centre for chapters.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
TI will increase the use of horizontal learning and knowledge exchange as a capacity development approach.

DFID Response: / TI-S has made very strong progress against this output, overachieving indicators 4.1 and 4.2, by 30% and 67% respectively. / TI-S are to be congratulated on the excellent results for this output, however, it would have been helpful if the narrative had provided an explanation as to why both indicators were so substantially exceeded. TI-S has provided information in the lograme as to why these milestones are set at the particular targets for each one, which is mainly due to a decrease in support for its work on capacity development. TI-S has informed DFID that both these targets are hard to predict but has agreed to revisit this output to see if more realistic targets could be set for 2015/16. / It is good to see progress on internal strengthening, especially leadership development. This is something that, with the huge span of chapters, stronger ones ought to be a good reservoir of skills for bringing on the weaker chapters. / Scoring: A++ - Outputs substantially exceeded expectation.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The organisation’s cost drivers remain the same, and include costs related to staff, travel, honoraria and premises at the secretariat, plus the expenditure incurred by our chapters and project partners. On the economy side, our commitment to ensuring more value from the resources we use is confirmed by our internal VfM assessment of policies and procedures, and travel-, honoraria- and premises-related costs. These highlighted a number of strengths and a few weaknesses, as well as recommendations in terms of further process improvements. On premises, current rental figures show very good value for money (average of €8.40/m², compared to a market range for a similar property of €11.00-€17.00/m²). On honoraria, we have identified the need to strengthen our procurement process, which will be done in 2015. In terms of effectiveness, as we manage a large number of donor grants, a key delivery driver is our programme management skills and practices; we started to implement Prince2 as the standard project management methodology and sought the qualification of project managers/coordinators and accountants. This is expected to increase efficiency in project management and implementation, and generate in the medium term substantial VfM. Finally, we are constantly improving our processes and approaches to monitor the impact of our work.

VfM performance compared to the original VfM proposition in the business case
During the reporting period, the secretariat developed a value for money policy, committing to the adoption of best practices in the delivery of VfM on all our activities. The policy sets out how we will ensure the delivery of VfM; it explains our underlying approach to VfM, and lays out the objectives, principles, implementation guidelines, as well as roles and responsibilities. We have been working towards adopting and mainstreaming the policy into our work. In the beginning of 2015 we started piloting the new approach. We also conducted a benchmarking exercise for staff costs, and will do so for travel costs. On the monitoring and control of costs, the new financial management information system is already providing higher-quality information faster and more efficiently; improving accuracy, control and transparency; and allowing for better decision making. On the monitoring and evaluation side we are strengthening feedback mechanisms to better track our impact, which is an important dimension of VfM. Regarding programme management, we are testing new project reporting templates that focus on classic VfM measures, and grant agreements with project partners were amended to include VfM. The Mid-Term Review of the secretariat’s implementation plan for the Strategy 2015, to which PPA support contributed, has also helped us identify key actions to increase VfM.

Assessment of whether the programme continues to represent value for money
The above shows that VfM is an integral component of the programme. Our robust programme management and procurement processes, cost savings efforts, and impact in the fight against corruption (see part B) demonstrate the outstanding value for money of TI’s PPA. Examples of improved efficiency include the move from a centralised model of undertaking the Global Corruption Barometer to a regional partnership-based model, which substantially decreases the cost of the survey, and the implementation of a new finance and accounting system.

Quality of financial management
The management of the secretariat’s finances is guided by a medium-term Finance Strategy, realised by the engagement of qualified finance staff (including fully certified accountants); the existence of, and compliance with, an array of policies and procedures; the implementation of best accounting practice (e.g. delegation of duties, four eye principle); as well as robust systems and processes. The effective financial management of projects is further materialised by the deployment of an effective partnership between the project implementation and finance teams.

DFID Response: / Although good to see that TI-S are aware of its key cost drivers, this section could have been strengthened if the costs associated with these had been specified and details on how TI-S are ensuring that it is minimising these costs was included. / We note that TI-S’ internal VfM assessment has identified strengths and weaknesses throughout the organisation; it is good to see that the cost for premises is at least €3.00 or more per m² cheaper than similar properties. However, the assessment has identified the need for TI-S to strengthen its procurement process in regard to personal costs for consultants; this will be done in 2015. DFID looks forward to hearing how this has progressed in future reporting. / DFID is pleased to learn that TI-S has now developed a VfM policy. We are also pleased to see that TI-S are using benchmarking for staff costs and plan to do the same for travel costs. / We note that TI-S has assessed the TI-S PPA as demonstrating outstanding value for money. The example of improved efficiency in regard to the Global Corruption Barometer moving from a centralised model to a regional partnership model is interesting and is a good illustration of TI-S' commitment to VfM. / It would have been useful to learn how TI-S has performed against set targets in the VfM offer which was submitted to DFID earlier this year.

E: RISK (½ page)

Overall risk rating: Low

Overview of programme risk
In this reporting year significant progress has been made on managing and preventing risk. Responding to our intention to speak out more boldly on corruption, our pro bono networks of lawyers was expanded. A Political Risk Management Panel was created to make rapid political and legal risk assessments and executive decisions when needed. There were increased attacks on civil society, notably on anti-corruption activists and whistleblowers, and protecting them is therefore more and more crucial. On Sri Lanka for example, we published a joint statement with four international journalist protection groups. We have worked with a security consultant to improve the security procedures in chapters in five countries in the Middle East and North Africa. Chapters then developed plans and policies and procedures to deal with safety and security issues. A “TI risk management health check” was developed to enable TI chapters to assess their risk management capacity, and develop action plans to address critical shortcomings. Meanwhile we continued improving contract templates.

Outstanding actions from risk assessment
We will consolidate our internal anti-corruption systems into one policy during year 5.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe: Y
Most of the targets have been reached. The number of visitors of our website and blog (outcome indicator 1.3 / output indicator 3.1) have not gone up as much as we had planned (+6.4% instead of +10% / 5.5% instead of 10%) mostly because we focused on our social media reach. This focus has led to an increase of social media supporters by 50% to 100% depending on the platform. Our continued focus on building our supporter base enables us to realise our ambition regarding outreach and influencing external stakeholders.

Performance of partnership (s)
Our key partners are TI national chapters, whose local reach and expertise have been essential to achieve collective impact. Many changes in policy and practice have come from chapters, supported by the secretariat through the design of anti-corruption tools, capacity development, etc. The secretariat also complements national work by advocating for global and regional reforms (e.g. Sustainable Development Goal on governance). More broadly, partnerships are at the core of TI’s work. For example, collaboration with Global Witness and ONE boosted our visibility and reach ahead of the G20 summit, and our work with the OECD has shed light on how well its convention against foreign bribery is enforced. Strategic engagement between TI and DFID was scaled up in year 4, e.g. with the joint side event on Corruption and the SDGs during the 2014 UN General Assembly. A high level meeting was also organised in March 2015 between TI and DFID senior leadership to examine global corruption trends and approaches and discuss ways to enhance our collaboration. We contributed to Bond’s paper “The changing role of UK-based INGOs” and to the IELG submission on unrestricted funding. Finally, TI led on a study comparing different donor approaches to unrestricted funding.

Asset monitoring and control
Robust policy, procedures, and practices guarantee a high level of confidence on the management of the organisation’s assets. A detailed step-by-step approach, from procurement to inventory count to disposals, and a clear demarcation of responsibilities, ensures accountability for all assets purchased for use in the operation of the business with a life exceeding one year and an initial purchase value higher than €410.

DFID Response: / TI-S has made significant progress on risk this year, including the creation of a Political Risk Management Panel. A TI risk management health check has also been developed which will allow TI Chapters to assess their risk management capacity and address critical shortcomings. TI-S will also consolidate its internal anti-corruption systems into one policy during the final tear of the extension period. / The overall risk rating for this programme is Low. All of the risk ratings for outputs 1-4 have remained the same as last year. As part of the Due Diligence exercise which took place in 2014, prior to extension funding, TI-S were asked to provide the following; updated Code of Conduct Policy, Conflict of Interest Policy and its Whistleblower Policy. All of which were submitted within the requested timeframe. / TI-S has met the majority of their targets apart from output indicator 3.1 because of a focus this year on its social media reach. TI-S is confident of meeting set targets by 2015/16. / Although TI-S' key partners are the national Chapters it is good to learn of TI-S' collaboration with other partners such as Global Witness and ONE and of its work with the OECD. / DFID notes TI-S' monitoring and control systems.

G: CONDITIONALITY (½ page)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
In 2014, with the PPA support, the TI secretariat conducted a Mid-Term Review (MTR) of its 5-year implementation plan. This review was designed to be participatory and feedback-oriented: it interviewed over 30% of staff and a considerable number of external stakeholders. Hence, the MTR contributed significantly to TI’s learning and internal accountability processes. Building on the MTR, in 2015 an organisational audit will be conducted to examine our processes, systems and ways of working and see how we can further improve our efficiency and value for money. An evaluation on the performance of our Asia Pacific Regional Programme and a learning review on the effectiveness of the Integrity Pacts were carried out. The TI movement is currently developing the new TI Strategy 2020. Stakeholders and partners globally have been consulted and provided their ideas on how TI can make the biggest difference in stopping corruption. While the theory of change for our PPA has remained the same, we are currently consolidating the consultations to see how we can make our global influence and voice even stronger.

Monitoring progress throughout the review period
The secretariat’s monitoring, evaluation and learning system involves quarterly reporting against the annual implementation plan. The quarterly reviews mainstream data collection in all departments and allow us to systematically assess the progress made. The findings are analysed and shared in quarterly summary reports to inform strategic decisions and improve programme design and implementation. Data collection is now mainstreamed in a systematised way and allows us to use the data for learning and to increase our accountability. We now maintain an impact log with evidence of our impact at policy and legislative level and at behaviour level. This data allows us to assess our performance and impact and, importantly, it has become the central information node of other units, namely our communications, policy and advocacy, and resources departments.

In 2014, the secretariat further developed and adopted a new approach to monitoring impact of anti-corruption work. This approach will be woven into the future Strategy 2020 and will be crucial to monitor its progress; it aims to build a more robust body of evidence regarding what works in stopping corruption, why and how it works. It is designed to capture the different change processes that the TI Movement is contributing to and achieving and it will also help us to plan stronger programmes and improve the allocation of resources from ineffective to effective initiatives. The approach consists of two complementary elements: a matrix to support impact-oriented monitoring in projects and programmes; and a limited number of impact assessments that provide in-depth insights on relevant topics and trends identified through the ongoing monitoring. Additionally, we conceptualised the secretariat’s first impact assessment, which will focus on women empowerment initiatives.

Following up on last year’s report, where we mentioned that seven chapters in the Americas conducted community-level participatory research, using beneficiaries’ feedback to shape advocacy recommendations, several successes came out of this project. For example, in September 2013, more than 12,000 mothers, beneficiaries of the Familias en Acción programme in Colombia, attended first social accountability event in Soacha, Bogotá. Following the recommendations of our chapter, local representatives of the programme publicly disclosed the budget and explained how to receive the transfers. The Local Government of Soacha, along with other four mid-size municipalities in Colombia, is now promoting similar public events to ensure higher levels of transparency and accountability in the programme.

DFID Response: / TI-S has demonstrated a commitment to monitoring and evaluation in this section of the report, but it would have been good to see examples of how TI-S has used the information generated. For example, what was the outcome of the evaluation on the Asia Pacific Regional Programme and what did TI-S do with the learning from this? / We note that TI-S has considered their ToC and that no changes have been made. / DFID looks forward to the publication of the new TI Strategy 2020 and appreciated being given the opportunity to comment on the draft version earlier this year. / DFID also notes that TI-S has further developed and adopted a new approach to monitoring the impact of its anti-corruption work. This sounds interesting and important and it's good to see that this approach will be used to monitor the progress of Strategy 2020. / Thank you for providing follow up information from last year's report on the community-level participatory research conducted by Chapters in the Americas, this was interesting and a good example of learning being used to ensure higher levels of transparency and accountability in similar public events.

I: DISABILITY (½ page)

Does your organisation consider disability in its policies and programmes:
If yes, please outline your approach.

Our support to victims and witnesses of corruption is based on the idea that people should have easy access to mechanisms to report corruption. Although we have not specifically targeted people with disabilities, many chapters have made efforts to reach out to vulnerable populations, and have opened various channels to increase accessibility (walk in centres, hotlines, SMS,  online platforms, community meetings).
Internally, the disability approach is embedded in the TI Secretariat’s gender and diversity policy. It highlights the principle of non-discrimination and equal treatment of every staff member, irrespective of gender or physical ability, and the secretariat’s commitment to promote diversity, both in the culture of the organization and in its management processes. The policy also applies to beneficiaries, and underlines that everyone should have equal access to TI-S’s programmes. It also takes into consideration the interaction between gender and disability.
Regarding human resources, German regulations require that 5-6% of employees must be people living with disability (PLWD). Any shortfall in this number requires organisations to contribute to a fund to support PLWD. We also implement other practices such as additional leave days and the provision of a suitable workplace.

DFID Response: / TI-S has provided an adequate baseline on disability however, we would suggest that TI-S moves beyond a minimum standard of non-discrimination to a consideration of how people with disabilities can be proactively included. / TI-S should consider how accessible their services are for people with varying communications needs. Is literature available in easy read, braille or audio formats. Does the website mean minimum accessibility standard for those using assistive technologies to access the internet (e.g. Jaws or Dragon text). / The statement assumes that equitable access is the product of non-discrimination. To achieve equitable outcomes Transparency International should consider what reasonable accommodations must be made on an anticipative basis to ensure people with disabilities can access services. They should also establish some kind of direct or proxy measurement system to monitor effective implementation. / We look forward to seeing more of TI-S’ progression in this area in future reporting.

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Transparency International (United Kingdom) Defence and Security Programme (TI-UK DSP)
Programme Value: £3,520,375 over 5 years		Review Date: 1 July 2015
Programme Code: 202505	Start Date: 1 April 2011	End Date: 31 March 2016

Summary of Programme Performance
Year	2011/12	2012/13	2013/14	2014/15
Programme Score	A+	A+	A+	A+
Risk Rating	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review
TI-UK DSP has had a strong year. In addition to either achieving or exceeding all milestones set for the 4 outcome indicators, the organisation is in a good position to achieve all PPA programme outcomes for December 2016. Its work and policy influence has achieved high profile media coverage. The DFID Secretary of State’s keynote speech delivered at the 2014 TI-UK Annual Lecture led to the establishment of a ‘Global Security’, policy working group which reflects the critical link between security, stability and corruption, and whose work will inform the 2016 UK-hosted Global Summit on Anti-Corruption. / Through TI-UK DSP engagement, 12 nations and a total of 18 international organisations to date have initiated counter-corruption initiatives for the defence sector; 30 major companies have improved their anti-corruption policies and systems; and 30 Civil Society Organisations (CSO) are showing enhanced capacity to work on reducing corruption in the defence sector. The organisation has also achieved deeper forms of anti-corruption engagement in a limited number of countries including Afghanistan and Ukraine. This deeper engagement includes the development of local policy and/or plans, organisational capacity, and regular, locally-delivered, training and educational programmes. TI-UK DSP also led the successful roll-out of its Companies Index (CI). Internally, TI-UK DSP managed a successful leadership transition and facilitated organisational growth through the development of a more robust management structure. / TI-UK DSP has learned about the utility of strategic funding, and PPA funding in particular, in promoting wider donor confidence and supporting innovation, risk-taking and organisational growth. It also continues to benefit from the support provided by ‘MEKANIC’, an in-house mechanism which supports the organisation’s ongoing monitoring, evaluation and learning. Based on the CI roll-out experience, and the regional consensus and ‘peer review’ process that this generated, it has also acknowledged the value of taking a region-by-region approach to the launch of future indices. The organisation has also realised the limitations of the current organisational structure and has developed a new structure which better aligns with the organisation’s strategic direction and growth. Furthermore, it has recognised the importance of ensuring that organisational growth plans are supported by effective personal development programmes for the majority of TI-UK DSP’s relatively young staff. Lastly, the organisation has acknowledged the greater impact achieved by the dissemination of shorter policy documents and practical tools.

Summary of recommendations for the next year
TI-UK DSP should move forward with plans to develop a new organisational strategy supporting both organisational growth and the development of its staff, systems and structures. Efforts to maintain and develop key programmes like the CI and GI will require further conceptual development of these initiatives as well as significant fund-raising efforts. The development of new strategic plans for the organisation must also be underpinned by the development of more meaningful and sophisticated performance and capacity management systems for both the organisation and its in-country partners.

A. Introduction and Context
DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme
TI-UK DSP works to reduce corruption in defence and security worldwide. It engages with governments, armed forces, security forces, defence companies, international organisations, civil society and others to advance this goal. In enabling this change, the organisation provides new tools, practical reforms, benchmarks and research. The organisation’s two flagship projects – the GI and the CI – enable robust engagement with a wide range of governments and companies and put pressure on these organisations to initiate reforms. / The intended outcome of TI-UK DSP’s PPA programme is that government defence establishments, defence companies, international organisations and civil society have enhanced knowledge of, and increased access to, the necessary practical tools to tackle corruption in defence and security. As such, the programme aligns with several of DFID’s and overall UK ODA objectives and is operational in most of DFID’s priority countries. It is in line with the suggested post-MDG Target (#16.5) on “Good Governance and Effective Institutions” and complements DFID’s work in fragile states. The programme is also aligned with the ICAI report on ‘DFID’s Approach to Anti-Corruption and its Impact on the Poor’ (October 2014).

## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment
TI-UK DSP is on its way to achieving the outcomes of the programme by the end of 2015/2016. All of the milestones set for the 4 outcome indicators have either been achieved or surpassed. As a result of engagement with TI-UK DSP, 12 nations as diverse as Afghanistan, Jordan, Lebanon and Ukraine have initiated new defence counter-corruption initiatives this year. For example, following a ‘Leadership Day’ workshop facilitated by DSP in Cote D’Ivoire, an anti-corruption action plan for the defence sector was drafted. In addition, as detailed in TI-UK DSP’s 2014/15 quarterly report, and corroborated by interviews with two industry leaders, 34 major defence companies (double of what was targeted) reformed their systems based on concrete suggestions emerging from both the CI and through engagement with TI-UK DSP. Some of these reforms included the introduction of new whistleblowing systems, and revising and publishing anti-corruption policies on company websites. Quarterly reports and MEKANIC summaries also detail a total of 30 CSOs reporting capability to tackle defence and security corruption. In this context, two of TI-UK DSP’s chapters jointly delivered Building Integrity training courses with core staff in both Serbia and Jordan. Examples include the development of ‘Obris’, a non-profit defence news and analysis website covering the Balkan countries. TI-UK DSP’s chapter in Czech Republic also used the CI to support their advocacy work. This resulted in the country’s main defence company, Tatra, committing to improve its CI score within one year and the Defence Minister publicly committing to putting pressure on the company to reform. Similar work is also taking place with TI-UK DSP chapters in Africa and the Middle East. / A total of 18 international organisations to date have also started defence integrity building initiatives. These initiatives include the EU’s European Defence and Security College new ‘Building Integrity’ training programme delivered jointly by TI-UK DSP and the UK Defence Academy.

Overall output score and description
The overall output score is A+. TI-UK DSP has exceeded almost every milestone set for each output indicator. The successful roll-out of the CI, and the robust engagement with a wide range of companies that this enabled, put immediate pressure on these organisations to initiate reforms. Efforts have also continued in support of the GI and an equally active level of engagement supporting anti-corruption initiatives with Governments. In addition, the fact that defence and security anti-corruption is a niche sector means that TI-UK DSP must continue to produce new tools and build the capacity of other CSOs and international organisations. Lastly, the organisation’s experienced and knowledgeable Senior Advisors have helped facilitate deeper engagement with several countries and defence and security companies.

Key Lessons
The following key lessons have emerged from the programme: / - Support for the development of evidence-based policy could benefit from empirical data maintained by TI-UK DSP. In this context, there is a need to ensure that central PPA funding outputs also support the work of in-country HMG representatives / - Strategic funding provides a good basis for organisational growth / - Effective organisational growth must be supported by the development of organisational strategy, structures and systems / - A sequential approach to the release of CI and GI data enables lessons to be learned in an ongoing way / - Anti-corruption plans and policies will only be effective if in-country advocacy capacity exists to sustain momentum / - Educational and training efforts to support anti-corruption initiatives are more effective if sustained by local capacity and if institutionalised as part of professional and personal development programmes. / - Effective approaches are required to measure, and support the promotion of, the outcomes and impacts of TI-UK DSP’s global anti-corruption initiatives

Key actions
During FY 2015/16, TI-UK DSP should: / -publish a new organisational strategic plan (by the beginning of the 3rd quarter FY 2015/2016) / -ensure that current monitoring, evaluation and learning processes/mechanisms evolve to reflect the new strategic plan (by the end of the 3rd quarter FY 2015/2016) / -by the end of the second quarter, amend the existing PPA logframe to include effective impact, outcome and output indicators / -engage more meaningfully with the UK Defence Attaché programme (by end of 3rd quarter) / -develop initial relationships with currently ‘untapped’ donors, as well as two trust/foundation organisations with a interest in exploring the anti-corruption agenda (by end of 3rd quarter) / -invest in an electronic tracking software to better evaluate the impact of TI-DSP’s practical tools (by the end of the financial year) / - develop a concept paper which provides a framework for meaningful capacity development of local partners (by the end of the year) / -clarify how both the CI and GI will be funded and maintained in the future - define what the organisation means by ‘deeper engagement’ to support anti-corruption and what countries will benefit from this deeper engagement (by the end of the 3rd quarter)

Has the logframe been updated since the last review?
The logframe has been changed since the 2014/2015 Annual Review. Although these changes have not been substantial, TI-UK DSP was encouraged to provide more qualitative information to supporting its quantitative reporting.

C: DETAILED OUTPUT SCORING

Output Title	High level governmental workshops and events addressing Defence and Security Reform best practice and initiatives conducted worldwide, including in Southeast-Asia, Africa, and wherever in the world governments express an interest.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of overall TI-DSP engagements (invitations, meetings).	390 (20 engagements in year 1 lead to increased awareness of defence and security anti-corruption.)	438 (119 new engagements this year. e.g. speaking at a high level conference in Jordan and organising a Senior Leaders’ workshop in Ukraine)
Level of oversight of the ANSF post 2014.	TI-DSP engagement with Afghan civil society, the ANSF and others leads to concrete proposals for strengthened oversight of the ANSF.	Extensive engagements currently leading to a project that will provide concrete proposals for strong oversight mechanisms.

Key Points
119 global engagements took place this year. These engagements ranged from speaking at a high level conference in Jordan and organising a Senior Leaders’ workshop in Ukraine to launching TI-UK DSP’s report findings in the presence of senior decision makers in the U.S. / TI-UK DSP also published a report entitled ‘Corruption: lessons from the international mission in Afghanistan’. The report led to strengthened relations with local Afghan NGOs, informed TI’s global approach to Afghanistan and led Royal United Services Institute to hold a roundtable discussion on anti-corruption in both Afghanistan and Mali. TI-UK DSP also delivered a “Building Integrity” (BI) course to senior commanders in Kabul and has since been requested to deliver more BI courses in 2015/16. Building on these and prior engagements, DSP is currently developing a project in consultation with Afghan CSOs. The project will provide a robust evidence-base and a proposal for an anti-corruption action plan and an oversight mechanism for the security forces in Afghanistan. / TI-UK DSP’s longstanding relationship with NATO’s BI Programme continues. It is worth noting that work on gender and corruption (in defence and security specifically) has formed part of the NATO BI initiative and that TI-UK DSP has briefed NATO regarding gender and corruption more generally. / TI-UK DSP enjoys various levels of engagement across policy development, organisational/institutional capacity development, advocacy and training and education. Requests for deeper engagement in some countries has posed questions concerning how the organisation strikes a balance between the ‘breadth’ and ‘depth’ of its future global engagements.

Summary of responses to issues raised in previous annual reviews (where relevant)
In the 2012/13 Annual Review DFID feedback letter, TI-UK DSP was encouraged to present more qualitative information supporting output 1 indicators. As a result of this feedback, information is provided which explains both the milestone and detail on the organisation’s engagements.

Recommendations
By the end of the third quarter, TI-UK DSP should clarify the level of ‘breadth’ and ‘depth’ that will shape its future national engagements. In this context, the organisation should be clear about where it will pursue a deeper level of engagement and why. / By the end of the year, TI-DSP should review its BI course delivery and explore ways in which the course could support ‘generational change’, perhaps in the form of ‘tiered modules’ and/or accreditation. It should also continue to support advocacy for anti-corruption in the defence and security sector by provide speakers for, and influencing, workshops and conferences which address institutional governance. In this context, and because TI-UK DSP has already exceeded the output 1 target set for 2015/2016, it is recommended that the target for the first indicator is revised upwards by 38 to 458.

Output Title	Defence industry and governments worldwide influenced to conduct arms trade and transfers more responsibly, with improved controls against corruption, industry standards and codes of conduct.
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Cumulative number and description of states TI-DSP engages (including via regional organisations) to convince them to implement the anti-corruption mechanisms in the UNATT.	10 (i.e., 10 states are engaged by TI-DSP to base their anti-corruption implementation plans on the strong ATT anti-corruption measures.)	12
Number of regional and national defence industry umbrella organisations TI-DSP works with.	11 (i.e., 4 new organisations work with TI-DSP to address defence and security corruption.)	18

Key Points
This year TI-UK DSP engaged 12 states in the run-up to, and following, the EU-COARM meeting. These efforts were aimed at working towards an Arms Trade Treaty (ATT) that is a “floor, not a ceiling” and focused on states with concrete anti-corruption implementation plans. TI-UK DSP also received a grant from the Network for Social Change to measure ATT compliance on anti-corruption globally and to advocate for compliance alongside members of the Control Arms Coalition. As part of this project, TI-UK DSP is measuring potential good practice through a specific updated question in the 2015 GI. The organisation is also an expert member advising the “ATT Monitor”; a global measurement tool run by Control Arms. / TI-UK DSP worked with 18 regional and national defence industry associations this year. This included consulting support to the Swedish Security and Defence Industry Association (SOFF) on how to upgrade its anti-corruption work, and jointly launching the CI with the Federation of German Security and Defence Industries (BDSV). Meetings held to discuss the future of the CI resulted in a number of stakeholders expressing an interest in either funding, or contributing to the future funding, of the CI’s ongoing development. / TI-UK DSP also took part in and presented at various forums (e.g. the annual Munich Security Conference, the annual ADS Business Ethics Forum, the Defence Integrity Initiative (DII) Ethics Forum, the IFBEC 5th Annual Conference and the European Club for Countertrade and Offset’s (ECCO) symposium). Some of these fora yielded encouraging results. For example, following the ECCO symposium, TI-UK DSP was invited to teach a module on ‘offsets corruption risk’ at the ESSEC Business School Advanced Management Program - Countertrade and Offset Academy in Paris.

Summary of responses to issues raised in previous annual reviews (where relevant)
In the 2012/13 DFID PPA Annual Review feedback letter, TI-UK DSP was encouraged to include qualitative information on this output. As a result, information is included which explains the milestones and well as detail on the organisation’s engagements.

Recommendations
By the end of the second quarter, TI-UK DSP should develop a concept paper outlining a proposed way forward for the future maintenance of the CI. By the end of the third quarter, the organisation should engage with defence industry to discuss ways in which the CI could be funded in the future (i.e. perhaps through corporate sponsorship and/or membership). It should continue also to promote its work through existing networks, fora, academic and industry conferences. / As this milestone, and the target set for the first and second indicators respectively, have already been exceeded, it is recommended that the targets for both indicators are changed to 17 (indicator 1) and 22 (indicator 2).

Output Title	Produce practical tools that can be directly applied by civil society, governments, and the defence industry so that they are better able to address defence and security corruption and have increased capacity to do so.
Output number per LF		3	Output Score	A++
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Cumulative number of new practical tools developed by TI-DSP to address defence and security corruption.	22 (i.e., 8 new tools are developed by TI-DSP to help civil society / governments / industry to address defence and security corruption.)	25
Number of experts trained in defence and security anti-corruption available to civil society, industry, and governments.	35 (i.e., 5 new experts whose capability to tackle defence and security corruption has been built by TI-DSP are available.)	55
Number of CSOs engaged by TI-DSP to build their capability in tackling defence and security corruption.	95 (i.e., 11 new CSOs are engaged by TI-DSP to build and/or improve their capability.)	161

Key Points
Output 3 indicators have all been exceeded this year, some significantly so. DSP has produced eleven practical and innovative tools including the handbook entitled ‘Corruption Threats & International Missions’, which addresses corruption risks during military interventions. The Handbook was used to train Kenyan soldiers deploying to Somalia this year. Similarly, the report entitled ‘Advocating for Peace, Justice and Security in Honduras’ (published in cooperation with Columbia University) presents a framework for assessing the effectiveness of CSOs in addressing corruption in the security sector. This framework has been used by partner organisations in Latin America to inform approaches supporting oversight of the security sector. / DSP trained 12 former senior military officers to be consultants and trainers for the Programme and to support the delivery of the practical tools. These consultants subsequently provided training to armed forces and CSOs in Afghanistan, Cote D’Ivoire, Ethiopia, Jordan, South Africa, and elsewhere. In addition, the organisation hosted 8 mid to senior military and civilian leaders from Ukraine, Georgia, Armenia and Afghanistan in its offices in London. The secondees were mentored to develop tailored training materials for training establishments in their countries. / 73 TI national chapters have become more involved in the research and verification process for the GI 2015 (16 are new to the GI process). This process will enhance their technical understanding of corruption risks in defence and enable them to work on this topic within their countries. This assumption is based on TI-UK DSP’s experience in 2013 when the first round of the GI was officially launched. TI chapters in Armenia, Yemen and OPT for example started to lead on defence and security anti-corruption work following involvement in the GI process. In addition, training has also been provided to TI National Chapters in Jordan, Ethiopia, New Zealand and South Africa as part of broader capacity building work this past year.

Summary of responses to issues raised in previous annual reviews:
In the 2012/13 DFID PPA Annual Report feedback letter, TI-UK DSP was encouraged to provide an appropriate level of detail for the score that it suggested for this output. As a result, greater detail has been provided on each of the output indicators.

  Recommendations
By the end of 2015, TI-UK DSP should develop a framework which supports meaningful and ongoing capacity development of national chapters and other key in-country partners. This will ensure that secondment, training and advocacy efforts supporting local partners are in line with the objectives set out in a capacity-building framework for each individual partner organisation. TI-UK DSP should continue to focus on the production of practical tools and short publications (versus longer peer-reviewed research papers) and, by the end of FY 2015/16, aim to produce 5 additional practical tools. Where appropriate, translated versions of these tools should be provided. / As the organisation has substantially exceeded all targets for this output, it is recommended that output 3 indicators are revised upwards to 33, 60 and 166 respectively.

Output Title	Policy makers and international organisations worldwide (including UN, AU, African Development Bank, World Bank, EU, and NATO) influenced to address the danger of defence and security corruption as a prominent issue on their agenda.
Output number per LF		4	Output Score	A++
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of international organisations TI-DSP is actively working with to convince them to initiate defence integrity building or countercorruption initiatives.	17 (i.e., 4 new organisations in 2015 are engaged by TI-DSP to convince them to initiate defence integrity building or countercorruption initiatives)	24
Number of high-level decision makers in international organisations TI-DSP is engaged with who acknowledge the importance of tackling defence/security corruption.	70 (i.e., 15 new high-level decision-makers are engaged by TI-DSP so that they acknowledge the importance of tackling defence and security corruption.)	76

Key Points
This year, TI-UK DSP engaged 7 international organisations. These included United Nations Development Programme (UNDP) in Tunisia, Southern African Development Community (SADC) in Botswana, European External Actions Service (EEAS) in Brussels, European Defence and Security College in Ireland, African Union, Challenges Forum in Beijing, and the EU Military Staff. Some of these engagements yielded encouraging results. For example, the EU EEAS’ European Defence and Security College (EDSC) organised a ‘Building Integrity’ training programme and invited TI-UK DSP and the UK Defence Academy to deliver to 11 international participants (including NATO) preparing to deploy to crisis operations. Feedback from participants was positive with some describing the programme as ‘an eye opener’. / 21 high-level decision makers in international organisations that TI-UK DSP is engaged with have acknowledged the importance of tackling defence and security corruption this year. Examples include the Director for Security Policy and Conflict Prevention at the European External Action Service and the Director General and Chief of Staff of the European Union Military Staff. Acknowledgements of many of these stakeholders were in the context of feeding into DSP’s programmes and tools/publications, such as the most recent ‘Corruption: lessons from the international mission in Afghanistan’. These announcements are important first steps, which TI-UK intends to build on to encourage the design of further programmes and initiatives.

Summary of responses to issues raised in previous annual reviews:
DFID’s 2012/13 Annual Review feedback letter encouraged TI-UK DSP to present more qualitative information on this output. As a result, information is presented which explains the milestones and some detail on the organisation’s achievements.

Recommendations
Through the existing DFID Working Group on Global Security, TI-UK DSP should draw on the knowledge of HMG policymakers to learn about important events and policy iniatiatives of regional and international organisations to which its work could contribute. / By the end of FY 2015/16, TI-UK DSP should invest in some digital communications software (such as VOCUS) to more effectively track the impact of its advocacy efforts. / Because TI-UK DSP has exceeded both targets for this indicator, it is recommended that the new targets for both indicators are revised upwards to 27 (indicator 1) and 81 (indicator 2).

## D: VALUE FOR MONEY &FINANCIAL PERFORMANCE
Date of last narrative financial report
Date of last audited annual statement

Key cost drivers and performance
TI-UK DSP continues to be committed to Value for Money. The key cost drivers remain (a) travels, (b) staff salary (c) senior advisors, and (d) office space and printing. The organisation has been successful at keeping costs low with optimal results. It continues to apply the same policies and procedures supporting VfM which, under ‘economy’, ‘efficiency’ and ‘effectiveness’, were described in a 2012 CHASE independent evaluation on VfM as ‘excellent’. / Staff salary: DSP has 16 full-time staff. In an effort to keep costs down, salaries are kept at median rates. There is a good gender balance across the staff, with the current Director also being female. The organisation has also augmented its staff with short term staff this year, including secondees from governments (typically two at any one time), and by engaging research students who are keen to do their thesis or dissertation on a subject that is relevant to TI-UK DSP. / Senior advisors: One of TI-UK DSP’s approaches to staff development is to pair a young professional with a highly experienced senior person such as former Ambassadors, Permanent Secretaries, and Senior Defence Leaders in each area of its work. This approach would be prohibitively expensive if TI-UK DSP were to pay anywhere near market rates, which range from £1000 per day for public sector work to £2000 for private sector work. This also provides valuable training and mentoring which would otherwise be very expensive. TI-UK DSP’s rate continues to be approximately £250 per day. Both Senior Advisers and full-staff staff are encouraged to travel at home and abroad with an appropriate number and selection of publications which, at various meetings, conferences and working group discussions, helps maximise the impact of their work. / Travel: Work on anti-corruption activities requires significant face-to-face contact. DSP has continued to rely on budget airlines, programmed travel during the less expensive times, and searched for the best possible hotel deals. Records also show evidence of TI-UK DSP staff travelling to multiple locations to synergise across a number of in-country engagements (e.g. travelling to Uganda and Ethiopia following the completion of work in Kenya). It also uses local chapters and partners to provide administrative, financial, and logistical support in-country. This reduces preparatory time, reduces costs and results in efficiencies, ensuring that the time spent by experts on the ground is used wisely. Partners are also encouraged to lead on the processing of feedback on training and to provide follow-up reports on training requirements, or the need for revised approaches and curricula. The contribution made by local partners also supports immediate follow-up with in-country TI-UK DSP stakeholders. This is particularly important when multi-country trips are taken by staff. / Office space and printing: DSP continued tracking the unit printing costs this year, and getting quotes for bulk printing. This has enabled a significant reduction (close to 25%) of costs from previous years. TI-UK DSP is based at Community Action Network (CAN) Mezzanine which solely offers office spaces for charities and at reduced rates. The use of existing (and leftover) training material which was used again for similar training programmes also contributed to reduced printing costs.

VfM performance compared to the original VfM proposition in the business case
TI-UK DSP’s commitment to value for money supports its VfM proposition in the original business case, which has been sustained throughout the PPA partnership period. It has continued to apply ongoing scrutiny to its VfM procedures and, where possible, has ‘scaled-up’ these efforts in view of new products, services and policy communities. The organisation defines value for money as ‘ensuring that maximum quality outcome is achieved for every resource spent’. It includes the 3 Es of economy, effectiveness and efficiency in this definition. In each strategic planning meeting (board meetings, MEKANIC, management meetings, etc.) TI-UK DSP always ensures that two central themes are discussed by way of incorporating VfM into our planning. These themes include: 1) what the organisation is learning about which interventions/approaches are effective and 2) how it might implement these interventions in an efficient and economical way.

Assessment of whether the programme continues to represent value for money
The programme continues to represent strong value for money. As outlined above, the programme is both economical in terms of the cost of key inputs such as office space and printing are adequately controlled and minimised. The programme is also efficient as the cost for hiring and retaining the high quality staff and senior advisors responsible for converting inputs into outputs is managed effectively. Lastly, based on the way in which TI-UK DSP innovates, and takes risks in order to reach its key objectives, the programme is effective. As reducing corruption in defence and security is ‘uncharted territory’, the organisation’s approach is to test several approaches simultaneously, rapidly discarding the less optimal approaches and scaling up the most optimal. The PPA structure enables the freedom to take this experimental approach. The PPA funding also communicates an element of confidence for other donors considering providing TI-UK DSP with strategic or programme/project funding.

Quality of financial management
TI-UK has a robust financial management system. Detailed budgets and business plans are prepared annually. Project expenditures are then monitored on a monthly basis by project managers and any variances are carefully reviewed and investigated. The organisation has not yet experienced an overspend on the the PPA or any other grant. All financial and narrative reporting requirments of TI-UK DSP’s funding partners are adhered to. It is audited on an annual basis, and all audit recommendations have been, and will continue to be, implemented. All annual financial and audit reports can be found on the TI UK website.

E: RISK
Overall risk rating
Low	Medium	High
	Meduim

Overview of programme risk
For this programme, risks include (1) DSP chooses countries where corruption is so deeply entrenched that it becomes difficult to make visible progress (2) based on the number of countries that TI-UK DSP could engage in, and the high number of countries and companies involved in both the GI and CI, the organisation spreads itself too thinly (3) a recent and significant growth in business activity cannot be supported by current organisational policy and structures, and (4) engagement in (post) conflict states such as Afghanistan or DRC pose a significant risk to the lives of team members. / These risks are mitigated through (1) enhanced research and analysis capacity which, together with the support of senior advisers, supports the thorough evaluation of target countries before planning any intervention (2) being strategic about where the organisation engages and having a future commitment to clarifying how TI-UK DSP should engage more ‘deeply’ with a limited number of countries; in addition, further conceptual clarity on how flagship products, such as the CI and GI, will be supported in the future will also mitigate against the risk of being spread too thinly as a result of two major programme commitments (3) by investing in a more robust management structure, and by being committed to the development of a new strategic plan in 2015, the organisation will develop appropriate policies, structures and systems to support organisational growth (4) travelling as safely as possible, e.g. with NATO / the UK military in Afghanistan, having adequate travel insurances and working closely with those on the ground where TI-UK DSP intervenes. DSP has also introduced an improved travel risk assessment system and requires staff travelling to higher risk regions to undertake hostile environment training.

Outstanding actions from risk assessment
TI-UK DSP has an organisation-wide Risk Register that is regularly reviewed and updated by the senior management team. Strategic risks are reviewed by the Board of Trustees, and further scrutinised in detail by the Finance and Audit committee on a quarterly basis. There are currently no outstanding actions. In April 2014, the organisation completed and submitted the Overseas Security and Justice Assistance assessment form, which indicates that the programme carries minimal risk of spending DFID funds in activities or interactions with actors that could raise human rights concerns. Whilst potential human rights abuses in TI-UK DSP’s countries of engagement have been identified, the organisation mitigates against these risks by following a general ‘TI approach to human rights risk’ procedure and good practice. The risk of human rights abuse is also mitigated through the due diligence efforts which are supported by local chapters and in-country partner organisations.

F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe
TI-UK DSP is currently ahead of schedule in delivering its set targets. Two of the targets for 2015/2016 were already met by the end of FY 2014/2015 and DSP is well on its way to meeting the targets for the rest of the indicators by 2015/2016. Without requesting additional funding, this Annual Review recommends that all but one of the agreed upon targets for the end of 2015/2016 are revised upwards (with future reporting also focussing on qualitative as well as quantitative aspects). As a result of this recommendation, TI-UK DSP is set to deliver more than what was agreed upon for the same amount of money and time.

Performance of partnership (s)
The majority of TI-UK DSP’s support to capacity-building, research, policy development and international influence is based on strong partnerships with both government and non-governmental organisations. However, the organisation does not provide financial support to any of its partners and is totally independent in how it manages its day-to-day operations. TI-UK DSP collects feedback from its partners and, through monitoring, review and learning mechanisms such as MEKANIC, involves partners in internal strategic planning. For example, TI-UK DSP has developed excellent partnerships with the Centre for Integrity in the Defence Sector (CIDS) in Norway and with the UK Defence Academy. It has jointly delivered Building Integrity (BI) training in a wide range of countries with them this year. Similarly, TI-UK DSP partners with international and regional organisations such as the UN, NATO, and the African Union. The benefits of this partnership include achieving goals through support to strategic partner organisations, knowledge transfer and sustainability. Whereas TI-UK DSP also enjoys a good relationship with DFID at the head office level, a limited number of in-country DFID staff appear to be less aware of its programmes. Closer interaction with in-country UK Defence Attachés, and the London-based Defence Attachés training programme, could facilitate wider cross-HMG knowledge of TI-UK DSP’s global work.

Asset monitoring and control
TI-UK manages assets through a system of asset monitoring and control. This responsibility lies with the department led by TI-UK’s Finance and Resources Director. The organisation has a Fixed Assets Register that is updated annually. Regular and on-the-spot asset checks and controls are undertaken by TI-UK DSP’s Office Administrator. The system is revised and updated regularly to ensure that it follows best practice in asset monitoring and control.

G: CONDITIONALITY
Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION
Evidence and evaluation
TI-UK DSP's ability to stimulate anti-corruption reforms depends on it effective, efficient and consistent delivery of programme results. For this reason, the organisation places significant emphasis on monitoring, evaluation and learning (MEL). As part of the 2015 change in leadership, an extensive review was initiated. This exercise involved the review of key internal documents and consultation with a range of organisational stakeholders. The review is now in its final stages. Findings from the review will impact on the theory of change of TI-UK DSP as a whole, how it is structured, and where/how the organisation works. / TI-UK DSP was also one of the organisations that was chosen to participate in the DFID fund-level evaluation this year. As such, Coffey undertook an evaluation of its work and, within the context of wider strategic discussions, TI-UK DSP’s management team is now deliberating on how to implement Coffey’s recommendations. Following the review, Coffey staff notified TI-UK DSP and stated that their own organisation was now seeking to learn from TI-UK DSP and adopt a MEKANIC-like process to support their own advocacy projects. / TI-UK DSP has had 4 ‘MEKANIC’ sessions this past year. MEKANIC meetings are all-day ‘learning’ events run once each quarter and which bring together key stakeholders who play an important role in the defence and security sector. The acronym MEKANIC stands for: Monitoring, Evaluation, Knowledge – Understanding and sense-making, Affirmation, Building Effective Networks, Influencing and Theory of Change. MEKANIC has been widely recognised as good practice within the Monitoring, Evaluation and Learning community. For example, DSP was asked to prepare a briefing note for INTRAC’s website in order to enable other civil society organisations to learn from it. / Finally, TI-UK DSP has also conducted external research into defence and security reforms in both Poland (deemed a powerful example by states in transition globally) and Honduras. These initiatives form part of TI-UK DSP’s ‘learning’ publication series that inform its strategy and theory of change, and help others (i.e. governments and civil society organisations) to learn from them.

Monitoring progress throughout the review period
TI-UK DSP collects data for monitoring and review purposes on a quarterly basis. Output and outcome indicators, as well as corresponding evidence, are assigned to project and programme leads responsible for documenting progress. The project and programme leads report to the MEL officer every quarter. The MEL officer then collates these notes and produces a quarterly monitoring report (also informed by the DFID CHASE PPA) that is shared with Management and the TI-UK DSP Board and which also forms part of the pre-reading material for each MEKANIC meeting. The data and analysis supporting MEL is fed both internally and externally through 3 different documents which are tailored for the requirements of each recipient group. These reports include a longer more detailed version of the quarterly report for internal management and information-sharing purposes; a shorter version of the report for meetings with both Board members and project/programme sponsors; and another shorter version of the report which serves as pre-reading for MEKANIC meetings. The cumulative approach taken to the development of quarterly reports ensures that updated and peer-reviewed (through the MEKANIC process) data is prepared for the timely publication of TI-UK DSP’s annual reports. / The organisation also uses a series of follow-up forms/questionnaires that are distributed to and completed by course and secondment participants. These forms were used in a range of countries this year including Jordan, Afghanistan and Ethiopia. Feedback received has been carefully reviewed and, where required and appropriate, course materials and teaching methods have been updated throughout the course of the year. Exit interviews are also used for both secondees and research interns.

I: DISABILITY
Does your organisation consider disability in its policies and programmes: Y/N. If yes, please outline your approach

Yes. TI-UK DSP is an equal opportunity employer. Its ‘Governance and Procedures Manual’ stipulates that the organisation does not discriminate based on anything other than merit in employment, including disability. In addition, the manual states that TI-UK DSP staff will treat each other and those that they work with respectfully and with due consideration for such things as disability. Equality is a key value that TI-UK DSP cultivates and abides by. In terms of programme activities, DSP attempts to mainstream disability as much as possible, despite some anticipated challenges of working at the global policy level.