Annual Review

Title: Responding to the Nutrition Crisis in Yemen (R2N)
Programme Value £ (full life): £96.5 million		Review Date: September 2019
Programme Code: 3000525	Start Date: October 2018	End Date: September 2021

Summary of Programme Performance
Year	2019	2020	2021
Programme Score	B
Risk Rating	Severe

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/36022579.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/49011936.xlsx

A. Summary and Overview (1-2 pages)

Description of programme
Why Nutrition in Yemen? / Nearly 80% of the population – 24 million people[1] – require some form of humanitarian assistance and protection. / Malnutrition leaves individuals more vulnerable to health risks, but only half of Yemen’s health facilities are functioning and 17.8 million people, of whom 50% are children, lack access to clean water and sanitation. / At least 1.8 million children and 1.1 million pregnant or lactating women are acutely malnourished.[2]
[1] https://reliefweb.int/sites/reliefweb.int/files/resources/2019_Yemen_HNO_FINAL.pdf
[2] https://reliefweb.int/sites/reliefweb.int/files/resources/20190402_Yemen_HNO_2019_Summary_V1.pdf, Page 4

As part of the wider UK Government objective to improve nutritional outcomes and support health services for women and children in Yemen, DFID is providing £96.5 million over 3 years to UNICEF and research initiatives. The programme is built around a life-cycle approach that aims to address the immediate and underlying causes of undernutrition. These include addressing malnutrition, health, water and sanitation needs, while also supporting technical analysis and evidence to inform the humanitarian response in Yemen.
DFID investments have been structured across three areas.
Output 1: Immediate Actions - Critical Nutrition, Health, Water, Sanitation and Hygiene service delivery – provide lifesaving, improved quality nutrition, health and wash services for affected populations, complemented by a focus on protection for the most vulnerable.
Output 2: Remedial Actions - System strengthening and risk management – maintain and strengthen systems delivering nutrition, health and water and sanitation services at a sub-national level. Improve efficiency and effectiveness of health risk management through improved planning and financing.
Output 3: Increase contextual understanding - Knowledge and evidence generation – address the information and data gaps that exist in Yemen by improving the knowledge and evidence base for the context and supporting analytical products to improve decision making.

Summary supporting narrative for the overall score in this review
Achievements
In the last year, UNICEF’s achievements include (all attributable to DFID funding unless recorded as otherwise):
- Provided over 3 million doses of critical vaccines (Polio, Measles, Rubella (MR) and Penta[3]) between October 2018 and June 2019, and logistic support (including cold chain) for distribution of vaccinations;
  [3] The Penta vaccine combines 5 critical vaccines in one diphtheria, tetanus, pertussis (whooping cough), hepatitis B and Haemophilus influenzae
- Delivered 6 mass immunisation campaigns (MR, polio, and 4 cholera), reaching more than 15 million people (10% attributable to DFID);
- Screened 3 million children under 5 years for malnutrition (20% attributable to DFID);
- Supported 449,680 pregnant and lactating women with nutrition counselling and education;
- Rehabilitated rural water provision and built urban water provision benefiting more than 170,000 people
Overall Score – B
A majority of indicators in Output 1, the main lifesaving response elements, were met, scoring an A, with a weighting of 40%. However, Outputs 2 and 3 fell short of expectations, both scoring a B with a weighting of 30% each. The review team recognise the ambition behind the programme and the challenges of operating in Yemen and these were factored into the scoring.
The Overall risk rating has increased from Major to Severe due to concerns around data quality and the efficacy of counter fraud systems.

B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	- Provide and maintain life-saving emergency nutrition, health and WASH services for affected populations with a focus on the most vulnerable / - Mainstream gender, disability, and protection-sensitive programming
Output number per LF		1.1 and 1.2	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	No

Indicator(s)		Baseline	Targets (June 2019)	Progress (June 2019)	Score and attribution to DFID
Output 1.1 - Provide and maintain life-saving emergency nutrition, health and WASH services for affected populations with a focus on the most vulnerable
Provision of health services for children (health facilities, outreach services, mobile health teams, vaccinations)	Number of [*consultations of] children Under 5 accessing primary health care through health facilities, outreach services, and mobile health teams	1,090,559	1,145,087	1,392,910 / (DFID – 65% 905,391)	Exceeded
	Percentage of targeted age group vaccinated during outbreak response campaigns.[4]
	Measles and Rubella campaign (February 2019)	Target: 95% / Achieved: 93%			Unmet / (DFID – 10%)
	Polio campaign (November 2018)	Target: 80-85% / Achieved 85% (5,535,816 children under 5)			Met / (DFID – 10%)
	Two Oral Cholera Vaccination (OCV) subnational campaigns (October 2018)	Target:50% coverage / Achieved 55% coverage 992,535 >1year			Met / (DFID – 10%)
	Two Oral Cholera Vaccination (OCV) (March and May 2019)	Target:50% coverage of 1,722,068 >1year, / Achieved: 91% or 1,567,082			Met / (DFID – 10%)
Critical reproductive health services available for women of reproductive age by skilled health personnel	Number of [consultations with] women of reproductive age receiving reproductive health services (including Antenatal (ANC), Skilled birth attendance (SBA), and Postnatal care (PNC)) from skilled health personnel (home and facilities)	559,909	587,904	953,096 / ANC1[5]: 619,183 / SBA: 164,335 women / PNC1: 169,578 women	Exceeded / (DFID – 40% 323,495)
Critical malnutrition screening and enrolment in SAM services available for children under 5 in health facilities and mobile clinics	Number [of screenings] for under 5 children for Malnutrition at health facilities and community levels	-	2,300,000	3,011,909	131% Exceeded / (DFID – 20 % 602,382) / [of screenings]
	Number of U5 children with Severe Acute Malnutrition (SAM) enrolled in management programs in health facilities and mobile clinics	-	5,000	5,000	Met
Quality nutrition services maintained in line with Sphere standard cure, death and defaulter rate	% U5 children with SAM discharged as cured ('cure rate')	81%	>75%	85.5%	Met
	% U5 children with SAM discharged as died ('death rate')	0.2%	<1%	0.3%	Met
	% U5 children with SAM who default ('defaulter rate')	16.3%	<15%	11.5%	Met
[4] https://apps.who.int/iris/bitstream/handle/10665/255575/WHO-IVB-17.03-eng.pdf?sequence=1
[5] ANC1 /PNC1 = number women with 1 ANC or PNC

Preventative nutrition assistance provided to pregnant and lactating women, children under 5 and school age 10 - 19 years	Percentage of pregnant and lactating women received counselling and education on infant and young child feeding (IYCF)	65%	70%	216% / 1,798,725	Exceeded / (DFID – 25% / 449,680)
	# of under two years children received growth monitoring and promotion	52,000	100,000	336,125	Exceeded / (DFID – 50% 168,063)
Water and sanitation services available in urban and rural areas and targeted for particular vulnerable groups	Number of people with access to improved rural water supply through rehabilitation of non-functional systems	146,391	148,391	173,953	117% Exceeded / (DFID – 100%)
	Number of people living in high-priority districts most at risk of famine/ malnutrition who have access to emergency WASH	-	50,000	631,061	Exceeded / (DFID – 50% - 315,531)
	Number of conflict-affected people with improved service delivery for urban water & environmental sanitation services	973,400	1,003,400	1,046,081	104% Met / (DFID – 100%)
	Number of IDPs and people living in host communities with access to emergency WASH (clean water, basic sanitation and hygiene materials)	668,154	668,154	390,210	Unmet / (DFID – 100%)

Output 1.2 - Mainstream gender, disability, and protection-sensitive programming
Integrated, protection sensitive services offered for children and people with disabilities	# District Hospitals / Health Centres offering Integrated Health and Nutrition Service Package	0	20	33	Exceeded / 33 hospitals and HCs offer the full package of: TFC, OTP, EPI, MNH, and IMCI.
	Percentage of health facilities that have an integrated management program for both severe and moderate acute malnutrition.	55%	70%	62%	Unmet / (DFID – 20%)
	Number of Therapeutic Feeding Centres (TFCs) and Outpatient Therapeutic Programme (OTPs) with functional child-friendly spaces (offering ECD services)	0	120	13	Unmet / (DFID – 100%)
	% of targeted Health Facilities applying the SOPs for integration of social welfare and psychosocial support (PSS) services into health and nutrition services	17%	33%	34%	Met / (DFID – 100%)

Narrative for the score
Overall, expectations against this output were met. Across a range of indicators UNICEF met or exceeded targets with only a few exceptions. This is all the more important because this output represents the delivery of critical lifesaving services across nutrition, health and water, sanitation and hygiene (WASH).

Output 1.1 - Provide and maintain life-saving emergency nutrition, health and WASH services for affected populations with a focus on the most vulnerable
Critical health services available for children with access to primary health care
UNICEF exceeded its target for the number of primary health care consultations of children under 5, reaching an overall milestone of 1,392,910 consultations. UNICEF also provided supply and logistic support to healthcare at multiple levels including infant and paediatric intensive care services.
UNICEF used DFID funds to support 4 major vaccination campaigns to prevent measles, rubella, polio, and cholera. UNICEF supported logistics of cold chain equipment, trained 1,163 staff, and supported vaccine logistics management. For measles this has made a significant difference with a dramatic reduction in the number of suspected cases in 2019.
Critical reproductive health services available for women of reproductive age by skilled health personnel
UNICEF met the indicator milestone for reproductive health providing reproductive services. In Yemen, it is not possible to track individual women across services so the total achieved will have duplications of women accessing the different range of services (i.e. antenatal care and delivery etc). This indicator will need to change prior to the next review to ensure it is fit for purpose.
Critical malnutrition screening and Quality nutrition services provided in line with international quality standards
UNICEF exceeded their child malnutrition screening and met their target for child enrolment in SAM programmes. Screening is critical to identify cases of malnutrition and referring these children for treatment.
The quality of programmes at the national level are consistent with international standards. 86% of children under 5 with SAM who were enrolled in management programmes were discharged as cured, 0.3% died, and 11.5% defaulted (within SPHERE standards). While this is positive at the national level, there is still a need to focus on quality at a subnational level. A review of the nutrition data by district and governorate shows a huge variability in quality (eg: defaulter rates ranging between 23% - 50%).
Preventative nutrition assistance provided to pregnant and lactating women, children under 5 and school age 10 - 19 years
UNICEF doubled its target for providing counselling and education to 1,798,725 sessions for pregnant and lactating women, 449,680 (25%) attributed to DFID. UNICEF also reports providing 350,077 <2 years olds with growth monitoring and promotion. The overachieved progress was attributed to the scale up in the training of the Community Health Volunteers (CHVs) on the growth monitoring module.
There is a need to adjust how these indicators are recorded and interpreted to ensure it is clear the indicator is recording the sessions as it is not possible to know if some women might have attended more than one session.
The iron supplements indicator is unreported as UNICEF will not commence roll out (in 8 districts and 4 governorates in collaboration with the Government of Yemen) until September 2019 to align with the beginning of the school year.[6]
[6] UNICEF Report, page 8
Water and sanitation services available in urban and rural areas and targeted for particular vulnerable groups
Overall UNICEF met and exceeded its targets under this output with the exception of the delivery of services for IDPs. The exceeded indicators are partially explained by the uplift in funding DFID delivered to UNICEF (£18 million in early 2019) for the cholera outbreak. The unmet target was reported as likely to be back on track in the next reporting cycle.
Output 1.2 - Mainstream gender, disability, and protection-sensitive programming
Integrated, protection sensitive services offered for children and people with disabilities
The number of district hospitals or health centres offering integrated Health and Nutrition Service Packages was exceeded with 33 facilities providing services against a milestone of 20. There have however been some delays in the full implementation of Early Child Development. Early child development kits have been delivered to 80 Therapeutic Feeding Centres (TFCs) and Outpatient Therapeutic Programmes (OTPs) but only 13 TFCs are offering some Early Child Development (ECD) activities (specific play and learning areas). UNICEF recognise there is need for a more unified guideline for how to operate the child-friendly spaces and is working to develop a national guideline for ECD in nutrition programs to scale up this service in all TFCs.

Additionally, UNICEF are below the target for health facilities having an integrated management program for Severe Acute Malnutrition (SAM) and Moderate Acute Malnutrition (MAM) due to clear gaps in MAM services (which are provided by the World Food Programme). This indicator will be reviewed to enable it to better reflect UNICEF’s performance.

Of note is the progress made to enhance the integration of social welfare and psychosocial support. UNICEF have worked with the Ministry of Public Health and Population to developed Standard Operating Procedure that will support case management systems initially within 550 health facilities in 10 Governorates (November 2019 - September 2021).

Output Title	Remedial Actions - System strengthening and risk management / 2.1 - Nutrition, health and WASH services strengthened at a decentralised level through increased human resource capacity and improved planning, implementation and governance / 2.2 - Risk informed planning and financing are used to improve the efficiency and effectiveness of the response / 2.3 - Respond to psychosocial distress and other conflict-related impacts on the most vulnerable and conflict-affected children
Output number per LF		2	Output Score	B
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

	Indicator(s)	Baseline	Targets (June 2019)	Progress (June 2019)	Score and attribution to DFID
	Output 2.1 - Nutrition, health, water and sanitation systems strengthened with a focus on maintaining service provision and managing risk
Decentralised capacity strengthened human resource, improved planning, implementation and governance	Percentage of Rapid Response Teams with trained female to respond to cholera and emergencies	60%	60%	60%	Met / (DFID – 30%)
	Output 2.2 - Risk informed planning and financing are used to improve the efficiency and effectiveness of the response
Risk management is embedded within the overall response	UNICEF updates and shares its / 1. Risk analysis / 2. Preparedness and Contingency plans	-	-	Not shared	Unmet / No plans were shared - UNICEF shared some reporting of risks associated with specific DFID programme elements – vouchers and child protection case management
	Number of analysis carried out on how the response efficiency could be improved - i.e. a return on investment analysis of investments	1	1	1	Met
	Output 2.3 - Respond to psychosocial distress and other conflict-related impacts on the most vulnerable and conflict-affected children
Child protection and case management services are improved	Number of children and caregivers in conflict-affected areas benefiting from resilience building activities (psychosocial support in health facilities)	0	100,000	54,771	55% / Unmet / (DFID – 100%)
	Number of children referred from health facilities to critical child protection services (PSS, legal aid, etc)	0	500	595	Met / (DFID – 100%)

Narrative for the score

Overall delivery within this output was below expectations, partly due to its ambitious nature (particularly in regard to information sharing). The underachievement in the provision of psychosocial activities was only seen as being partially explained by contextual constraints and an area that UNICEF could have communicated more to DFID through the course of the reporting cycle.

Output 2.1 - Nutrition, health, water and sanitation systems strengthened with a focus on maintaining service provision and managing risk

Decentralised capacity strengthened human resource, improved planning, implementation and governance

Given the gender norms in Yemen, female participation in promoting hygiene and cholera awareness is critical to ensuring Rapid Response teams have the required access to households. UNICEF met their target of achieving 60% female representation within Rapid Response Teams (RRTs).

This was the only indicator in this category that had a milestone in Year 1. Other indicators in this category that will deliver results in future review periods include
- Percentage of mothers received a post-natal visit from a Community Health Worker
- Number of people with improved water services in urban and rural districts (Water Safety Planning)

Output 2.2 - Risk informed planning and financing are used to improve the efficiency and effectiveness of the response
Risk management is embedded within the overall response
This indicator aimed to the increase the level of transparency around risk management given the complexity of operating in Yemen. The purpose being two-fold: (1) to ensure that DFID remain aware how the DFID programme could be affected by the context; and (2) to better anticipate how DFID could flexibly support UNICEF to adapt to changing needs on the ground.
This is a new approach, unseen elsewhere, and it is therefore somewhat understandable that UNICEF did not fully meet expectations (eg: share the country level risk assessment and preparedness plans). UNICEF did share specific programme risks associated with DFID funding, in particular vouchers and child protection case management.
Further work is required between DFID and UNICEF to develop a shared understanding of this indicator, its purpose and how it will be used.
Return on investment
UNICEF carried out one of the first humanitarian-focused Return on Investment analyses (ROI). This showed efficiencies generated by a shift to solar power over a year compared to using diesel generators. At the end of 10 years the investment generates a $1.4m saving.

UNICEF have acknowledged the caution needed in interpreting findings as the investment in solar cannot be done without an investment in water resources management and governance. UNICEF have requested HQ support to conduct a comprehensive ROI exercise covering many systems across different governorates in Yemen.

Child protection and case management services are improved
UNICEF has improved integrating health and child protection services. In seeking to increase the availability of child protection and case management services, UNICEF provided training for 194 social workers have been embedded within 194 health facilities. Unfortunately, however only 55% of the expected number of children benefited from these services. UNICEF provided several reasons why this was the case:
1. Bank accounts were changed for some implementing partners which delayed disbursement of funds (Al-Amanah governorate).
2. Local authorities suspended all child protection related activities (Sada); or
3. Activities were affected by fighting in Hajjah, Saada and Al-Jawf.
4. Reports were not received at the time of the annual review.

It is expected that in the next reporting period that these milestones would be back on track.

Output Title	3. Improved knowledge and evidence base for better understanding of the context and analytical products necessary for decision making
Output number per LF		3	Output Score	B
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Baseline	Targets (June 2019)	Progress (June 2019)	Score and attribution to DFID
UNICEF shares on a monthly basis / 1. Results portal on a monthly basis for nutrition, health and wash / 2. Spend and forecast spend / 3. Fraud and safeguarding numbers - # cases reported (no details), # investigated (no details) and # legitimate cases (details provided) / 4. Access analysis	-	-	-	Partially met / UNICEF was able to share expenditure reports. However, was not able to report against results portal, fraud and safeguarding and access analysis. / UNICEF requested an adjustment to this indicator.

Narrative for the score

Milestones for much of this output were not as expected. UNICEF are currently planning technical surveys for rural and urban WASH projects, and an assessment on prevalence of psychosocial and mental health disorders. UNICEF are also planning reflections on several WASH aspects (RRT effectiveness study, ROI study for solar systems, and water basin management/water scarcity study for some key urban areas) and a child protection case management system review report.

The results portal is a new and innovative approach to sharing data and results proactively. This has been delayed. UNICEF have noted reporting difficulties due to Yemen’s difficult operating context (sharing data, access issues, and challenges around consolidating data from different sources), however this lack of data has made it challenging to review the outputs of the programme. From January 2020, UNICEF expect the results portal to be made available on a quarterly basis.

At the start of the programme it was assessed that residual fraud risk would remain “major” due to the large number of downstream partners and the financial pressure on health workers (who benefit through this programme from small incentive payments for delivering certain health services) due to the non-payment of their salaries by the relevant authorities. It was therefore agreed to include an indicator on fraud reporting in the logframe. DFID made repeated requests for information against this indicator and ultimately was told that no fraud had been detected. This seems unlikely in the Yemen context. There was an equivalent lack of reporting on safeguarding. DFID requires a higher level of engagement from UNICEF on this issue and is extremely concerned by performance to date.

DFID shared cholera risk modelling and Met Office data to support cholera activities. It was reported that the model was used to plan preventive measures during Ramadhan, and UNICEF believes this prevented the spike in cholera originally predicted.

Lessons identified this year, and recommendations for the year ahead from all outputs
The following recommendations are made to improve clarity and transparency.
1. Simplification of the Logframe - January 2020. - UNICEF and DFID to agree an updated logframe, to include only critical indicators necessary to assess the output / outcome. Where there has been an underachievement or overachievement, all targets will be adjusted for 2019/20 to better reflect progress against indicators:
  1. Milestones and targets should be adapted to reflect expected progress. Where delays have been made, these should be captured (i.e. voucher programme)
  2. Number of indicators should be reduced and simplified. It may be helpful to group them by area (WASH, nutrition, health). Indicators better defined including data source, and any indicators that cannot be clearly measured will be removed / not added.
  3. Indicators should be tested to ensure they reflect the intended output - some indicators should be checked for technical relevance (i.e. reproductive health) or could be moved from output 2 to output 1 (e.g. child protection services) or made more ambitious.
  4. The micro-finance project will be removed from the logframe
  5. Indicators should be included to reflect outputs from the emergency funding (£18 million).
  6. A reallocation of funding has been requested for the IDP response ($5 million), UNICEF reflect the adjustment in the indicators. Should DFD secure additional funding, this reallocation will be prioritised.
  1. DFID should clarify what is expected from output 2.2, as these targets are currently unclear.
  1. UNICEF will actively seek to fill gaps in mental health psychosocial services provision, including the introduction of an online electronic child protection database (CPIMS+). Follow up on this required with the DFID protection advisor.

1. UNICEF Reporting Quality - February 2020 – The progress report required a number of iterations to secure one that could be used. An overall improvement in the quality of the data is needed. such that it ensures progress reporting is clear and appropriately disaggregated. Specifically, this should involve (actions for UNICEF and DFID):
  1. UNICEF and DFID to agree to annual / quarterly report review report structure. Additional, quality assurance of data presented is essential, including clear explanations for which indicators have not been met or have been substantially exceeded and the reasons for this.
  2. The numerators (e.g. number of people vs number of consultations / contacts) should be clarified for each indicator, and percentages should ensure that the correct numerators and denominators are used.
  3. When no milestones have been achieved, there should be a clear narrative as to why this has taken place (this has now been done for most but not all indicators).
  4. DFID and UNICEF should explore any capacity gaps that might exists and how their internal data systems could be strengthened. (action needed by end January 2020)
  5. UNICEF should ensure the consistency between the report and logframe and should include a clear narrative of challenges / lessons learnt / areas for improvement.
  6. Delivery chain map explains in more detail where funding is being directed and what the associated risks are, (this will need to be discussed with UNICEF HQ as they have advised the country office not to include risks of downstream partners)

1. Risk, Fraud and Audit - Ongoing - In line with the DFID UNICEF Framework agreement, UNICEF to provide details of credible fraud and safeguarding cases as soon as they arise. DFID and UNICEF should agree to define credible as anything that requires an investigation. An audit had recently been completed. DFID to work with UNICEF to ensure the audit’s recommendations are fully implemented. It will be important going forward that
  1. Monthly calls between the DFID Programme Manager, lead Humanitarian Advisor and UNICEF are arranged to draw out emerging and escalating risks including fraud, aid diversion and safeguarding,
  2. Reviewing the risk register as a fixed agenda item on monthly calls
  3. Delivery chain map illustrated to articulate flow of funds with associated risks,
  4. UNICEF pro-actively inform DFID of any significant changes during the reporting year including underspend, and delays in the implementation of activities
  5. DFID seek out more opportunities for face to face meetings.

Results portal - Ongoing - It was agreed during the partner meeting that UNICEF would deliver this on quarterly basis with indicators broken down by month and disaggregated. UNICEF may require support to increase Health Information Management System expertise and capacity, and to strengthen their internal data systems.

Contextual understanding and Research areas - Ongoing - The context is complex, with access to populations clearly being a challenge. This review would recommend exploring 1) local epidemiology and disease burden, demand side barriers, 2) data sharing, and 3) quality of support provided.

Impact weightings – January 2020 - A greater emphasis should be placed on the weighting for Output 1 as this involves the largest spend and the greatest area of impact – recommended a weighting of 50%.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

Assumptions
- Access to intervention locations remains open for UNICEF, partners and beneficiaries.
- Coordination between social welfare and health sectors maintained.
- Supplies prices remain stable and supply importing remain viable.
- Local authorities continue support to nutrition, health and WASH assistance both at national and sub-national levels.
- UNICEF continues to have access and additional funding to maintain incentives for health workers
- Local authorities granted the access to implement the nutrition assessments

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead.

The logframe describes an overall intended impact of improving nutrition status across the life course for all vulnerable populations in Yemen, to be measured through the proxy of GAM (global acute malnutrition) and under 5 mortality rates.

Broadly, the indicators are on track however the logframe will be adjust at the outcome level to simplify the indicators and ensure they have credible means of verification.

Explain major changes to the logframe in the past year (1/2 page)
No

Describe any planned changes to the logframe as a result of this review (1/2 page)

Indicators should be updated in light of the recommendations above.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

Economy - Inputs of the appropriate quality at the right price
UNICEF costs are in line with other UN partners. DFID’s contribution includes an indirect cost recovery charge of 8% (a standard board-approved rate). A further 11.7% in country management cost (which will remain under review to ensure it remains appropriate in an evolving context) has been applied which covers operations (6.5%), M&E (1.3%), emergency and field operations (0.9%) and security costs (2.5%). In addition, direct staff costs were projected to be 6.86% of the total budget. This information still holds true.

UNICEF has reported that the key cost drivers continue to be supplies, field logistics and human resources. The VFM indicators set, continue to be broadly in line with what was set out in the business case with one exception:

Cost of Community-Led Total Sanitation (CLTS) in one village (includes CLTS and water supply incentive to villages achieving open-defecation-free status) - This was a carry-over from the previous business case. CLTS is no longer a part of the current programme and will therefore be removed as a VFM indicator.

Efficiency - How well are inputs converted into outputs?

Economies of scale – UNICEF, globally is the one largest procurers of basic child vaccines, mosquito nets, nutrition supplies, and other equipment which gives UNICEF leverage in negotiating the lowest prices with suppliers.

Use of long-term agreements to lower costs - Procurement of Community Engagement Toolkits for volunteers which UNICEF expects to be procured through existing Long-Term Agreements (LTAs) maintaining specific suppliers for standard items which the agency expects to order multiple times over the course of a year. LTAs are typically in place for one year at a time, securing predictable prices and expediting the procurement process. Others include the Tolumus solar power investment which is expected to break even in just over two years and save over $500,000 at year 5 with a 15% return investment on year 10. This is based on the assumption that there will be (a) a one-year time lag in construction, (b) that fuel costs will be held constant at $1/liter and (c) the system is brought up to 100% capacity when previously running at 40% capacity. At the end of 10 years the investment generates a $1.4m saving.

Taking a protracted crisis approach; Use of existing health facilities and structure UNICEF’s approach of working through Local Governorate Health Offices (GHO) and NGOs continues to ensure a more comprehensive service in Yemen and enables DFID to access programming throughout the country. Delivery through GHOs makes use of the existing health infrastructure and exercises long term benefits by supporting and strengthening systems resilience. The combined delivery mechanism ensures reach and helps harmonise and manage costs across different geographical areas.

Managing financial partnerships – When transferring funds to implementing partners, UNICEF applies the Harmonised Approach to Cash Transfers (HACT), which includes assessment and strengthening of partner financial systems, spot checks and scrutiny of use of UNICEF funds. Capacity building, monitoring and financial regulations such as limits on overhead costs help to reduce the risk of mismanagement of funds.

One example of UNICEF’s efficiency is its use of mobile teams which costs $4,000 to $6,000 per month reaching an average of 50 SAM children per month. Although the cost per child is around $100 (within the average cost of managing a SAM child without supplies) each mobile team is also providing an integrated health and nutrition service, consequently offering greater impact for the cost incurred per child. Furthermore, the mobile team activity is simultaneously decreasing the transportation cost burden on families to access health facilities in the first place.

Effectiveness - How well are outputs having the intended effect?
DFID Yemen’s previous funding to UNICEF spanned important periods of escalation of the conflict and deterioration of health and nutrition in Yemen, including the beginning of the cholera outbreak and the international attention on the risk of famine. As such, implementation throughout this turbulent period has contributed to significant lessons about the effectiveness of the programme in a complex emergency context. The following lessons will be taken forward in this programme to ensure effectiveness throughout this intervention:
- Investment in preventive services as well as traditional development-context health and nutrition interventions, rather than limiting the support to the emergency/humanitarian response only.
- Integration and multi-sectoral programmes and interventions at both community and health facility levels. This includes the importance of expanding availability of integrated health and nutrition services in the second and third level of coverage through several modalities, including Community Health Volunteers (CHV), Community Health Workers (CHW), mobile teams and integrated outreach services, to reach vulnerable and rural populations that cannot access health facilities due to high transportation costs and social exclusion considerations. This also includes ensuring Internally Displaced People (IDPs) and other conflict-affected populations have access to essential routine health and nutrition services, in addition to humanitarian support.
- Strengthening monitoring and reporting systems at a sub-national level plays an important role in improving quality of services and performance indicators. Centrally-led monitoring and reporting are not sufficient, especially as project interventions move to more decentralised levels.

UNICEF is a member of the United Nations Country Team and therefore benefits from a seat at the table with the de facto authorities in the north and the Government of Yemen in the south. UNICEF has ensured that its interventions reflect the importance of implementing preventative services i.e. development context health and nutrition interventions, as well as emergency and humanitarian responses ensuring a holistic and longer-term response. This includes integration and multi-sectoral programmes at both community and health facility levels, expanding the availability of integrated health and nutrition services in the second and third level of coverage through several modalities, including Community Health Volunteers (CHV), Community Health Workers (CHW), mobile teams and integrated outreach services, to reach vulnerable and rural populations that cannot access health facilities due to high transportation costs and social exclusion considerations. This also includes ensuring IDPs and other conflict-affected populations have access to essential routine health and nutrition services, in addition to humanitarian support.

UNICEF’s analysis of the effectiveness and impact of their Rapid Response Teams is ongoing.

Equity

UNICEF continues to benefit all Yemenis. As a UN agency, UNICEF has no political affiliation and has consolidated its reputation as a development agency working to benefit all vulnerable individuals and communities irrespective of their political, territorial or sectarian affiliations. Beneficiary needs are the guiding factors for response.
Some of UNICEF’s interventions targeted vulnerable, marginalised pregnant and lactating women and new-borns, malnourished children with medical and nutrition complications, and those with disabilities primarily through the health voucher scheme. These target groups are identified in communities, IDP camps, when presenting in health facilities, and other points for nutrition services. In addition, 100% of Community health workers (CHW) are female, 99% of Community health volunteers (CHV) are female (only 200 out of 18,078 CHVs are male) and 50% of the Rapid Response Teams are women.
Specific VfM Example of DFID Funded Solar Project
In addition to the above UNICEF has preliminary return on investment analysis for one DFID funded WASH project in Sadaa Governorate. The Tolumus solar investment will break even in just over two years. This is a conservative estimate based on assumptions of a) one-year construction lag time assumption, b) fuel costs held constant at $1/litre, and c) the fact that the system was brought up to 100% capacity but was previously running at 40% capacity. Cumulative undiscounted savings will be over $500,000 USD at year 5 and over $1.4 million USD at year 10. Over a 10-year projection, the return on investment will be 15% when applying DFID’s 10% discount rate.
Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The programme should continue given the criticality of the services provided. UNICEF as a partner also offers additional opportunities to leverage and influence the behaviour of other donor contributions to this sector, such as the World Bank. For example, in 2018, DFID was able to utilise it’s relationship with UNICEF and World Bank funded cholera preparedness work to facilitate the provision of critical early warnings in the form of weekly rainfall forecasting and a monthly cholera risk assessment. These informed the deployment of mitigating measures. This is the first time in the world that these types of products have been used together in real time to tackle the spread of cholera providing more advanced notice of potential disease spikes.

E: RISK (½ to 1 page)
Overview of programme risk (noting the rating from p.1) and mitigation
This programme was rated major residual risk at the business case approval stage. The humanitarian context in Yemen remains high risk and since the business case was approved the overall context deteriorated, increasing delivery, fiduciary and safeguarding risks. In addition, there has been a lack of reporting from UNICEF on fraud/aid diversion, particularly given the large number of downstream partners. This has resulted in the residual risk being increased to severe. The programme still operates within DFID Yemen’s risk appetite across the six different risk categories (external context, delivery, fiduciary, safeguarding, operational and reputational).

Risk mitigation
UNICEF continued to report throughout the reporting year that they have robust risk mitigation measures in place; office wide audits, Harmonised Approach to Cash Transfers (HACT) audits, micro-assessments of partners, Programme Monitoring Visits (PMV). These measures should help to mitigate the risk of fraud occurring. However, a recent internal audit completed by the Office of Internal Audit and Investigations has identified several weaknesses including:

- on how HACT us applied – UNICEF has agreed to address this weakness by putting in place an appropriate risk mitigation strategy, based on a robust methodology that transcends the existing HACT framework;
- no cohesive risk management strategy including no comprehensive assessment of the risk of fraud and aid diversion – UNICEF has agreed to introduce a risk management strategy, framework and data and trend analysis mechanism which will help address concerns raised; and
- concerns with direct cash transfer to authorities in Aden and de facto authorities in Sana’s, as a result of issues with sourcing qualified NGO partners – UNICEF aim to strengthen the capacity of Implementing Partners to address this risk.

DFID will continue to follow up with UNICEF on the findings of this internal audit and the action that is being taken to address the issues identified.
UNICEF report on risk on a quarterly basis and new and increasing risks are discussed in quarterly meetings. UNICEF at times change risk ratings without clear explanation as to why that is the case. At our last quarterly meeting in August we challenged UNICEF on several amendments they had made to risk on delivery, conflict sensitivity, aid diversion/collateral damage and safeguarding. UNICEF agreed to clarify the changes and report on any additional mitigation measures put in place that perhaps lead to a reduction in the residual risk rating. We have not yet received this clarification but will continue to press UNICEF on the importance of robust risk management and communication with DFID.

We expect levels of fraud, aid diversion and issues surrounding safeguarding to be present in the Yemen humanitarian context particularly given the World Food Programme’s decision in June 2019 to partially suspend their food aid due to significant levels of aid diversion in Houthi-held areas. As the Framework Agreement will be renegotiated in due course, it is recommended that reporting of fraud, aid diversion and safeguarding should be quarterly with major cases to be reported in real time.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues

Out of a total grant value of GBP £96 million, to date DFID has disbursed GBP £53,677,497 (equivalent to $70,262,974 with a further £8,777,349 recently being paid taking the total disbursed to £62,454,846.97) to UNICEF Yemen. Of this amount, $43,470,128 has been spent leaving an unspent balance of $26,792,846 as of 31 July 2019. An additional $14,008,005 is committed in legally obligated expenditures, resulting in a total utilisation of $57,478,133, which amounts to 82 per cent of the funds received to date.

Delivery against planned timeframe
Timeliness of narrative and financial reporting has been adequate. However, in terms of quality and coherency of data there is significant room for improvement. For example, UNICEF’s reporting and presentation of data in relation to the logframe has been incomplete and at times inaccurate, and it would be useful for reporting to directly relate to indicators and outputs. In terms of financial reporting the following issues have been experienced:
- UNICEF has submitted on occasion inaccurate financial reports/payment requests indicating a lack of internal quality assurance.
- UNICEF changed the way they provided financial information and whilst not disallowed under the Framework Agreement, DFID was not alerted to this in sufficient time before making a payment, resulting in confusion and delays in DFID processing the payment which almost led to DFID not meeting its monthly forecast.
- UNICEF failed to inform DFID in advance of potential £13 million underspend in April 2019 which led to a lot of additional work for UNICEF to rectify.

DFID continues to work with UNICEF to ensure they are clear on our expectations and we will continue to monitor the situation and escalate any issues to DFID Yemen Management Team as they arise.

Recommendations
It will be important going forward that
  1. Delivery chain map explains in more detail where funding is being directed and what the associated risks are, (this will need to be discussed with UNICEF HQ as they have advised the country office not to include risks of downstream partners)
  2. DFID support UNICEF in capacity and capability around reporting and financial management
  3. Indicators are linked directly to outputs to enable simpler and clearer reporting.

Performance of partnership
Overall DFID recognises the complexity and access constraints in delivering in Yemen. DFID sees UNICEF as one of the critical actors in Yemen whose programmes are essential in saving lives and maintaining systems.

UNICEF reputation is currently seen as good however this can be affected by performance. The transparency, and credibility of UNICEF reporting, whether in donor reports, fraud or research (e.g. SMART surveys) is essential to maintaining UNICEF’s reputation. An improvement in UNICEF’s level of transparency is needed to improve the quality of the partnership. This relates to programme and operational factors.

Specific to operations and programme management, UNICEF should continue to improve its communication with DFID on this programme particularly around projected underspend, reporting risks including fraud cases, safeguarding issues and aid diversion (of which no cases have been reported since the start of the programme) and maintaining an open and transparent relationship.

Recommendations – see Risk, Fraud and Audit recommendations above.

Asset Monitoring and Control
UNICEF maintains an asset register which is formally reviewed by DFID at each annual review as well as through this PCR. Asset management is in line with UNICEF policy and procedures as agreed in the Framework Agreement between DFID and UNICEF.

Date of last narrative financial report(s)	28/08/2019
Date of last audited annual statement (s)	31/12/2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

Since the beginning of the project, UNICEF has conducted 87 programmatic monitoring visits, 5 micro-assessments, 4 audits, and 6 spot-checks of DFID-funded activities. Based on the financial assurance activities, no potential cases of fraud have been detected.

DFID is currently working on contracting an independent monitoring organisation (Transtec). They will provide third party monitoring services for DFID of UNICEF programme. Our UNICEF programme will be prioritised and will provide DFID with more robust data going forward.

Recommendations
Going forward it would be useful for UNICEF to provide (as previously agreed under the previous programme)
1. Regular data around monitoring to DFID, for example, the number of field visits, spot checks, micro-assessments and more detail around findings,
2. Provide data from the results portal on a quarterly basis with a 3-month breakdown,
3. Data should be disaggregated by sex and disability where appropriate,
4. DFID will hold regular discussions as well as formal quarterly meetings to discuss progress, context, needs, risk and aid diversion. Should progress go off track, DFID Yemen will work with UNICEF to put in place a Performance Improvement Plan which would include an action plan as well as monthly progress meetings. Should this programme cease to represent good VFM then an action plan in consultation with UNICEF will be put in place to seek improvements. If no or little improvement is made, then DFID could consider ending this programme early.

Evidence

Drawing on wider DFID expertise and services, DFID has engaged MQSUN to review critical nutrition elements of the programme including the SMART nutrition surveys, availability of breast milk substitute etc. This has revealed concerns around the sample frames and the validity of the surveys.

Learning
Health and Nutrition
- UNICEF may benefit from having epidemiological input to process and present data and may require support to increase EPI and Health Information Management System expertise and capacity, and to strengthen their internal data systems.
- UNICEF has been working on enhancing coordination between health and social welfare sectors to facilitate the identification of children with psychosocial distress symptoms and other vulnerabilities. This requires further support for implementation, as well as quality monitoring.
- Ensuring quality of care will require disaggregation of the data by location, to better monitor at district or if possible sub-district level and identify where actions can be taken to improve care.

Cholera
The following lessons have been identified from the acute cholera response:
- Poor case surveillance and data sharing, due to non-systematic sharing of line lists at Governorate level, often depends on personal relationship between GHO staff, RRT coordinators and UNICEF officers, and inaccurate case information.
- Many water trucks still refuse to chlorinate water due to concerns of 1) truck damage, 2) perceived risks of drinking chlorine. Approaches to improve this include law enforcement strategies and supporting behavioural change. UNICEF have proposed a behavioural study to support next steps.
- Coordination of the WASH response to Cholera/AWD at the Governorate and district level is difficult, and UNICEF will advocate for the activation of a regular WASH Governorate level coordination in 7 critical areas (Amanat, Sanaa, Dhamar, Al Hodeidah, Hajjah, Ibb, Taiz) to improve joint epidemiological analysis and support integrated responses, with government and NGOs.
- The high numbers of reported cholera / AWD have resulted in RRTs being spread too thin, reviewing many that do not meet the case definition, and possibly not reviewing cases that are more likely to be cholera. Only 1/3 of suspected cases have been seen by the RRTs (weekly range: 18%-58%). Evidence from other countries using RRT suggest that a >80% coverage results in better control. Possible actions include:
    - Strengthening the reporting (currently duplication and false reports)
    - Review of the case definition
    - Greater RRT capacity
    - Training in triaging of cases for RRT
    - Monitoring of this output indicator (% of reported cholera cases seen, minimum target 80%).
    - Inclusion of a medical member to create a “cholera rapid response team”

IDPs
UNICEF have reported that the first line IDP response has had low levels of funding allocated to it for WASH, which has made their response in this area challenging.

Going forward it would be useful for UNICEF to
1. structure their learning around specific sectors and
2. for DFID to look at making the reporting template to be more explicit.