Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Monitoring and Evaluation of the UK’s Framework for Results for Malaria (“Breaking the Cycle: Saving lives and protecting the future”) and RMNH (“Choices for Women: Planned pregnancies, safe births and healthy newborns”)
Programme Value: £4.5m		Review Date: January 2016
Programme Code: 203368	Start Date: April 2012	End Date: July 2017

Summary of Programme Performance
Year	Jan 2014	Jan 2015	Jan 2016
Programme Score	B	A	B
Risk Rating	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

This programme was set up to deliver a mid term review (MTR) and final evaluation for the Frameworks for Results on malaria and reproductive, maternal and newborn health (RMNH), which were published in December 2010. The mid term review was completed by end 2013. Subsequently an external reviewer examined a set of draft Terms of Reference and concluded that the final evaluation was feasible but unlikely to be good value for money. Synthesising and sharing evidence and lessons from DFID malaria and RMNH programmes was more likely to generate more widespread lesson learning at lower cost.

During the year covered by this Annual Review there was no spend from the programme. Human Development Department has been considering what lesson learning could usefully be done in 2016/17 to support policy and programming decisions. This work is currently on-going.

Summary of recommendations for the next year

1. Concrete plans for lesson learning on malaria and RMNH should be developed separately by the relevant teams, rather than being managed together. By end March 2016.
2. The logframe should be revised to reflect changes in approach since the programme was approved. By end April 2016.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	4818046
DevTracker Link to Log frame:	4925580

Outline of the programme

The UK government is committed to reduce poverty in poorer countries, in particular through achieving Global Goal 3 ‘Ensure healthy lives and promote well-being for all at all ages’. The goal includes targets on maternal mortality, newborn and under 5 child mortality, HIV/AIDS, TB, malaria and neglected tropical diseases. While progress was made towards attainment of MDG 4 (Reduce child mortality), MDG 5 (Improve maternal health) and MDG 6 (Combat HIV/AIDS, malaria and other diseases), the rate of progress was insufficient to attain the targets in some countries, with particular challenges in reaching the poorest and most disadvantaged.

To support attainment of the MDGs, in December 2010 DFID published Frameworks for Results on malaria and reproductive, maternal and newborn health (RMNH):

•	Breaking the cycle: Saving lives and protecting the future. The UK’s Framework for Results for malaria in the developing world and
•	Choices for women: Planned pregnancies, safe births and healthy newborns. The UK’s Framework for Results for improving reproductive, maternal and newborn health in the developing world.

 These set out frameworks for delivering on UK Government commitments to:
   •	help halve deaths from malaria in at least ten high burden countries by 2015;
   •	provide access to modern methods of family planning for 10m additional women, including 1m young women aged 15 – 19 by 2015;
   •	prevent more than 5m unintended pregnancies by 2015;
   •	ensure at least 2m safe deliveries, particularly for the poorest 40% by 2015; and
   •	save the lives of at least 50,000 women during pregnancy and childbirth and 250,000 newborn lives.

Together these two Frameworks for Results committed up to £7 billion (up to £4.4 billion for women’s and children’s health and up to £2.5 billion for malaria).

This programme was set up to evaluate the implementation and outcome of the two Frameworks for Results. A mid term review was completed in 2013 which found that the Frameworks have served an important and effective role. DFID is broadly on track against its commitments in the Frameworks. In addition, the programme has delivered a review of the progress DFID has made towards the commitments laid out in the 2011 HIV position paper Towards Zero Infections.

The approach to evaluation has been reviewed and revised following the mid term review.

## PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Overall the programme has delivered its planned outputs so far. There is more we need to do to learn lessons from the implementation of DFID’s malaria and RMNH programmes and share across country offices to improve effectiveness. Identifying opportunities which will be most useful for future programming decisions has been the emphasis of this year’s activities. This has taken longer than expected, partly because of a series of reviews of DFID’s future bilateral and multilateral strategy.

The aim of the programme is to improve the effectiveness and value for money of DFID and partner malaria and RMNH programmes. The MTR did not recommend any major changes to DFID’s policy direction on malaria and RMNH although it did find that continued attention to strategies to reach marginalised people will be key to meeting global and DFID targets. It also found that strengthened health systems, together with increased government efforts and commitment of resources, will be required to sustain the gains made.

Overall output score and description

This year, the programme has scored a B. Progress to identify cost-effective lesson learning activities was put on hold during 2015 when DFID was conducting strategic reviews of its business.

Key lessons
Last year’s review found that evaluation of such wide-ranging strategy documents is extremely complex and challenging to do in a way that generates useful learning. It also found that learning can be generated at much lower cost and reduced risk through synthesizing evidence and lessons learnt. The main lesson from activities this year is that because of the differences between malaria and RMNH, the lesson learning activities would benefit from being de-linked.

Key actions
The priority is to identify cost-effective activities to learn lessons from DFID’s malaria and RMNH programming.

Has the logframe been updated since the last review?

No. The logframe is out-of-date and should be updated when outputs have been agreed.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 1: Availability of evidence on effectiveness and relevance of Frameworks for Results
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	80%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2016	Progress
1.1 Concise reports delivered as specified by TORs on the evaluation of the FfRs on time, with only 2 drafts needed befor final version and with limited comments from external reviewers.	Delivery of evidence products (to be defined)	No evidence products planned or delivered.
1.2 Deliverables as specified by TORs for the review of the 2011 HIV Position Paper, complete on time to publish DFID review paper by World AIDS Day 2013	None planned	None
1.3 Number of products reviewed externally with comprehensive comments delivered within agreed deadlines.	2	No products have been reviewed as none delivered.

Key Points
No evidence products were planned or delivered this year. HDD has been working with DFID’s Heads of Profession and other DFID Departments to identify what lesson learning could usefully be done in 2016/17 to support policy and programming decisions. This work is currently on-going. It was put on hold during 2015 when DFID was reviewing its future priorities and programming through strategic reviews. While these reviews were ongoing the value for money of further study was not clear. Lesson learning activities are highly resource intensive and need to be focused on issues of most use to decision-makers. With a large and diverse programme portfolio across two complex policy areas, determining key areas of focus and ensuring staff engage in the process is not straightforward.

Following scoping work it has been decided to delink the lesson learning work on malaria and RMNH from each other. This means that the respective policy teams can decide, in consultation with health advisers across DFID, which activities will be of most value.

Summary of responses to issues raised in previous annual reviews (where relevant)

HDD should incorporate key Framework commitments not currently included in the DFID Results Framework into its mid year report publication in February 2015. This was done.

HDD should work with the DFID Head of Profession for heatlh during January to June 2015 to synthesise lessons from implementation of programmes under the Frameworks for Results, including how value for money is assessed and monitored. These should be captured and shared with country offices. Scoping work was carried out which concluded that information contained in Annual Reviews was not sufficient to support lesson learning – more in depth review of programme documents would be needed.

The approach for the final evaluation should be revisited in summer 2015, taking into account the purposes for the evaluation as set out in the Frameworks: 1) to synthesise and examine DFID’s progress and results for accountability and 2) lesson learning. The decision should also take value for money into account. This has been delayed.

The logframe should be reviewed in autumn 2015 to ensure the 2015 milestones are realistic in the light of changes to the timeframe for the programme. The logframe has not been reviewed because the future activities for the programme have not been determined.

Recommendations

- Concrete plans for lesson learning on malaria and RMNH should be developed separately by the relevant teams, rather than being managed together. By end March 2016.
- The logframe should be revised to reflect changes in approach since the programme was approved. By end April 2016.

Output Title	Output 2: Strengthened accountability for malaria and RMNH across DFID
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2016	Progress
2.1 Number of DFID health advisers contributing to the gathering of evidence	15	No evidence products produced so no advisers involved.
2.2 Number of DFID Departments or country offices involved in discussions on implementing the recommendationsf rom the MTR and evaluation.	10	MTR recommendations were implemented by 10 Departments.
2.3 % of health advisers aware of MTR and evaluation findings.	100%	MTR findings have not been further communicated.

No evidence products were delivered from output 1 for stakeholders across DFID to be engaged in.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
No expenditure in this reporting period.
In future periods the costs for the programme will be determined by fixed term agreements with suppliers. These will be driven by salary costs and particularly the mix of personnel involved in the consortium and the number of days they are used. Experience from the Mid Term Review is that having sufficient days from relevant health experts built into the contract is critical.

VfM performance compared to the original VfM proposition in the business case

The approach for the programme has been driven by value for money considerations, to ensure that planned activities are focused, important for future decision-making and used.

The initial estimate for the evaluation costs (£4.5 million) in the business case have so far proved to be more than was needed. The evaluation assessment and Mid Term Review together cost £664,912,000.

Assessment of whether the programme continues to represent value for money
The programme continues to represent value for money. Activities will not be carried out unless they are considered to provide value for money both in programme costs and staff time.

Quality of financial management
No expenditure in this period.

Date of last narrative financial report	n/a
Date of last audited annual statement	n/a

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

The risk log has been reviewed, see table below. The key risks are that HDD staff and stakeholders across DFID do not have the capacity to generate lesson learning and act upon it. Mitigating actions will be taken but this remains a risk.

Risk	Impact	Likelihood	Direction / of travel	Action to mitigate risk
Insufficient expertise and capacity within HDD to maintain momentum over time.	M	H	→	Include responsibilities in job objectives of programme staff. Keep relevant team leaders in HDD up-to-date on progress.
External evaluator does not have sufficient expertise to conduct the final evaluation.	M	M	↗	Focus on lesson learning and review the approach to the final evaluation in the light of this.
Findings from lesson learning and final evaluation not acted on.	M	H	↗	Ensure there is wide-spread involvement in lesson learning activities and key issues are raised with senior management.
Insufficient reliable DFID monitoring data available for the evaluation.	M	M	→	The approach to the final evaluation must be feasible and take account of availability of information on DFID programmes.
Evidence generated is not disseminated to external stakeholders.	M	L	→	Develop communication plan for internal and external stakeholders from lesson learning and final evaluation.
Partners do not act on evidence generated.	M	M	→	HDD teams identify opportunities to influence for change through global forums.

Outstanding actions from risk assessment

None.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The Mid Term Review was completed on time. Since then the approach has been reviewed and no new evidence products have been planned.

Performance of partnership (s)
Not applicable.

Asset monitoring and control
Not applicable.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
No further evidence has been gathered this year.

Monitoring progress throughout the review period
This review has been led by Penny Innes, Senior Responsible Owner, with input from team leaders and advisers from the Health Services Team and Sexual and Reproductive Health and Rights Team and Scott Hardie, project officer.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process