## Sheet1
PROJECT NAME | Climate Research and Information Services in South Asia (CRISSA)
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (2020)
| Enhanced evidence-based inputs into policy processes | Planned | Policies and programmes based on limited evidence from South Asia |  | Feedback from policy makers recognising the availability of an enhanced policy-relevant evdence base (May 2016) | Evidence of absorption of evidence reviews in decision-making processes (the evidence could be based on specific policy actions that draw from research outputs)
Evidence-based policy and programmes drawing on South Asian research |  | Achieved
Source
CRISSA documents, policy documents, feedback from policy-makers
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increased coherence among climate research programmes | Planned | Limited jointly funded climate research in South Asia and duplication and gaps in many areas of climate research |  | Informed dialogue among policy makers on coherence in climate research (May 2016)
Achieved
Source
CRISSA documents, policy documents, feedback from dissemination activity
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
More coordinated and coherent regional approach to research | Level of duplication of research efforts | Planned | Significant duplication of research efforts | International funders agree to share research plans to reduce potential for duplication (2012) | Regional research priorities discusssed among national and international donors (May 2016) | Major research programmes do not duplicate (expected) results or outputs (2020) | The regional and international research community are interested in working collaboratively.
Achieved
Source
CRISSA documents, project reports, feedback from dissemination activity
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Improved evidence base available to decision makers from jointly funded research and high quality evidence reviews | Planned | Variable quality of evidence from reviews and research in South Asia | Subjects for reviews and key research topics discussed among research funders (2011) | Key research and reviews produced that are disseminated and discussed with decision-makers (May 2016)
Achieved
Source
CRISSA documents, project reports, feedback from disemination activity
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 2600000 |  | 450000 | 500000 | 3550000 | 73
INPUTS (HR) | DFID (FTEs)
0.4
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumption
| Enhanced multi-country coordination in climate research (in the context of CRISSA projects) | Planned | No regional process in place to help drive strategic direction of research | Expert framing paper sets out needs and approaches for better coordination (2011) | Enhanced multi-country inputs in climate research (No of multi-country or regional research programmes with multi-donor inputs) (May 2016) |  | It is possble for international and national donors to reach agreement on research priorties. There is willingness among international funders to reach agreement on division of labour
Coordination with research funders |  | Achieved
Source
Donor meeting minutes and feedback from dissemination ctivity
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increased sharing of research outputs among funders | Planned | No formal arrangement for sharing research outputs |  | Research outputs and policy briefs formally shared in an appropriate forum (May 2016)
Achieved
Source
Donor meeting minutes and record of dissemination events
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20 | Number of jointly funded research programmes | Planned | Limnited numbers of jointly funded climate research programmes in South Asia |  | Felt need for co-funded research better recognised based on CRISSA evidence (May 2016) | Reduced duplication of funding priorities and/or priority setting based on mappling of donors' / users' priorities
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Records of disseminationa activity |  |  |  |  | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 110000 |  |  |  | 110000 | 100
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Quality of evidence base available for policy makers and programme managers | Evidence on the needs of users with regard to climate information | Planned | Limited knowledge of users needs for climate information | WRI evidence review commissioned (2011) | Review disseminated (2014) |  | Governments in the region and donors accept the outputs of systematic and other evidence reveiws
Achieved
Source
WRI report and feedback from users
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Rigorous research findings available on key topics on policy and programming importance | Planned | Key topics (glacier, high altitude precipitation, CC and conflict, CC and groundwater, conjunctive water use, Pakistan floods) not currently researched | Projects commissioned (2012) | All projects completed, and reports and journal papers prepared (2015)
Achieved
Source
Project reports, policy briefs, papers
IMPACT WEIGHTING (%)
50
RISK RATING
Medium
INPUTS (£) |  |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 1940000 |  | 450000 | 500000 | 2890000 | 67
INPUTS (HR) | DFID (FTEs)
0.2
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Capacity of south Asian climate community to produce high-quality and influential research | Number of papers on climate science published in high impact journals with South Asian lead or sole authors | Planned | Limtied number of papers from South Asian authors on climate research |  | 3 Writeshops completed with key academics and researchers (2013) | 10 papers published or accepted (2020)
Achieved
Source
Project documents, publication searches
IMPACT WEIGHTING (%) | [6 empty] | Risk rating
30 | [6 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 550000 |  |  |  | 550000 | 100
INPUTS (HR) | DFID (FTEs)
0.1