Annual Review - Summary Sheet

Title: Adolescent Girls Initiative – Kenya
Programme Value: £9.96 million		Review Date: January 2016
Programme Code: 202874	Start Date: December 2013	End Date: November 2019

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	C	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress

Most components of the Adolescent Girls Initiative – Kenya are now under implementation with the majority delivering expected results.

The Adolescent Girls Initiative – Kenya (AGI-K) has made good progress over the last year and 6,500 are expected to benefit once all activities are under implementation. The design of the four key interventions in violence prevention, education, health promotion and wealth creation was finalised and their implemention has begun, to varying degrees, in both Nairobi and Wajir. There has already been greater than expected interest in the programme at the household level with the result that more children enrolled in the programme than anticipated, a significant achievement. The programme manager, the Population Council (PC), selected and interviewed 4,552 girls for baseline data collection and produced a report capturing the key findings from this activity. The findings were widely disseminated, including to sensitise beneficiary communities around the challenges to be addressed and the nature of project interventions. Sensitisation will require ongoing efforts. The AGI-K logframe was revised to incorporate baseline findings and now contains 21 output indicators against five outputs. An innovative monitoring system to track school attendance using biometric data has been established in both sites and is functioning well after some early setbacks. AGI-K’s Expert Research Committee and External Advisory Committee have operated effectively and as planned, with the former approving the final research design after a comprehensive review. Good progress has also been made in laying the foundations for effective cost benefit analyses although there is scope for implementing partners to improve their financial reporting. As a result of these activities, four out of five outputs met expectations during the review period and the programme as a whole therefore scores “A” in this annual review. This is note-worthy given the challenges faced in operating in an informal settlement in Nairobi (Kibera), and Wajir County with its vast and difficult terrain, poor transport infrastructure, inter-ethnic tensions, and low education levels. Output 5 scores “B” for the reasons outlined in the paragraph below.

Major challenges during this review period have included: (i) achieving the desired attendance rates at both health promotion and financial literacy training meetings in Nairobi; (ii) collecting data on attendance at these meetings in Wajir; (iii) establishing adequate numbers of bank accounts for the conditional cash transfer programme in Wajir; (iv) working with 79 highly dispersed communities in Wajir to begin the process of developing violence prevention “contracts”; and (v) identifying, training and retaining mentors for the health promotion and financial literacy interventions in Wajir.

The very high quality of AGI-K’s research will not be compromised if these challenges are addressed in the first quarter of calendar year 2016. Given the strong performance of Plan International (PI) and Save the Children International (SCI) over the current review period, and the scope for further strengthening lesson learning between partners, the prospects for getting the implementation of AGI-K fully on track in the coming year are high.

Key program lessons
Three key lessons have emerged over the course of this review period. First, the need for a highly differentiated approach to programme implementation in Wajir. The human and financial costs to implementation in Wajir are already higher than anticipated and should be further reviewed as soon as possible. Failing this, the implementation timeframe may need to be adjusted. Second, the importance of investing early and strategically in identifying and targeting the most influential stakeholders for adolescent girls’ well-being in Kenya. Although an influencing strategy has already been developed for AGI-K, it would benefit from a broad-based review of its goals and strategies and the clear allocation of human and financial resources to its implementation. Last, the need for rigorous and ongoing risk assessment and mitigation. Kibera and Wajir are challenging environments and AGI-K’s interventions are innovative both in terms of the activities themselves as well as their combinations. Taken together, it can be expected that AGI-K will continue to encounter risks to implementation that will require thoughtful management. All partners have shown considerable agility in responding to risks thus far and this strong beginning should be maintained and expanded.

Key recommendations for the next year

#	RECOMMENDATION	RESPONSIBLE	DEADLINE
1	Review AGI-K’s risk register systematically with a focus on the human and financial implications of mitigating any identified risks.	PC and implementing partners	Ongoing
2	Review the AGI-K influencing strategy and develop a costed schedule for implementation.	PC and DFID	31/03/16
3	Consider how lesson learning and coordination between AGI-K’s partners can be strengthened.	PC	27/02/16
4	Strengthen financial reporting by implementing partners with a focus on eventual cost effectiveness and value for money analysis.	PC and implementing partners	30/04/16
5	Revise the AGI-K logframe to respond to targets that have not been met in this annual review.	PC and DFID	30/04/16
6	As a matter of urgency, consider how delayed activities in Wajir can be fast tracked and in particular the conditional cash transfer programme.	PC	15/03/16

A. Introduction and Context

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

AGI-K is a six-year (2014 – 2019) action research programme aimed at assessing which combination of interventions for vulnerable, adolescent girls is most effective in improving their life chances. The overall programme budget is £9.96m. AGI-K will test the impact of four interventions on 6,500 girls aged 11 – 14 in the arid county of Wajir and the informal settlement of Kibera in Nairobi. The interventions will be implemented for two years from mid-2015 to mid-2017 and currently include a combination of girl-, household- and community-level activities. The research to evaluate their impact will continue until 2019.
The evidence generated by AGI-K is intended to: a) influence the policies, budget allocations, and social and cultural norms and practices which affect adolescent girls; and b) identify which combination of interventions can be most cost-effective and scalable in Kenya. AGI-K evidence is also intended to inform policy, programming and further research internationally.
The Population Council were awarded the contract to design and manage AGI-K in December 2013 following a competitive procurement process. PC have an office in Nairobi with a small team dedicated to the programme. Other members of the implementing consortia include: Save the Children International (SCI), implementing activities in Wajir; Plan International (PI), implementing activities in Kibera; the African Research and Population Consortium (APHRC), supporting research activities; and ITAD, carrying out cost benefit analyses and value for money research.
AGI-K has a comprehensive advisory and governance structure which has functioned well over the last year. The AGI-K Expert Research Committee (ERC), comprising international experts and DFID research and evaluation experts, serves in an advisory capacity without management responsibilities and this last year has helped ensure the technical rigour and independence of the study. In particular, the group provided valuable inputs during the review period into the finalisation of the AGI-K research design and implemention approach.
The national AGI-K External Advisory Committee (EAC), comprising the Kenya Women Parliamentary Association, the Kenya National Gender and Equality Committee, representatives from national and county government, private sector and multilateral organisations, met twice during the review period to ensure the relevance of AGI-K based on existing knowledge and evidence and support the dissemination and uptake of research findings. It will be important in the coming year to focus on building the capacity and commitment of this body to influence the enabling environment for adolescent girls using the evidence from the programme. The two (sub) county-level EACs have met three times over the review period.
AGI-K includes four interventions in the areas of violence prevention, education, health promotion, and wealth creation. The interventions are designed as follows:

Violence Prevention - preventing violence against girls: Committees are established in participating communities to identify the key challenges facing girls in that community and then to subsequently develop a ‘contract’ to prevent violence against girls. The contracts include specific steps to address issues affecting girls and an action plan for implementing the related activities. The committees include religious and community leaders, parents, teachers and young men and women. Some funding is provided to support the implementation of the contracts.

Education - incentivising girls to stay in primary school: Cash transfers are provided to beneficiary households conditional on the 80% school attendance of participating girls during each school term. School fees are also paid directly to the school at the start of each term as well as an incentive of £3 per girl enrolled in the program. Basic school kits, containing sanitary towels and school supplies, are provided to the girls at the beginning of the term

Health - promoting good health for girls: Girls meet in groups once a week under the guidance of a female mentor from the community. These “safe spaces meetings” include facilitated discussions using a health, life skills, and nutrition curriculum, as well as time for open discussion.

Wealth Creation - increasing financial assets for girls: Girls are provided with weekly financial training in additional “safe spaces meetings” to understand how they can manage savings. In addition, the girls receive an annual incentive of £2 to allow them to put into practice the financial skills they have learned. In Wajir, this is provided through a home bank (piggy bank); in Kibera, this is provided through a girl-friendly savings account.

AGI-K is implementing a randomised control trial (RCT) to examine the impact of the interventions in different combinations and the causal mechanisms driving the impact. The interventions have been combined as follows:
Combination 1. Violence Prevention (1625 girls)
Combination 2. Violence Prevention + Education (1625 girls)
Combination 3. Violence Prevention + Education + Health (1625 girls)
Combination 4. Violence Prevention + Education + Health + Wealth Creation (1625)

Context
Adolescent girls in Kenya face considerable risks and vulnerabilities that affect their education, health and general well-being. These include early marriage, teenage pregnancy; early unprotected, and/or unwanted sexual activity; violence; and social isolation. For the most part, adolescent girls younger than 15 who live in risk-prone environments have not yet experienced these negative outcomes. It is critical therefore, to intervene early and increase girls’ capacity to overcome these risks before the challenges result in outcomes that are irreversible.

Research to date has tended to show that single sector interventions (e.g. in health) are not adequate to obtain the range of outcomes needed to help girls enter into adulthood in a healthy, safe and productive manner. However, there is insufficient evidence regarding the most cost-effective combination of multi-sectoral interventions to achieve the greatest positive impact on girls’ well-being.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

With AGI-K interventions having only started this year, and no research conclusions yet available, no progress was anticipated against outcome indicators 1 and 2. For outcome indicators 3 to 5, the baseline study affirmed that the outcome indicator baseline values were the same for both control and intervention groups. Having achieved beneficiary and control groups with similar characteristics is important for the future research.

Outcome	Outcome Indicator	Milestone – November 2015	Indicator Score
Influence on policy, budget allocation and cost-effective programming for adolescent girls.	1. Number of citations of AGI-K research in National Strategy Plans, Budgets and DFID business cases (annual).	0
	2. Number of other donors and partners adopting the AGI-K approach and/or using lessons to inform their programming, policies and strategies (annual).	0
	3. Percent difference between AGI-K and control in girls experiencing first birth.	0% - confirmed in baseline data
	4. Percent difference between AGI-K and control in girls transitioning into marriage in Wajir.	0% - confirmed in baseline data
	5. Mean difference between AGI-K and control in years of schooling completed	0 years - confirmed in baseline data

Overall output score and description

Four out of five output indicators set for the review period were met and the programme as a whole therefore scores “A” in this annual review. The greater than expected interest in the programme at the household level, which resulted in more children enrolling in the programme than anticipated, is particularly noteworthy. The outlying output indicator (output 5) scored “B” due to delays in implementation in the very difficult operating environment of Wajir and the great distances involved in reaching the 79 participating villages. Plans are underway to address the challenges faced in Wajir.

AGI-K’s interventions have progressed as follows. 423 meetings for health promotion have already been held in Nairobi benefitting 1201 girls. 479 have been held in Wajir benefitting over 1000. 146 meetings for financial literacy training have been held in Nairobi for 589 girls while 379 have been held in Wajir benefitting over 500 girls. 50 mentors have been trained in total in Nairobi and 63 in Wajir. 1,851 girls are registered to the education intervention in Nairobi – out of a planned total of 1,935 - across 154 schools. 2,198 girls are registered to the education intervention in Wajir – out of a planned total of 2,648 - across 68 schools. School kits have been distributed to 3,526 girls in both counties and school fees paid for 3897 girls. Double the number of planned violence prevention community meetings have been held in Kibera (14 against a planned 7). None of the planned 79 violence prevention community meetings have taken place in Wajir for reasons that will be described below, although good progress has been made in sensitising communities around AGI-K’s goals.

Output	Score	Weighting
1. Evidence on most cost-effective combinations of interventions for adolescent girls generated and disseminated.	A	60%
2. Adolescent girls benefitting from programme interventions in health improve their health and social capabilities	A	10%
3. Adolescent girls benefitting from programme interventions in wealth creation improve their financial capabilities	A	10%
4. Adolescent girls benefitting from programme interventions in violence prevention experience decreased exposure to violence	A	10%
5. Adolescent girls benefitting from programme interventions in education improve school enrolment and attendance	B	10%

Key lessons

In addition to the key lessons outlined above, the key lessons in Wajir relate to: (i) the additional effort required to work with the high number of participating villages (79) dispersed over a large area; (ii) the need for repeated community sensitization; (iii) the difficulty in getting Equity Bank agents to villages to facilitate cash transfers; and (iv) the difficulty in finding qualified mentors amongst a largely uneducated adult population. In addition, across both Kibera and Wajir, 303 girls who have been identified as eligible to benefit from AGI-K interventions, have in fact not registered to participate.

The key lesson in Kibera is the need to focus on enabling high attendance rates for the health and wealth creation meetings.

Key actions

In addition to the recommendations outlined above, in Wajir, it is recommended to fast track, possibly through the hiring of temporary staff, (i) finalizing the establishment of bank accounts; (ii) encouraging the 303 girls who have not yet registered to do so; (iii) carrying out spot checks across programme implementation and collecting school and meeting attendance data in a timely manner; and (iv) setting up violence prevention committees in the 79 villages in Wajir.

In Nairobi, it is recommended that PI and the mentors (i) ensure there are no conflicts in meeting times; (ii) find venues that are conducive to mentorship meetings (e.g. not noisy and busy); and (iii) continue to reach out to the girls and the parents of those who are not attending regularly to encourage them to attend.

Has the logframe been updated since the last review?

Yes. In July 2015 the logframe was revised to reflect the data from the baseline survey. In some cases this involved inputting data for the given indicators; in others it involved rephrasing the indicators and/or updating the targets for 2017 and 2019 based on the baseline figures. In addition, the number of girls benefitting from AGI-K interventions in Kibera was reduced to reflect the baseline data. All logframe changes were approved by the ERC.

## C: DETAILED OUTPUT SCORING

Output Title	Evidence on most cost-effective combinations of interventions for adolescent girls generated and disseminated
Output number per logframe		1	Output Score	A
Risk:		Medium	Impact weighting (%):	60%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
1.1 Number of national and county-level government meetings, technical working groups and policy events where AGI-K is represented (annual).	4	9 national and county-level government meetings; 5 technical working groups	A+
1.2 Research implemented on time.	Findings from Baseline Survey published and disseminated	Dissemination conference held on 29 September 2015 with 77 participants	A
1.3 Number of submissions to peer-reviewed scientific journals and academic book chapters (annual).	1	Study protocol submitted to BMC Public Health	A
1.4 Research to determine most cost-effective combinations of interventions implemented	Initial costing data collected	Costing templates agreed and data collected	B

PC and the AGI-K implementing partners have invested heavily over the last year in outreach to key stakeholders as demonstrated by the strong score for indicator 1.1. The baseline data collection process, although challenging given the constraints inherent in Kibera and Wajir, was successfully completed and validated by the ERC. AGI-K’s research framework is therefore now well established and lays a promising foundation for robust and reliable research results in the coming years. For this reason, output 1 scores an “A” in this review. This is an important outcome given that output 1 accounts for 60% of AGI-K’s overall progress and is critical to the delivery of AGI-K’s key goal of producing research which influences policies and budget allocations for adolescent girls in Kenya and elsewhere.

Key Points

Indicator 1.1. Over the past year, AGI-K partners met with a wide range of stakeholders to discuss issues pertaining to the wellbeing of adolescent girls in Kenya and the focus of AGI-K. Key meetings included those with the National Aids Control Council; the Ministry of Health; the Ministry of Education, Science and Technology; the Wajir County Government; and the Nairobi County Government. As a result of the effort deployed against this output indicator, the milestone for the review year was exceeded and the indicator score is a subsequent “A+”. Given AGI-K’s objectives with regard to influencing policy and programming in Kenya and beyond, it will be important to maintain this level of effort while clarifying the aim or desired outcome of representation in targeted fora.

Indicator 1.2. The September AGI-K baseline dissemination conference was a well-attended event in Nairobi which brought together some key stakeholders, including the Governor of Wajir and Nairobi County Council representatives, resulting in a score of “A” for this indicator. It is notable, however, that not all stakeholders were represented at the level of seniority required for effective policy influencing (this is particularly true for the relevant lines ministries). Looking forward, given AGI-K’s far-reaching consequences for a variety of sectors in Kenya (health, education, the judiciary etc), it will be important to build on the baseline dissemination event to reach out to stakeholders who were not represented at the September event and, in particular, to ensure that senior decision makers in the Government of Kenya (GoK) are well briefed and consulted as appropriate.

Indicator 1.3. It is early in the implementation of AGI-K for research publications nevertheless submission of the study protocol to the Bio Med Central Public Health journal is a good start and allows for an “A” for this indicator. PC intend to submit to a number of journals in the coming year. It will be important to consider how key GoK stakeholders can be involved in the dissemination of AGI-K results.

Indicator 1.4 Progress has been good over the review period in determining cost data requirements and developing a clear template for data collection. Partners have received technical support to collect and submit cost data using the provided templates and DFID staff are confident that this data, if consistent and reliable, will enable a range of robust value for money analyses to be carried out. This said, AGI-K implementing partners continue to experience challenges in providing the agreed data (as outlined in the most recent Itad report). It will be urgent to focus on this issue in the first quarter of the next reporting period given AGI-K’s key focus on establishing the cost effectiveness of different interventions as well as their impact. For this reason, this indicator scores “B” in this review.

Summary of responses to issues raised in previous annual reviews (where relevant)

In the previous annual review, recommendations included to: 1) revise the log frame; 2) debrief on the pilot exercise to assess the questionnaire; 3) create a wider AGI-K forum so as to understand the roles of all partners; 4) produce an estimated cost per treatment package (exclusive of research costs); and 5) put in place plans to publish the study design and literature review and anticipated papers for 2015-2019. All of these recommendations have been met with the exception of (5). A study design paper has been submitted for publication, but a listing of the papers anticipated to be produced between 2015-2019 has yet to be developed.

Recommendations

1. PC to outline to the extent possible the anticipated research papers for 2016 – 2019.
2. PC to map critical stakeholders to determine how best to deploy influencing efforts in future.
3. PC to work with implementing partners and Itad to ensure that (a) expenditure data are consistently reported and (b) VfM templates are completed sufficiently so that an effective VfM assessment can be made.

Output Title	Adolescent girls benefitting from programme interventions in health improve their health and social capabilities
Output number per logframe		2	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
2.1 Number of girls enrolled in safe spaces meetings (annual).	1000 girls in Nairobi; 1250 girls in Wajir enrolled in groups	Exceeded: 1385 in Nairobi; 1732 in Wajir	A++
2.2 Average proportion of parents/guardians participating in parents’ meetings/community sensitization (annual).	Nairobi: 50%; Wajir: 50%	The planned parents’ forums have not yet been held in either Nairobi or Wajir. However, extensive sensitisation meetings were held with parents across both sites with attendance rates around 85%.	C
2.3 Average proportion of girls initially enrolled in program participating in weekly sexual and reproductive health trainings (annual).	Nairobi: 75%; Wajir 75%	68.5% in Nairobi; not yet known in Wajir	B
2.4 Mean score on sexual and reproductive health knowledge scale (min: 0; max 9).	Baseline values: Nairobi: 4.98; Wajir: 1.24	Strong baseline process. Targets established for coming years	A
2.5 Mean score on self-efficacy (min: 0; max 6).	Baseline values: Nairobi: 3.92; Wajir: 2.14	Strong baseline process. Targets established for coming years.	A

Results were mixed against the indicators for output 2 (and indeed outputs 3 through 5 which all relate to the implementation of AGI-K’s four primary interventions). There are two main reasons for this differentiated progress. First, in both Kibera and Wajir, it took longer than anticipated to identify the girls who would be included in the research in an appropriately randomised way. This in turn delayed the start-up of programme interventions. Second, Wajir in particular presented a range of hurdles to programme implementation. This included vast and difficult terrain, poor transport infrastructure, inter-ethnic tensions and low education levels. As a result, implementation in Wajir lags behind Kibera. Interestingly, while this is an immediate programmatic challenge, it is also a longer term strategic dividend – in the future, AGI-K will be in a strong position to demonstrate whether and how its interventions can deliver results in some of Kenya’s most exigent environments. The robust and reliable baseline values now in place for a range of indicators will also help build a stronger knowledge base around the life circumstances of adolescent girls in some of Kenya’s most challenging communities. In addition, the high levels of household interest in AGI-K, as demonstrated by higher than anticipated enrolment in the programme, are promising. As a result of this assessment, and as detailed below, the progress achieved overall under output 2 is considered in this annual review to have largely met expectations for the year, and to have laid very strong foundations for future progress, with a subsequent score of “A” for the output.

Looking forward, it will be important to build on the lessons of the current review year to develop realistic milestone targets for future years and, through comprehensive and real time risk assessments, develop risk mitigation strategies that will respond effectively to future implementation challenges.

Key Points

Indicator 2.1. 1,385 girls were enrolled in Nairobi in 43 safe spaces groups against a target of 1,000. 1,732 girls were enrolled in Wajir in 73 safe spaces groups against a target of 1250. As a result of this exceptional interest, this output indicator scores “A++” in this annual review. The reasons for the higher enrolment are: (i) successful efforts to sensitise and inform households and communities; (ii) higher than expected interest from households. The targets for AGI-K were derived from patterns of enrolment in a similar programme in Zambia.

Indicator 2.2. The planned parents’ meetings have not yet taken place given the unforeseen delays in programme implementation outlined above. However, much has been done to sensitise parents to AGI-K’s goals. Introductory meetings were held with parents between June – September 2015 in both Wajir and Kibera, during which parents were introduced to the programme. These events, and other efforts to engage parents, have laid a good foundation for parental engagement as evidenced by the very high enrolment levels outlined under indicator 2.1. Given that it is not possible to report accurately on the targets for this indicator and that all of the anticipated meetings were not held but that many other forms of parents’ meetings were held, this indicator scores “C” in this annual review.

Indicator 2.3. The milestones for this indicator have not been met. The percentage of girls attending weekly sexual and reproductive health trainings is 68.5% in Nairobi against a target of 75%. The result for Wajir is not yet known as the attendance data are still being collected and/or uploaded, however, the available data for Wajir suggests attendance levels around 58%. As a result, the score for this indicator is “B”. The delay in collecting data for Wajir arises from the fact most villages in Wajir do not have network connectivity. This means that the data recorded with the Open-Kit Data (ODK) data collection software on Android tablets have only been uploaded once SCI staff are back in the SCI office in Wajir town, resulting in delays in data collection. Looking forward, it will be important to ensure that the “enabling” environment for the safe spaces meetings is both understood and facilitated. There is some anecdotal evidence to suggest that both girls and mentors in Nairobi have not always found the meeting venues conducive.

The results outlined above are all the more impressive given the challenges experienced in rolling out AGI-K. During health mentor training in Wajir, the curricula had to be modified to respond more appropriately to the context in Wajir. The nomination of qualified health mentors was difficult and time-consuming given the very low levels of adult literacy in Wajir. In addition, following 8 days of mentor training in Wajir, a substantial number of the trained group decided that the pay was too low and resigned from the programme. This required additional recruitment efforts to find new mentors. Going forward, it will be important to monitor mentor activities closely and develop risk mitigation strategies for mentor resignations/demotivation. It will be important also to register, if possible, the girls who were identified for enrolment in both Kibera and Wajir but have not yet been registered due to parental resistance.

Indicator 2.4. As outlined above, this indicator scores “A” based on the strong progress in finalising robust and reliable baseline values and establishing targets for 2017 and 2019.

Indicator 2.5. As outlined above, this indicator scores “A” based on the strong progress in finalising robust and reliable baseline values and establishing targets for 2017 and 2019.

Summary of responses to issues raised in previous annual reviews (where relevant).
It was recommended that DFID finalize contract amendments so that partners could begin implementation. This has been completed.

Recommendations

1. In order to improve attendance at safe spaces meetings in Nairobi, it is recommended that PI and the mentors work to ensure an appropriately “enabling” environment (e.g. that there are no conflicts in meeting times and venues are conducive to mentorship meetings).
2. It will be important to record what measures were taken to improve attendance in safe spaces meetings in order to ensure any successful efforts are included in the eventual assessment of what has worked (or not).
3. In both Wajir and Nairobi, girls who were selected for enrolment but are not registered should be encouraged to enrol to the greatest extent possible.
4. Sensitization of parents and community leaders may need stepped up and more frequent efforts.
5. Contingency measures should be put into place to mitigate the programme implementation risks of mentors resigning or taking a temporary leave of absence.

Output Title	Adolescent girls benefitting from programme interventions in wealth creation improve their financial capabilities
Output number per logframe		3	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
3.1 Number of girls enrolled in safe spaces meetings in the wealth creation arm only (annual).	500 girls in Nairobi; 600 girls in Wajir enrolled in groups	681 enrolled in Nairobi; 860 in Wajir	A++
3.2 Average proportion of girls enrolled in program participating in weekly financial education trainings (annual).	Nairobi: 75%; Wajir 75%	62% in Nairobi; TBD in Wajir	C
3.3 Average proportion of girls with accounts/piggy banks making at least one deposit every 6 months into their savings accounts (Nairobi) or piggy banks (Wajir) (annual).	Baseline values: Nairobi: 1.7%; Wajir: 0%	Strong baseline process. Targets established for coming years	A
3.4 Mean score on financial education score (min: 0; max 10).	Baseline values: Nairobi: 5.7; Wajir: 4.1	Strong baseline process. Targets established for coming years.	A

As with output 2, excellent progress has been made in enrolling girls in the safe spaces meetings for the wealth creation intervention. This, combined with strong baseline data, results in an overall score of “A” for this output. However, as with output 2, it is clear from indicators 3.1 and 3.2, that there is a considerable difference between enrolment and attendance - attendance levels for the weekly meetings are already lower than anticipated. If, as might be expected, attendance levels diminish over time (as interest wanes and other priorities reassert themselves), as for output 2, it will be important to ensure that no unnecessary factors contribute to poor attendance (e.g. inappropriate meeting venues). As with the health intervention, it has been notably challenging to nominate, train and retain financial literacy mentors.

Indicator 3.1. Excellent progress has been made in enrolling girls in the wealth creation programme resulting in enrolment targets for both Nairobi and Wajir being exceeded by a considerable degree for the reasons described above.

Indicator 3.2. As above, the milestones for this indicator have not been met. The percentage of girls attending weekly financial trainings is 62% in Nairobi against a target of 75%. The result for Wajir is not yet known as data is still being collected and uploaded, however, the available data suggests attendance levels at 62%. As a result, the score for this indicator is “C”.

Indicator 3.3. As outlined above, this indicator scores “A” based on the solid progress in developing robust and reliable baseline values and the establishing of targets for 2017 and 2019.
Indicator 3.4. As outlined above, this indicator scores “A” based on the solid progress in developing robust and reliable baseline values and the establishment of targets for 2017 and 2019

Summary of responses to issues raised in previous annual reviews (where relevant). The recommendation was for DFID to finalize the contract amendments so that partners could begin implementation. This was done.

Recommendations

As for output 2.

Output Title	Adolescent girls benefitting from programme interventions in violence prevention experience decreased exposure to violence
Output number per Logframe		4	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
4.1 Number of violence prevention community meetings held (annual).	7 in Nairobi; 80 in Wajir	14 meetings in Nairobi; 0 meetings in Wajir	C
4.2 Average percent of items in community contracts implemented (cumulative).	N/A	N/A	N/A
4.3 Percent of girls who reported experiencing violence in the previous year who sought help	Baseline values: Nairobi: 56%; Wajir: 25%	Strong baseline process. Targets established for coming years	A
4.4 Percent of girls who report that any type of wife-beating is justified	Baseline values: Nairobi: 50%; Wajir: 51%	Strong baseline process. Targets established for coming years.	A
4.5 Percent of girls in Wajir who report that they intend to circumcise their daughters	Baseline value: Wajir: 87%	Strong baseline process. Targets established for coming years.	A

As with all four AGI-K interventions, the violence prevention community mobilisation interventions only began in the second half of the review period and progress has been mixed thus far. To date, in Nairobi seven violence prevention community groups have been formed; training was held for the group facilitators; and the first two violence prevention community meetings have been held. In Wajir, given the scope of intervention (79 villages), it was not possible to train nearly 160 community group leaders and instead a much smaller group of trainers has been trained to, in turn, train the community group leaders in the first quarter of 2016. The first violence prevention community meetings are scheduled for Wajir for the first 3-6 months of 2016. Indicator 4.1 therefore scored “C”. With a strong baseline process, however, resulting in excellent data now available for AGI-K, output 4 scores “A” overall, all indicators considered.

Indicator 4.1. The target for this indicator for Nairobi was exceeded but missed completely for Wajir resulting in a score of “B”. 14 meetings took place in Kibera against a target of 7. No meetings have taken place so far in Wajir although these are scheduled for early 2016. As outlined above, the reasons for the delays in Wajir are largely logistical: SCI is working with 79 villages across 30,000 km in a region with poor roads that is insecure and prone to violent clashes.

Indicator 4.2. Although it is too early to expect “contract” activities to have been achieved, some progress has been made in laying the foundations for this to happen. See above for the formation of the violence prevention community groups.

Indicator 4.3. As outlined above, this indicator scores “A” based on the strong progress in finalising robust and reliable baseline values and establishing targets for 2017 and 2019.

Indicator 4.4. As outlined above, this indicator scores “A” based on the strong progress in finalising robust and reliable baseline values and establishing targets for 2017 and 2019.

Indicator 4.5. As outlined above, this indicator scores “A” based on the strong progress in finalising robust and reliable baseline values and establishing targets for 2017 and 2019.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations

1. Consider delaying the collection of endline data given the delays in programme implementation.
2. Consider hiring temporary staff to assist with fast tracking implementation.

Output Title	Adolescent girls benefitting from programme interventions in education improve school enrolment and attendance
Output number per Logframe		5	Output Score	B
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
5.1 Number of registered girls receiving the first cash transfer payment which is conditioned on enrolment (annual).	Nairobi: 1,675; Wajir 1,920	Nairobi –1,676; / Wajir – 1,405	B
5.2 Average percent of eligible cash transfer payments made on time (annual).	75%	76%	A
5.3 Average percent of registered girls receiving first payment meeting 80% school attendance (annual).	85%	N/A	N/A

The AGI-K cash transfer programme encountered significant challenges in the period under review, namely the nationwide teachers’ strike in September and October, when nearly all public schools were closed, and the banking conditions in Wajir. As a result, only one of three indicators met the milestone targets for the period under review and this output as a whole scores “B” in the annual review. With schools now open for the beginning of the new school year, and efforts underway to establish bank accounts for all cash transfer recipient households, the outlook for 2016 is positive. In addition, school kits have been distributed to 3526 girls (out of a total of 4,049 listed beneficiary girls); school fees have been paid for 3897 girls to 225 schools (out of a total of 4,049 listed beneficiary girls in 227 schools); and the attendance monitoring system in all schools has been well established, including biometric attendance data collection.

Cash transfers conditional on school attendance have had mixed results internationally and in Kenya. It will be important to ensure that attendance data is scrutinised closely so that it is reliable (the biometric data collection will help in this process), and to monitor closely the human and financial costs of implementing such a scheme to evaluate its replicability. Efforts should be made to collaborate with other cash transfer programmes in Kenya to share lessons and understand the broader implications of AGI-K.

Key Points

Indicator 5.1. There have been mixed results for this indicator. In Nairobi, 1,676 registered girls received their first cash transfer (against a target of 1,675) while in Wajir the target was missed by a considerable margin with only 1,405 registered girls receiving their cash transfer (against a target of 1,920). As a result, this indicator scores “B” in this annual review. This first cash transfer is conditioned on enrolment.

The main challenge in Wajir has been that 27% of beneficiary households do not currently hold bank accounts. Establishing accounts has proven difficult given that many households do not have the official identity documents required by banks. PC and PI aim to meet with Equity Bank to discuss how best to fast track this process and consider alternative approaches.

Indicator 5.2. Overall, 76% of planned cash transfer payments were made on time against a target of 75% resulting in a score of “A” for this indicator. This breaks down as follows: in Nairobi, the first cash transfer payment was made on time (September 2015) while the second was delayed due to the teachers’ strike (November 2015 instead of October 2015 as planned). In Wajir, the first cash transfer payment against enrolment was made on time (October 2015).

Indicator 5.3. N/A. Due to the teachers’ strike in the last quarter of the school year, it was not possible to condition cash transfers on school attendance (schools were closed). However, nearly 100% of registered girls in Kibera enrolled in school, representing a very strong foundation for this component of the overall AGI-K programme. In Wajir, 28% of the girls registered for the cash transfer programme were out of school at the time of AGI-K registration. This number has dropped to 17%.

Recommendations

1. In Wajir, prioritise establishing bank accounts, to the extent feasible, for households with girls eligible for cash transfers. In parallel, map out the risks associated, if any, with a lower than planned number of cash transfer recipients.
2. Ensure plans are in place to tackle the backlog of cash transfers upon bank account set-up.
3. Continue spot checks to verify and collect attendance data

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

AGI-K is able to compare its costs to another, similar programme – the Adolescent Girls’ Empowerment Program (AGEP) in Zambia. This is helpful but further analysis will be needed to ensure comparisons are meaningful.

Cost analysis

The AGI-K costs are disaggregated as follows: staff 15.5%, data collection 11% and sub awards to implementingpartners 41%. For AGEP in Zambia, costs are disaggregated as follows: staff 24%, data collection 26% and sub awards to implementing partners 16%. There are good reasons for the major differences. On staff, AGI-K has contracted well-experienced, international NGOs whilst AGEP is working with a smaller, national NGO. PC support and oversight requirements for AGEP in Zambia are thus higher. Data collection costs are lower for AGI-K as only three rounds of data will be collected in Kenya compared to five rounds in Zambia.

Key cost drivers

The remote, vast and difficult terrain in Wajir is the main cost driver for AGI-K. SCI transport costs are 30.4% compared to 2% for PI working in Nairobi. At the same time, SCI M&E costs are 19% which, while more than DFID’s recommended ceiling of 15%, can be considered appropriate given the 79 villages being monitored and the intensity of start-up activities.

Partner actions to maximise VfM

Economy: AGI-K partners have worked to keep costs low by ensuring (i) competitive recruitment processes benchmarked to the local market, (ii) community-based venues for meetings rather than hotels, (iii) locally delivered training to reduce participant travel and accommodation costs, and (iv) careful negotiation of staff time in partner contracts, whilst maintaining quality of outputs, These negotiations have led to a variety of savings across the programme.

Efficiency: (i) SCI and PI are using biometric technology to track girls’ attendance lowering the cost of monitoring (ii) SCI and PI are also training trainer trainers to reduce training costs, (iii) PC has established an efficient system for monitoring the quality of data collection using only three rounds of data collection rather than five as in Zambia; and (iv) joint procurement for both Wajir and Kibera sites leading to efficiency savings from economies of scale.

VfM performance compared to VfM proposition in the Business Case

The Business Case for AGI-K was approved in December 2012 for £12.96 million to reach 10,000 girls. The same research outcomes will now be achieved with a budget of £9.96 million.

Assessment of whether the programme continues to represent value for money

- Results: AGI-K has scored “A” in this and the last annual review.
- Theory of Change: Remains valid.
- Risks: The risk rating remains at Medium (see below).
- VfM practices: Good measures are in place to cap costs
- VfM measures: These are reasonable, although going forward the analysis should be further deepened to include specific costed examples on efficiency savings.

Recommendations

1. Implementing partners to report quantitative data semi-annually (March and September) via the agreed VfM Actions Template.
2. Ensure uniform financial reporting across all partners using similar template.
3. Partners to use benchmarking data across comparator programmes to allow for robust cost comparisons.
4. Ensure quality assurance of implementing partner efficiency savings.

Quality of financial management

Overall, financial management during this period has been satisfactory. A milestone-based payment plan is in place with PC. Payments are made subject to satisfactory proof of milestone completion. In addition, PC submits a bi-annual statement of expenditure, presenting data by output as well as type of expenditure which is analysed by DFID. 2015/16 spend is on track and stands at 99%.

All partners have provided their appropriate audited annual statements which were unqualified (true and fair).

Date of last narrative financial report	June 2015
Date of last audited annual statement	PI, June 2014, / PC, 31 December 2014 / APHRC, 31 December 2014, / SCI, 31 December 2014 / Itad, January 2015

E: RISK

Overall risk rating: Medium

Lack of research uptake by GoK: Impact: “High”. Likelihood: ‘Medium’. The work under Output 1 will mitigate against this risk by supporting activities to foster policy advocacy and research uptake. Over the review period, key GoK officials, bi-lateral aid organisations, foundations, and multi-lateral organisations in Kenya were invited on 29 September, 2015 to participate in the baseline data dissemination. Senior DFID Kenya staff used also opportunities available in their negotiations with GoK and other donors to engage in policy conversations to influence AGI-K research uptake. As outlined above, there is scope to refine and improve the AGI-K influencing strategy.

Security: Impact: “High”. Likelihood: “Medium”. In both Wajir County and the informal settlement of Kibera security remains a high concern. In Wajir, terrorist attacks and inter-clan conflicts have already disrupted or delayed some field activities and this is likely to continue in the coming years. SCI long-standing presence in Wajir, and its understanding of how best to operate in this environment and manage risk, go some way to mitigating this risk. In Kibera, the security risks are harder to predict. While there is no known terrorist threat, the situation in many informal settlements in Nairobi is volatile. It will be important for PI to continue monitoring the situation closely and maintain well developed systems to ensure the safety of their staff.

Contamination/Quality of research findings: Impact: “High”. Likelihood: “Low”. There are a high number of organisations undertaking research activities within AGI-K sites. This has the potential to compromise the quality and strength of AGI-K evidence due to contamination. PC will continue to proactively engage with others to minimise this risk. In addition, with already low attendance at the safe spaces meetings, there is a real risk that the quality of research findings will be affected if those who do not attend are different on key characteristics compared to those who do attend. Every reasonable effort should be made to maintain or increase attendance.

Loss of UKaid funds through fraud: Impact: “Medium”. Likelihood: “Low/Medium”. PC has conducting measures are in place to manage and mitigate fiduciary risk. PC has conducted due diligence assessments on the contracted partners and is working closely with partners to mitigate or eradicate identified risks. PC and DFID staff undertake periodic spot checks on partners to ensure effective programme implementation. Strong programme monitoring systems (e.g. biometric data collection) are in place.

Lack of an effective consortium: Impact: “Medium”. Likelihood: “Low”. Each of the consortia partners plays a significant role in the delivery of AGI-K. Over the past year the consortium partners have demonstrated a high level of commitment. The ability of the consortium partners to carry out proposed activities along agreed timelines and costs has been demonstrated despite the challenges faced in Wajir. All consortium partners have clearly defined TOR, and a partners’ forum has been developed that enables partners to share lessons and experiences. Since the last AR, meetings are now held frequently between all partners to ensure effective communication, continuity in services delivered, and a high quality research design. In addition, a planned visit by Plan staff to Wajir will happen early in 2016, as well as a visit by SCI staff to the Nairobi site. Efforts to share lessons across partners should continue.

Acceptability: Impact: “High”. Likelihood: “Low”. A low risk for AGI-K is that the communities will refuse to allow the interventions to be implemented and/or the data to be collected. This past year this risk has been greatly minimized through intensive community sensitization efforts prior to data collection and implementation of the interventions themselves. The national- and county- level EACs are also important as advocates for AGI-K and the momentum behind these should be maintained. Given the nature of risks to the programme, AGI-K should continue to put in place systems to regularly assess ‘conflict sensitivity’ and continue to perform community sensitization activities. Failures and delays to deliver the cash transfer programme in Wajir should be carefully managed to mitigate conflict with households and communities.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

As explained above, AGI-K is now largely on track. Key concerns remain delays in implementation of the violence prevention intervention in Wajir and difficulties in establishing bank accounts for 27% of cash transfer households in Wajir. While it is anticipated that the violence prevention intervention will pick up pace in 2016, the prospects for the establishment of bank accounts in Wajir is less positive. Alternative approaches are under review but if a rapid and effective solution cannot be found this will represent a key risk to the programme both in terms of what it might mean for the research design and the potential conflict with disappointed households and communities. Reviewing progress in implementation in Wajir will require sustained efforts in 2016 to maintain the momentum that has been built up in the latter half of 2015.

Performance of partnership

AGI-K is implemented by a consortium consisting of PC, APHRC, Itad, SCI and PI, all with a proven track record in Kenya and other regions. The programme has a functional management structure for programme oversight which includes the Expert Research Committee and External Advisory Committee. Key performance indicators for the programme and a revised logframe were agreed in 2015 all of which set out clear performance expectations. DFID and PC hold monthly meetings with clear lines of responsibility on actions. As part of the annual review process, DFID staff met all implementing partners and their feedback suggests a positive and effective consortia. At the last AR there was a need for some clarity between the roles of PC and that of APHRC. This has since happened, with APHRC having been responsible in supporting PC on data collection and analyses. The partners meet monthly in order to monitor performance.

Asset monitoring and control

The asset list is maintained by PC and is up-to-date. A spot check calendar is in place and verification of assets will be undertaken through spot checks by DFID and PC staff. During this review period, assets were procured by a DFID procurement agent.

G: CONDITIONALITY

Update on partnership principles (if relevant)

AGI-K does not use government financial systems for delivering its results. DFID Kenya has judged that the partnership principles do not apply in the detailed management and monitoring of this programme.

H: MONITORING & EVALUATION

Evidence and evaluation
AGI-K is a randomized control trial that is designed to answer the following two research questions:
1. Which combination(s) of interventions in violence prevention, education, and health and wealth creation produce(s) the greatest change in the well-being of adolescent girls?
2. What is the most cost-effective way to achieve the greatest impact for adolescent girls?

Although a critical risk to the programme remains that AGI-K’s interventions have a less than anticipated impact on key outcome indicators - and thus little impact on policy and budget allocations for adolescent girls in Kenya. However, although attendance at health promotion and wealth creation meetings is already lower than expected in Nairobi, there is no reason at this point to interpret this as a failure in approach. In the coming year, it will be important to monitor dropout from the different interventions to ensure that the required statistical power is maintained. There is a need also to clarify the scope for implementation risk mitigation (e.g. changing programme activities to prevent beneficiary dropout or non-attendance) against the integrity of the research.

Monitoring progress throughout the review period

The monitoring activities for this review period have been largely around baseline data collection and the beginning phases of implementation of the interventions. The Population Council established a system for monitoring the quality of data collection – including using electronic data capture with pre-programmed consistency checks to minimize errors in the data – and this has been shown to be effective. The design of the intervention monitoring system has begun, including the use of a web-based system, combined with multiple mobile applications for attendance data collection. These allow for regular, timely and accurate monitoring of intervention activities. In most villages in Wajir there is no network connectivity, requiring SCI staff to visit each community in order to retrieve the monitoring data for later input at the SCI office in Wajir town. For baseline data collection, tools to monitor interviewer productivity on a daily basis were used so that any drops in performance could be addressed immediately. These tools have been used by both the implementing partners for direct monitoring, as well as the PC for overall quality control and reporting to DFID.

This annual review was initially carried out by one international and one Kenya-based consultant over a period of 43 person days. The consultants carried out a desk review of relevant documents; conducted field visits to Wajir and Kibera; and met with all AGI-K partners as well as DFID Kenya staff , Sandra Barton (Education Adviser) and Sophia Chemei (Senior Programme Officer). The final version of this annual review was drafted by DFIDK staff based on the consultants’ findings and conclusions. The output scores remain the same.

DFID Kenya’s Kenya Accountability and Results Team reviewed and approved the final draft.