Annual Review

Title: Unitaid
Programme Value £ (full life): 790 million		Review Date: November 2019
Programme Code: 111074	Start Date: February 2007	End Date: March 2026

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017	2018
Programme Score	A	A	A	A	A+	A+	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate
Year	2019
Programme Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	Project Approved prior to Business Cases
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-111074/documents

A. Summary and Overview

Description of programme

Established in 2006 by Brazil, Chile, France, Norway and the UK, Unitaid is a global health initiative and hosted partnership of the World Health Organisation (WHO). Unitaid is a small but significant and high-performing player within the global health landscape. It aims to improve access to medicines, diagnostics and preventative items for people affected by HIV/AIDS, TB and malaria (the three diseases) and their related co-morbidities in lower income countries. Through calls for proposals, Unitaid finds partners best qualified to put key innovations into practice. Unitaid provides these health partners with financial grants, designed to fast-track access and reduce costs of more effective medicines, technologies and systems. In this way, Unitaid’s investments shape the market and establish the viability of quality health innovations, allowing partner organisations to make them widely available by tackling various access barriers such as affordability.

By bridging the gap between upstream product innovation and downstream programmes, Unitaid offers a mechanism to bring promising new health technologies, such as medicines and diagnostics, to scale. One example of this is Dolutegravir – a new optimal ARV to effectively treat HIV/AIDS. As a result of work done by Unitaid and its partners the cost of this WHO-recommended first line optimal ARV was reduced significantly to $69 per person per year and the drug is now being taken to scale by the Global Fund to Fight AIDS, Tuberculosis and Malaria (The Global Fund).

The UK remains the second largest donor (21%) after France (58%). The UK has a 20-year donor arrangement with Unitaid within which three-year funding tranches are agreed. Our contribution for the current funding tranche (2018-2020) equates to average of £44m per year. Within the UK’s wider health portfolio, Unitaid improves the cost effectiveness of the UK’s bilateral, multilateral and research funding for the three diseases. For example, Unitaid enhances the impact and reach of our Global Fund spend by bringing new, improved medicines through the pipeline quicker and at reduced prices. Unitaid also makes an important contribution to the fight against Antimicrobial Resistance (AMR) by expanding access to the right WHO-recommended diagnostics and treatments and reducing the risk of resistance emerging.

Summary supporting narrative for the overall score in this review

Unitaid has performed well against all outputs, and in some cases exceeded expectations. To reflect this continued positive trajectory and strong performance against high expectations, Unitaid scores an A in the current review period. This annual review assesses performance against outputs in the first year of the 2018-2020 funding tranche. The logframe indicators align with a selection of strategic and operational Key Performance Indicators (KPIs) agreed by the Executive Board (EB), on which the UK has a seat, in 2016.

At the end of 2018, the total value of the Unitaid portfolio was $1.14 billion, split across HIV/AIDS and co-
infections/co-morbidities, tuberculosis, malaria and other cross-cutting areas, as detailed below.

Portfolio area	Grants	Grant value / (US$ millions)	% of overall
HIV and COIMs	22	496	44%
TB	6	215	19%
Malaria	10	301	26%
Cross-cutting	7	129	11%
Total	45	1141	100%

These areas of intervention reflect Unitaid’s mission to accelerate equitable access to innovations for the poorest and the underserved.

The recent mid-term review of Unitaid’s 2017-2021 strategy also highlights impressive progress in strengthening Unitaid’s operational model. Unitaid now has well-structured processes to scan the global health landscape for opportunities within its focal diseases, define areas for intervention, solicit applications and review grant proposals. Unitaid is also exhibiting strong programme delivery and portfolio management, with substantial improvements in monitoring, risk management and course-correction in recent years. Operationally, Unitaid has improved its efficiency whilst maintaining a lean Secretariat.

This progress provides a platform at the midpoint of the strategy for a discussion of the future priorities and direction of the organisation. Within the current strategy there has already been a shift beyond the core three diseases mandate into co-infections and co-morbidities (e.g. work on Hepatitis C, childhood fever management and cervical cancer). Unitaid has also engaged increasingly with the fight against AMR. The UK has been supportive of this evolution and we strongly believe that we should be seeking ways to deploy the model more widely. The Board and Secretariat are exploring the most rational directions in which to expand the model within a suitable framework. Unitaid has secured additional contributions this year and is making steps towards securing further annual commitments. Unitaid continues to demonstrate excellent Value for Money (VfM), both in terms of the aims and outcomes of its projects, and through its processes.

Recommendations for the year ahead

Output	Recommendation
1.1	Unitaid should develop a prioritised, clear and strategic framework for identifying higher risk, innovative opportunities that will utilise Unitaid’s unique position in the global health architecture to achieve maximum impact. Learning should be used effectively, and level of Board involvement agreed.
2.2	Unitaid to use analysis of the root causes behind the late disbursements to address issue where possible.
2.3	Unitaid should work with implementers to ensure that critical recommendations are feasible, and facilitate identification of root causes where possible to improve efficiency and effectiveness in areas for improvement.
3.3	Unitaid to gather further data disaggregated by age, sex and disability, to ensure inclusion of different groups
3.5	Unitaid and DFID’s safeguarding unit to work together to develop policy for more robust monitoring of safeguarding. Unitaid should also present the findings from their biannual staff survey to the Board or committees once completed for 2019. DFID to share examples of questions from the DFID People Survey.
4.1	Unitaid will need to utilise a clear, prioritised and strategic resource mobilisation strategy, using all levers at their disposal. For the remainder of the current strategy, expanding into new areas beyond the three diseases should not use resources redirected away from the three diseases, but rather new funding
4.4	Unitaid should make questions more open-ended and adjust the survey to follow up on areas for improvement identified in the last survey.

## B: DETAILED OUTPUT SCORING

Output Title	Effective Implementation of the Unitaid 2017-21 Strategy
Output number per LF		1	Output Score	A+
Impact weighting (%):		25	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Completion of Mid Term Review of Unitaid Strategy 2017-2021 on time and to a high standard	a) Mid Term Review completed, to a high quality, responding to strategic and donor priorities on process and content b) Board endorses a set of recommendations as an outcome of the MTR process.	a) The mid-term review of the Strategy was completed on time, to a high quality, in a highly consultative manner, receiving positive feedback from across the Executive Board. / b) The Executive Board endorsed the recommendations of the mid-term review and formally adopted the report at the June 2019 Executive Board. / Output met expectation (A)
1.2 Percentage of active grants designed to benefit the poorest / [KPI 5.1 Investing for the poorest]	100%	100% / Output met expectation (A)
1.3 Percentage of active grants designed to benefit the underserved / [KPI 5.2 Investing for the poorest and underserved]	100%	100% / Output met expectation (A)
1.4 Percentage of portfolio (by number of grants) addressing AMR	>50%	60% / Output moderately exceeded expectation (A+)
1.5 Percentage of portfolio (by number of grants) support a more integrated approach	>50%	73% / Output moderately exceeded expectation (A+)

Supporting narrative for the score

Output 1.1.
Quality and responsiveness to strategic and donor priorities:
The mid-term review (MTR) focused on three objectives:
- Progress in strategy implementation – a review of how well Unitaid is delivering against its Strategy.
- Operating model – a review of Unitaid’s progress on the four operating model priorities and its agility
- Opportunities – key opportunities for Unitaid to maximise impact by 2021 and beyond.
On progress in strategy implementation, the review found that Unitaid has made highly impactful progress. Its innovations bring impact in five ways: increasing efficiency, optimising resources, empowering individuals, reaching underserved groups, and addressing resistance issues. Lessons learned include the variability of scale-up across countries and products. In respect of the operating model, Unitaid has improved its speed of grant development, its ability to right-size grants for funding approval (generating net savings of $110m from initial proposal to final grants) and has diversified its pool of proponents and implementers. Looking forward, Unitaid needs to ensure that its model is agile enough to respond to global health needs and innovations whilst maintaining a strategic focus in line with its mandate. Finally, on opportunities, to respond to evolving needs in health (e.g., increased focus on Universal Health Coverage (UHC)) and to the changing innovation landscape (e.g., expansion beyond the drug, diagnostics and preventatives space), the MTR was less strong. Discussions are ongoing on a strategic and practical approach to identify and take forward future opportunities.

Unitaid is implementing actions falling out of the review, notably the roll-out of a ‘Scalability Framework’ and encouraging closer collaboration with key scale-up partners.

Following the PSC discussions, there was a retreat that concluded that the existing model was largely fit-for-purpose for most of the portfolio but that more flexible approaches may be warranted in exceptional circumstances. The retreat discussed the creation of a funding window that would allow for potentially higher risk, more innovative and more transformative opportunities to be pursued – with a greater level of delegated authority to the Secretariat for decision-making. This envelope should be framed within a clear set of principles/parameters that would provide the strategic framework for the window and assurance to the Board.

Output 1.2. and 1.3 These output indicators are assessed against new projects starting within a given calendar year, in this case 2018. The same positive result was also achieved in 2017. “Poorest” is defined as low- and lower-middle income countries, as classified by the World Bank. “Underserved” relates to disease-specific categorisations. For example, with TB this could include those living in extreme poverty and high-risk groups such as prisoners.

Output 1.4 Unitaid’s Strategy places strong emphasis on Antimicrobial Resistance (AMR) - making investments to address the challenge of resistance to medicines and preventives in the three diseases. Unitaid also has an important role in the UN Interagency Coordination Group on Antimicrobial Resistance. 29 of 48 (60%) active grants and new investments (65% of the overall portfolio value) address AMR in some form. Examples include:
- New tools for Vector Control, covering 3rd generation indoor residual spray, the new nets project, Ivermectin and Spatial Repellents.
- Accelerating access to optimal HIV treatments, such as dolutegravir, which has a stronger genetic barrier to resistance, which are supported by multiple clinical trials.
- Recent investments in multi-drug resistant TB such as adherence technologies and platforms to monitor the spread of resistance.
Output 1.5 Unitaid’s Strategy places strong emphasis on integrated approaches to enable access to a health product that addresses more than one disease or condition (e.g., polyvalent diagnostic platforms); address the needs of people affected by more than one disease (e.g., treatment of co-infections); reach people for one health issue through a different programme or clinical interaction (e.g., leveraging child health programmes to diagnose malaria in children). In July 2019, 35 of 48 (73%) active grants and new investments (76% of the overall portfolio value) help to address integration in some form, for example through investing in point-of-care diagnostics spaces to test for HIV, TB and Hepatitis C.

Lessons identified this year, and recommendations for the year ahead linked to this output
Output 1.1 Unitaid should develop a clear, strategic framework and utilise flexible, responsive window of funding that could allow for potentially riskier, more innovative, more transformative opportunities to be pursued. This funding envelope should be framed within a clear set of principles/parameters that would provide the strategic framework for the window and learning from initial investments should be gathered and used ahead of investing in further investments through this window. The Secretariat and Board should discuss how to most efficiently involve the Board in prioritisation of future investments.

Output Title	Efficient and effective grant implementation
Output number per LF		2	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1. Average time taken from Grant Agreement Development (GAD) kick-off to GAD submission to Executive Board. [KPI C Speed of grant development]	6 months	5.6 months / Output moderately exceeded expectation (A+)
2.2. Proportion (%) of disbursement requests executed within 8 weeks of request received. [KPI E Disbursement efficiency]	85%	82% / Output met expectation (A)
2.3. Proportion (%) of grants implementing critical recommendations identified in semi-annual/annual reviews in a timely manner. [KPI F Grantee responsiveness]	95%	86% of grants; 94% of recommendations / Output met expectation (A)

Supporting narrative for the score

Output 2.1 Unitaid’s operational KPI C measures the average time between the kick-off of a grant agreement development (GAD) process to the point of submission to the Board for review. Successful applicants then receive a formal “go-ahead” and work with the Secretariat staff develop a concrete project plan with clear activities, deliverables, project countries, budgets and timelines which are sufficient to deliver on the intended impact of the Area for Intervention. The final step is submission of the full grant agreement to the Board for funding approval.
In 2018, 12 GAD packages were submitted for approval. Given the pivotal role it plays in Unitaid’s operating model, the GAD process has been an area of focus for process streamlining to support meeting and exceeding, the GAD timeline target of 6 months, through additional guidance, simplification of processes, and fast-tracking the process where applicable. Over 2018, Unitaid successfully reduced the length of grant development from 6.5 months in 2017 to an average (mean) of 5.6 months in 2018.

Output 2.2 Unitaid’s operational KPI E measures the percentage of disbursement requests executed by the Unitaid Secretariat within 8 weeks of a complete disbursement request being received. The data reported here covers all active grants from 1 January to 31 December 2018.

In 2018 Unitaid made 51 disbursements to its grant implementers, totalling $161 million. Unitaid typically disburses funds twice per year for each grant. There was no Board-level target for 2018 for operational KPI E. Instead, the target is set to reach 100% of disbursements being executed within 8 weeks by the end of 2019. For the DFID annual review, an intermediate target was agreed of 85%.

In 2018, 42 (82%) disbursements were executed in 8 weeks or less and 100% within 12 weeks. Compared to 2017, the proportions of disbursements executed within 8 and 12 weeks have both increased by 10% (from 72% to 82%, and 90% to 100% respectively). Of the 9 disbursements which were beyond the 8-week target, 2 (i.e. approximately 4%) were delayed for specific grant management related reasons. One was due to a decision to wait until a financial audit was completed to disburse, the other due to the finalisation of a reprogramming exercise. In both cases, the projects in question had adequate financial resources to continue operations. The average time to execute a disbursement request was also reduced from 6.5 weeks in 2017 to 5.7 weeks in 2018.

Output 2.3 A critical component of programme management is the timely implementation of critical recommendations, identified in semi-annual and annual reviews, and communicated to grant implementers. Operational KPI F measures the responsiveness of grant implementing partners to action recommendations made by the Secretariat, in line with case-specific deadlines. There is no Board-level target KPI F in 2018. For the DFID annual review, an intermediate target was agreed of 95%. The performance on KPI F for 2018 is 86% (24 of the 28 grants in scope) of the grants implemented all the critical recommendations identified.

Looking at the performance in terms of the number of recommendations that have been implemented (instead of the number of grants), offers a more nuanced picture. Out of the 161 critical recommendations identified, 152 were implemented in a timely manner (94%). Of note, the number of recommendations issued by the Secretariat has doubled from 2017 to 2018, while the number of grants increased by a third. The recommendations have also shifted from being mainly operational to being more strategic and programmatic, occasionally depending on external factors outside of the grant implementers’ control.

Lessons identified this year, and recommendations for the year ahead linked to this output
Output 2.2 The Secretariat has undertaken an in-depth analysis of the root causes behind the late disbursements and should aim to address each case individually and encourage on-time disbursement for all grants. Some proposed changes to this KPI will be made at the Policy and Strategy Committee (PSC) in October 2019 to better reflect the lessons learned from the monitoring of this indicator.

Output 2.3 Unitaid should work with implementers to ensure that the recommendations are feasible and to identify root causes where possible. Some proposed changes to this KPI will be made at the PSC in October 2019 to better reflect the lessons learned from the monitoring of this indicator.

Output Title	Unitaid governance, management and operational work is economical, efficient and effective and embraces equity consistent with its New Operating Model
Output number per LF		3	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1. Unitaid Secretariat annual operational expenditure as a % of total value of Unitaid grant portfolio. [KPI A Secretariat efficiency]	2%	1.87% / Output met expectation (A)
3.2. International Aid Transparency Initiative’s (IATI) score for reporting financial information for all active grants	75	86 / Output moderately exceeded expectation (A+)
3.3. Strong assessment of Impact and Value for Money / Strong performance could be demonstrated through effective analysis of Impact and Value for Money at both the grant- and portfolio-level.	All new projects have a robust results framework to appropriately measure impact and Value for Money.	All new projects have a robust results framework and steps have been taken over the last year to further strengthen Unitaid's approach to impact and VfM, including through rolling out an Impact Cost and Risk tool. / Output met expectations (A)
3.4. Strong active risk management at portfolio and grant level and proportion (%) of grants with an up-to-date risk review. [KPI H Risk management]	100% of grants with up-to-date risk review and evidence of strong active risk management at portfolio and grant level	100%. List of examples of proactive steps provided in narrative / Output moderately exceeded expectations (A+)
3.5. Robust safeguarding policy and its effective implementation.	The Secretariat to a) undertake proactive steps to ensure the awareness of the WHO safeguarding policy, and specific legal obligations and policy initiatives to grant implementers and contractors, and b) effective coordination with close partners (such as The Global Fund and Gavi) to benchmark standards and best practice in safeguarding	The Secretariat has promoted awareness of the WHO safeguarding policy, and specific legal obligations and policy initiatives to grant implementers and contractors. This includes the inclusion of clauses in grant agreements to ensure compliance, a session on Safeguarding during the 2019 grant implementer forum and coordination with The Global Fund to benchmark standards and best practice / Output met expectation (A)

Supporting narrative for the score

Output 3.1 Operational KPI A measures the efficiency of the Secretariat in relation to the proportion of the Secretariat annual operational expenditure (as defined in the approved budget) relative to the size of the total grant portfolio being managed. At end 2018, the total value of the Unitaid portfolio was $1.14 billion, and Unitaid’s total annual Secretariat operating costs were $21.3 million. Thus, Unitaid’s Secretariat operating costs were 1.87% of the total size of the Unitaid portfolio, despite the portfolio expanding in both scale and scope. Within this funding envelope, the Secretariat manages the day-to-day operations of the organisation including identifying new areas for intervention, reviewing proposals, grant development and implementation, and managing external relations.

Output 3.2 As at 25 July 2019 the IATI score of 86, placed Unitaid 14th overall (out of more than 1,000 listed organisations), and 7th in the category of multilaterals. The score is based on assessment of three dimensions: Timeliness, Forward-looking and Comprehensiveness.

Output 3.3 All new projects have a robust results framework to appropriately measure impact and Value for Money. An Impact, Cost and Risk tool has also been rolled out and was used to support portfolio analysis for the grant portfolio update submitted to the Board for the June 2019 meeting. A by-product of this approach has been to help identify where different results frameworks can be further standardised. This refreshed approach has started to be used in recent GAD kick-off discussions.

Unitaid’s Results team has continued to collaborate with the Global Fund on impact and Value for Money, with a joint presentation planned for the November 2019 Unitaid Board, to include analysis of how innovation is helping to deliver the global health response.

Some of Unitaid’s projects have a specific focus which leads to the generation of data and evidence on disaggregated populations (e.g. by age, gender, disability), e.g. the clinical trials for Dolutegravir-based (DTG) regimens, where data is being collected on late-stage presenting pregnant women and to determine whether DTG has an impact on weight gain in some female populations. On more generalised investments, which target broad populations, the level of data disaggregation is considered on a case-by-case basis.

Ouput 3.4 Operational KPI G measures whether ongoing, proactive risk reviews of Unitaid grants are taking place and covers all 31 active grants from 2018. In 2018 all active grants had an up-to-date risk review. Project teams review risks at least twice per year, at semi-annual and annual reporting cycles, and may undertake more frequent risk reviews depending on the context of the project. Unitaid finalised the organisational-level risk register, the definition of risk appetite and the finalisation and approval of a Risk Management Policy. The Secretariat has also developed and rolled-out a risk library to provide a common set of risk definitions to improve the consistency of risk assessment across the portfolio.

Output 3.5 Unitaid completed an enhanced due diligence exercise for DFID covering safeguarding, whistleblowing, HR recruitment and selection, risk management, code of conduct, and governance and accountability. Unitaid has zero tolerance against Sexual Exploitation and Abuse (SEA), harassment and abuse of power in the workplace and operational settings. All Unitaid staff have completed a mandatory training on prevention of harassment, sexual harassment and abuse of authority and are re-trained every 3 years, in line with DFID’s requirements. Unitaid does not have in-country offices and Unitaid staff do not have direct contact with beneficiaries of the grants, and so much of the responsibility is devolved to grant implementers and downstream partners.

From March 2018 onwards Unitaid includes a clause in grant agreements specifically related to SEA. It set out Unitaid’s zero tolerance stance towards SEA, requires Grantees to take all reasonable and appropriate measures to prevent SEA, immediately report any incidents and ensure that any third-party recipients also comply with these provisions. From July 2018 onwards, Unitaid also included a new clause requiring the grantee to comply with all WHO Policies on wrongdoing, including WHO’s policy on Sexual Exploitation and Abuse Prevention Response. Unitaid is also planning to supplement the capacity assessment questionnaire, to further prospective grantees’ understanding of the safeguarding standards that are required to be cascaded down throughout their delivery chains. Additionally, a session at the 2019 grant implementer forum focused on the topic of wrongdoing, with an emphasis on safeguarding. The Secretariat will be strengthening further its SEA guidance, which will be formally communicated in a letter from the Executive Director to all grant implementers.

Finally, Unitaid works with the Global Fund to share best practice to align on standards both at the organisation and implementation/country level, learn from experiences, and explore sharing resources in countries that they both operate in.

Lessons identified this year, and recommendations for the year ahead linked to this output
Output 3.3 The Unitaid Secretariat should look for further opportunities to gather data disaggregated by age, sex and disability, to ensure that where programmes are not targeting a specific demographic (e.g. pregnant women), specific groups are not being inadvertently omitted.

Output 3.5 With grant implementers and downstream partners taking much of the responsibility for monitoring safeguarding issues with sub-grantees, Unitaid should put in place a robust system to monitor grantees’ actions and performance in this area, for which Unitaid will need to assess their Secretariat capacity. When it comes to investigating cases, Unitaid should consider linking up with Gavi and Global Fund systems. Due to the similar issues faced by other global health funds that DFID funds, DFID’s safeguarding unit should provide further guidance on monitoring. Unitaid should also present the findings from their biannual staff survey to the Board or committees once completed for 2019, and DFID should share examples of questions from the DFID People Survey.

Output Title	Coordinated partnership to ensure alignment and engagement
Output number per LF		4	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Net increase in annual commitments from 2016 baseline. [KPI B Resource mobilisation]	Increased staff and staff time dedicated to RM; Systematised engagement and outreach with prioritised potential donors; Successful engagement with stakeholders in donor countries and prioritised potential donors; $40m in additional annual commitments achieved.	Ongoing conversations with potential donors. An increase in $69.1m in overall contributions, including a jointly funded project on “New Nets” for which Global Fund contributed US$ 33 million, which DFID as match funding rather than an increase in annual commitments, leaving additional contributions at $36.1m. / Output moderately did not meet expectation (B)
4.2. Enhanced and well coordinated partnerships / Strong performance could be demonstrated through high-profile partnerships that clearly amplify Unitaid's impact or that align well with UK objectives.	Demonstrated evidence of multiple quality partnerships, co-investments, and collaborations that amplify Unitaid's impact	Unitaid continues to expand and enhance its partnerships with a wide range of partners in the global health arena. New strategic frameworks have been put in place with the Global Fund, UNICEF and the Government of Rwanda. Unitaid has a presence and visibility at a range of high-level discussions, including the G7 and G20. This includes having a prominent position in the ongoing activities related to mitigating and managing AMR. / Output met expectation (A)
4.3. Enhanced partner engagement. / Strong performance could be demonstrated by through partner engagement and key/flagship events that clearly amplify Unitaid's impact or that align well with UK objectives.	Strong demonstration of partner engagement to amplify Unitaid's impact (including with the private sector)	Strong, continuing partner engagement across a range of organisations, including through delivery of the second Grant Implementer forum in March 2019, engagement with the Global Fund and PEPFAR on project-specific issues, engagements with private sector industry. Unitaid’s Strategy team scan investment opportunities to align stakeholders on the most efficient and effective means of investing into the global response. / Output met expectation (A+)
4.4. Percentage of grantee satisfaction (%). / Measured on two questions: Q8 on effectiveness of partnership with Unitaid, and Q47 on overall experience with Unitaid. Positive responses are defined as very effective, effective, excellent, or good.	At least 85% positive on Q8, and 75% on Q47	Q8 - 82% (another 14% moderately effective) / Q47 - 77% / Output met expectation (A)

Supporting narrative for the score

Output 4.1 Over the last year, Unitaid has received a net increase in contributions of $69.1 million in 2018 compared to the 2016 baseline. The results were possible through two new funding opportunities: a £27 million additional contribution from DFID towards malaria control, and a jointly funded project on “New Nets” with the Global Fund in the amount of US$ 33 million. DFID views the latter contribution as match funding for a specific intervention and so would not include this as an increase in annual commitments, leaving additional contributions at $36.1m. DFID will work with Unitaid to secure further annual and multi-year commitments. We do, however, commend Unitaid for their innovative approach to raising additional funds for malaria and offsetting potential funding gaps for the investment plan in other areas.

In December 2018, a RM strategy was developed and presented at the December 2018 Board meeting. During 2018, Unitaid has engaged with six potential new donors through country visits, bilateral meetings with key decision-makers, organisation of multi-stakeholder events, and briefings with stakeholders at mission and capital levels. Unitaid has given priority to pursuing potential donors who are aligned with its mission and strategy and committed to a long-term engagement with the organisation. A potential new donor beyond those originally prioritised in the RM Strategy was identified in December 2018 with the support of the Board, and a funding proposal is currently under negotiation.

The recruitment of new long-term donors is a multi-year endeavour, particularly in the context of elections which often result in changes in development prioritie. In 2018, Unitaid decided to further strengthen its RM efforts by initiating the recruitment of a Senior Resource Mobilisation manager.

Output 4.2 Unitaid continued to expand and enhance its partnerships with a range of partners in the global health arena and over the past year. Key highlights include:
- Strengthened partnership with the Global Fund. In May 2019, Unitaid and the Global Fund signed a Strategic Framework for collaboration, which focuses on: Clear guiding principles and scope that includes working together in an evidence-based way; ensuring alignment; and recognition of the wider health ecosystem. A strategic approach to collaboration; and Alignment of implementation and oversight activities.
- In May 2019, Unitaid established a Memorandum of Understanding (MoU) with UNICEF to align their complementary efforts to end malaria, pneumonia, HIV, TB and cervical cancer, to expand access to innovative point-of-care diagnostics, and to improve fever management in children.
- Unitaid and Rwanda’s Ministry of Health signed a MoU to collaborate on better and more affordable health solutions for the people of Rwanda and beyond.
- In 2018-2019, Unitaid participated in G7 and G20 meetings on primary healthcare, AMR and UHC.
- Unitaid contributed to several global health initiatives related to AMR; notably, to chair the Subgroup on Innovation, R&D and Access of the UN Interagency Coordination Group on AMR (IACG).
- Unitaid was one of 12 signatories to the SDG3 Global Action Plan to align efforts to accelerate progress in global health. Unitaid Secretariat staff led the coordination and drafting of a section on investment case approaches and on alignment.
- Unitaid has increased its efforts in engaging with the G20, with the aim to i) continue the inclusion of health on the G20 agenda, (ii) drive increased political support via engagement with politicians, and (iii) advocate for the recognition of global health as a central economic factor of global development.
- At the G7 level, Unitaid participated in the Health Working Group meeting in Paris in April 2019. health care. Unitaid’s Executive Director also participated in the Health Ministers meeting in Paris.

Output 4.3 The Unitaid Secretariat engages with its partners and broader stakeholders in several ways, including through technical consultations, participation in international conferences and using major events such as the World Health Assembly to engage with other key investors and stakeholders. Unitaid’s move to the Global Health Campus in Geneva in August 2018 has also increased the efficiency and effectiveness of collaboration with other partner organisations nearby.

Across all diseases in scope of Unitaid investment, the Unitaid Strategy team scans the innovation pipeline, consolidating this information into market landscape reports, alongside stakeholder engagements, to identify potential Areas for Intervention that could lead to direct investment by Unitaid in line with a framework to focus its efforts in areas that offer comparative advantage and best value for its investment.

Highlights from across the disease areas include:
- HIV: Unitaid engages with civil society in conjunction with CHAI and academic institutes funded by Unitaid to accelerate access to optimal HIV treatments. The Secretariat has a productive relationship with the WHO HIV department, the Global Fund, PEPFAR and a range of high burden, high priority countries across the breadth of innovations supported by Unitaid, including HIV Self-Testing.
- TB: Over the reporting period a major milestone was the UNGA High-Level Meeting On Ending TB in September 2018, where Unitaid had a prominent role in both side events and the central discussions.
- Malaria: A notable highlight from 2019 was Unitaid’s participation in the Asia Pacific Leaders Malaria Alliance (APLMA) Senior Officials meeting and World Malaria Week.
- Hepatitis C (HCV), with a focus on HIV/HCV co-infection: The Secretariat holds regular meetings with the projects working on HCV.
- Intellectual property (IP): with its ongoing investment in the Medicines Patent Pool, and three projects that started in the second half of 2018, the Secretariat organises a yearly meeting with all projects working on IP. Unitaid has remained actively engaged in IP discussions, for example through its participation in the World Conference on Access to Medical Products Achieving the SDGs2030
- Over the past year, Unitaid has established itself as a key partner in the cervical cancer space, working closely with partners including the WHO and CHAI.
:
Unitaid hosted the second Grant Implementers’ forum in March 2019, gathering 26 grant implementers which provided an opportunity for increased partnership and exchange on common challenges and opportunities across Unitaid's grant implementers. The participants included representatives of UK Grant Implementer organisations including IVCC, University of Liverpool, and the MTV Staying Alive Foundation.

Unitaid and Global Fund staff engage on a regular basis. In general, there is extensive engagement with Fund Portfolio Managers, supply/procurement focal points, and the Wambo team on implementation-related issues, and Senior Disease Advisors and related individuals on strategic issues, including prospective Areas for Intervention (e.g. in advanced disease), expert input to proposal reviews (e.g. for vector control and MDR-TB), and activities related to the transition and scale-up of Unitaid investments. A pertinent example is the New Nets project, led by IVCC, co-funded by Unitaid and the Global Fund.

With PEPFAR, Unitaid is collaborating in a range of ways, including:
- Unitaid facilitating the introduction of 3HP (Rifapentine and INH combination) and Advanced Disease commodities in a total of 14 high burden countries.
- In general, Unitaid projects help to de-risk PEPFAR investments in countries and give country programs enough time and evidence to plan implementation/scale-up more efficiently of innovations supported by Unitaid.

Unitaid has a close partnership with WHO, which help to facilitate the process of in introducing innovations. This technical partnership has been operationalised and supported through the WHO Enablers.

The Unitaid secretariat has increased engagement with private sector industry across a few dimensions, spanning across the market access dimensions of affordability, innovation and availability, and quality. To ensure compliance and accountability, in line with Unitaid’s values, industry engagement was conducted strictly in compliance with WHO’s Framework of engagement with non-State actors (FENSA), principles of public procurement and in consultation with civil society partners.

On affordability, the secretariat led a few price negotiations with industry stakeholders. Building upon the agreement in summer 2018 with Cipla pharmaceuticals (where a 30% price reduction treatment of Latent TB infection (LTBI) in people living with HIV was achieved), over this reporting period Gilead Pharmaceuticals announced a cut in the price of the WHO-recommended drug AmBisome® to treat cryptococcal meningitis, an opportunistic infection responsible for 15 percent of the world’s HIV-related deaths. Also, the CHAI/UNICEF Point of Care project facilitated price reductions on the GeneXpert® and the Hologic Panther® diagnostic platforms to enhance access to HIV, HPV, HCV and HBV virology tests in LMICs. This includes collaboration with MedAccess (a UK-based social finance company, owned by CDC which is a development finance institution owned by DFID). More broadly, Unitaid and MedAccess are actively exploring areas for further collaboration.

To support the innovation pipeline, the secretariat continued its engagement with key pharmaceutical companies such as Macleods, Mylan, Cipla and ViiV to accelerate the availability of essential quality assured products, such as prodcuts for paediatric antiretroviral therapy, rifapentine based generic medicines for treatment of LTBI.

On quality-assurance, the Medicines for Malaria Venture enabler project expanded its scope of the Quality-Assured Medicines to Prevent and Treat Malaria project to include support to two indigenous manufacturers in Nigeria to achieve WHO prequalification status for intermittent preventive treatment in pregnancy, a critical tool for prevention of malaria in pregnancy.

Output 4.4 As a proxy of overall grant implementer satisfaction, two questions from the broader grant implementer survey were selected: 8) How effective is your partnership with Unitaid in bringing innovations to the global health response that would not otherwise be introduced or would take significantly longer to bring to market in low and middle-income countries (LMICs)?, and 47) Overall, how would you rate your experience with Unitaid? Whilst both indicators’ positive responses have fallen from one survey to another (Q8: 100% in 2017; Q47: 86% in 2017), this should be put into context with the evolution of the portfolio and the increasing expectations of the Secretariat. In addition, Unitaid lack good external benchmarks on this type of measure, thus it’s unclear whether the existing targets reflect the right benchmark.

For example, in recent times the Secretariat has put in place a range of new guidelines and reporting templates to strengthen grant management and assessment of impact cost and risk. 57% of grantees who responded to the survey found Unitaid’s reporting requirements more challenging than other major donors. Moreover, the increased maturity of the portfolio has led to reprogramming several grants. Thus, there are trade-offs between delivering effective grant management and overall satisfaction of grant implementers.

Lessons identified this year, and recommendations for the year ahead linked to this output

Output 4.1 Unitaid should utilise a clear, prioritised and strategic resource mobilisation strategy, using all levers at their disposal. For Unitaid to expand into new areas beyond the three diseases for the next strategy period, additional resources will need to be raised to avoid redirecting funds away from the three diseases.

Output 4.4 As Unitaid’s expectations of grant implementers increase, Unitaid should provide further guidance on how to meet them in a prioritised manner. Unitaid should make questions more open-ended, and adjust the survey to follow up on areas for improvement identified in the last survey.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

UK support to Unitaid was approved with a project memorandum in 2006/7. This was before the requirement to develop a theory of change for each programme. However, the Unitaid Strategy 2017-21 broadly describes a theory of change (see diagram below). This remains valid, and supporting evidence and assumptions hold up against implementation experience. There is no new evidence which challenges the programme design or rationale.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Unitaid is on track to contribute to the expected outcomes and impact. Four projects were completed in 2018 and were thus in scope of assessment against the impact and outcome indicators:

Project name	Investment Area	Timeframe	Investment level, budget (US$)
Access SMC	Malaria prevention	2014 – 2018	68 m
MSF HCV	HIV co-infections	2015 – 2018	15 m
Wambo	Cross-cutting	2016 – 2018	5.8 m
Pre-Qualification (WHO)	Cross-cutting	2017 – 2018	21.4m

The table below provides a summary of the projects’ performance against each of the Impact and Outcome Indicators, where applicable:

	Indicator	Milestone	Progress
Impact 1	Additional number of lives saved (cumulative) / [KPI 4.1 Increasing public health impact]	N/A	ACCESS SMC (seasonal malaria chemoprevention) project estimated to support averting an additional 81 m cases and 365,000 deaths from malaria in children under 5 up to 5 years beyond the project life
Impact 2	Financial savings and health system efficiencies (cumulative) / [KPI 4.2 Generating efficiencies and savings]	N/A	Net savings of $2.5m could be achieved as a result of the ACCESS SMC project. This also involves a positive distributional effect away from household burden, to health systems (i.e. more prevention, less treatment costs). / wambo.org is estimated to have generated savings of $117.5m to date.
Impact 3	Average rate of return of Unitaid investments / [KPI 4.3 Delivering positive returns]	5 dollars return per dollar invested	ACCESS SMC project is estimated to deliver a return of investment (RoI) of >100 to 1. / WHO PQ study estimates its RoI at between 30-40 to 1. / Estimates of the wambo.org RoI are around 10 to 1.
Outcome 1	Percentage of Unitaid -supported products with completed product development activities / [KPI 1 Catalysing innovation]	80%	N/A (applies to projects that include a product development component. In 2018, no project in scope for reporting contained product development activities)
Outcome 2	Percentage of critical access barriers overcome / [KPI 2 Overcoming market barriers -Critical access barriers cover the following market dimensions - Quality, Affordability, Demand & Adoption, and Supply and Delivery]	80%	89%. 8/9 access barriers fully or largely overcome. / 7 out of 9 (78%) of access barriers were fully overcome. / 1 access barrier (MSF HCV – Affordability) was largely overcome. The project has contributed to the downward trajectory of direct acting anti-viral (DAA) prices. MSF negotiated a price of $120 for sofosbuvir/daclatasvir regimen. Even though this price is not immediately available to other actors and governments, it serves as a global benchmark for affordability.. / 1 access barrier (ACCESS SMC – Supply & Delivery) was moderately overcome. Good progress but some delays in bringing a second manufacturer to market. A product from a second manufacturer was not secured by the end of the project but was recommended for use by the Global Fund’s Expert Review Panel (ERP) in February 2019 and is expected to get prequalified by the WHO by the end of 2019.
Outcome 3	Proportion of project countries with scale-up funding secured at grant closure (%) / [KPI 3.1 Securing funding]	80%	100% / ACCESS-SMC: Transition funding from new donors is fully or partially in place for all seven target countries. and the success of the project has led to 5 additional countries rolling-out SMC programmes. / MSF HCV: MSF has put in place key building blocks for scale-up of HCV care. However, the long-term impact of the project is limited by the current lack of domestic and international funding available for HCV. Despite this, it should be noted that following this project, MSF adopted an HCV strategy, continuing activities in all relevant project countries and securing funding to start HCV activities in 6 new countries. Building on the achievements of the MSF grant, Unitaid is investing in complementary projects to address the gap.
Outcome 4	Additional number of people who benefit from a Unitaid-supported product (cumulative) / [KPI 3.2 Scaling-up coverage]	N/A	The scale-up of SMC in project countries and beyond has been successful. Before ACCESS-SMC, only 800,000 children were receiving any SMC treatment in the Sahel region. This number has increased to 15.7 million in 2017 and could reach 18.6 million in 2020 (2 years after project end) in 12 countries.For 2020, this corresponds to a coverage of 59% [53-66].

Explain major changes to the logframe in the past year
The current tranche of UK support to Unitaid (2018-2020) is being monitored using a new logframe. The new logframe was drafted in consultation with Unitaid and is closely aligned with Unitaid’s new strategic and operational key performance indicators, at the impact, outcome and output levels.

Describe any planned changes to the logframe as a result of this review
At the PSC in October, Unitaid will propose some changes to the KPIs as discussed in the Outputs section. DFID will assess whether to amend the logframe to align with the KPI amendments, if approved.
## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year
Performance against the four “E”s of DFID’s value for money framework
Economy	Efficiency	Effectiveness	Equity
Unitaid continues to maintain a lean organisational structure relative to the value of its grant portfolio. Over 2018, Unitaid’s Secretariat costs were 1.87% of its active grant portfolio value, meeting the target of 2%. / The main cost drivers of Unitaid’s projects include procurement of health commodities, staff costs, external expert costs, travel-related costs, general administration costs and ad-hoc operating expenditures. / Budget development follows Unitaid Financial Guidelines and benchmarking from other projects of a similar type. / Unitaid has established maximum thresholds to limit its funding contribution to general administrative expenses - specifically (2% on health and health equipment expenses commodities / 13% on other project expenses).	The Operating Model has been streamlined further for grant management – the average time of grant development has been falling and has reached 5.6 months, exceeding the target for 2018 of 6 months. / Following the Board presentation of the portfolio performance in June 2019, 82% of projects are on track or exceeding performance. / Unitaid has good allocative efficiency. 60% of the portfolio has a focus on antimicrobial resistance and 73% on integrated approaches. The focus on drug resistance is based on strong evidence of the economic costs of the three epidemics, which is in all cases much higher for drug (and insecticide) resistant strains, and which threatens the gains made in the fight against HIV, TB and malaria. Also, Unitaid’s strategic focus is on low-income and lower-middle income countries. 100% of the projects started in 2018 were designed to benefit the poorest and the underserved.	Unitaid has a set of strategic KPIs which align to the objectives of Innovation, Access and Scalability, which reflect the outcomes of Unitaid’s investments. / No projects closing in 2018 were in scope of assessing innovation, however many innovative products have been identified. / 89% (8/9) access barriers were overcome, in relation to the Access objective. / ACCESS-SMC achieved particular success in scalability and was a hugely effective project, with a RoI of >100 and an increase in children receiving SMC from 800,000 to 15.7m in 2017.	Equity remains a key focus of Unitaid’s 2017-2021 Strategy and accompanying KPIs. For example, Strategic KPIs 2.1 and 2.2 are focused on reducing inequities in access for the poorest and underserved, and Unitaid’s mission statement includes a reference to “equitable access”. / Strong equity focus reflected by grant portfolio, with a focus on: / Pediatric formulations – children are a key under-served population – e.g. child-friendly antiretrovirals / Rectal artesunate – to support management of severe malaria for children detached from basic health services. / Access to preventive treatment against malaria for pregnant women. / Point-of-care diagnostic tests – offering scope for decentralized testing and treatment, notably for the early infant diagnosis of HIV. / Demonstrating the feasibility of offering HIV prevention (PrEP) to the most high-risk groups. / Drug resistance – this requires the most expensive and time-consuming treatments, often leading to impoverishment; / HIV and Hepatitis C treatments – for the most at risk population groups – securing access to better and cheaper treatments. / Screening and treatment of pre-cancerous lesions for secondary prevention of cervical cancer

Unitaid plays a key role in enhancing the cost-effectiveness of the UK’s bilateral, multilateral and research funding for the three diseases, by ensuring that new innovations reach those who need them most at the lowest price and in the quickest time. For example, Unitaid enhances the impact and reach of our Global Fund spend by bringing new, improved medicines through the pipeline quicker and at reduced prices.

UK funding to Unitaid represents very strong VfM, especially in light of the key role it plays in increasing the cost-effectiveness and availability of life-saving health commodities. The estimated return on investment across Unitaid’s portfolio is $7 to $20 per dollar invested. By 2028, Unitaid estimates to save 1.2 million lives and achieve US$3.4 billion in cost savings.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
UK funding to Unitaid seeks to increase the cost-effectiveness and availability of life-saving health commodities, and therefore represents strong VfM. Since its creation in 2006, Unitaid has also evolved as an organisation, shifting its focus from procurement activities to a mixture of interventions along the value chain. Under the Operating Model, the implementation of a robust VfM framework across the grant portfolio has enhanced the quality and end result of Unitaid investments, while also helping to simplify internal processes for Secretariat staff, grantees and the Board by offering greater clarity on the impact expected from grants. We are satisfied that Unitaid continues to represent a strong VfM proposition.
E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation
Unitaid risk management: While the Executive Board has overall responsibility for risk oversight, the Finance & Accountability Committee has oversight functions and responsibilities for internal control, internal and external audit, risk management and fraud prevention. Updates on risk are a standing agenda item on the FAC. Unitaid has significantly strengthened its approach to risk management (as detailed in Output 3.4) more recently and continues to undertake risk assessment of all active grants in the portfolio.

A Unitaid risk register reflects the latest risk profile and details the highest risks to achieving its mission and strategy, covering strategic, operational, governance and portfolio risks. Three have been scored by Unitaid’s Senior Management Team as being the highest: (i) “Shortfall in resource mobilization” ii) Non-alignment of areas for intervention with key partners and (iii) “Negative media coverage”.

DFID risk management: DFID has assessed Unitaid’s overall risk rating as ‘Moderate’, consistent with previous annual reviews. DFID programme teams regularly review risks to programme performance and identify relevant mitigation actions through an internal risk register. The programme team has also supported Unitaid work to develop a stronger risk framework. The top risks for DFID are presented below:
Risk Description	Risk Category	Mitigation Strategy	Likelihood	Impact	Residual Risk
Decrease in secretariat performance and/or management change affects operational efficiency and/or leads to the deprioritisation of UK priorities.	Delivery	UK to utilise high level and working level meetings with the Secretariat to reinforce UK priorities for Unitaid, including AMR and low-income countries. DFID to share lessons from DFID’s internal staff survey. and Unitaid to share the results of their internal staff survey. DFID to engage closely in Board dialogue and decision-making on leadership and management issues.	Possible	Moderate	Major
Unitaid is not able to identify, select and-or properly develop game-changing innovative projects. Unitaid misses opportunities for impact by not having a sufficiently flexible operational model and/or too much bureaucracy.	Delivery	Proven processes have been put in place and secretariat are actively reaching out to identify opportunities. DFID are encouraging additional flexibility through the Board.	Possible	Minor	Moderate
Consensus is not reached by the Board on future directions, or the Board moves to a position that is not aligned with UK priorities.	Context	Push for future directions to be explored within a clear, prioritised and strategic framework that also allows for flexibility. Ensure that lessons learnt from new areas identified in this way are captured and fed into future programme design effectively.	Possible	Minor	Moderate
Unitaid fails to secure sufficient, sustainable financing for the upcoming strategic period, undermining its ability to meet ambitions set out in the 2017-2021 Strategy.	Context	UK to push for a focused and more strategic RM effort. UK to work with the Secretariat to share lessons learned from other multilateral programme replenishments and to help identify upcoming lobbying opportunities.	Possible	Minor	Moderate
Unitaid does not align well with key partners at Afi and/or proposal stage leading to investments not being fully aligned with the priorities of the partners.	Delivery	Significant secretariat engagement across the funds, enhanced collaboration with closest partners (e.g. GFATM). UK to monitor through position on the Board and role in grant reviews.	Unlikely	Moderate	Moderate
Failure to deliver impact, unsuccessful transition and scale-up of grants	Delivery	Unitaid takes a portfolio approach to investment, so any one failure is balanced. Careful grant design and management reduces the likelihood. DFID to play a prominent role in funding and programme management of scale up partners e.g GFATM, Gavi.	Unlikely	Moderate	Moderate
Risk that Secretariat staff, intended beneficiaries of Unitaid’s grants or individuals engaged in the implementation of Unitaid funded projects are exposed to or perpetrators of sexual exploitation, harassment and/or and abuse during the course of their work; thus negatively impacting the confidence in Unitaid and/or having an adverse effect on Unitaid’s reputation.	Safeguarding	Unitaid completed an enhanced due diligence exercise for DFID covering safeguarding, whistleblowing, HR recruitment and selection, risk management, code of conduct, and governance and accountability. DFID to monitor regularly through engagement with the FAC, and raise any areas of concern with DFID’s internal reporting service. DFID to engage with Unitaid secretariat on oversight and capacity issues to ensure that grant implementers’ monitoring is robust and effective. Unitaid to present findings from the biannual staff survey to the Board or committees once completed for 2019, and DFID should share examples of questions from the DFID internal staff Survey.	Rare	Moderate	Minor

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
The quality of Unitaid’s financial management continues to improve. Overall, the Secretariat has made good progress in improving the quality of reporting to the FAC, including robust and timely updates on budget performance, financial planning and risk management. In 2018, 100% of Unitaid’s grants had an up-to-date financial audit. Each of Unitaid’s current set of projects has a nominated lead who is responsible for scrutinising the budget and activity plan, negotiating costs, advising on disbursement requests, monitoring progress and recommending corrective action as necessary.

The main cost and cost drivers of the operational expenditure (OpEx) budget remain the same as in previous years. However, the evolution of OpEx costs since 2015 has been much less (just over 30%) than the increase in Unitaid’s cost drivers such as the total number of grants (an increase of more than 60%) or portfolio size (an increase of more than 80%). In 2018, Unitaid’s total annual Secretariat operating costs were US$21.3 million, the majority of which were staff costs (78%, US$16.6 million). WHO hosting costs, rent and other operating costs made up respectively 7% (US$1.6 million), 8% (US$1.7 million), and 7% (US$1.4 million) of the Secretariat OpEx in 2018. The main cost drivers of the OpEx budget are:
- Secretariat staff costs (approximately 78% of OpEx). The Secretariat has increased from 50 people in 2015 to 89 at the end of 2018. This reflects the changes in Unitaid strategy, operating model and increasing size of the portfolio. The main drivers of staff costs are UN cost of living and annual step increases in salary scales for Geneva based staff. Over 2018, Unitaid’s Secretariat costs were 1.87% of its active grant portfolio value, meeting the target of 2%.
- The Governing bodies envelope’s main costs are budgets for the Proposal Review Committee (PRC - a group of external independent experts who input to the Joint Review Committee (JRC), which is composed of senior Unitaid Secretariat staff and the PRC), Office of the Chair, Executive and Committee meetings, and Support to Constituencies (African Countries, Communities). The main cost driver for the Expert Group is the number of proposals it considers. The increasing cost in this reporting year reflects the growing numbers of proposals that are being reviewed. The main cost driver for the Executive and Committee meetings is the room rental rates in Geneva. The move to the Global Health Campus is supporting operational efficiencies, e.g. enabling access to facilities for large meetings etc.
- Other Secretariat costs support Strategic development and implementation support (SDIS), Business development and market intelligence (BDMI), communication, advocacy and travel needs.

The Secretariat will continue to optimise their controllable costs and ensure that budget is used effectively and efficiently to support delivery of strategic goals and objectives. An efficiency target of 4% (delivering the same level of activities with a 4% reduction in budget) was set for 2019 and the Secretariat is on track to deliver beyond these efficiency gains across a range of areas. A broader review of all the metrics that demonstrate the efficiency of the full Secretariat activities will take place in the coming months.

Date of last narrative financial report(s)	11 April 2019 (FAC)
Date of last audited annual statement (s)	31 December 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring
DFID’s logframe aligns closely with Unitaid’s Operational and Strategic KPIs. As a result, DFID is able to draw on Unitaid’s formal results reporting tools, such as the annual KPI Report, published in June of each year, for detailed updates on performance. In addition, progress is monitored through regular engagement with the Secretariat, UK representation on the Unitaid Board, on the FAC and PSC, and targeted discussions at Board and Committee meetings.

Unitaid monitors the implementation of its strategy and investments predominantly through two mechanisms: (i) strategic and operational KPIs, which track progress in aggregate for the organisation; (ii) annual performance reviews of grants which summarise the assessment made by the Secretariat based on end-of-year reporting packages from grant implementers. Both mechanisms involve reporting to the Board once a year. As the portfolio is structured around Areas for Interventions (AfIs), and as these AfIs have matured, the Secretariat has begun exploring an ‘AfI dashboard’ to provide a clear perspective to monitor the progress made by Unitaid at the AfI level.

Evidence
Unitaid commissions external project evaluations of its investments at the end of a project, and at relevant points in time such as the mid-point of the project cycle. Evaluations complement other oversight and assurance activities such as semi-annual/annual project performance reviews, audits and onsite verifications. Once complete, an evaluation is analysed within the Secretariat to inform future investment decisions, and published on Unitaid’s website.

Unitaid has increased its efforts on evaluation and learning in the last year; in this context, the analysis of Unitaid’s portfolio, performance and lessons – and in particular the recent external evaluations - is no longer conducted through a one-off analysis of recent evaluations, but rather the content was substantially enhanced and split across multiple documents through a broader set of complementary analyses:
1. Strategic KPI reporting, which involves a thorough analysis of each recently closed project (including final evaluations) to inform the assessment of KPIs;
2. The mid-term review and an analysis of Unitaid’s ability to address access barriers, achieve scale up, equity, VfM, health systems impact;
3. Two deep dives to learn from ACCESS SMC project and the molecular Diagnostics portfolio

Learning
Much of the learning from the last year was captured in the mid-term review. In the last three years, Unitaid has solidified and formalised its learning. Whilst each project has its own specificities, Unitaid has broadly gained more experience in analysing context, and applying the appropriate combination of interventions, tools and partners to overcome barriers. Stronger methods and tools have improved the way Unitaid shapes its grants and projects and introduced greater flexibility.

The Review shows that Unitaid’s Strategy is on track and remains relevant. Underlying components of this Strategy, such as innovation and integration, have gained traction in the global health landscape. Unitaid’s work on impact, performance and scalability should be maintained, as it will provide a strong basis for assessing progress at the end of the strategic period, especially on recent grants linked to new areas such as fever management and cervical cancer. The three overarching themes emerging from the findings and recommendations that are likely to remain priorities for 2021 and beyond are i) Scalability ii) Agility and iii) New potential areas for investment, as described in Output 1.1.

Unitaid is cognizant that its impact is mainly driven by the scale-up of the innovations it supports. Assessing and engaging in various approaches and new partnerships on scalability is key to achieving success on the current grant portfolio. Although Unitaid has shown progress in becoming agile and uses its current flexibilities to a large degree, the model can be further adapted to keep pace with today’s innovations. Unitaid should continue to explore new opportunities for impact based on changing global health needs and the evolving innovation landscape, and ensure that lessons learnt from these explorations are incorporated into the development of future projects.

Progress on recommendations from previous reviews
The below tables indicates progress against the 2018 annual review recommendations.

Strategic level recommendations for Unitaid:
No.	Recommendation	Actions taken
S1	Unitaid to consider whether, when and how, to broaden its engagement to include different kinds of partnerships, including with the Global Fund.	New Strategic Framework for collaboration with Global Fund; MoU with UNICEF; MoU with Government of Rwanda; Increased engagement through G7 & G20
S2	Unitaid to continue to strengthen its approach to ensure a more strategic, portfolio approach that achieves greater and more sustained impact.	Roll-out of Impact Cost and Risk tool
S3	In order to support the delivery of its strategic objectives Unitaid to review whether it continues in its current size and scope of activities: in an SDG world, how can its market-shaping approach support other areas.	Mid-term review findings – Output 1.1.
S4	Unitaid to step up its efforts on resource mobilisation, to deepen and widen the donor base. Unitaid must pursue this challenge with greater intensity and urgency to ensure sufficient resourcing to deliver on its strategy. Several Executive Board members expressed support for the establishment of a working group on resource mobilisation and it was suggested that this be discussed during a call. To progress the MTR of the Strategy - this will be important to help Unitaid address the above challenges.	See the full response on Resource Mobilisation in Output 4.1.

Operational Level recommendations for Unitaid:
Indicator	Recommendation	Actions taken
General	Unitaid to build on the work it has undertaken to strengthen grant management and oversight, use the grant implementation process to gather lessons to improve effectiveness, and provide continued evidence of impact and return on investment.	Range of interlinked initiatives including the roll-out of the Impact Cost and Risk tool, the introduction of a risk library, Value for Money analysis conducted for the mid-term review, Secretariat wide presentations of evaluation findings.
3.3	The partnership with the Global Fund has steadily improved, with the move to the Global Health Campus already reaping benefits from greater collaboration. Unitaid should consider whether the existing MoU with the Global Fund is fit for purpose and amend as appropriate.	As above, a new Strategic Framework for collaboration has been approved
3.4	Unitaid Secretariat should consider whether a standardised approach should be developed across projects to support transition and scale up e.g. by assessing effectiveness of direct engagements with countries and partners to document any lessons for the wider portfolio to support transition.	Development and roll-out of the Scalability framework
4.6	Unitaid should strengthen guidance to proponents and grant implementers on how to estimate impact (e.g. return on investment, including calculation of benefits) and, where applicable, ensure such figures are estimated through a consistent and robust approach.	Refreshed methodology, linked to Impact Cost and Risk; Roll-out of refresh to latest grant agreement development processes
6.2	Unitaid should continue to prioritise resource mobilisation efforts, ensuring systematic engagement with key stakeholders. Unitaid should develop a costed and prioritised resource mobilisation plan. Regular updates should be provided on the implementation and progress towards the deliverables of the resource mobilisation plan.	Resource Mobilisation plan presented in December; Discussion at the FAC April 2019
6.3	Unitaid Secretariat takes actions to address Executive Boards request for future KPI reporting and annual grant portfolio update to place further emphasis on the challenges faced to deliver outcomes and impact,	Two dedicated sessions, one on SMC (Dec 2018 Board) the other on Diagnostics (April 2019 PSC) / Grant portfolio update document refreshed to reflect successes and challenges (June 2019)

Operational level recommendation for the Governance Working Group:
Indicator	Recommendation	Actions taken
5.4	The governance working group (GWG) should recommend updated policies on ethics/conflict of interest, and an approach for including new donors into the governance structure.	Resolution on new donors approved by the Board (UNITAID/EB32/2019/9). GWG and Secretariat to take forward ethics/conflict of interest policies.

Operational level recommendation for DFID:
Indicator	Recommendation	Actions taken
5.4	DFID should consult with the Executive Board on progress in addressing the recommendations of the Board’s performance assessment survey.	Recommendation included in work on organisational risk management, which we have been taking forward actively.