Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Education Data, Research and Evaluation in Nigeria (EDOREN)
Programme Value: £5,998,766		Review Date: September 2014
Programme Code: 202643	Start Date: 11/03/2013	End Date: 10/03/2017

Summary of Programme Performance
Year	2014
Programme Score	A
Risk Rating

Summary of progress and lessons learnt since last review
EDOREN has made significant achievements in its first year of operation, generating evidence, supporting high quality data collection and contributing to delivery within other DFID Nigeria education projects. Key achievements include:
- Evaluation framework for DEEPEN and TDP including impact evaluation design. GEP3 evaluation framework under preparation.
- Annual review for DEEPEN complete and preparation for TDP annual review underway
- Research on political economy of education financing, female teachers’ and the supply and demand constraints for teachers completed, contributing to programme learning and course correction.
- Technical support to improve Annual School Census in GEP3 states and design of a school database to collate information on all schools supported by DFID
Website launched and literature review of basic education in Nigeria published.

The project has put in place a high quality team and established effective relationships with partners. There have been some changes in core team and management structure in response to needs and demands of specific roles. This has included initial steps to move towards more Abuja-based operations and capacity. Initial relationship building and delivery of outputs with other DFID education projects was slower than initially envisaged, particularly due to project and staff changes in UNICEF/GEP3 which underwent a project improvement plan and redesign process over the last year.. Close working relationships have now developed with the projects, particularly through the development of their evaluation frameworks. Further work is needed to embed work stream 3 and 4 activities across DFID Nigeria’s education portfolio and beyond.. Progress to formalise EDOREN’s capacity development strategy is also imperative for delivery of outcomes, institutional and behaviour change. This should be considered in relation to EDOREN’s longer term strategy and the institutional and behavioural changes and prerequisite levels of capacity that EDOREN would hope to have in place for it to achieve their longer term goals. EDOREN has reviewed its theory of change and is currently developing a logical framework for the project. This will be key to ensuring stronger management and monitoring of the project.

Summary of recommendations for the next year
- With project evaluation frameworks finalised to cover activities up to 2020, DFID should extend EDOREN contract to March 2021, to ensure adequate planning and management of inputs (May 2015).
- EDOREN to agree revised Theory of Change and logframe with DFID. This should incorporate PEA and capacity building but not as distinct outputs(February 2015)
- DFID to review how EDOREN is managed on internal system and set up as a discreet project on ARIES (March 2015).
- EDOREN to include within activity workplans interim milestones and points for DFID’s engagement and agree a sign off process for research outputs (on-going).
- EDOREN to finalise VFM strategy (February 2015).
- DFID to conduct a value for money analysis with EDOREN of the different evaluation frameworks and baseline surveys planned to inform approach going forward (September 2015)
- EDOREN to develop knowledge management/dissemination plans for all research activities and data quality review work at design stage and share with DFID (on-going). EDOREN to retrospectively develop KM plans for research outputs already completed or at final draft stage, where appropriate and not already completed (January 2015).
- EDOREN to further elaborate internal policy on ethical standards for research (March 2015)
- EDOREN to draft an Operational Research Strategy (Sept 2015)
- EDOREN to propose new workstream leader for Operational Research (WS2) (January 2015)
- EDOREN to include within their knowledge sharing work mechanisms to share updates from their work on independent activities e.g. progress on the NEDS, with DFID and its education projects, highlighting implications for the projects (February 2015). EDOREN to capture this within knowledge management plans for all future review work.
- EDOREN to include within their knowledge sharing plan processes and tools through which to regularly capture lessons learnt on data quality and harmonisation and ensure review recommendations are followed up (February 2015)
- EDOREN to finalise their dissemination strategy and knowledge sharing plans (February 2015).
- EDOREN to register with DFID’s research website, R4D, as a platform to further disseminate research outputs.
- DFID to facilitating linkages with DFID’s Research and Evidence Department (RED) to support workstream activities (February 2015).
- EDOREN to establish a regular, systematic process for updating the literature databases and assessing quality of new updates (February 2015).
- EDOREN to establish Steering Committees for thematic research studies (January 2015).
- EDOREN to finalise capacity development strategy and clarify the capacity building priorities and strategy for each workstream within this. (April 2015)
- EDOREN to include risk section in all future Quarterly and Annual Reports (on-going).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:	Under GEP3

Outline of the programme

The Education Data, Research and Evaluation in Nigeria (EDOREN) programme is a four year DFID funded programme (2013 to 2017). It was designed to generate evaluation and research evidence on what works to support equitable access and improved learning outcomes for all Nigerian children, and to enhance national capacity to generate and use this evidence.

The project seeks to address specific issues identified by DFID Nigeria around the generation, quality and use of data and research. There is limited availability of high quality data and gaps in evidence of what works to improve access and learning in Nigeria. This is coupled with low levels of use of evidence to inform policy-making and education planning; and low levels of capacity to do so.

EDOREN has three outcomes:
1. Enhanced use of quality assessed education data, innovative research and evaluation in DFID’s basic education project portfolio and by the Nigerian States which the portfolio serves and supports.
2. Enhanced capacities to generate and use high quality education data, research and evaluation for better basic education policy and practice in States supported by DFID’s basic education portfolio, and nationally.
3. Enhanced availability of quality assessed data and innovative education research and evaluation to inform DFIDN’s next round of basic education sector programming.

The EDOREN project seeks to add value to the performance of DFID’s other basic education projects in Nigeria which focus on improving basic education provision. EDOREN works with these projects to strategically build and strengthen their capacity to generate and use data, research and evaluation. It is financed by these projects through their external monitoring and evaluation budgets. It is also responsive to their research and evaluation needs, engaging with them as required.

By working across all of DFID Nigeria’s education projects EDOREN is in a position to ensure comparability of data generation and use, strengthening reporting of results for DFID Nigeria’s education portfolio and evaluation of projects. Contracting one supplier to provide these services and support to projects is also helping to ensure value for money in DFID Nigeria’s monitoring and evaluation of their education portfolio.

EDOREN also works independently to produce knowledge and develop capacity on research and evidence above and beyond DFID education projects, although this has been a more limited focus for the project in the first year.

EDOREN’s had a five month inception period from March – August 2013. Implementation then commenced on 1st September 2013 and will run initially to March 2017, with a second four year phase recommended up to 2021. This review will cover implementation from September 2013 to August 2014.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
After a busy first year of operation the project is on track to achieve its outcomes. However these are a couple of ways in which the likelihood of the project achieving these objectives could be strengthened:

In May 2014 EDOREN undertook an internal review of its theory of change to reflect upon contextual changes since the project was designed and lessons learnt. This included a review of assumptions underlying the theory of change and drafting of a logical framework. Both should be finalised and agreed with DFID following this annual review.

EDOREN was originally designed as an 8-year project, but at contracting stage this was split into two phases, with OPM contracted until 2017 for the initial 4 year phrase with the possibility of extension. Given that the evaluation work EDOREN is now supporting extends beyond 2017 it is recommended that the contract is extended now. This will also support longer-term investments in capacity development and use of data and evidence to achieve institutional changes and embed good practice.

Overall output score and description

Output	Impact Weighting	Output Score	Risk
1	30%	A+	Medium
2	15%	B	Medium
3	15%	A	Medium
4	10%	B	Medium
5	20%	A	Medium
6	10%	B	Medium

Overall Score A

The output scoring is based on the M&E framework and Year One workstream workplans set out in EDOREN’s inception report. The project is currently developing its logframe. This will be used for future annual reviews.

EDOREN by nature of its cross cutting support and involvement with DFID’s other education projects has to be responsive to changing needs and situations, but also means that delivery of EDOREN outputs are often dependent on activities of their partners. This has been challenging for EDOREN in their first year of operation during which TDP and DEEPEN were also in inception phases and GEP3 was undergoing an intensive project improvement plan (PIP) and redesign process. The latter in particular affected EDOREN’s workplan and their engagement with GEP3/UNICEF. But EDOREN have responded well to the changing context identifying opportunities for engagement, building relationships with the project teams, and agreeing with DFID where a change or delay in activities is required. This has, however, affected the scoring of some workstreams, where EDOREN has been unable to deliver as anticipated because of factors often beyond their control.

Key lessons
EDOREN has a strong leadership team. There have been some changes during the first year to ensure that the management structure is responding to needs. Workstream leadership has changed for WS1, 3 and 5, with the result that all workstreams, except WS 4, are now led by OPM staff. This reflects the higher proportion of managerial work as well as technical inputs required for the workstream leader role. Use of OPM staff provides EDOREN with greater control over work planning and ensuring sufficient staff time is allocated to this function. Technical expertise is still being provided through consultants, who have remained engaged with the project. Generally within the project there is a predominance of OPM staff engaged on delivery of outputs. The EDOREN manager expressed that this has enabled them to have greater flexibility to provide technical inputs in line with requirements of the other education projects, as well as providing more consistency of staff who are working with the project. However, staff are still brought in to provide short term inputs, leading to multiple requests for CV approvals. Moving forward quarterly reports and/or activity work plans should include within their forward looking workplans where additional consultancy inputs are required and plan to be utilised. This builds upon recent efforts within the May quarterly reports to detail experts involved in delivery of different outputs.

There has also been a shift towards greater management and research capacity within Abuja. EDOREN are in the process of recruiting 3 members of staff: a programme officer to support the Country Director with programme administration, and two research specialists with quantitative and qualitative backgrounds. The Programme Officer post has been filled and it is hoped that this will enable the Country Director to take a more strategic role. EDOREN are struggling to find suitable candidates for the two research specialist posts. EDOREN should also consider how it can increase use of Nigerian consultants for short term consultancy inputs.

In EDOREN’s project structure political economy analysis (PEA) and capacity building are not classified as distinct workstreams because they are seen to be cross-cutting, yet there are routinely reported upon separately and discrete activities have been undertaken in these areas over the first year of operation. It is recommended that both of these areas become part of the revised logframe, but not as output areas. This is particularly critical for capacity building given that it is a specific outcome for EDOREN and therefore needs to be more robustly planned and monitored going forward. The on-going work on the capacity development strategy should inform the development of this output. For the purposes of this review PEA/ capacity building and other strategic issues have been collectively reported under section C as a sixth output area. This is also as currently conceptualised in the M&E framework.

There are opportunities to do further work to strengthen the strategic linkages between workstream activities so that they are bringing added value to achieving each other’s aims. For example activities and outputs under workstreams 1 and 2 to improve use of evidence within DFID’s education programmes should be more explicitly feeding into knowledge management activities under workstream 4 and capacity development activities around the use of data and evidence. There are opportunities under workstream 4 to more systematically capture learning from other workstream activities where these have worked well to improve use of evidence and areas where this could be strengthened.

There is need to strengthen work on knowledge communication so that outputs are practical and policy-focused to support better use of evidence within projects as well as externally. Movements towards this have been demonstrated by the knowledge management and dissemination plans currently in development. DFID should support this by facilitating linkages with DFID’s Research and Evidence Department (RED). RED’s Evidence in Action (EiA) team are currently implementing five capacity building programmes focused on building the capacity of policy makers in the use of evidence. Connections should be made with the EiA project team to share lessons and experience.

Communication between DFID, EDOREN and projects, and DFID’s level of engagement with EDOREN’s activities could be strengthened. Many deliverables persist at final draft stage and DFID is often less aware of on-going work under workstreams 3 and 4 that do not have hard deliverables. To address this EDOREN should include within activity workplans interim milestones and points for DFID’s engagement, and specify a clear sign off process for research outputs. Where possible submission of deliverables should be spread throughout each quarter to avoid submission of multiple documents with the Quarterly Report and allow DFID Education Advisers to provide a timely response to all reports received. A DFID focal point should also be agreed for each activity at the outset.

EDOREN is an innovative and quite unique programme for DFID, combining research, evaluation, evidence uptake and capacity building. As such it would be useful to capture lessons learnt and share with RED and other country offices, the approach being taken to activities such as research mapping, and more broadly on the added value of having a cross-cutting programme with an evidence focus to a programme portfolio.

EDOREN is an umbrella project providing support across DFID Nigeria’s education portfolio. However it was set up within DFID systems as a contract under GEP3 (with the understanding in the TORs that it would also support other DFID projects and programmes) rather than as a project in its own right. This has led to some challenges in its first year of operation for DFID’s internal management of the project. It is recommended that it is set up as a separate project within ARIES to allow for stronger financial and project management.

Has the logframe been updated since the last review?

At inception, the project developed a theory of change and detailed workplans for each workstream. A logframe was not initially developed at inception stage; the project was conceived to deliver M&E outputs for other DFID projects, each with their own logframes. This is now being developed for the project going forward and will be used for future annual reviews.

## C: DETAILED OUTPUT SCORING (1 page per output)

Workstream	Project evaluation and review: Demonstrable improvement in the quality of DFID basic education project evaluation
Workstream number		1	Workstream Score	A+
Risk:		Medium	Impact weighting (%):	30
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Outputs(s)	Milestones	Progress
1.1. Project generated M&E frameworks assessed and improved	1.GEP3 Evaluability study (Nov 2013)2. Support to GEP3 VFM and financial monitoring (Sep 2013 – Mar 2014) / 3. Advise and comment on TDP M&E framework (Sep – Dec 2013)	1. Evaluability study of GEP3 completed (May 2014). First draft was peer reviewed and submitted for comment by early Dec 2013, and a workshop held. Provided additional technical QA on GEP3 Strategy documents as part of the redesign of the programme.2. GEP3 led on this with a VFM consultant brought in during the PIP. / 3. Scope of original milestone extended. Due to delays with GEP3, EDOREN requested to design TDP evaluation framework.
1.2 High quality independently conducted annual project reviews and other formal evaluation supported and completed	4. Develop GEP3 evaluation framework (Aug 2014) / 5. Contribute to design and development of GEP3 Annual Review 2014 / 6. Develop DEEPEN evaluation framework (Mar 2014) / 7. Conduct ex ante theory based review of DEEPEN (May 2014)	4. Design of GEP3 evaluation framework now underway, being finalised with redesign. / 5. GEP3 Annual Review design managed by DFID. EDOREN contributed some documentation. / 6. Design of DEEPEN evaluation framework underway, completion expected in Sept 2014. Provided QA in preparation of DEEPEN baseline study. / 7. Ex ante theory based review of DEEPEN final draft submitted (May 2014) / Additional activities: DEEPEN AR conducted and TDP AR planned.
1.3 High quality research for project evaluation supported and conducted	8. Prepare Girls Out of School survey baseline (Aug 2014) / 9. Support GEP3 to conduct a School Intake and Drop Out Survey (Aug 2014) / 10. Support GEP3 to conduct tracer surveys (Aug 2014)	8/9. Not completed. Major survey work postponed until after GEP3 PIP. GOSS to be incorporated in baseline survey and redesigned evaluation framework (Milestone 4). Community mapping exercise undertaken by UNICEF (with EDOREN review) instead. / 10. FTTSS tracer survey developed (Final draft received June 2014). Other potential tracer surveys are to be confirmed in evaluation framework and redesign[1] / Additional activities: Katsina Teacher Supply and Demand study.
[1] Linked to FTTSS operational research delivered under WS2. At inception, WS2 activities were to be managed by the University of Sussex’s Centre for International Education, but tracer studies were planned and budgeted under Workstream 1 so they are reported on separately here. Moving forward these activities will be reported on together.

Key Points

Workstream one has been a substantive area of project activity and one where the programme has shown flexibility and responsiveness beyond the original work plan agreed with DFID. EDOREN has supported the development of evaluation frameworks for three education projects, and undertaken other research activities to support project evaluation. Particularly under Output 1.2 they have gone above and beyond the agreed deliverables. However a majority of agreed deliverables under Outputs 1.1 and 1.3 have been delayed. Where this has occurred postponed delivery of milestones have been agreed with DFID. Many of the reasons for these delays are related to delays within the other DFID education projects and dependencies on them for inputs and engagement.

Following the design of EDOREN and development of the inception report GEP3 was placed on a Project Improvement Plan (PIP) by DFID. This focused GEP3 activities on a core set of minimum expectations to turn the project around and involved the change in senior management of the project, with an interim team in place during the first half of EDOREN’s operational year. This limited EDOREN’s ability to work with GEP3 on planned activities resulting in delays to delivery of some components such as the FTTSS tracer survey. The decision to redesign GEP3 has also led to a re-thinking on activities such as the Girls Out of School baseline survey. The GEP3 PIP and redesign period has been a time of uncertainty and sometimes frustration for EDOREN in their ability to deliver and to identify how best to engage and support GEP3, particularly in late 2013/early 2014. With the introduction of the new UNICEF management team and DFID’s decision to redesign GEP3, EDOREN has been able to refocus their support on this process. The new GEP3 team have appreciated the inputs provided by EDOREN on the revised theory of change and strategy papers for the redesign. In addition whilst the concurrent development of the evaluation framework with the redesign has slowed the pace of delivery, it has provided a valued source of critical inputs into the redesign.

EDOREN has undertaken additional activities beyond the agreed workplan, as noted in the progress table above. Notably EDOREN has supported the development of TDP’s evaluation framework, which goes beyond the originally envisaged work which was limited to advice and comments. This addition to the workstream has required significant inputs from EDOREN, who quickly mobilised to support the work. DFID’s Specialist Evaluation and Quality Assurance Services (SEQAS) was impressed and commented that: ‘The team should be congratulated for delivering what is, in my opinion, the best example of a design of a theory based impact evaluation that I have assessed under SEQAS.’. Contracting of the evaluation raised issues concerning actual vs lump-sum costing for baseline survey work, with EDOREN’s preference for the latter due to the high transaction costs of actuals for fieldwork, but the former approach being adopted in the final contract agreed.

During Year 1 workstream leadership changed from Dr Paul Bennell to Ian MacAuslan. This decision was taken to reflect the increase coordination and management work required. It was felt that this could be more easily managed by a full time OPM staff member.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations

DFID to conduct a value for money analysis of the different evaluation frameworks and baseline surveys to inform approach going forward (February 2015)

Workstream	Operational research: Demonstrable improvement in the design, implementation and application of operational research in GEP3.
Workstream number		2	Workstream Score	B
Risk:		Medium	Impact weighting (%):	15
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Output(s)	Milestones	Progress
2.1 GEP3 operations practices and capacity understood	1. Assessment of OR operations, practices and capacity (Oct 2013 – Jan 2014)	1. Work postponed until after GEP3 PIP process and redesign.
2.2 GEP3 FTTSS assess and recommendations made for improvement and alternative strategies	2. FTTSS OR study (Oct 2013 – March 2014)	2. Final draft of study completed (June 2014). Delays to start and final delivery of report. OR approach included capacity building of state CoE staff and state-level workshop to disseminate results. Results used to inform FTTSS strategy within GEP3 redesign.
2.3 GEP3 school choice and quality work assessed and recommendations made for improvement	3. Assess assumptions about school choice and parental demand for and support to girls’ education	3. Work postponed until after GEP3 PIP process and redesign.

Key Points
Overall 1 out of 3 planned milestones were delivered under this workstream. Planned work for outputs 2.1 and 2.3 was postponed in agreement with DFID pending the redesign of GEP3. Revised priorities for OR will be agreed with UNICEF, EDOREN and DFID following the conclusion of the GEP3 redesign. There is an opportunity within the redesign to strengthen the research agenda within GEP3. Good relationships have been established between GEP3’s new senior management team and EDOREN.

There were delays in the implementation of FTTSS OR which meant that the research report was not available for sharing with the GEP3 Annual Review team in April 2013. The delays were a result of internal issues (staffing of the study by GEP3 and availability of external teams) as well as external factors (including strikes in Colleges of Education and delayed return of student affecting timing of field work). However feedback from GEP3 on the process has been largely positive, with the related FTTSS workshop providing opportunities to discuss the findings with key state-level actors and agree action plans to address some of the issues raised. The findings have also informed the revised FTTSS strategy.

This workstream was designed to focus on GEP3. EDOREN should also consider its long term strategy for operational research and how this is supported by its capacity building strategy and the opportunities that operational research provides to build capacity of local partners involved in research, and the use of evidence in decision-making. Lessons should be learnt from the FTTSS study to inform this.

Workstream 2 was originally contracted to be implemented the Centre for International Education (CIE) at the University of Sussex (consortium partner), with the workstream being led by Máiréad Dunne. CIE notified EDOREN in Q2 that they wished to withdraw from the project following completion of the FTTSS OR, the final draft of which was submitted in June 2014. Having an academic partner leading on this workstream has helped produced a rigorous, high quality research product for FTTSS, however restrictions of the academic calendar meant that they could not always provide the most flexible, in-country resourcing for operational research which by its nature requires high levels of project-based activities. This should be considered in identifying the new workstream leader. A further decision on personnel to support this workstream and planned OR are pending following completion of GEP3’s redesign.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
EDOREN to develop a knowledge management/dissemination plan for all operational research activities at design stage (on-going).

EDOREN to develop policy on ethical standards (March 2015)

EDOREN to draft an Operational Research Strategy (Sept 2015).

EDOREN to propose new workstream leader (April 2015).

Workstream	Quantitative data quality review: Demonstrable improvements in the quality assessment of DFID project, State and Federal education data.
Workstream number		3	Workstream Score	A
Risk:		Medium	Impact weighting (%):	15
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Output(s)	Milestones	Progress
3.1 Quality of key and already available basic education data assessed	1. Review of National Household Surveys (Nov 2013)	1. Completed (Nov 2013)
3.2 On-going quality assessment of future data collection activities within DFIDN education projects and EDOREN provided	2. Interim EMIS DQR tracking study/audit report for 2 GEP3 states (Feb 2014) / 3. Support GEP3 to conduct EMIS validation surveys / 4. Review of GEP3 TDNA/GEPLA (Jan 2014) / 5. Ex-ante survey review of DEEPEN baseline (March 2014) / 6. Ex-ante survey review of ESSPIN survey of school and community-level indicators (Aug 2014) / 7. Ex-ante survey review of EDOREN school effectiveness surveys (if applicable, WS5; Aug 2014) / 8.. Ex-ante survey review of proposed EDOREN/GEP3 girls out of school survey (if applicable, WS1, Aug 2014)	2/3. Support to the 2013/14 ASC was revised due to delays in carrying out the survey. EDOREN provided more intensive support to planning and delivery of the ASC than originally envisaged. / 4. Draft completed (May 2014) / 5. Final draft received (May 2014), to be finalised by end Aug 2014. / 6. EDOREN provided methodological support to Composite Survey design / 7 and 8. Postponed linked to GEP3 redesign.
3.3 Harmonisation of methodologies and concepts, particularly across DFIDN education projects, improved	9. Review of GEP3 and ESSPIN data collection approaches, recommendations for areas of potential harmonisation	9. No review report with recommendations received. On-going work reported in quarterly report including EDOREN support to LGEA database work and harmonisation work undertaken as part of workstream 1. .
3.4 Deeper analysis of existing education data supported or conducted.	10. Report on secondary analysis of existing household survey data (Jan 2014)	10. Final draft received (May 2014)

Key Points
Deliverables under this workstream have been completed (where still appropriate), but there have been slippages in the timeframe of delivery, and some change in scope to respond to needs. For example EDOREN have provided significant support to GEP3 to conduct the 2013/14 Annual School Census (ASC), including conducting training and helping to monitor field work and data processing. EDOREN have provided a summary of lessons learnt from this experience and recommendations for the way forward. They have also supported GEP3 to develop their EMIS strategy as part of GEP3’s redesign and identified other areas of support such as schools database and harmonisation workshop.

Activities under this workstream have focused on a combination of specific data collection work, such as TDNA and GEPLA. A majority of the focus has been on GEP3. Moving forward EDOREN’s support to all DFID’s education projects should be reflected in the logframe. As well as ensuring quality assurance of data collection there are lessons and good practices that should be shared between projects on achieving this. EDOREN should begin to systematically capture and share this. Lessons should also be learnt from ESSPIN on the capturing of evidence as a project scales up, and implementation of their composite surveys.

Reporting of activities under 3.3 could be strengthened so that DFID is fully aware of depth of work and recommendations going forward. Monitoring progress within this workstream is a key area to be clarified within the logframe. This will include monitoring the follow up of recommendations of review work undertaken under outputs. More broadly EDOREN should consider how activities under workstream 3 feed into activities under workstream 4 around the use of data and associated capacity requirements. For example how can improved quality of data collected in Annual School Census or surveys be communicated and used to encourage further data analysis and communicated to improve its use in policy-making and planning?

More opportunities could be made to capitalise and share the work undertaken independently of the DFID education projects. For example, EDOREN have been working with OECD/Paris 21 on standardisation of methodology and indicators for education statistics. A concept note on future work in this area is expected. This should draw out the implications for DFID and each of the projects. Similarly EDOREN have been in contact with RTI for discussions around the NEDS 2015. There are potentially further opportunities here for influencing and stronger engagement around data harmonisation that EDOREN should explore. EDOREN could also take more of a strategic leadership role in advising projects on the post-2015 agenda and implications of new goals and indicators.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations

EDOREN to include within their knowledge sharing work mechanisms (e.g newsletter, portfolio meetings, policy or evidence briefs) to share updates from their work on independent activities e.g. progress on the NEDS, with DFID and its education projects, highlighting implications for the projects (February 2015). EDOREN to capture this within knowledge management plans for all future review work.

EDOREN to include within their knowledge sharing plan processes and tools through which to regularly capture lessons learnt on data quality and harmonisation and ensure review recommendations are followed up (February 2015)

Workstream	Knowledge Management: Demonstrable improvement in access to and the capacity to use robust basic education data, research and evaluation
Workstream number		4	Workstream Score	B
Risk:		Low/Medium/High	Impact weighting (%):	10
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Output(s)	Milestones	Progress
4.1 An EDOREN repository of knowledge on basic education in Nigeria is created	1. Literature review database updated and made public (Nov 2013) / 2. Publication of EDOREN Household Survey report and Literature Review (Jan 2014) / 3. Research capacity database and mapping exercise completed (Dec 2013) and published (Jan 2014), then updated / 4. Library created at EDOREN office and open to the public (Jan 2014)	1. Over 1,000 entries in database. Website to be launched in Year 2 Q1 / 2. Literature review published online (full report + executive summary). / 3. Initial mapping undertaken and published on website. / 4. Not completed.
4.2 Core knowledge base of ‘what works’ in basic education in Nigeria distilled	5. List of distillation reports to be agreed with DFID following publication of literature review	5. Work on-going. List of distillation reports to be agreed
4.3 In context specific ways basic education knowledge for key Nigerian stakeholders communicated effectively	6. EDOREN dissemination plan (Dec 2013) / 7. Knowledge sharing plan agreed (Oct 2013) / 8. Annual conference to share research findings	6. Not completed. / 7. First draft shared for comment (Nov 2013) but not taken forward / 8. Agreed to postpone, following development of further plans and identification of key policy opportunities
4.4 GEP3’s knowledge management strategies improved	9. Agreed knowledge management support with GEP3 (Oct 2013) / 10. Review of KM approach (Sept 2013)	9. Discussions held between GEP3 and EDOREN, final nature of support to be agreed after redesign. / 10. On-going, delays linked to PIP and redesign

Key Points
Key achievements under this workstream include work on the literature review database, publication of the literature review and launch of the website. In addition, two education portfolio meetings have been held to date (March and June 2014). These have provided opportunities for projects to discuss areas of synergy and thematic issues of common interest. These are a useful platform for inter-project discussion and learning. Going forward EDOREN should consider and agree with DFID how these meetings can be used to achieve specific objectives alongside the broader aim of knowledge management, so that there are tangible outputs and actions around joint areas of work resulting from these meetings.

Whilst a number of milestones have been met under this milestone there are opportunities to achieve more and extend this workstream further. Unlike other workstreams this is an area less affected by dependencies on other education projects to achieve deliverables and where a solid foundation for knowledge management processes should have been established during EDOREN’s first year of operation, but strategic activities under this workstream are still in development. A draft dissemination strategy was shared with the review team. This includes a helpful knowledge mobilisation plan template that should become standard practice to complete at the start of all research activities. The document also includes discussion of monitoring indicators to track the effectiveness of different types of products. These indicators should be included within the knowledge mobilisation plan for all research outputs with details of how they will be monitored and by whom. The plan also details a number of interesting formats for dissemination beyond reports and policy briefs including presentations, data visuals, blogs and radio. These should be explored by EDOREN as future dissemination plans are developed. There are also opportunities to strengthen linkages with DFID’s RED team for dissemination and knowledge sharing for sharing of information but also to learn from each other on ways to improve research update and monitoring of this.

EDOREN should reflect on strategy and approach for internal sharing and learning within DFID’s education portfolio as well as EDOREN’s broader focus of improving access to and use of basic education, research and evaluation. Building upon existing forums for engagement (particularly the PEC and portfolio meetings) EDOREN should continue to play a facilitator role in establishing mechanisms to improve evidence based dialogue between projects. When finalising the final knowledge sharing and dissemination plans EDOREN should reflect on the management structures in place to support and embed these activities. Effective dissemination and knowledge sharing should be timely, opportunistic and relevantly positioned. In-country support to respond to emerging opportunities for better knowledge sharing and dissemination should be strengthened with Government and programme counterparts. To date the Country Director has played a key role here and capacity is now increasing with the introduction of the programme officer’s role.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
EDOREN to establish a regular, systematic process for updating the literature databases and assessing quality of new updates (February 2015).

EDOREN to finalise dissemination strategy including templates for research and review activities (January 2015).

EDOREN to develop knowledge management/dissemination plans for all future research and review work (ongoing) and retrospectively for completed review work (January 2015).This should include strategies for internal sharing and learning as well as external dissemination, and a mapping of all current and planned research activities being undertaken across DFID Nigeria’s education portfolio.

EDOREN to register with DFID’s research website, R4D, as a platform to further disseminate research outputs.

DFID to facilitating linkages with DFID’s Research and Evidence Department (RED) to support workstream activities (February 2015).

Workstream	Thematic research: Provide significant policy and practice insights on how to improve basic education in Nigeria
Workstream number		5	Workstream Score	A
Risk:		Low/Medium/High	Impact weighting (%):	20
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Output(s)	Milestones	Progress
5.1 Thematic study designed and conducted	1. Thematic research proposal (Nov 2013) / 2. Thematic research design study (Aug 2014)	1. Research proposal completed and discussed with DFID at June PMC meeting. / 2. Work on studies was postponed to allow further consultation with DFID projects and discussion with DFID Education team. Consultant to lead on teacher deployment and management study has been identified.

Key Points
As set out in EDOREN’s TORs thematic research work is still at its early stages. Proposals for thematic research were developed in early 2014 and presented to DFID for discussion at the June quarterly meeting. Chosen studies were drawn from priority themes and research gaps identified in EDOREN’s literature review. They were also subject to discussion with education partners. Proposed areas of research include (i) review of UBEC reforms, (ii) education and conflict in northern Nigeria, (iii) teacher deployment and management, and (iv) student voice. It was agreed with DFID to proceed with research on UBEC and teacher deployment during Year 2. Research on conflict and education was postponed pending the publication of ESSPIN’s research with Save the Children that assesses the effects of conflict on education.

As research studies move forward the governance arrangements for each study should be formalised to provide additional guidance and broader stakeholder engagement in the research.

Leadership of this workstream has passed from Dr Paul Bennell to Ian MacAuslan.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations

EDOREN to establish Steering Committees for thematic research studies (January 2015).

Workstream	Strategy/PEA/capacity: Manage EDOREN to maximise contribution to outcomes through cross-workstream coordination synergy and learning, and embedding in Nigeria context
Workstream number		6	Workstream Score	B
Risk:		Low/Medium/High	Impact weighting (%):	10
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Output(s)[2]	Milestones	Progress
6.1 Capacity to generate and use quality education data assessed and improved	1. Individual workstream capacity development strategies (Nov 2013). / 2. Capacity strengthening strategy paper (Sept 2014)	1. Capacity building activities undertaken within workstreams but strategies not produced. / 2. Draft phase 1 findings to inform strategy produced (Aug 2014)
6.2 DFIDN education projects’ use of PEA improved	3. PEA in 2 GEP3 States (Feb 2013)	3. Final draft PEA report completed (June 2014)
6.3 Understanding of PEA in basic education in Nigeria improved
6.4 DFIDN post-2016 education strategy improved
[2] EDOREN’s inception report considers PEA to be a cross-cutting that underpins all work rather than a distinct workstream. However the M&E framework in the Inception Report includes these outputs and milestones, so they have been used to report on within this Annual Report. .

Key Points
DFID agreed with EDOREN that work on political economy analysis would initially focus on support to GEP3. EDOREN worked with UNICEF on the development and implementation of the PEA study “Leveraging State Resources for Girls’ Education” which examined the political and institutional factors affecting financing of girls’ education in Zamfara and Niger states. This detailed analysis was well received by UNICEF. Further work still needs to be undertaken with UNICEF to develop PEA template for state level PE assessments and to strengthen regular reporting. The place of PEA within the overall project outputs needs to be clarified in the revised logframe.

In addition to the main workstreams and support to PEA, the inception report included deliverables for capacity development. Rather than being conceived as a standalone workstream, capacity development activities have been integrated across the workstreams. It was originally planned that specific strategies documents would be developed for each workstream within the first quarter. This has not happened. Instead focus has been placed on developing a long-term strategy by September 2014, unfortunately this was not complete at the time of the review as planned.

Several ideas for the direction of capacity development within EDOREN were articulated during interviews with the EDOREN management team. These now need to be articulated in a final strategy as soon as possible. A draft report of findings from desk review, interview and a stakeholder workshop was shared with the review team. These findings will be used to inform EDOREN’s capacity strengthening strategy. The report also recommended undertaking further situational assessment of capacity for demand and supply of evidence for decision-making and a baseline study in two States. Finalisation of the capacity development strategy should be a priority for EDOREN going forward given that this is central for delivery of outcomes.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
EDOREN to include PEA and CB as output areas in revised logframe (February 2014)
EDOREN to finalise capacity development strategy (Nov 2014)

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

A significant proportion of budgeted costs related to project activities, particularly fieldwork for surveys. There is a risk that the costs of some of these activities may be negatively affected by the deteriorating security situation in the north of Nigeria.

EDOREN share office space with other DFID-funded projects. They have a cost-share agreement on rent, maintenance, security, transport, connectivity, equipment and administrative staff reducing the average costs of these items to the project.

EDOREN’s current accounting has been based on workstreams and by DFID education project. EDOREN plan to shift to task-based accounting in Year 2. This will allow more detailed unit cost analysis.

Having a project that provides support functions across DFID Nigeria’s education portfolio provides value for money through consistency of approach, development of effective working relationships with project teams and development of local survey and research capacity.

VfM performance compared to the original VfM proposition in the business case

EDOREN committed to develop a VFM strategy by November 2014 within their inception report. A draft of the strategy was not available at the time of the review.

Assessment of whether the programme continues to represent value for money
VFM assessment will be made in 2015 based on agreed strategy.

Quality of financial management
An internal audit is planned for November/December 2014.

The shift to activity-based accounting should also improve financial projections and expenditure forecasting

Date of last narrative financial report	TBA
Date of last audited annual statement	TBA

E: RISK (½ page)

Overall risk rating: Low/Medium/High

Overview of programme risk
The deteriorating security context and potential for unrest around the elections in February 2015 represents a risk for all DFID projects to undertaking work in northern Nigeria. Security support to EDOREN has been consolidated with other OPM projects in Nigeria under the leadership of security consultants, Spearfish.

A continued operational risk for EDOREN is their dependence on inputs from other DFID education projects to complete their deliverables. Hopefully the risks around this will decrease over year 2 following the completion of the GEP3 redesign and as DEEPEN and TDP move from inception to delivery. Risk mitigation strategies should continue to be put in place and monitored closely with DFID.

EDOREN’s risk management approach involves regular update of “risk inventories” by the project manager, country director and workstream leaders. These are then consolidated within a risk matrix. This was reported in first quarterly reports, but no further updates have been provided. This should be routinely reported on in Quarterly and Annual Reports.

The revised Theory of Change (May 2014) seeks to expand upon assumptions and link to risk registry.

Outstanding actions from risk assessment
N/A