POST-2015 DELIVERY FUND RESULTS FRAMEWORK

Outcome by September 2015	Indicators		Delivery Date if not by September	Risk		Impact Weighting
CiC Research Project (204932-101)
Senior figures in key capitals with the seniority to catalyse cross-governmental conversations at home, will have been identified. CiC will have worked with this group and a wider set of opinion formers who can stimulate thinking, with the aim to increase their interactions, explore potential flashpoints, develop a stronger narrative, reframe contentious issues and increase ambition on each agenda item / The development of sharper political strategies among the proposed informal network of pathfinders, and a wider range of stakeholders, by delving deeper into issues too broad brush to advance negotiations / Results delivered through implementing a strategy for influence, outreach and communications	Indicator / Substantive and facilitative support to the ‘pathfinder network’. CiC will take undertake a facilitative role, working with project partners to identify key stakeholders to participate in an informal network, and undertake political ‘pathfinding’ research and analysis to support this network / Milestones / 4 meetings per year on behalf of and facilitated by the network (retreats and side meetings during intergovernmental negotiation sessions) / Written outputs tailored to pushing forward the debate at each interaction, focused on the post-2015 narrative, on levels of ambition for goals and for implementation, and on crunching through areas of contention and potential solutions. / Indicator / Focused research work on flashpoint issues, solutions to political divisions and major questions of ambition, delivery and implementation / Milestones / A series of short (2-4 page) briefing papers on flashpoint issues, including CBDR, MOI, the FFD summit, the new data revolution, the role of the private sector and peaceful societies. / A second series of longer papers that will stimulate the ‘solutions debate’ – drawing together existing national, regional and global initiatives that demonstrate how priorities can be delivered and by whom. These papers will help drive the focus beyond 2015 and will cover both contentious sectoral issues and broader implementation questions. / Continuous update of CiC’s ‘What Happens Now?’ series, with a focus on the priorities and potential underlying interests of key countries and blocs. Based on intensive canvassing of member state views in NYC and in capitals, the information will be shared with the informal network of pathfinders and the UN secretariat. / A single volume of all papers (also available online) together with an over-arching agenda-setting paper taking stock of the state of negotiations and setting out a big picture proposal for what can realistically be achieved at the September summit. To be the go-to scene setter for the large numbers of policymakers and other actors who would become players at this late stage. / Final volume taking stock of international agreements and implementation commitments. / Indicator / CiC will serve as an advisory resource to the UN Secretary-General’s Office, other relevant parts of the UN, and influential member states, by providing drafting support, and advice, ideas and political intelligence for the UN and progressively minded Missions is New York / Milestones / Outreach and communications activities in capitals through follow-up presentations to publications and participation in discussions in capitals. / Dissemination of findings through a dedicated on-line strategic communications plan to key stakeholders.	Ongoing / May/June 2015 / March 2016		Low		8%
Saferworld (with CiC) (204932-102)
Increased awareness among policy makers and influencers across the broad range of member states regarding the linkages between conflict, violence and development, and thus of the importance of addressing conflict and violence in the post-2015 framework / Increased dialogue among different stakeholders (from rising powers, traditional donors, and conflict-affected states) about their respective perspectives, positions and policies, in order to help build consensus around this agenda / A research base, including policy and actor analysis, and policy options on how this agenda can effectively be included in the new international development framework	Indicator / Analysis of stakeholders’ positions and policies on the inclusion of conflict and violence in the post-2015 agreement / Milestones / Regular monitoring and updating of the baseline assessments to reflect changes in perspectives, policies and positions of the five rising powers. / Face-to-face meetings with project partners and donors to provide regular updates on current perspectives, positions and policies of the five rising powers. / Continuous engagement with key stakeholders in NYC to assess the state of play of the post-2015 debates, including meeting with Member States and key institutional actors. / Indicator / Increased dialogue and engagement between policy makers and influencers from rising powers, traditional donors and conflict-affected states on the need to address conflict and violence in the post-2015 framework / Milestones / Organisation of further Track 2 expert-level dialogue seminars in rising powers. / A further four dialogue events on conflict, violence and the post-2015 framework with a broad range of stakeholders in NYC. Saferworld participation in CiC-led activities in NYC, with the aim of providing opportunities for dialogue to bridge differences and debate approaches to integrating conflict and fragility issues into the new development framework. / Organisation of two regional consultations in Africa and Latin America, targeting African Union members in Nairobi or Addis, and Latin American states in Mexico City. Timed to inform key meetings by members of the AU and Latin American states on post-2015 issues. / With national partner organisations, the organisation of further Track 1.5 dialogue seminars in rising powers to raise awareness among both policy makers and influencers of the need to address conflict and violence in the post-2015 framework. / Facilitation of 50 bilateral meetings between representatives from conflict-affected states and policy makers and influencers in rising powers on the need to address conflict and violence in the post-2015 agenda. / Organisation of a side-event at UNGA 2014 to convene a roundtable in order to promote the peaceful and safe societies agenda. / Co-organisation of a high-level conference with Wilton Park in Istanbul on ‘Linking peace, stability and development: engaging new global actors in the debate’. / Indicator / Evidence base and options on how to include conflict and violence in the post-2015 agenda, which are sensitive to the perspectives and principles of different stakeholders, are shared with key actors / Milestones / Continuous research on options for the inclusion of conflict and fragility issues into the post-2015 agenda. This research work will recommend areas where dialogue between key stakeholders is needed as they work to build consensus. / Four further briefing papers, developed and published by CiC that draw on research and consultations with a wide range of member-state and institutional stakeholders in NYC on the issues of conflict and fragility. These papers will serve as the basis for informed discourse surrounding the inclusion of conflict and fragility issues, and provoke new thinking on these issues among decision makers. / Continuous publication of briefing papers, blogs and video-blogs on the policies, positions and perspectives of rising powers on conflict and development in post-2015, to raise awareness of their perspectives and principles. / Continuous engagement with policy actors in London, Brussels and other European capitals to share perspectives, positions and concerns emerging from the dialogue in rising powers. / Ongoing bilateral meetings with US stakeholders from CiC. / Extensive bilateral meetings with policy makers and influencers in rising powers to discuss options on how to include conflict and violence in the post-2015 agenda. / Organisation of a Seminar on Peace, Security and Governance in the post-2015 development debate in the Hague. / Production of a final report summarising the outcomes of the overall project to synthesize the outcomes of the policy analysis, political outreach, convening and research work carried out by both Saferworld and CiC	Ongoing / September 2014 / December 2014 / Ongoing / Ongoing / Ongoing / Ongoing / 2nd quarter of 2014		Medium		8%
Advocates for International Development (204932-103)
An event to inform and sensitise the audience to the ways that establishing a clear link between the Rule of Law (ROL) and development represents a paradigm shift from a simple reaffirmation of the MDGs to a post-2015 development agenda that is people-centred, that focuses on the root causes of poverty and addresses inequalities	Indicator / An introductory presentation that explains the shift from the MDGs to the SDGs; the reasons/objections for (not) including a ROL dimension in the post-2015 agenda; the language shift in Goal 16 from ROL to access to justice and the consequences thereof / Three papers that explore arguments (exemplified through Goal 16 and specific targets currently included in the SDGs) in favour of the integration of a stand-alone goal on the ROL in the post-2015 agenda as an essential element to a successful and sustainable development framework. / An intervention on measurement and indicators that will contest the argument that the ROL is not measurable. This will use examples related to the targets discussed in the receding section. / An exploration of how the ROL is of equal importance for developed and developing countries, looking at the universality of the element of the ROL; their adaptability to domestic priorities; the measurability of the targets given existing statistical data that could cover these topics; and accordingly its place in Goal 16. Discussion will be a key part of this session.			Low	8%
Save the Children Reality Check Roundtables (204932-104)
National leaders articulate the challenges the SDGs present in their current form and how these could be addressed through the intergovernmental negotiations / The exercise acts as a useful ‘litmus test’ for Member State alignment on implementation issue and acts to help identify likely allies in advocating for a Framework that works / Governments become sensitised to the financial (and non-financial) resources required to deliver the SDGs – with roundtable dialogues possibly fedding into the Financing for Development negotiations track	Indicators / Amplifying the voices of non-Northern government officials on the implications/challenges of implementing the SDGs (in their current form) / Making the case for ‘implementability’ as the main success indicator of the Framework (demonstrating the casual link between focus and delivery) / Creation of the political space for a continued conversation in 2015 to ensure delivery of a Framework that works at national level / Overall: An outcome document that includes a summary of the top-line findings from the series of roundtables that synthesises messages on what works, doesn’t work and flags asks and obstacles from participants. To be shared with delegates in NYC and govt representatives in key capitals. / Possible physical session in NYC, bringing together representatives from the national roundtables and sharing the key findings of the dialogues with insider audience.			Low	8%
United Nations Secretary-General’s International Expert Advisory Group (IEAG) (204932-105)
To provide a point of reference on the discussion of data and statistics needed to underpin the new development agenda. The recommendations of the IEAG will inform the Synthesis Report of the Secretary-General and the subsequent intergovernmental process anticipated thereafter, including the work if the HLPF	Indicator / The IEAG will craft a strategic framework and advise the Secretary-General on what the “data revolution for development” would mean in practice, how it can be funded and what institutional and governance implications it would possibly entail. / Milestones / An IEAG report to inform the Secretary-General’s Synthesis Report on Post-2015 that provides recommendations on: / A definition of data revolution and illustration of what data revolution would concretely mean nationally, regionally and internationally / The status of all ongoing initiatives on the data revolution for post-2015 and how they can best be connected to achieve maximum synergies / The means of implementation and funding to fill critical gaps in the production, in all these areas and use of statistics, including by reinforcing national capacities in all of these areas and introducing innovation in the use of ICTs / Opportunities to take advantage of big data / A proposed strategy for scaling up successful approaches to increasing the availability and accessibility of data / Possible outreach and advocacy activities to maintain the high visibility of the recommendations of the group and to facilitate their implementation		31 October 2014	Low	8%
Save the Children/ Action 2015 (204932-106)
The convention of an active national civil society coalition of at least 100 organisations in each, reflecting a range of sectors and thematic priorities / National coalitions are fully engaged in campaign planning and decision-making through key governance functions such as the Campaign Assemblies and Action Teams / National coalitions effectively deliver agreed campaign delivery moments, with a focus on full preparation for and participation for and participation in the January 2015 launch	Indicators / An elected, geographically representative Reference Group (one man and one woman from seven regions around the world) overseeing delivery through task-oriented Action Teams. / A prominent group of Nobel Laureates, moral and religious leaders and social justice campaigners sending a strongly-worded open letter on behalf of the campaign (picked up by the media around the world) calling on world leaders to make 2015 a transformative year. / Creation of global moments to push ambition levels at key 2015 decision points. For example the January 2015 launch, and before the final agreement on the SDGs in September. / Indicators / From a campaign implementation perspective, the campaign will track levels of ambition and engagement in our priority countries as a primary measure. / It will also measure awareness of and participation in the campaign. Metrics will include the number of supporters who have watched a film, taken an online action, taken an offline action, or attended an event. / An in-depth review of action/2015 will follow the culmination of the campaign, as with the recent Enough Food For Everyone IF Campaign.			Medium	10%
UNDP Governance Pilot (204932-107)
An initial feasibility study on the implementation of a ‘governance’ goal in the UK that will be a technical exercise assessing the theory of change, potential indicators, data sources, reporting and capacity requirements and other issues regarding measurability.	Indicators / The study will inform the inter-governmental negotiation process as it unfolds (it is often stated that governance isn’t measurable) and highlight to UK government departments any steps that would need to be taken to satisfactorily set, implement and report against a universal post-2015 goal on governance / Milestones / A brief theory of change outlining how each target could be reached, with indicators at each step. / A technical description of how national statistics (or other UK data) can be used to measure each indicator, an assessment of the extent to which these data are generally collected in national statistics, and a description of the additional burden it would entail to begin collecting it / A description of any data gaps which preclude us from measuring any of the targets in the UK at present, alongside a proposal of how these data could be collected by ONS or other UK government bodies, and an estimate of the burden and cost which this would impose on the collecting agency / Issues highlighted with OWG’s proposed targets in relation to their measurability			Medium	10%
Copenhagen Consensus Center (204932-108)
Seminars to ensure media coverage of the post-2015 process with regards to choosing the smartest targets, focusing on the costs and benefits of each target	Indicators / Five articles on the post-2015 process from each journalist at the seminars / A movement of journalist asking the hard questions of national politicians and diplomats, with a vested interest in following up on the promises and possible failures over the next 15 years. / Milestones / Of the three cities that DFID will co-fund the seminars for, at least 15 journalists will write extensively about the target setting process, generating at least 75 articles on the post-2015 process / Material generated for the country specific presentations will generate three op-eds (one for each country) by CCC/Bjorn Lomborg. / 9 country-specific videos on especially interesting topics for the three countries / 9 economic position papers by CCC experts in the chosen topics for each country			Low	8%
Mexico-UK Post-2015 Event (204932-109)
An informal space for reflection on the post-2015 process to date and discussion ahead of the upcoming consultation on goals and targets in New York / Perspectives shared on key issues, including Rule of Law/Goal 16, and how to ensure the final framework is implementable and measurable	Consolidation of the consensus among UN member states around proposed Sustainable Development Goal 16 on peaceful and inclusive societies, good governance, and access to justice.			Low	8%
Least Developed Countries (LDCs) Trust Fund (204932-110)
The participation of developing countries, with priority to LDCs, at all meetings on negotiations	The support of travel and participation of the representatives from developing countries, in particular LDCs, in the meetings of the process of the intergovernmental negotiations on the post-2015 development agenda.			Low	8%
Business Leadership SDG Commission (204932-111)
The launch of an SDG Business Commission to support the implementation of the SDGs	DFID funding will be purely for the ‘inception period’ of this commission, but the outputs are as below: / Indicators / The setting up of a Global Private Sector Commission for the SDGs with a clear charter and mandate to engage the business community in the SDG agenda by July, ahead of the UNGA in September at which the SDGs will be formally approved. / The developing of recommendations for “fast track” actions that business can take to help deliver the SDGs as soon as they are formalized in September 2015 (some of which are already likely to be under development). / The creating of meaningful private sector-led taskforces for each of the main SDGs, together with a strategy and delivery plan that can mobilise a broad set of business players to be part of the solution. Ensuring that these taskforces complement and leverage existing efforts, such as SE4All, UNGC.			Low	8%
Post-2015 Events at UNGA 2015 (204932-112)
Funding for the DFID led/involved events at UNGA 2015	Indicators / A ‘Leave No One Behind’ Event to position the UK as an SDG leader / A Secretary of State hosted Event on the Economic Empowerment of Women & Girls to position the UK as an SDG leader.			High	8%