Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Yemen Social Fund for Development
Programme Value: £100,000,000		Review Date: January 2016
Programme Code: 201427	Start Date: 10/05/2010	End Date: 31/12/ 2016

Summary of Programme Performance
Year	2011	2012	2013	2014	2015	2016
Programme Score	n/a	A	A	A	A	A
Risk Rating	High	High	Medium	Medium	Medium	High

Summary of progress and lessons learnt since last review

This review was completed by the 31st January as required by DFID’s programme management rules, in the midst of a major ongoing humanitarian crisis and open conflict in Yemen. In September 2014, following years of conflict with government and tribal forces, the Houthis staged a de-facto takeover of the capital Sana’a. Following a failed peace deal and with support from forces loyal to former President Saleh, the Houthis consolidated their control over northern Yemen in early 2015 and attacked President Hadi in Aden in mid-March. In response, at the request of President Hadi, a Coalition of mainly GCC countries began military action in Yemen on 26 March.

This review is based on SFD’s reporting of their progress during 2015 which was shared with us via two Progress Reports (Sept 2014-March 2015; and April-September 2015) and partly presented at a technical meeting of SFD and partners held in Amman in early November 2015.

SFD have operated under very difficult working conditions since the conflict started in March. These include: damage to their headquarters in Sana’a leading to relocation to a safer, temporary office; frequent temporary closures of Branch Offices (BO) in Aden and Taiz (with Taiz BO remaining closed); reduced working hours; relocation to third countries of certain key staff (who have continued to work remotely); acute fuel and electricity shortages; and the daily threat to personal security of SFD staff.

As at September 2015, SFD had 93 active projects out of a portfolio of 1841 projects registered in their MIS as “under implementation”, and mainly in the labour-intensive public works and water sectors. During April–September 2015, SFD completed 119 projects compared to 670 projects completed during the period October 2014-March 2015.

Significant sources of funding have been suspended (formally or informally) or delayed. The World Bank’s suspension of all disbursements to Yemen in early March has been particularly challenging for SFD. Disbursement in the period April-September 2015 was $13.5 million, compared to $63.7 million in the preceding six-month period (October 2014-March 2015), and $109.1 million in the 12 months before. During this same period, only 11 new projects had been assigned to a source of funding (compared to 111 in 2014 and 738 in 2013). On the positive side, in December, SFD reported verbally that the number of active projects had increased slightly (to 138); and that in November they had had the highest disbursement rate since the war started. While these are welcome improvements, the situation remains dire if compared to SFD’s historic performance rates.

SFD has remained resilient and have responded in a flexible and pragmatic manner to these challenges. They have adapted their existing risk management strategies and used their local knowledge and networks to deliver where conditions and funding have allowed.

SFD’s Director has maintained regular dialogue with the Chair of their SFD Board (Prime Minister/Vice President Bahah currently based in KSA). VP Bahah has indicated he expects SFD to have an important role in any post-conflict recovery and reconstruction phase.

SFD have largely met the milestones against Output 1 (which carries a 70% weighting against DFID commitment) and only moderately not met milestones against the other outputs. Despite all the difficulties and scaled down operations, SFD has been able to deliver because it had made strong progress in previous years. This is a marker of their reach and experience in Yemen given the current context.

Currently, the two major challenges for SFD are the active conflict and the lack of funding. The coming year will be an important one for SFD. In the second half of 2015, they undertook strategic thinking on their future plans and in July produced a draft Crisis Response Paper outlining plans for an extended Phase IV, as well as their role in a post-conflict recovery context. We encouraged them to consider meeting with partners to share their plans and, with financing from the World Bank, this meeting took place in Amman in November 2015. With support from a World Bank-funded consultant and on basis of inputs from partners, SFD shared a revised proposal with partners in late December. DFID is currently considering this.

Summary of recommendations for the next year

For SFD	For DFID
Extension of Phase IV
Finalise proposal and raise donor funds	Continue to engage with process (including sharing consolidated DFID comments on the proposal) and in coordination with other donors
Agree an extended MoU to cover the additional year of support and accompanying Logframe targets
Financing Gap
Continue lobbying donors for funding and provide an update on the latest financial position and progress on securing new donor funding at next Joint Donor Review meeting.	Lobby GoY and donors to ensure release of existing pledged or suspended or delayed funds, or to re-prioritise other pledges to support SFD.
Enact sensible cost-saving measures that provide good value for money but do not negatively affect the organisation’s operational integrity	Continue to monitor SFD’s financing shortfall closely, including its impact on the operational integrity of SFD.
	Encourage a wider mix of long-term donor support to ensure that SFD can continue to perform with efficiency through donor funds being coordinated and through delivery of resources at a national scale
Programmatic Issues
Undertake regular scenario planning to adapt to any change in context on the ground
Ensure that any decisions to build or rehabilitate education or health infrastructure are based on clear agreements for maintenance with relevant stakeholders.	Monitor implementation in its regular meetings with SFD.
Provide regular assessments of the feasibility of multi-year LIWP.	Consider removing the multi-year indicator from our logframe for the next 12 months.
Financial Management
Continue to closely monitor the status of the Yemeni banking and financial system in order to mitigate any developing risks as well as to report them to donors.	Monitor Yemeni and international banking system, in order to alert SFD and donors of potential barriers to get funding to SFD in Yemen.
	Advocate the use of non-earmarked funding by other donors to improve effectiveness and flexibility
	Complete the desk-based Due Diligence Assessment by March 2016. / Engage with the findings of the updated Fiduciary Risk Assessment (FRA) contracted by the EU in December 2015 and due in the next three months.
Monitoring and Evaluation
SFD to continue to engage with DFID’s Independent Monitoring programme and use the findings to improve performance and inform Phase IV extension.	Share results of Independent Monitoring studies and encourage cooperative Monitoring and Evaluation amongst donors. Identify what further Independent Monitoring for SFD we will plan to conduct.
With DFID, SFD should formally establish metrics to measure VFM (e.g. through the ‘3E’ methodology). Leading candidates could include: / Economy: Administration fee. / Efficiency: disbursement ratio. / Effectiveness: % of projects meeting or exceeding expectations. / Cost effectiveness: disbursement rate, cost per beneficiary.	Maintain and improve communications with SFD management in order to keep up to date on situation on ground and together address any emerging risks. / Establish a regular monthly tele/video conference with key partners (building on momentum of Nov 2015 Amman meeting) and ensure to develop direct relationships with Gulf donors to SFD. / Maintain close contact with the WB Country Manager and SFD with respect to the proposal to exempt SFD from WB suspension of disbursements.
	Continue to monitor SFD’s value for money, including through measuring economy, efficiency and effectiveness indicators, and keeping a close track of SFD’s evolving responses to the current situation in Yemen.
DFID and SFD to jointly engage on the recommendations of the Independent Monitoring programme’s recent verification study and discuss with an action plan for response.
Act effectively upon the results of the National Demographic and Health Survey results when they are released	Agree a systematic process for agreeing future disbursements, including any additional evidence we will require SFD to submit with their requests and drawing on available information from other donors (i.e. the EU commissioned Fiduciary Risk Assessment).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Log frame

Outline of the programme
In 2010, DFID committed to provide £100 million over five years between January 2011 and December 2015 to Phase IV of the Yemeni Social Fund for Development (SFD) to improve access to basic services, enhance economic opportunities, and reduce the vulnerability for the poor.

DFID support will enable SFD to meet their overall aim to improve the lives of the Yemeni poor. The main objectives of our support are:
- Improve access to basic services, such as education and health facilities;
- Create economic opportunities and improve the business environment;
- Create employment opportunities for the poor; and
- Increase the ability of local authorities, NGOs, and communities to manage, monitor and evaluate development programmes.

This is a multi-donor supported project and DFID’s actual contribution equated to 24% of the SFD’s disbursed funds over the period 2011 to February 2015. This report assesses SFD’s overall performance on basis of the Results Framework agreed between SFD and partners (and of which our logframe is a sub-set). The key results currently attributable to DFID over the period January 2011 to February 2015 include:
- 79,000 pupils enrolled in SFD-supported schools[1]
  [1] Supported through reconstruction or rehabilitation
- 148,000 people provided with access to improved water sources (within 30 mins walking distance or less)
- 101,000 people benefitting from cash transfers in 2014 (61,000 in 2013, 37,000 in 2012.

Given the current situation – and following discussions with DFID and other partners - SFD have decided to extend current Phase IV rather than launching a new phase in 2016 as originally planned. This is a sensible approach which we have been encouraging since the conflict started. SFD are therefore planning a two-year extension and in late December submitted a proposal to partners which DFID is currently considering. In December, we agreed a no-cost extension of 12 months to allow disbursement of the outstanding £11.6 million. Individual disbursements will be made subject to an assessment of risks and benefits at that time.

Context

SFD’s Phase IV has been conducted in an extremely challenging political, economic and security context starting with the “Arab Spring” popular protests in 2011 that led to the resignation of Yemen’s President and started a period of political transition. The current conflict coupled with insecurity, political instability, restrictions on food and fuel deliveries, and economic crisis has led to a severe humanitarian crisis which has exacerbated Yemen’s already fragile situation as one of the poorest countries in the Middle East. The 2016 UN Humanitarian Needs Overview (HNO) estimates that 21 million people or 82% of the population need some form of humanitarian assistance. 7.6 million people are currently considered severely food insecure and 1.3 million under-fives are malnourished and 320,000 with severe acute malnutrition. Furthermore, approximately 19.3 million lack access to water or sanitation and 14.1 million cannot access basic health services. At least 1.8 million children have had to drop out of classes, adding to the 1.6 million who were already out of school before the crisis began.
The current context therefore means that the already challenging environment in which SFD was operating has significantly deteriorated. Significant sources of funding have been suspended (formally or informally) or delayed.While SFD has continued to operate in the more remote parts of the country, there are parts that they cannot now access. SFD regularly monitors accessibility by district with the last assessment of October 2015 indicating that 67 districts out of 330 were difficult to access. A number of SFD-supported projects (123 - predominantly schools) have been damaged (partially or totally). SFD have also worked hard to maintain their established political neutrality and organisational autonomy within a tense political environment in which the capital Sana’a (where SFD HQ are located) is under Houthi control.
As at September 2015, SFD had 93 active projects (mainly in the labour-intensive public works and water sectors) out of a portfolio of 1841 projects registered in their MIS as “under implementation”. The limited number of active projects is largely due to those donors who have continued regular disbursements namely Germany (KfW and GIZ), IsDB, the Arab Fund, and The Netherlands. DFID disbursed £1.5million in September for works completed up to the start of the conflict. This permitted SFD to clear outstanding obligations to contractors and beneficiaries. SFD’s engagement with donors has become more difficult since the majority of SFD’s donors are no longer present in country; there has been understandably increased scrutiny and more requests for assurances.
B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
This has been a challenging year for SFD. The combination of conflict, physical damage, fuel shortages, increased costs, and loss of funding has negatively impacted SFD’s ability to operate. However, SFD has shown resilience and has been able to continue activities in parts of the country. Indeed, SFD have repeatedly said that, were funding available, they would be able to do more.

Despite the challenges, we judge overall progress towards the outcome to be broadly on track. We expect our one year no-cost extension to allow SFD to use the DFID remaining funds.

Overall output score and description – A: Outputs met expectation
The output scores in this report are based on cumulative milestones (to Dec 2015). As such they assess the progress over the programme’s lifetime to date. It is recognised that performance over the past twelve months has been significantly affected by external factors; the narrative explains this for each output area. In determining this score, we have accounted for constraints to delivery against objectives which have been well beyond SFD’s control while at the same time acknowledging that progress against many of the milestones reflects stronger than expected delivery in the previous year: many targets were already in large parts achieved while SFD delivery this year has been by necessity very limited.

As the disbursement of £1.5million which we made in September 2015 was for work completed prior to end March 2015, we do not have any results directly attributable to DFID in 2015.

Key lessons
- SFD’s flexible approach and sound risk mitigation measures have helped them to remain active in a very challenging context.
- Regular and frequent dialogue with SFD has been mutually beneficial: it has informed our understanding of the situation on the ground and SFD’s understanding of our own operating context; and has allowed exchange of ideas on the way forward.
- UK diplomatic and donor support for SFD in discussions with both donors as well as the GoY has helped keep attention on SFD.
- Releasing a payment (£1.5 million in September for works completed) sent a positive signal to SFD as well as the international community.

Key actions
- Continue to support SFD in finalisation of Phase IV extension ensuring it is appropriate to current environment.
- Continue to work with SFD to develop plans for how they will support recovery.
- Work with other and potential new donors to secure funding for SFD e.g. WB to de-suspend, EU to start/scale up support, Gulf to resume.
- Continue to use all available channels to lobby for recognition of SFD’s role and capacity to support recovery in Yemen.
- Consult with SFD on possible areas for technical support and consider whether these can be delivered under current financial support framework.
- Support SFD’s capacity and neutrality.

Has the logframe been updated since the last review? No. The SFD Results Framework (RF) has not been amended this year, therefore we have not amended our logframe (which is a subset of the RF).

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Community and Local Development Programme: Basic Services Improved
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	70%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	2015 Milestone[2]	Cumulative achievements[3]
Number of classrooms constructed or rehabilitated	9000	8,943[4] (6148 constructed; 2795 rehabilitated)
Number of formal teachers trained	100 (male) / 100 (female)	200 (male)[5] / 226 (female)
Total km of rural roads built or upgraded	1300	1723[6]
Number of people provided with access to improved water sources (within 30 mins)	646,000	760,220[7]
Number of Primary Health Care workers qualified (3 year qualification) (sex disaggregated)	300 (male) / 300 (female)	231[8] (male) / 203 (female)
Number of people provided with access to improved sanitation facilities	265,000	227,234[9]
[2] This represents the total cumulative milestone since the start of Phase IV, January 2011 through to September 2015.
[3] These figures represent total cumulative results since the start of Phase IV, January 2011 through September 2015.
[4] Between April-September 2015, 91 schools were constructed and none rehabilitated
[5] Both targets for male and female had been reached by March 2015;
[6] This amount had been achieved by March 2015; no new activity between March and September 2015.
[7] Cumulative up to March 2015: 712,864. April to September 2015: 47,356.
[8] These were achieved by March 2015; no new activity was delivered between March and September 2015.
[9] Cumulative to March 2015: 224,594.

Key Points
From 2011-2014, SFD have been able to deliver the majority of their key targets, mostly due to good progress made in the previous years. They have exceeded expectations against 3 of the 6 indicators and nearly achieved the remaining three.

In 2015, SFD has been severely hampered by the armed conflict and the restrictions of movement of goods and imports into Yemen, which has led to increases in costs and slowdown of implementation by contractors. In addition, they have been limited by a lack of funds: they report that 450 projects under implementation were put on hold due to suspended or delayed donor funding.

On balance and taking into account the current challenges, we have scored them an A (“outputs met expectations”).

Education
The education sector represents a high proportion of SFD’s interventions in the Community and Local Development (CLD) programme. During 2011-2015, nearly 9,000 classrooms have been built and rehabilitated, and the newly constructed classroom space is expected to accommodate an estimated number of 133,790 boys (compared to the end 2015 target of 201,600) and 108,490 girls (against a target of 158,400).

During 2015, 19 infrastructure projects were completed with a total cost of $4.2 million. These included 91 new classrooms handed over to the Ministry of Education; constructing, furnishing, and equipping female student residences in Hajjah Governorate; and creating 70,500 workdays. The CLD also provided some limited capacity building on professional development and life skills.

Health
For Phase IV, SFD had developed a total of 481 projects for an estimated cost of USD 50.6 million, in partnership with the Ministry of Public Health and Population (MoPHP) and its governorate offices, and by September 2015, had completed 368 projects. Of these, only 4 were completed between April and September (at a total cost of $171,000). These included: construction / rehabilitation and equipment of a health facility; training of 20 community mid-wives on community-based maternal and newborn healthcare; and training of 45 physicians, medical assistants, and nurses on mental health.

Water and Environment
SFD exceeded the 2015 (cumulative) target for the indicators on access to improved water sources by March 2015. However, SFD delivered further results for this indicator by reaching an additional 47,356 people between April and September 2015.

In 2015, given the severe shortfall of funds, SFD has not approved any new projects during the reporting period. Moreover, SFD reports that the implementation of 419 subprojects approved and under implementation has been paused for about one year, and the amount of funds needed to close these subprojects is $38m.

Roads
During 2015, 8 projects were completed at a cost of US$2 million. However, SFD had already over-achieved their milestone (number of kilometres built) early in March 2015.

No new projects were started during the reporting period and the 108 projects that are under implementation, with an estimated cost of US$35.8 million and contracted amount of US$25.2 million, are on hold due to lack of funds.

Summary of responses to issues raised in previous annual reviews (where relevant)
In the education and health sectors, sustainability and maintenance of infrastructure remains a longer term challenge. Although this is the responsibility of GoY and/or communities and outside of SFD’s direct control, in future SFD should ensure that any decisions to build or rehabilitate infrastructure are based on clear agreements with relevant stakeholders. This is particularly relevant given the current conflict and likely future scarce resources.

Recommendations
- SFD should ensure that any decisions to build or rehabilitate education or health infrastructure are based on clear agreements for maintenance with relevant stakeholders.
- DFID should monitor implementation in its regular meetings with SFD.

Output Title	Small and micro enterprise development programme: Economic Opportunities Created
Output number per LF		2	Output Score	B
Risk:		High	Impact weighting (%):	5%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	2015 Milestone[10]	Cumulative achievements[11]
Number of active borrowers / % female / Number of additional branches in rural areas	100,000 / 60% female / 6 (rural)	103,837[12] / 56% / 6
Enabling Environment: Credit bureau legislation / regulation submitted to the government
Enabling Environment: Code of conduct regarding consumer protection adopted by Yemeni Microfinance network (YMN)	No milestone for 2015 as indicator was achieved in 2014	Completed in 2014
Financial Sustainability: Number of MFIs that are financially sustainable	7	1 out of 11[13]
[10] This represents the total cumulative milestone since the start of Phase IV, January 2011 through to September 2015.
[11] These figures represent total cumulative results since the start of Phase IV, January 2011 through September 2015.
[12] Down from 118, 223 in 2014.
[13] Same as 2014 and decreased from 2013

Key Points
On balance, we have scored this output a B (“outputs moderately did not meet expectations”) whilst recognising that SFD’s performance has been affected by a number of factors beyond its control. Though the number of borrowers has decreased compared to last year, SFD has gone over this target because last year it exceeded it by 30%. Similarly, SFD had already reached the target for new rural branches. However, this has been slightly offset by the percentage of female borrowers increasing but coming in below target and significantly offset by the drastic reduction in the number of MFIs that are financially sustainable.

The Small and Micro Enterprise Development (SMED) Unit has continued to provide financial and technical assistance to MFIs and other partners although its portfolio has declined steadily since the start of the conflict. The banking sector entered the crisis with a loan book that was highly vulnerable to defaults: according to the IMF, around 22% of bank loans were not being properly serviced by their customers[14]. According to the UNDP and the Small and Micro Enterprise Promotion Services (SMEPS)[15], between March and October, 35% of medium enterprises, 27% of small businesses, and 24% of micro businesses were forced to shut their doors compared to 17% of large firms. According to the SMED Unit, the loan portfolio quality of the microfinance sector deteriorated substantially in 2015, with 29% of the outstanding portfolio classed as ‘at risk’ in August 2015, compared to less than 5% in March 2015. This deterioration could continue as the situation worsens.
[14] Nonperforming loans to gross loans ratio. IMF Article IV, Yemen: http://www.imf.org/external/pubs/cat/longres.aspx?sk=41901.0 Accessed 5 Jan 16
[15] UNDP SMEPS Rapid Business Survey: Impact of the Yemen Crisis Report on Private Sector Activity: http://www.ye.undp.org/content/yemen/en/home/library/crisis_prevention_and_recovery/undp-smeps-rapid-business-survey.html Accessed 23 Dec 15

The SMED Unit report that only one Microfinance Institution (MFI) of the 11 which make up the sector was currently classed as ‘financially sustainable’. This is a strong downward trend from March 2014 when 5 of the 11 were financially sustainable, and means that SFD has not been able to achieve the target on this key indicator. According to SFD/MoPIC[16], one MFI has had its physical assets completely destroyed, and a further two have suffered substantial damage.
[16] Yemen Socio-Economic Update, MOPIC, No. 10, Dec 2015.

Overall, the current lending activity in Yemen is only a fraction of what it used to be prior to the war. However, SMED report that, although most MFIs have slowed their pace of lending, the majority have started to adapt to the new environment. Those operating in areas relatively less affected by conflict have developed new lending products for instance products for renewable energy (solar power). Most are now shifting their focus to rural and agriculture finance where there is a huge demand for microfinance services. Paradoxically, the conflict has raised new opportunities for MFIs in rural areas.

he Business Development Services represented by SMEPS was financially supported with an amount totaled 1.8 million U
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations

SFD’s proposal for extension of Phase IV should demonstrate how SMED (and SMEPS) have adapted. SFD should consider whether the indicator on financial sustainability remains realistic.

Despite contingency plans being implemented at sector level, there may be a situation which will necessitate a more strategic, systemic and wide reaching approach to donor support for the microfinance sector in a post-conflict scenario. SFD and SMED have been laying the ground for a number of post-conflict initiatives meant at reviving the microfinance sector[17], including a Credit Guarantee Fund (that would encourage MFIs to approach viable clients with insufficient collateral) and supporting solidarity funds (designed to compensate borrowers who suffer significant loss, physical damage or death). Moreover, SMED has produced a concept policy paper on capitalization of MFIs.[18] And DFID should maintain active policy engagement with Yemeni institutions on these issues.
[17] Social Fund for Development, op cit
[18] Social Fund for Development, op cit

DFID’s Economic Advisor should continue to develop relationships with SMED and SMEPS, both to support SFD’s current operations as well as to consider initiatives for the SME and microfinance sectors in the future. In doing this, DFID should incorporate lessons identified through its (closing) ‘Building Yemen’s Investment Climate’ programme.

Output Title	Labour Intensive Works Programme (LIWP): Reduced Vulnerability for the Poor
Output number per LF		3	Output Score	B
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No yes	Impact weighting % revised since last AR?	No

Indicator(s)	2015 Milestone[19]	Cumulative achievements[20]
Number of people directly benefitting from multi-year workfare[21] assistance in rural areas	90,000	0 (Start of multi-year assistance delayed)
Number of people directly benefitting from short term workfare assistance in: / Rural areas / Urban areas	Rural - 900,000 / Urban - 416,900	636,077 / 390,860 / (Total: 1,000,000)
Indirect beneficiaries: Number of days employment created under workfare assistance programme for multi-year activities in rural areas	1,417,000	0 (Start of multi-year assistance delayed)
Number of days employment created under workfare assistance programme for short term activities in: / rural areas / Urban areas	Rural – 13,100,000 / Urban – 2,640,000	8,800,000 / 1,800,000
Land: Total area of rehabilitated terraces and land (Hectares)	2,700	3,858
[19] This represents the total cumulative milestone since the start of Phase IV, January 2011 through to September 2015.. .
[20] These figures represent total cumulative results since the start of Phase IV, January 2011 through September 2015.
[21] Labour Intensive Works Programme

Key Points
The LIWP is one of the programmes which has been able to continue as SFD operations have shrunk in the current context. This is partly because SFD have themselves prioritised it as a measure which provides much-needed cash to households while creating community assets. SFD are also able to work in very remote areas which are less directly affected by the conflict. It is also partly because LIPW has been a priority for those donors who have continued disbursing, namely Germany (KfW) and IsDB. Our last payment of £1.5 million for works completed prior to the conflict starting contributed to clearing outstanding dues owed in this sector.

Nonetheless, since April (i.e. just after the war started), LIWP operations have slowed down significantly due to the shortfall of funds. For example, in the 6-month period April–September, only 23 projects were completed with a total cost of US$5.9 million; 8 new projects were approved with an estimated cost of US$1.6 million; and implementation of 61 projects at a cost of US$13.2 million continued.

As at end September 2015, LIWP had developed a cumulative total of 615 projects with an estimated cost of USD148.5 million. Of these, 213 projects have been implemented with an estimated cost of USD53 million. And, as of September 30, 2015, about 10.6 million workdays had been logged, and one million people had benefited from the transferred cash.

It is important to note that SFD had planned to start implementation of the multi-year cash for work interventions but this had to be suspended when the conflict started. SFD’s draft proposal for extended Phase IV indicates that SFD is looking to resume this from 2017 (when a Phase V could be launched subject to conditions allowing).

We have scored this output a B (“outputs moderately did not meet expectation”) although we recognise that SFD has been negatively impacted by factors outside of their control.

In future, SFD’s priority will be to get cash into the hands of those most at risk of food insecurity as well as to create jobs so LIWP is therefore a primary focus of the proposed two-year extension of Phase IV. It will account for a significant share of the estimated budget across the three proposed budget scenarios.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations

- SFD should provide regular assessments of the feasibility of multi-year LIWP.
- DFID should consider removing the multi-year indicator from our logframe for the next 12 months.

Output Title	Capacity Building: Stakeholders capable and empowered
Output number per LF		4	Output Score	B
Risk:		High	Impact weighting (%):	5%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	N

Indicator(s)	2015 Milestone[22]	Cumulative achievements[23]
Number of people trained in M&E, participatory methods, planning or other strategic information management (disaggregated by male, female and Local Authority (LA) members trained on Empowerment and Local Development programme	Male: 2500 / Female: 1500 / LA: 1500	887 / 702 / 4,868
Number of village councils in pilot areas which are functioning effectively: / - meeting regularly / - wide participation (sex disaggregated) / - initiate self-help initiatives	1,500	3983
Organisation supported / - Number of NGOs supported / - Number of local authorities supported / - Number of Community-Based Organisations formed	NGOs: 90 / LAs: 90 / CBOs: 2500	55 / 50 / 1832
[22] This represents the total cumulative milestone since the start of Phase IV, January 2011 through to September 2015..
[23] These figures represent total cumulative results since the start of Phase IV, January 2011 through September 2015.

Key Points

Due to lack of funds, there has been no progress against the main indicators compared to March 2015. Support to the NGO sector was particularly affected with almost all activities stopped, and no new subprojects developed or funded. SFD have worked to maintain the capacity they helped build. On the positive side, the community-based structures (Village Cooperative Councils (VCCs) and Uzlla Committees) supported by SFD have been playing active roles in self-help humanitarian and relief initiatives (and have been sharing their reports with SFD BOs and Local authorities).

We have scored this output a B (Outputs moderately did not meet expectation) although we recognise that SFD has been negatively impacted by factors outside of their control.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations

Last year’s review had flagged the need for SFD to reconsider what they measure, namely not numbers of people or authorities trained but rather the number of district level project plans that exist; and the number of overall SFD interventions and self-help initiatives that have been identified and are being supported through district planning processes. While the context has changed, the general concept still applies; we should assess the Phase IV proposal with this in mind.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

During the Phase IV period January 2011 to September 2015, SFD completed 4,533 projects at a cost of $605 million. The estimated number of people directly benefiting from these interventions is 6.9 million (3.2 million males and 3.7 million females). Completed and ongoing projects have generated 30.7 million person days of temporary employment, of which 10.5 million person days have been through Labour Intensive Works Projects. For a country with a population of only 24 million, SFD investments therefore continue to have a major impact on the country’s economy and particularly on the lives of the most vulnerable.

However, during the last year the deteriorating political and security context in Yemen has had a significant impact on SFD’s key cost drivers. SFD operations have also had to face national cost drivers currently affecting the whole of Yemen. According to the World Food Programme, for example, the average price of fuel rose by nearly 250% between the start of the crisis and September 2015, and by as much as 400% in Taiz Governorate. As well as increasing needs within Yemen (less fuel available to meet basic requirements such as food production etc.), the increase in fuel costs has also added to the operational costs of SFD, e.g. SFD have had to stockpile enough fuel to operate their offices for one year in case supplies were to cease.

Performance has also been affected by funding pressures due to the suspension of funds from donors (for example, the suspension of World Bank disbursements due to World Bank’s Operational Policy), delays in transferring funds, and security challenges. Along with the conflict, SFD cite their funding shortfall as the most fundamental delivery challenge: between April and September 2015 SFD completed only 119 projects, just 18% of the 670 projects completed in the previous reporting period (October 2014 to March 2015).

This funding shortfall needs to be monitored closely by DFID. Without sufficient and timely funding, SFD will not be able to deliver at the scale and reach that provides the organisation with their comparative advantage. An inability to deliver services nationally across Yemen could also place SFD’s neutral status at risk by leading to a prioritisation of certain regions over others. In a worst case scenario, a lack of timely funding could also threaten the operational integrity of SFD. SFD have already enacted cost-saving measures such as cutting staff numbers by 20%, reducing salaries across the organisation by 15%, and are planning further salary cuts if funding does not improve.

VfM performance compared to the original VfM proposition in the business case

SFD performance in terms of value for money is considered satisfactory in comparison to the original VfM proposition in the business case. When considering the VfM of DFID’s contribution to SFD, this Review applies the ‘3E’ principles: Economy, Efficiency, and Effectiveness:

Economy: the operating costs associated with managing the Fund were originally set at 6.4% of total costs, which is positively comparable with other internationally coordinated mechanisms and would represent good VfM. The actual annual allocation (according to the latest audited accounts, 2014) represents the lower than expected figure of 3.2% of total allocated funds to operating costs demonstrating a positive performance of economy.

Efficiency: DFID’s contribution represents one of 21 donor contributions in the last year across a range of sectors on a national scale. This breadth and reach has many advantages as donors have attempted to harmonise their efforts to ensure the whole country is covered. There are, however, two ongoing challenges to SFD’s efficiency. Firstly, there is a danger that - due to the current suspension of funding from some donors as a result of the conflict - the donor pool becomes smaller, with previous supporters establishing separate independent projects that are not coordinated with others. Secondly, there is a concern that limited funding will harm SFD’s ability to deliver at a national scale, thereby reducing its efficiency of scale. DFID must continue to mitigate these risks through encouraging a wide mix of donor support.

Effectiveness can be measured by assessing progress against targets. Considering that SFD remains broadly on track or close to its results targets - despite the funding shortfall – we assess that programme remains effective and demonstrates strong resilience.

Assessment of whether the programme continues to represent value for money

In consideration of its’ low operating costs ensuring economy, current breath and scale of support leading to efficiency and effectiveness at achieving results, SFD continues to represent good value for money, especially in the context of the current crisis.

Whilst SFD is not a humanitarian organisation, its’ delivery of basic services has the potential to contribute to a reduction in humanitarian needs and lay the basis for the future of recovery of Yemen. In recognition of this role, SFD’s extended Phase IV (2015–2017) will increase its focus on the Labour Intensive Works Programme to promote social protection by ensuring that cash is provided to those most food insecure. SFD will also prioritise women and youth as beneficiaries of its projects meaning strong alignment with DFID’s strategic priorities.

DFID should continue to monitor SFD’s value for money, including through measuring economy, efficiency and effectiveness, and keeping a close track of SFD’s evolving responses to the current situation in Yemen. In line with DFID Yemen’s new VfM strategy, SFD should, with DFID, formally establish (easy to measure) metrics to improve VfM assessments in ‘real time’. Leading candidates could include:

VfM Principle	Measure	Detail
Economy	Administration Fee	Relatively easy way of identifying overhead/unit costs. Directly comparable with similar vehicles, including Trust Funds.
	Operational costs as a % of total disbursements	Direct relationship between ‘input’ costs and output costs.
Efficiency	Disbursement Ratio	Disbursement volume divided by total project funds for the year. Measures how well SFD is utilising its budget.
	Number of active donors as a share of all donors in Yemen	Captures potential ‘economies of scale’ associated with better donor coordination through SFD systems.
Effectiveness	% of projects meeting or exceeding expectations.	A direct measure of portfolio quality.
Cost Effectiveness	Cost per beneficiary	Can be defined in a number of ways; a rough estimate of how project funding is benefitting Yemenis.
	Disbursement rate	Bears a strong correlation with project activity.

Quality of financial management

SFD has historically had a strong financial management track record: it has received unqualified opinions by annual external auditors since 1997; the World Bank’s financial management experts have consistently given SFD positive ratings; and all disbursements by the Islamic Development Bank have been individually audited. SFD’s automated, multicurrency/multi-donor financial management system allows SFD to track and record each transaction made across the organisation. SFD Branch Offices and HQ also regularly undertake sample checks on payments.

Since the conflict started, SFD have activated their backup servers to protect their management information/financial systems. They have also started requesting photographic evidence to be submitted with payment requests from the field.
The EU has very recently commissioned a fiduciary risk assessment of SFD which will provide important up to date information on the performance of SFD’s financial management. DFID’s own Due Diligence of SFD (due to be completed in March 2016) will also look into financial systems and performance.

Whilst there have been concerns about the state of the banking system in Yemen, SFD currently reports that all local banks with which SFD has accounts are still functioning and are safe and feasible. DFID should continue to watch the status of the banking system within Yemen closely to mitigate developing risks, as well as the ability of donors to get funding to SFD in Yemen through the international banking system.

From DFID’s perspective, SFD can maximise its effectiveness if donors provide funding that is not earmarked for specific projects. However, this is a longstanding issue with many donors holding a preference for supporting specific projects. This has resulted in SFD internally earmarking funding for specific projects even for those donors, such as DFID, who have not requested that support is channelled to specific projects. DFID should therefore: a) continue to hold discussions with other donors to advocate the use of non-earmarked funding to improve effectiveness and flexibility, and; b) explore with SFD whether it is possible to increase internal flexibility in its allocation of resources when Phase V begins in 2018.

Date of last narrative financial report	30 September 2015
Date of last audited annual statement	31 December 2014

E: RISK (½ page)

Overall risk rating: High

Overview of programme risk

Under the current security and political situation in Yemen, the overall programme risk is high. SFD has recognised this increase in risk and undertaken an internal exercise (in consultation with donors) to update risk and mitigation measures. Top risks have been identified as:

1) The possibility of SFD becoming unable to maintain its political neutrality;
2) Increased fiduciary risk due to the conflict;
3) SFD’s operational capacity being limited due to staff layoffs (as a result of insufficient funding).

A series of mitigating measures have been proposed in SFD’s risk updated risk matrix. DFID should continue to track these risks and the implementation of mitigating measures.

Safety of staff and consultants - as well as operational constraints due to insecurity - is also a particular concern to SFD. SFD offices are now regularly collecting data on security problems and staying abreast of OCHA security briefings to ensure that they have up-to-date mapping of security threats. In order to reduce staff exposure through travel in insecure areas, SFD has also adapted approaches to monitoring. This has included monitors for Labour Intensive Works Projects residing with the projects for their duration rather than commuting, as well as less regular verification missions from branch offices. Other mitigating measures already taken by SFD include moving their headquarters to safer zone in Sana’a, operating their Taiz branch office from the nearby Governorate of Ibb, and establishing a backup emergency centre in case of a significant escalation of insecurity.

Over the last year DFID has been exposed to less risk through our support to SFD as a result of transferring funding (£1.5 million) after works had been completed. Future payments in the next financial year will be made subject to assessment of the risk of doing so at that point in time and against the benefit to be achieved. A further risk in DFID’s support to SFD is the potential loss of key staff who have significant valuable expertise and with whom DFID has built up reliable and effective relationships.

Outstanding actions from risk assessment

As SFD’s risk matrix was updated in December 2015, a number of outstanding and ongoing actions are required from SFD. These include:

1. Reducing the risk of interference in SFD’s political neutrality by effectively communicating the (neutral) nature of its work to all stakeholders and parties; and informing donors of any events that affect SFD’s autonomy;
2. Reducing the risk of theft of funds by keeping payment instalments (from donors to SFD and from SFD to contractors) smaller but more frequent;
3. Reducing the security risk to staff by increasing security measures at central and branch offices and minimising travel;
4. Reducing the risk of limited funding by promoting SFD’s response paper for an extended Phase IV (2016 – 2017) to partners;
5. Mitigating the consequences of increases to staple foods by increasing stipend and contracting rates, and increasing the use of Labour Intensive Works Projects as a way of getting cash to the most vulnerable households so that they can better meet their most basic needs.

A number of actions are also required from DFID. These include:

1. Inserting a clause in the extended MoU (to cover the one year programme extension) concerning SFD’s responsibility to raise any incidents of political pressure with donors immediately.
2. Maintaining regular communication with SFD on their ability to operate in the current security situation and ability to perform under their current funding shortfall.
3. Continue to mitigate risk by regularly sharing information across donors; holding regular conversations with SFD; using our networks and local staff to understand any actual or risks of interference with SFD, and; continuing to use our Independent Monitoring programme to provide third party verification of SFD’s work.
4. Continuing to encourage SFD to demonstrate and emphasise their neutrality and autonomy to reassure donors.
5. Reducing the size and increasing the frequency of payments to SFD to mitigate the risk of funds being misused or diverted.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

SFD’s Phase IV, as well as DFID’s aligned £100 million programme of support, was due to end on 31 December 2015. Due to the conflict SFD, in close consultation with donors, proposed extending an adapted Phase IV (January 2016 – December 2017) to respond effectively to the current deterioration and start building towards Yemen’s recovery. During this period, SFD will develop its Phase V proposal, which will be submitted at least one year prior to January 2018. Considering the need to effectively and rapidly respond to the current crisis, DFID judges along with SFD’s other donors that this is the most sensible course of action. DFID’s programme of support has therefore been extended by an initial year (to 31 December 2016) during which time the remaining £11.6 million commitment to SFD may be disbursed in regular instalments on the approval of DFID Yemen’s Head of Office subject to considerations of risk/benefit in doing so.

Performance of partnership(s)

SFD performs well as a partner with a strong track record for delivery in the most challenging contexts. As well as continuing to provide good value for through operating with strong economy, efficiency and effectiveness, SFD continues to perform as a respected, neutral and critical actor in Yemen. SFD’s central role in Yemen has been recognised by a wide array of groups, including the Government of Yemen who have stated that SFD will be central to the rebuilding of the country. SFD have also been trusted by the international community and the Government of Yemen to carry out an important role in contributing to the Damage Needs Assessment led by the World Bank, United Nations, European Union and Islamic Development Bank,, including by carrying out a specific damage assessment for Aden at the request of the Government of Yemen. DFID therefore continues to see SFD as a critical institution that needs protecting to help contribute to Yemen’s recovery.

Asset monitoring and control

Due to multi-donor support to SFD, DFID does not claim ownership of assets. However, SFD do hold the assets on their accounts and have been keeping track of projects damaged during the conflict, reporting that in total 157 have been damaged, of which 55 have been fully destroyed and 102 partially destroyed. Of these projects, 28 were projects to which DFID funding had been allocated; 9 were fully destroyed and 19 partially damaged. DFID is now following up on plans for those projects partially damaged and should ascertain with SFD whether there is a value for money case for fixing partially damaged projects.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Given the current political and security instability in Yemen, there is a high degree of uncertainty around any assessment of the Government of Yemen’s commitment to, and the direction of travel against, all of the partnership principles. We will therefore ensure we review our partnership principles at the earliest opportunity, whilst in the meantime continuing to monitor SFD’s relationship with the Government of Yemen, including through Government of Yemen representation on SFD’s board.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

SFD’s Monitoring and Evaluation Unit

DFID’s core funding includes support to SFD’s Monitoring and Evaluation Unit. This Unit serves two stated primary objectives: a) supporting accountability to the Government of Yemen and donors, and;
b) Supporting internal learning and development.

The unit tracks the progress of sub-projects under implementation and SFD conducts annual project and community-level surveys to obtain beneficiary feedback. SFD uses external sources of data[24] to target communities most in need. SFD map data using a Geographical Information System to visualize how well SFD interventions are benefiting its intended beneficiaries.
[24] External sources include: 2004 Census, the 2005-2006 Household Budget Survey, and educational facilities’ surveys

National data

In last year’s Annual Review, we hoped that new data from national statistical products would help SFD to update its geographical targeting. Unfortunately due to the political and security situation, only the Demographic and Health Survey (DHS) has been published, though the micro-data is not available. DFID should continue to encourage SFD to use Government data sources where possible.

Monitoring progress throughout the review period

Targeting Analysis

SFD carried out a desk review of their data to monitor targeting performance from April–September 2015. The analysis covered 81 currently active cash for work, and water and sanitation projects located in rural areas. Results showed that 80% of SFD resources reached the most deprived populations, with 100,564 beneficiaries in villages with a deprivation index 75% or higher.

Utilisation Surveys
In 2015, SFD assessed 1,073 Phase IV projects, mostly located in rural areas of eight governorates, to determine the degree to which projects completed prior to the recent conflict are being used and delivering benefits. The survey interviewed community groups and key informants and found that the majority of SFD infrastructure projects are being used and deliver benefits. Education, health and water project usage ranged between 90-98%. For infrastructure built using cash for work, 83% of the respondents reported that the infrastructure is fully utilised, while 16% is partially utilised. For NGO capacity support, 78% of the 27 projects visited were still operating and delivering services. 89% of respondents rated SFD projects as good or excellent.

Independent Monitoring

The high risk security situation makes it extremely challenging for DFID and other donors and partners to effectively monitor and evaluate the delivery and impact of projects across Yemen. Therefore, DFID runs an Independent Monitoring programme to provide field verification of the quantity, quality and targeting of DFID plus information from beneficiaries. The programme gives DFID an ability to focus on specific areas of concern if required. At the end of 2015, the Independent Monitoring programme undertook a Verification Study of SFD’s Water and Sanitation projects. The final report was received after the completion of this Annual Review.

Evaluation

There is no formal DFID commissioned evaluation planned for SFD. However SFD does conduct its own impact evaluations (see here: www.sfd-yemen.org).

Review Process

This Annual Review was completed by the SRO (Social Development Adviser) and the Programme Manager, with technical inputs from the Economic Adviser, through a desk-based review. The data for the review is based largely on narrative and financial reports provided by SFD as well as information provided by SFD at the partner meeting held in Amman in November 2015. The AR has been quality assured by DFID Yemen’s Results Adviser.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C