Annual Review

Title: UK Aid Direct
Programme Value £ (full life): £150 million		Review Date: August 2018
Programme Code: 202035	Start Date: 6 Sep 2015	End Date: 31 Mar 2025

Summary of Programme Performance
Year	2015-2016	2016-2017	2017-2018
Programme Score	A	A+	A
Risk Rating	minor	moderate	minor

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5557245.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5703558.xls

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

UK Aid Direct (UKAD) is DFID’s main centrally managed programme for small and medium sized civil society organisations, working to achieve sustained poverty reduction and deliver the Global Goals. The programme offers funding for projects in the lowest 50 countries on the Human Development Index or those considered by DFID to be of moderate or severe fragility. To be eligible for UK Aid Direct funding, civil society organisations must be based either in the UK or in one of DFID’s eligible countries.

At the beginning of the reporting year 2017/18, UK Aid Direct was comprised of three types of grant: Impact grants and Community Partnership grants and the newly announced Small Charities Challenge Fund, a pilot programme designed to provide grants to very small UK-based charities and to help DFID better understand how to work with organisations of this size. By the end of the reporting year, two further types of grants had been designed, announced and were open for application - Jo Cox Memorial Strengthening grants and Jo Cox Memorial Networking grants. The eligibility criteria for each type of grant are different, particularly in terms of the size of organisation able to apply. This helps to ensure that the programme works with a diverse range of partners.

The total value of the UK Aid Direct fund is £150 million covering the period October 2015 to March 2025. £4 million of this is currently ring-fenced for the SCCF and £10 million for the Jo Cox Memorial Grants. The remainder is disbursed across Impact and Community Partnership grants.

Summary supporting narrative for the overall score in this review (1/2 page)

Overall the fund is on target at outcome level, with outcome indicators 2 and 3 exceeding their milestones.

In terms of fund manager performance, MannionDaniels has met or exceeded all quarterly KPIs in the following strategic areas:

- Financial management
- Risk management
- Performance management
- Transparency
- Learning
- Communications
- Capacity building

With regards to outputs, UKAD has scored an A or higher in four out of six, and a B in the remaining two. When weightings are applied, this aggregates to an overall score of A. Where outputs did not score an A, or where an A was only just achieved, there are a number of lessons that will be actioned in the coming year.

Logframe

One major challenge for the programme is how best to reflect the adaptive and flexible nature of the fund through the logframe, as well as how to ensure that indicators are relevant across the broad range of projects. Recent funding rounds have been either broadly focussed or responsive to a new departmental priority (for example, the Small Charities Challenge Fund), with proposals approved based on merit rather than how they contribute to logframe outputs. As a result, not all outputs are relevant to all projects and there is some misalignment between the logframe and current portfolio. How best to respond to this will be considered as part of a detailed review, and likely refresh, of the logframe scheduled for autumn this year.

The fund has made significant progress on outputs not included in the logframe, in response to new priorities. Most notably, the design and implementation of the Small Charities Challenge Fund (SCCF) and Jo Cox Memorial Grants (JCMG). For the first round of SCCF, the fund manager managed 101 applications through a detailed review process and assurance process with 17 projects starting or about to start. During this process the UKAD fund manager successfully adapted a due diligence approach designed for larger organisations with 90% of organisations meeting the minimum standards at this stage. This was a considerable achievement given the amount of support and capacity building required. The second round is well under way, with due diligence assessments currently being finalised and quality assured. For JCMG, the fund manager and DFID team delivered the design and launch of a new, strategic funding round focussed on two specialist themes. First round applications have been scored and moderated with the second round just opening. The DFID team will consider how best to reflect the flexibility and time needed to deliver such specialist and responsive funds in the logframe refresh.

Finally, the fund manager also provided a wide range of interactive support for grant holders, including but not limited to:

- Three workshops for provisional grant holders where guidance and technical support was provided on a one to one basis
- An impact evaluation workshop for round two grant holders and in-country implementing partners - bolstering skills in monitoring and evaluation strategies, methodologies, and developing work plans to carry out impact evaluations.
- Five general guidance webinars
- Five application specific webinars
- A learning and capacity building workshop for grant holders in Bangladesh.
- Ten regional presentations and learning events.

Whether such activity should be reflected in the logframe in more detail will be considered in the autumn.

Milestones

Accurately predicting this year’s milestones was challenging. Milestones from year two were considerably overachieved and year 3 milestones were not in all cases appropriately revised. This is complicated by the fact that legacy grant holders were only required to provide narrative reports and data on an annual basis, making it difficult to adjust milestones in either direction accurately or in a timely manner. The move to quarterly reporting for all grant holders should improve the fund manager’s capacity to adjust milestones in a more thoughtful, nuanced way on a project by project basis. That this reporting will be completed through a new online platform should also allow the fund manager to access more relevant, real time information, allowing milestones to be adapted more accurately.

Timings

There was a considerable delay in the commencement of UK Aid Direct round two projects which impacted performance against some outputs. Both the UKAD team at DFID and the fund manager had originally anticipated that these 37 new grants would have started in time to report during this period; however, grant agreements only started being signed from February and this was therefore not the case. This delay has also resulted in some of this year’s output level recommendations, which were designed primarily with these new grants in mind, being largely the same as last year’s. For example, recommendations around the mandatory disaggregation of sex and disability data, as well as beneficiary feedback mechanisms, were made mandatory for new grant holders only and so were inappropriate for many of the organisations reporting during this period.

Recommendations for the year ahead (1/2 page)

Recommendation	Owner/ main implementer	Deadline
Refresh logframe based on areas identified for improvement throughout this report	DFID	Dec 2018
Use the recommendations of the fund manager survey and other feedback from stakeholders to adapt UK Aid Direct processes and continue to make it as straightforward as possible for a diverse range of civil society organisations to apply for and access grants.	FM	Dec 2018 (sooner for SCCF)
Embed and refine better risk management processes across the fund, drawing on Inclusive Societies Department new risk strategy and recommendations from the recent IAD report.	DFID	Sep 2018
Incorporate new safeguarding standards across all grants and mainstream safeguarding considerations into all stages of the project lifecycle and wider programme activities.	FM	Ongoing
Revise UK Aid Direct’s learning strategy, including around how civil society organisations can learn more effectively between themselves, and how civil society organisations and DFID can learn from each other.	FM	Ongoing
Continue to develop relevant capacity building initiatives, focussing on where specific gaps have been identified and where larger partners may be able to provide a supporting role in building the capacity of smaller ones.	FM	Ongoing
Discuss how UK Aid Direct can better support DFID’s strategic directions as well as civil society policy objectives.	DFID	Ongoing
Develop a strategic approach for the remaining UK Aid Direct funds and communicate with the sector as appropriate.	DFID	Dec 2018
Use new quarterly reporting approach and other lessons learned to review and improve current milestone planning.	FM	Dec 2018
Increase DFID’s direct oversight of in country project delivery as recommended by the IAD report.	DFID	Ongoing
Continuously review the SCCF to make strategic improvements and build evidence base on the advantages of working with small charities.	DFID/FM	Ongoing
Consider whether JCMG and SCCF should be mainstreamed into the overall UKAD Theory of Change and Logframe and make these changes if appropriate.	DFID	Oct 2018
Provide more targeted support to organisations to ensure greater understanding of methods of measuring and collecting evidence of improved economic empowerment.	FM	Dec 2018

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Improved access, supply and quality of basic services for specific target groups
Output number per LF		1	Output Score	A++
Impact weighting (%):		20	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of people benefitting from increased access to basic services	318,530	425,628
Number of people trained in basic service provision	5,529	7,843
Number of projects with fully functioning beneficiary feedback mechanisms	80%	97.5%

Provide supporting narrative for the score

This output is scored as an A++ as all milestones were exceeded significantly.

Output 1 is a key driver in the UK Aid Direct theory of change. It is the output benefitting the greatest number of beneficiaries and covers basic services such as health, education and WASH as well as working towards improving livelihoods and women’s empowerment.

Output indicator 1.1: The number of people benefitting from an improved access to basic services in Year 3 was 425,628 – this exceeded the milestone of 318,530 by more than a third. This baseline is disaggregated fully by DFID’s Results Framework (DRF) categories. The DRF with the greatest number of beneficiaries is Reproductive Maternal Newborn and Child Health RMNCH (237,118), and the lowest is TB (262). These results are partially disaggregated by sex, with 28 grants providing sex data for a total of 339,342 of all beneficiaries). This shows at least 213,526 of beneficiaries were female (more than 50% of all beneficiaries), and at least 125,816 were males. The baseline has not been disaggregated by disability. 34 grants reported against this output for this reporting period.

Output indicator 1.2 The number of people trained in basic service provisions in Year 3 was 7,843 – this exceeded the milestone of 5,529 by more than 40%. This baseline is disaggregated by type of service. The type of service with the greatest number of people trained is general health workers, and the lowest is health workers supporting HIV. There were no people trained as health workers specifically supporting TB, malaria, immunisation, nutrition or mental health. 30 grants reported against this output for this reporting period.

Output indicator 1.3 This is the first year in which all new grant holders have been required to have fully functioning beneficiary feedback mechanisms. In year 3, 42 out of 43 grants had fully functioning beneficiary feedback mechanisms (97.5%), despite this not being mandatory for legacy grants. This significantly exceeds the Year 3 milestone of 80%. The fund held both a webinar and a 2-day workshop for grant holders to build their capacity on number of areas – including beneficiary feedback mechanisms – and this is reflected in the progress made for Output 1.3. All grants reported against this output for the reporting period.

What constitutes a fully functioning beneficiary feedback mechanism differs between projects and so is judged on a case by case basis by the fund manager. Grant holders are asked to demonstrate the methods they use to gather beneficiary feedback and evidence as to how this evidence has informed meaningful change to the project. If feedback requires changes that cannot be made to the project, the organisation is then asked about what other measures they may have taken. The majority of grant holders focus their efforts on focus groups, questionnaires and surveys.

For new grant holders, the effective use of beneficiary feedback mechanisms is mandatory. The fund manager has provided training to all new grant holders who will also be required to submit evidence of their mechanisms on a regular basis. This should allow more robust analysis of the different types of mechanism.
Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons Learned:
- This milestone captures the provision of basic services. Ideally, we would like to be able to track the quality also. Currently, not many of the grant holders report on this as part of their logframes and so capturing this data is a challenge. Going forward, the fund manager must encourage and support grant holders to include this as part of their quarterly and annual reporting.
- Given the legacy grant holders have only recently been mandated to include beneficiary feedback mechanisms into their reporting and many of the projects are in their final period of reporting it is not possible to say how effective they’ve been at improving the relevance and effectiveness of the project. Now that they are mandatory for all new grant holders, and that training has been provided accordingly, the fund manager will be better equipped to analyse the effectiveness of the mechanisms.
- Grant holders are not necessarily able to demonstrate that the mechanisms are/ have the potential to be an accountability tool and help hold grant holders to account.

Recommendations:
- Revise the year four milestones and if applicable, increase the targets according to the grant portfolio and its ability to deliver on output one
- Ensure all new grants disaggregate for sex and disability.
- Maximise the use of the new reporting requirements to better assess the impact and effectiveness of different types of beneficiary feedback mechanism and include a review of this in the new learning strategy. This could include:
  - Taking a sample of grant holders and tracking against metrics such as:
    - Ability to action feedback and adapt the project
    - Accountability and empowerment – i.e. does the host community feel that the project has been accountable and responded to their needs?
    - Trust and ownership – has the BFM resulted in greater trust between the community and implementing partner? Is the result of this more effective programmes?
  - Comparing responses across different sizes of grant, locations and types of organisation.
- Support grant holders to report on the quality of the services provided, and build assessment of this into any project visits or other monitoring activity conducted by the fund manager.
- Include a robust assessment of the impact of beneficiary feedback mechanisms as part of the new learning strategy.

Output Title	Better informed citizens hold decision makers to account
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of beneficiaries supported, and events completed, to have choice and control over their own development and to hold decision-makers to account	25,216 beneficiaries and 271 events	69,673 beneficiaries and 1,917 events
Number of local accountability mechanisms established	43	28

Briefly describe the output and provide supporting narrative for the score

This output is scored as an A since whilst the second indicator underperformed considerably (progress was 65%) and scored a C, the first indicator was significantly exceeded and scored an A++. When weightings are applied, this correlates to an overall score of A, although this was a close call and considerable work will be needed to improve performance against this indicator in the coming year.

Output 2 reflects the ability of the fund to support and build on accountability, which we see as a crucial function and objective of civil society. The fund supports projects that support choice and control by informing and educating citizens on their rights and how to hold local and national decision makers to account. Events are defined as: active participation in meetings with duty bearers/decision makers for lobbying purposes; engagement in community activities; participation in cooperatives; participating and contributing to planning.

Output indicator 2.1 The number of beneficiaries supported to have choice and control over their own development, and to hold decision makers to account, was 69,673 – with 1,917 events held for this purpose. This exceeds the Year 3 milestones of 25,216 (beneficiaries) and 271 (events) by 176% and 607% respectively. These results are partially disaggregated by sex, with data available from 14 grants for 42,757 of all beneficiaries (61%). This shows at least 40,718 of beneficiaries were female (more than 95% of all beneficiaries), and at least 2,039 were males. The baseline has not been disaggregated by disability. 21 grant holders reported against this output for people supported, and 14 reported for events in this reporting period.

Specific events included: advocacy sessions with sub-district level government health staff as part of a women and girl’s empowerment grant in Bangladesh; monthly community health fora under a RMNCH grant in Liberia; meetings between disabled people’s organisations (DPOs) and mainstream agencies to discuss inclusion in access to resources and income in Nepal.

Output indicator 2.2 The number of local accountability mechanisms established was 28. This is just 65% of the Year 3 milestone of 43. Mechanisms included sexual & reproductive health rights school clubs, parents and disability associations, and village health and water committees. This underperformance comes despite: i) the Year 3 milestone reducing by 18% compared to Year 2; and ii) the fund manager liaising with DFID policy teams and consortium partners to look at a clearer definition of accountability. 23 grant holders reported against this output for this reporting period.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons learned:
- If grant holders are contributing to the first indicator, it may be the case that they are doing so through local accountability mechanisms, which would mean that the second indicator is redundant. Further analysis in the year ahead will be needed to understand if this is the case and this will be reviewed as part of the logframe refresh.
- Defining specifically what local accountability mechanisms are is difficult as there are numerous types of mechanisms and each one is context specific. We can support grant holders at the design phase to encourage them to include approaches to accountability in their projects and to collect data to demonstrate how they are contributing towards this output. Many grant holders when questioned do include an element of accountability in their projects but only those for whom accountability is a primary focus report data on the effectiveness of accountability.

Recommendations:
- Review year four milestones and indicators and if applicable, adapt to the current grant portfolio.
- Ensure all new grants disaggregate data for sex and disability.
- Delivery to this indicator must be improved. The fund manager should provide detailed guidance as part of project design and it should be included in project review criteria and publicised as such. Capacity building workshops should also be held, especially with new SCCF grant holders.

Output Title	Increased opportunities for economic empowerment
Output number per LF		3	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of beneficiaries with access to financial services as a result of DFID support	8,915	7,155
Number of households reporting an improvement in household income/status	20,986	3,443
Number of people taking up a new job in the last 12-month period	82	863
Number of beneficiaries provided with skills training	22,891	9,580

Provide supporting narrative for the score

This output is scored as a B, as whilst it significantly exceeded on output indicator 3.3, it failed to reach the remaining three indicators, underperforming slightly against indicator 3.1 and considerably underperforming against indicators 3.2 and 3.4. This score makes this the weakest performing output in the logframe for the second year in a row. Activities related to this output include: economic empowerment training, agriculture and environmental conservation training; non-formal vocational training for girls; and basic book keeping and business plan training for girls.

Output indicator 3.1 The number of beneficiaries with access to financial services as a result of DFID support was 7,155. This represents 80% of the Year 3 milestone of 8,915. Financial services were often accessed through village micro savings schemes and credit and savings groups. Of the 7,155 beneficiaries, sex disaggregation data was available from 12 grants, for a total of 6,105 people (85%). This data shows at least 5,134 of beneficiaries were female (more than 84% of all beneficiaries), and at least 971 were males. These results have not been disaggregated by disability. 14 grant holders reported to this indicator during the reporting period.

Output indicator 3.2 The number of households reporting an improvement in household income/status was 3,443. This represents just 16% of the Year 3 milestone of 20,986 and is the lowest performing indicator for this output. This underperformance comes despite the Year 3 milestone reducing by 35% compared to Year 2. The fund manager will work with new grant holders on ensuring they adopt a rigorous approach to measuring improvements in household income, and potentially encourage more applications in this area in subsequent rounds. In terms of those who are currently reporting against this output, the fund manager has sought to improve practices by drafting guidance for grant holders, and has suggested a revision of the outcome indicator language to better convey to grant holders how this output can and should be measured. 7 grant holders reported to this indicator during the reporting period.

Output indicator 3.3. The number of people taking up a new job in the last 12-month period was 863 – this exceeded the Year 3 milestone of 82 by more than 900%. However, only three grants reported data for this output indicator, as they aren’t mandated to report specifically on this. Of this, sex disaggregation data was available from 2 grant holders, for a total of 854 people (over 98%). This data shows at least 671 females (78%) were successful in taking up a new job during the 12 month period, and at least 183 males. These results have not been disaggregated by disability.

Output 3.4 The number of beneficiaries provided with skills training was 9,580. This represents just 42% of the Year 3 milestone of 22,891 and comes despite the Year 3 milestone reducing by 53% compared to Year 2 because the majority of projects were coming to an end. This is due, at least in part, to the majority of reporting projects being in their final stages when skills training is less likely to take place. 17 grant holders reported to this indicator during the reporting period.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons learned:

- Output 3 is now the lowest scoring indicator for the second year in a row, and there is clearly an issue around how it relates to the range of projects we fund, as well as how the logframe should shape our selection criteria. This will be prioritised for consideration during the logframe review in the autumn.
- During the fund manager’s assessment of annual reviews it became apparent that there were issues on how grant holders were reporting increases and collecting appropriate supporting data to demonstrate economic empowerment
- Skills training is more likely to happen at the beginning of a project and this must be better factored in to milestone planning going forward.

Recommendations:

- As part of the logframe review, consider encouraging more significant economic interventions in future funding rounds to ensure more projects are contributing towards this output. Also consider rewording output indicator 3.2 to make it more easily measurable for grant holders.
- Support grant holders during the design process to ensure that in the final year of implementation the project can still reach new beneficiaries and if it can’t, ask projects to explain why not and what kind of consolidation and continuous skills building will take place with current beneficiaries in the latter years of implementation.
- Work closely with grant holders during implementation to identify ways to potentially increase the beneficiary reach should the project be overperforming in early years. Create a clear case for scaling up if appropriate, within existing budgets.
- Ensure all new grants disaggregate for sex and disability.
- Provide more targeted support to partners with regards to measuring economic empowerment, including leveraging case studies from grant holders who have done this successfully.

Output Title	Shift in social attitudes and behaviours resulting in positive norm change in targeted groups
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of beneficiaries reached and events with behaviour change commu­nications promoting positive norm change	457,540 beneficiaries and 2,175 events	436,842 beneficiaries and 2,447 events
Number of beneficiaries implementing positive behaviour change in the communities where CSOs are working	78,151	125,904

This output is scored as an A, as whilst the second milestone was exceeded considerably the first milestone underperformed slightly in terms of beneficiaries reached even though the number of events delivered was above target.

Specific work that contributed to this milestone includes health education sessions, workshops and women’s health groups.

Output indicator 4.1 The number of beneficiaries reached with behaviour changing communications promoting positive norm change was 436,842 – with 2,447 events held for this purpose. This underperforms against the Year 3 beneficiary milestone of 457,540 by 4.5%, but exceeds the Year 3 events milestone of 2,175 by 13%. Key projects for reaching beneficiaries included an information, education and communication campaign to empower women and girls in Bangladesh. These results are partially disaggregated by sex, with 22 grants providing data for 223,157 of all beneficiaries (51%). This shows at least 163,289 of beneficiaries were female (more than 73% of all beneficiaries), and at least 59,868 were males. These results have not been disaggregated by disability. 32 grant holders reported to this indicator for people reached and 16 reported for events held during the reporting period.

Output indicator 4.2 The number of beneficiaries implementing positive behaviour changes in the communities where civil society organisations are working was 125,904 – exceeding the Year 3 milestone of 78,151 by 61%. This is measured based on self-reported change as a result of project activities. Examples of such behaviour change include an increase in adolescent boys and girls accessing SRHR services in Bangladesh and an increase in handwashing and water purification in Pakistan. These results are partially disaggregated by sex, with 23 grants providing data for 60,958 of all beneficiaries (48%). This shows at least 48,996 of beneficiaries were female (more than 80% of all beneficiaries), and at least 11,962 were males. These results have not been disaggregated by disability. 34 grant holders reported to this indicator during the reporting period.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons learned:
- For legacy projects, we have relied on the grant holders self-reporting on behaviour change, which is difficult to measure and operates as a proxy indicator. For new grants, the fund manager has worked with grant holders to incorporate stronger indicators of change into logframes, encouraging them to be clearer on what change will look like and how this will be documented. This will be verified wherever possible with independent monitoring and evaluation checks, for example with project visits.
- Indicator 4.1 is a result of some legacy grant holders reporting on the numbers of events and some on the numbers of beneficiaries. In recognition of the fact that number of beneficiaries is a stronger indicator, we have worked with new grant holders to focus on this and will revise accordingly.

Recommendations:
- Review what is intended by this indicator, how it fits with the programme and whether it should be updated as part of the logframe review.
- Revise the year 4 milestones to reflect the current grant portfolio and if applicable, increase the target and their ability to deliver on output 4.
- Ensure all new grants disaggregate for sex and disability.
Output Title	Improved delivery of interventions because of shared evidence and learning within the Fund
Output number per LF		5	Output Score	A+
Impact weighting (%):		10%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of grant holders attending webinars or workshops	80%	81%
Number of grant holders contributing to a shared evidence base quarterly	15%	32.6%

This output is scored as an A+ as whilst it only slightly exceeded for output indicator 5.1, it considerably exceeded for output indicator 5.2.

This output is intended to measure the contribution the fund makes to learning. The fund manager’s most significant action in support of this was a two day workshop in Bangladesh, attended by eight grant holders. This covered capacity assessments, monitoring and evaluation, beneficiary feedback mechanism, value-for-money and theories of change. Following the success of this event, another in-country learning event has been scheduled to take place in Nepal in September 2018. This event was also designed based on feedback from grant holders who requested support on value for money, partnerships and beneficiary feedback mechanisms in particular.

Output 5.1 The number of grant holders attending webinars or workshops was 35 (81%) - exceeding the Year 3 milestone of 80% very slightly. The events included reference group meetings, the regional workshop in Bangladesh, UK visits and learning events and five webinars. The themes of the events included adaptive programming and communication, value-for-money, financial reporting and building resilience into project design and delivery.

Output 5.2 The number of grant holders contributing to a shared evidence base quarterly was 14 (32.6%) – exceeding the Year 3 milestone of 15% considerably. These contributions have enabled UK Aid Direct to develop 4 learning products (all available to grant holders on the UK Aid Direct website), including an audio recording discussing partnerships, a booklet about value-for-money, and papers on adaptive programming and working in fragile states. Data shows that two of the learning products (one on disability (downloaded 334 times) and one on livelihoods (downloaded 134 times)) are in the top 10 and top 20 downloads respectively from the website – indicating that these products are generally appropriately targeted and useful to grant holders.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons learned:
- More work is required to understand whether and how the activity that contributes to the indicators leads to improved interventions.
- Feedback provided through the BOND Fund Manager survey indicates that grant holders are seeking more learning between themselves and between themselves and DFID. We will work to improve this over the coming year.
- In terms of what has worked well as part of our current offering, we have found that direct, face to face engagement is most effective. Events such as PRM meetings, reference group meetings, learning events and workshops provide the most learnings and offer grant holders the best opportunity to share them.
- Webinars have also worked well, although more so when it is the grant holder themselves sharing their learnings, rather than the fund manager. Going forward the fund manager will increasingly take the role as learning facilitator, for example, setting up a platform where organisations working in the same country can contact each other.
- In terms of fund level learning, and how this is fed into DFID, we want to do much more of this and this will be a focus for the next year.

Recommendations:
- Revise the Year 4 milestones to reflect the new number of active grant holders.
- Leverage the feedback from the survey, as well as work on whether this activity leads to improved interventions, to improve the fund’s learning offering.
- Continue to work with partners to understand knowledge gaps and tailor learning offer accordingly.

Output Title	Improved access to flexible, responsive and adaptive funding
Output number per LF		6	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Proportion of fund budget going to small-sized organisations	20%	14%
Proportion of fund budget going directly to recipient country-based CSOs	20%	16%
Proportion of Key Performance Indicators (KPIs) met each quarter	100%	100%
Number of stakeholders satisfied with Fund Management	a) 80% b) 90% c) 60%	a) 75% b) 75% c) 60%

This output is scored as a B, as whilst it met its target for indicator 6.3, it underperformed moderately against indicators 6.1, 6.2 and 6.4. This output is intended to measure the type of organisation the fund supports, and feedback on the fund management process.

Output indicator 6.1 The proportion of fund budget going to small-sized organisations was 14% - this is 6% less than the Year 3 milestone of 20%. However, this represents only the amount of funds disbursed to small-sized organisations during the last year, rather than identifying the proportion of active grants held by small organisations, which was 37% by the end of the year. We are content that had second round UK Aid Direct grant holders commenced their projects soon enough to report and receive funds, this milestone would have been exceeded considerably.
[note] Small sized organisations for UK Aid Direct means organisations with under £1 million in annual income

Output indicator 6.2 As above, whilst the proportion of funding going to recipient country based CSOs missed the target this year, the number of grants going to these organisations by the end of year was 28%. We are content that this output will be more comfortably met next year.

Output 6.3 indicator This indicator was added in Year 2. For the second year running, all KPIs have been fully met or exceeded each quarter.

Output indicator 6.4 This indicator seeks to judge the number of stakeholders satisfied with Fund Management, measured by the following statements:

a) It feels like my organisation and the fund manager are working towards a common goal
b) The fund manager is responsive to communication from my organisation
c)The fund manager adds/ has added value to my organisation’s work

Answers to these questions were generated by the fund manager survey, run by BOND between April and July 2018. Organisations were asked these questions on a scale, as follows:

- Largely agree
- Somewhat agree
- Neither agree nor disagree
- Somewhat disagree
- Largely disagree

For this review, responses of largely or somewhat agree were counted towards the total.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons learned:
- As also found in the BOND survey, improvement is required in the fund manager’s relationship with grant holders, especially in terms on responsiveness and communications.
- Small should be defined more clearly for next year.
- Given the direction of the fund, it is unclear to what extent indicator 1.2 is relevant and this will be reviewed with the broader logframe later this year.
- Assessing the number of grants rather than the proportion of funding is more helpful for indicators 1.1 and 1.2.
- Flexibility and responsibility to ministerial priorities should also be considered as part of this indicator.

Recommendations:
Update output to focus more on fund management and capacity building.
- Continue to encourage a diverse range of partners to apply for our funds, especially through SCCF and JCMG which make specific provision for both small and local organisations
- Use the findings of the fund manager survey and other feedback from stakeholders to adapt and improve UK Aid Direct processes and continue to make it as straightforward as possible for a diverse range of civil society organisations to apply for and access UK Aid Direct grants.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The existing theory of change seeks to tackle extreme poverty amongst vulnerable and marginalised communities. It aims to do this through:

- Strategic and flexible funding rounds
- Enhancing the competence and capacity of our CSO partners
- Technical analysis and advice through consortia
- Cost effective fund management

These efforts are intended to support the following outcomes:

- Improved access, supply and quality of basic services for specific target groups
- Better informed citizens hold decision makers to account
- Increased opportunities for economic empowerment
- Shift in social attitudes and behaviours resulting in positive norm change in targeted groups
- Improved delivery of interventions as a result of shared evidence and learning within the Fund
- Improved access to flexible, responsive and adaptive funding

The theory of change remains largely relevant but amendments have been made recently to include two new programmes – the Small Charities Challenge Fund and the Jo Cox Memorial Grants. At present, these changes have been made in the form of annexes, indicating our intention to bolster outputs through more targeted funding mechanisms and work more effectively with small UK based organisations. Over the next year, the team will consider whether it is appropriate to mainstream these funds into the principal theory of change and log frame.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

There are three key outcomes for year 3 and the fund is on target to meet them all, with outcome indicators two and three exceeding their targets.

Outcome Indicator 1: The first outcome is the number of grants directly contributing to DFID’s results framework commitments. In year 3, all 43 grants (100%) are contributing to categories in DFID’s results framework, for example: RMNCH (16 grants), income generation (10 grants), HIV (3 grants), violence against women and girls (3 grants), WASH (3 grants), improving market access (1 grant), tuberculosis (1 grant) and girls’ empowerment (1 grant). All 43 grants are also working in countries either considered to be of high or moderate fragility by DFID, or ranked in the bottom 50 of the UN Human Development Index. That being said, based on the progress against output 3, the fund manager could encourage more “income generation” applications in subsequent rounds.

Outcome Indicator 2: The second outcome is the total number of vulnerable/marginalised people reached by CSOs in targeted countries. The number of people reached in year 3 is 574,259 – exceeding the milestone of 520,268 by more than 10%. Cumulatively, the fund has reached 3,446,443 vulnerable and marginalised people over the past three reporting years. This means the fund is also on track to meet its final Year 5 milestone for this outcome.

Outcome Indicator 3: The third outcome is the number and proportion by cohort of participating CSOs with an increase in Organisation Capacity Assessment. Revising the OCA tool has been a key focus for UK Aid Direct in year 3, including through organising a webinar to address the three areas highlighted as weaknesses in the assessment - partnership arrangements, value-for-money and beneficiary feedback mechanisms. This effort is reflected in the outcome with 86% of new grant holders (32 out of 37) completing the OCA fully – exceeding the year 3 milestone of 60%.

Explain major changes to the logframe in the past year (1/2 page)

Only minor changes have been made to the logframe in the past year, in order to better demonstrate learning within UK Aid Direct. Output indictor 5.1 was changed from “Number of grant holders using lesson-learning to inform practice/results”, which was particularly difficult to report against, to “Number of grant holders attending webinars or workshops”. This is a weaker indicator and we will revisit this decision as part of the broader review of the logframe later this year.

Describe any planned changes to the logframe as a result of this review (1/2 page)

The process of compiling this annual review has triggered an in depth review of the logframe for the forthcoming reporting year, as detailed throughout this report.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

In the UKAD business case, the team committed to ensure VfM at four levels. Action has been taken to ensure compliance across all of these, as set out below:

Type of VfM	Example
That the VfM potential of UK Aid Direct’s flexibility is maximised – i.e. that UKAD will respond to key priorities where there is a need for DFID funding that can best be satisfied by centrally managed CSO programming.	UK Aid Direct has been able to respond to departmental priorities, for instance by introducing the SCCF in response to interest in learning about how DFID can work better with small charities, and similarly with the introduction of the Jo Cox Memorial Grants.
VfM of the fund manager – i.e. that the procurement of the Fund Manager will be tendered through a competitive process and that the contract will be proactively managed.	The fund manager was procured through a competitive process and their performance managed formally by the quarterly setting and review of KPIs. As indicated above, the fund manager has consistently met or exceeded all KPIs, with the exception of fund manager satisfaction that was narrowly missed.
VfM at project selection – i.e. that VfM will be considered at the application stage	VfM is explicitly considered at the full application stage across all grant mechanisms.
VfM through the life of projects – i.e. that projects will be required to demonstrate VfM throughout the life of the grant at annual review.	One of the key focus areas of project annual reviews is the assessment of VfM. The fund manager has developed guidance and provided training to our partners on how best to provide and measure VfM.

Flexibility: The fund manager has provided excellent value for money in terms of their flexibility in responding to changing DFID priorities; for example, with the introduction of the new SCCF programme. In the set-up of the SCCF, the fund manager needed to design and implement a new application and due diligence process, as well as improve their capacity building offering, to reach an entirely new type of organisation. Early indications demonstrate that the fund has been successful in doing this. This value for money at the fund manager level is also demonstrated by the introduction of the JCMG. As with the SCCF, the fund manager designed a new process, as well as a thematically focused round, working collaboratively with policy and technical leads.

Fund Manager: The fund manager also continues to support VfM through the driving down of costs. For example, through better economies of scale and the use of their online application portal - SMILE. They have used national consultants for field work, and ensured that the use of consultants corresponds to a clear need which has driven down rates and maximized returns. We expect to bolster value for money still further with the addition of the UK Aid Match programme to the fund manager’s portfolio. For example, an upcoming international visit and workshop will include both UKAM and UKAD grant holders, driving down the cost of such activity.

Project selection: During the reporting period, the fund manager has successfully adhered to the value for money manifesto it designed last year in accordance with DFID’s guidelines. For example, the fund manager has successfully ensured that most concept notes and full applications are relevant as is demonstrated by the levels of success in our recent funding rounds. For UK Aid Direct 2, just three of the 40 grants shortlisted for ministerial approval failed to proceed to implementation, indicating effectively managed application and due diligence stages. Crucially, the fund manager also undertakes a light touch due diligence at the application review stage, ensuring better efficiency for both applicant and DFID alike as those considered too high risk are not taken forward. For SCCF 1, 17 out of 21 shortlisted organisations are on track for implementation and although this is a lower rate of success than for UKAD, we are content with this result given that this is a new funding round with new higher risk partners.

Projects: In terms of project level value for money, support has been given to new UK Aid Direct grant holders to strengthen their understanding of value for money; and the fund manager has worked closely with the successful applicants to refine their project design to ensure better targeting of vulnerable populations and greater effectiveness of delivery. Value for money has also been supported through the capacity building of existing grant holders in financial management, logframe development and sustainability, as well as specific technical support to those underperforming. This approach has been successful – of the four projects scoring a B in last year’s annual review process, three have now scored an A. More broadly, the fund manager has developed a case study based on an existing grant holder which was shared with partners and published on the website. Specific webinars have also been held on VfM over the past year and it is frequently discussed at regional events, reference group meetings and workshops.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

We are content that the programme continues to demonstrate strong Value for Money across the four categories set out in the business case. As is set in the output indicator sections above, the project continues to deliver effectively as it has done in the previous two years also.

Flexibility: During this reporting year, we have been particularly pleased with the fund and fund manager’s responsiveness and flexibility in adapting to changing departmental priorities. It is clear that the fund can deliver. The introduction of the JCMG and SCCF are particularly strong examples of this. Working with and adapting to small charities continues to be a major ministerial priority and it is our view, therefore, that the fund should continue. In addition to this, DFID is currently working with the fund manager to adopt a more strategic approach to funding rounds going forward and will communicate this with the sector as appropriate.

Fund Manager: As is detailed above, the fund manager has consistently met or exceeded KPIs over the reporting year. They also scored well in DFID’s recent Strategic Relationship Management (SRM) scorecard exercise. This has been particularly encouraging since they took on the management of the UK Aid Match portfolio. We are expecting further cost efficiencies from having the same fund manager across both funds and will continue to monitor their performance over the coming year.

Project Selection and project lifecycle: We are content that Value for Money is considered explicitly and sufficiently at project selection and is also delivered throughout this process. We will continue to build the capacity of our partners, especially the smaller ones who are new to DFID funding in achieving, measuring and reporting on value for money.

Across the portfolio more broadly, it is clear that the fund remains relevant both in terms of the outcomes it delivers and its contribution to the ‘leave no one behind’ agenda’, but also in terms of the need for flexible and cost-effective programming.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The fund manager has developed a robust risk management approach, financial monitoring procedures and a programme level risk matrix. They are also working increasingly closely with grant holders to manage, address and reduce risk at grant level.

The risk management process starts pre-grant award. Each provisional grant holder must undergo a detailed due diligence assessment (in accordance with DFID’s guidelines) prior to commencing work. This assessment gives a risk rating to the organisation in question and the SRO and ministers then agree whether a particular project is within the programme’s risk appetite. Where mitigating actions are needed to bring the project within the programme’s risk appetite, they are written into the grant agreement. Where no mitigating action can bring the project sufficiently within the programme’s risk appetite, the offer of a grant is withdrawn.

During the reporting period, the fund manager was also required to adapt the standard due diligence approach to be more appropriate to smaller organisations applying to the SCCF. We worked with DFID’s Better Delivery Department to agree an approach that was more commensurate whilst still providing appropriate assurance over high risk partners.

Risk is also managed through the quarterly claims process, with any issues reported to DFID on a monthly basis at least and payments withheld if necessary.

We have recently significantly strengthened our risk management. Performance and risk managers at the fund manager track risk across the portfolio, in accordance with the latest DFID risk management framework. A detailed grant risks and issues tracker is used to monitor and mitigate against these risks, and is reviewed with DFID during the monthly meeting. Grant holders are also asked to review and update their risk registers through quarterly reports and the annual review assessment, which is then appraised by the fund manager and shared with DFID at quarterly meetings. Where risks are particularly high in a project, the fund manager may choose to undertake a project level audit, or put the organisation in question on an action plan.

In addition, both the fund manager and DFID team have taken concrete steps to tackle risks at the overall programme level. Work is still ongoing, but good progress has been made thus far. This includes:

- Bolstering oversight of the fund management bank account through adding a review of added a review of bank statements to DFID/MD quarterly meetings.
- Bolstering joint risk management through introducing programme level discussion of risk into monthly fund manager/DFID meetings based on a tracker compiled and managed by MD. DFID have also shared their risk management SMART guide with the fund managers.
- Protecting against aid diversion efforts through DFID sharing documented guidance on delivery chain mapping with the fund managers, to support anti-aid diversion efforts. A subsequent delivery chain mapping exercise took place at the end of June.
- Closely monitoring fund managers’ oversight ability, through quarterly meetings and robust KPIs.
- Exploring how fund managers can further strengthen interaction between themselves and grant holders to ensure effective communication.

In reflection of these efforts, the UK Aid Direct logical framework’s output and risk weightings correspond with a rating of “minor”, which reflects the types of organisations and projects currently supported, and their proactive risk management efforts at the overall programme/portfolio level. However, the introduction of new funding rounds targeting smaller organisations may lead to an increase in the overall programming risk in the next year.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

As is noted above, the fund manager has consistently met or exceeded their KPIs over the reporting period. The fund manager was also introduced to DFID’s Strategic Relationship Management (SRM) programme this year, for which they were recently judged as part of the SRM scorecard exercise. They did not score below a ‘5 – good performance’ for any category in this assessment. Areas for which the fund manager was found to be exceeding expectations on a regular basis include responsiveness, communications, personnel, innovation and compliance. Agreed areas for improvement include attention to detail in deliverables and on learning and lesson sharing.

The fund manager’s partnership with DFID is formally managed through monthly and quarterly face to face meetings with the UK Aid Direct team and SRO. These formal sessions complement very regular more informal communication on grant issues and fund management. The fund manager is also in regular contact with other parts of DFID on issues such as fraud and fraud management, specific policy areas and finance. The fund manager is currently exploring how to further improve their engagement beyond the immediate UKAD team; for example, with policy teams on accountability mechanisms and economic empowerment and on how to improve lesson learning and sharing across the portfolio.

With regards financial management, project spending to date is currently on track. The fund manager utilises grant holders’ quarterly claims to identify over or under spend against the agreed budget and work plan. This helps to ensure good budget management, provides assurance that spend is reasonable and justified, and allows them to provide an updated forecast of expected annual spend to DFID on a regular basis. The addition of new funding rounds may result in project spending exceeding original expectations and the fund manager is currently re-evaluating the cost for the next 2 years of delivery to determine what the spending impact of this will be.

In terms of the civil society partners delivering projects, they have continued to deliver as expected. All partners are provided with capacity building support throughout the lifetime of their grant including in areas such as financial management, logframe development and sustainability. More intense, tailored support was provided for the four projects which scored a B in last year’s annual review process; three of which have subsequently scored an A. A considerable amount of extra time has also been dedicated to organisations successful under the Small Charities Challenge Fund and we are content with the progress made to date and will continue to monitor.

The fund manager has worked with its consortium partners to review all fund applications and provide technical oversight throughout the project lifecycle. These partners have been directly involved in reviewing annual reviews and PCRs. They also had oversight of the review process for their designated portfolio of applications working closely with the Performance and Risk Managers, who monitored the workflow to ensure that the reviews were completed in line with the agreed timelines. Finally, each partner is actively engaged in the Learning Working Group to identify clear areas for learning and support to grant holders.

One particularly complicated issue that has arisen over the last reporting year is the impact of the Mexico City Policy on the SRHR focussed projects in the portfolio. The fund manager has worked closely with the UK Aid Direct team and SRHR team in DFID to understand the implications of this. One grant caused concern but we are content that this issue was handled as well as possible and lessons have been learned for the future.

Date of last narrative financial report(s)	30 July 2018
Date of last audited annual statement (s)	16 August 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

The fund manager has responsibility for the day to day monitoring and evaluation of projects for UK Aid Direct (UKAD) and is accountable to DFID for the overall performance of the fund and of individual grants. Monitoring by the fund manager is principally conducted through narrative reporting, financial reporting and the claims process, annual reviews and if necessary, risk based audits. More informal monitoring is also conducted via regular dialogue between Performance and Risk Managers (PRMs) and grant holders, including:

Email correspondence
- Monitoring on social media
- Monitoring of website
- Catch up calls

In terms of reporting, narrative reporting was previously conducted on an annual basis for legacy grant holders, but is now conducted on a quarterly basis for all UK Aid Direct grant holders. Grant holders update their risks and issues log as part of this quarterly review and the most severe of these risks are then discussed by the fund managers and DFID at the monthly meeting. Grantees also submit annual reviews each April, which are reviewed by the fund managers. Where annual reviews indicate that an organisation is found to be underperforming, the fund manager puts an action plan in place which is then followed up with either monthly or quarterly meetings (depending on the level and severity of the risk) to ensure that follow up actions are completed.

On the claims process specifically, grant holders submit a claim every quarter, which fund managers use to identify over or under spend against the agreed budget and work plan, ensure good budget management, provide assurance that spend is reasonable and justified and provide an updated forecast of expected annual spend.

A selection of projects are also audited every quarter, prioritised based on risk, to provide greater assurance that DFID funds are expended in a transparent and compliant fashion. All organisations also submit their annual audited accounts for review on an annual basis – these are reviewed by the finance and risk team to confirm that DFID funding is accurately and transparently reported. The fund manager’s bank statement is also provided to DFID for review on a quarterly basis.

With regards visits to UK headquarters and project sites, these are generally conducted in line with risk assessments. If there are concerns about a project, the fund managers will subject the project to a number of scrutiny exercises, which may include a visit to the project delivery location. If concerns remain, the project is considered for a more formal Quality Assurance Visit. The team is increasingly trying to take a more proactive approach to country visits, as demonstrated by the recent capacity building workshop in Bangladesh. We are also seeking to improve DFID staff’s oversight of projects, and will be increasing country visits.

Evidence (1/2 page)

As outlined in the detail on output 5, we have made significant progress on the number of UK Aid Direct grant holders feeding into the shared evidence base. Improving how we use this evidence more strategically, as well as how we share it between partners and across DFID is a key priority for the forthcoming year.

With regards evaluation, all UK Aid Direct projects are required to undertake an independent evaluation of the impact of their projects as they are closing. In addition to this, an evaluation workshop was recently held for ten UKAD2 grant holders and their implementing partners to set research questions for additional impact evaluations that will run the course of the projects. The aims of this workshop were to: equip all participants with an understanding of the range of evaluation methodologies; refine impact evaluation research questions; select methodologies most appropriate to individual projects, and draft evaluation workplans. Technical advisors from the fund managers’ consortium partners have continued to work with individual grant holders to finalise these plans with a view to commencing evaluation activities in July.

Learning (1/2 page)

On cross CSO learning within the fund, the fund manager is focusing on:
- Encouraging CSOs to share experiences and best practice
  - Online (e.g. through youtube videos)
  - At reference group meetings
  - At workshops
  - In webinars
- Using lessons learned to inform training sessions and regional roadshow content
- Developing communities of practice and increasing networking

On CSO/ DFID learning, DFID and MD are currently:

- Starting to implement a strategy to drive out more cross-fund learnings (since the commencement of UKAD2 projects)
- Generating evidence from grant holders based on their quarterly reports
- Using lessons learned from CSOs experience to design and tailor funding rounds
- Learning specific lessons when issues arise
- Feeding into ISD learning plans and planning how to disseminate expertise within the department to CSOs and vice versa

At a fund level, both DFID and the fund manager are learning a significant amount about working with small charities through the Small Charities Challenge Fund pilot programme. This has recently culminated in the inclusion of small charities in the BOND fund manager survey and applying the learnings from this will be a focus for the coming year as we seek to make improvements to the funding mechanism.

The design of the JCMG also provided an opportunity for DFID and the fund manager to learn lessons from civil society. Civil society organisations were engaged throughout the design process, most particularly in a panel session and workshop with representatives from the gender equality sector.

Improving our learning offering is a focus for the coming year.

Progress on recommendations from previous reviews (1/2 page)

Recommendations	Actions taken
To build on the portfolio analysis of the UK Aid Direct 2 funding round and identify areas of need (thematic, geographic, populations) for possible recommended focus in subsequent funding rounds.	A draft timeline of potential rounds and thematic focus was shared and discussed with DFID. Subsequent themes and funding round approach were developed on the Jo Cox Memorial Grants and for the Small Charities Challenge Fund.
To strengthen partnership and capacity between UK grant holders and in country implementing partners.	A strategy was developed that included in-country learning events twice a year, allowing capacity building of implementing partners and strengthening their understanding of the fund. UK grant holders were also actively encouraged to invite their implementing partners to join webinars and review/progress meetings.
To revise the Year 3 milestones to reflect the number of actual annual reviews and PCRs expected. To also include disaggregated milestones to reflect the new grants under the UK Aid Direct 2 and SCCF grants.	Year 3 milestones have been reviewed and amended, albeit not sufficiently.
To ensure all new grants disaggregate male/female/disability and encourage further disaggregation of population groups where possible. To encourage existing grant holders to disaggregate data.	Discussed with all new grant holders during their pre-contracting meetings. Developed an online tool to allow for disaggregation of m/f and disability.
To ensure all new grants have fully functioning beneficiary feedback mechanisms. To work closely with existing grant holders to build beneficiary feedback mechanisms into existing projects.	Discussed with grant holders during their pre-contracting meetings. The capacity-building session on beneficiary feedback mechanisms for both new and existing grant holders took place in a webinar in March. A session on beneficiary feedback mechanisms was carried out during the Bangladesh learning event in February.
To provide guidance to all grant holders on the definition of accountability mechanisms.	MannionDaniels is liaising with DFID policy teams and consortium partners to look at a clearer definition of accountability. This has not been rolled out to date.
To provide guidance to all grant holders on measuring economic empowerment.	MannionDaniels is liaising with DFID policy teams and consortium partners to look at a clearer definition of economic empowerment.
To strengthen the dissemination of lessons learned – both internally and externally to the fund – and encourage greater use of fund learning by grant holders.	Activity to support lesson learning has been set out throughout this report and will continue to be a priority area for improvement for the forthcoming year. At a fund level, both DFID and the fund manager have learnt most significantly about working with small organisations.
To improve the data capture and reporting of the number of grant holders using learning materials.	Whilst we do currently track the number of grant holders attending learning events or accessing learning products, there is more to be done here in terms of how these are used.
To revisit indicator 6.1 and either remove or change it to an indicator	Upon review with DFID colleagues, it was decided to retain this output.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g. on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (e.g. first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided