Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Evidence for Action to Reduce Maternal and Newborn Mortality in Africa (E4A)
Programme Value: £18,220,491.00		Review Date: December 2015
Programme Code: 201512	Start Date: August 2011	End Date: April 2016

Summary of Programme Performance
Year	2012	2013	2014	2015 / (This review)
Programme Score	A	A	A	A
Risk Rating	M	M	M	M

Summary of progress and lessons learnt since last review

E4A is designed to result in better maternal and neonatal health services and outcomes by promoting more effective use of evidence to generate political commitment, strengthen accountability, and improve planning and decision-making – working both at country level and to support strengthening of regional and international accountability frameworks.

The programme aims to improve maternal and newborn survival through a combined focus on evidence, advocacy and accountability. The programme has made good progress in this reporting period. The endline reporting on the overall outcome statement for E4A ‘More, and better, evidence-based use of resources for Maternal and Newborn Health (MNH)’, will be completed in Q1, 2016 and available for the project completion report. The mid-line reporting was done in the last annual review which showed that most countries were on track to achieve the outcome on data for decision making and improved political will.

At the output level all six country programmes (Ethiopia, Ghana, Malawi, Nigeria, Sierra Leone, and Tanzania) and the regional component have made significant progress in achieving output indicators. These achievements are tabulated as:

- Output 1 represented 24 indicators for all six countries, 7 indicators were over-achieved, 12 achieved and 5 on track to be achieved.
- Output 2 represented 26 indicators for all six countries, 10 indicators were over-achieved, and 14 achieved, 2 on track to be achieved.
- Output 3 represented 14 indicators for all six countries, 7 indicators were over-achieved, and 4 achieved, 3 on track to be achieved.
- Output 4, the regional component had 3 indicators, 1 Indicator over-achieved, 1 achieved and 1 partially achieved and at risk.

E4A agreed to conduct a Strategic Review of the programming to focus country programs and re-align the log-frame in early 2014.  Midway through the Strategic Review process – but independently from it – due to budget realignments within Africa Regional Department. As of 17th July 2014, DFID and Options agreed £3m reduction to the remaining E4A budget, £1.3m in 2014/15 and £1.7m in 2015/16.

Lessons learnt

Including prospective policy study in the evaluation component has added value by allowing honest reflection by independent researchers to E4A staff and other stakeholders. Similarly, having a wider independent evaluation team assess the delivery of the Theory of Change will hopefully yield information on the success of the programme overall. It will also provide useful evidence to the wider field on how advocacy, accountability and the use of evidence contributes positively to reducing maternal and newborn health.

Any future advocacy or catalytic programme should consider a number of different routes to sustainability from the design stage. They should be reviewed mid-way through the programme to ensure they reflect the actual partnerships achieved during implementation and the activities appropriate at every stage in the country context. One lesson learnt is that activities/interventions need to be agreed with all the partners from the start, to ensure that ownership is built at all times; this would improve sustainability.

Implementing budget cuts is always a difficult decision-making process in choosing how best to mitigate effects. There were difficult choices to be made, some of which had an impact on outputs and outcomes. With DFID support the logframe was adapted accordingly across all countries.

Summary of recommendations

E4A should capitalise on the wealth of information collected, particularly in countries that have received follow-on funding, to demonstrate how advocacy works and its impact (e.g. briefing of appropriate decision-makers on how E4A worked).

E4A should demonstrate their innovative model on building political leadership from Nigeria and Tanzania to other E4A countries and consider the use of national sports personalities as local champions to bolster accountability and transparency mechanisms.

E4A should consider embedding the Maternal and Newborn Health evidence hubs with local governments/private sector to make the websites more sustainable and consider producing a ‘How to Note’ on achieving better alignment between national and regional MNH initiatives.

E4A should consider early engagement (survey/questionnaire) with the newly established Maternal Death Surveillance and Response (MDSR) virtual network to promote ownership, and follow up on the independent policy finding to establish what contributes to more evidence of impact (longer demonstration) in all countries.

E4A has learnt a great deal on what works and doesn’t work in terms of using data and evidence to effect change.  It is important that DFID integrates such learning in current and future programming (eg Malaria programme and future work on Disease Preparedness).  DFID should arrange a suitable dissemination event (e.g. Africa Health Advisers meeting), in Q2/Q3 2016 when the independent evaluation is complete, to ensure lessons are learned more widely across the organisation. E4A, the independent evaluation team, and the independent M&E quality assurer could contribute to this event as appropriate, to be agreed depending on timing/resources available’.

Action on previous recommendation

A key recommendation from the last annual review was on sustainability, consolidation and documenting evidence. The E4A team have developed detailed plans for each country and the regional component around the three key pillars of E4A - evidence, accountability and advocacy. Data use for decision making has been enhanced by the development and strategic use of scorecards in Ghana, Nigeria, Sierra Leone, Malawi and Tanzania. At sub-national level capacity of managers has been strengthened to collect, use and share data (for example through Quality of Institutional care (QuIC), dashboards or scorecard approaches). Learning from these approaches is being documented and discussions are on-going to scale-up initiatives to national level but whether that can be achieved within the timeframe of DFID funding is uncertain.

The ‘pathways to change’ work is ongoing and will be documented by the independent evaluation, after which E4A will synthesise learning from the evaluation for sharing with advocates. In this context E4A has started this process by developing “the creative assets book” (E4A’s approach to using visual communication) and “the case study book” (stories which describe how E4A theory of change was translated into action).

A. Introduction and Context

DevTracker Link to Business Case:	Link 3715354
DevTracker Link to Log frame:	Link 5083052

Outline of the programme

DFID is providing £17,256,376 over five years to a consortium led by Options (a UK-based international health consultancy), and including a range of technical, academic, and advocacy partner organisations, to implement the Evidence for Action to reduce maternal and newborn mortality in Africa (E4A) programme. The programme period is 2011-2016; following a lengthy inception phase programme implementation began in the second half of 2012. DFID is also supporting an independent evaluation of the programme.

The programme aims to improve maternal and newborn survival through a combined focus on evidence, advocacy, and accountability in six countries (Ethiopia, Ghana, Malawi, Nigeria, Sierra Leone, Tanzania) and regionally focused on the Maternal Death Surveillance and Response Network (MDSRN), Africa Health Budget Network (AHBN), Campaign for Accelerated Reduction of Maternal Mortality in Africa (CARMMA), AfricaHealth Stats and alignment to the Commission on Information and Accountability (CoIA) goals (working with regional and global institutions and partnerships, such as the African Union, WHO, and the Partnership for Maternal, Newborn and Child Health (PMNCH)). E4A is designed to result in better maternal and neonatal health services and outcomes by promoting more effective use of evidence to generate political commitment, strengthen accountability, and improve planning and decision-making – working both at country level and to support strengthening of regional and international accountability frameworks.

DFID started as the sole funder of this programme. In the past year, additional funding has been secured from the Gates Foundation for work in Ethiopia, Malawi, Nigeria and for the regional component of the work. Further funding from DFID Ethiopia and the DFID Maternal and Newborn Child Health (MNCH)2 projects in Nigeria have enabled expansion of E4A work into further districts/regions. NORAD has also funded a specific activity within the programme in the form of the QuIC tool, a low-cost approach to capturing Emergency Obstetric and Newborn Care (EmONC) data quickly and in real-time from health facilities. This was initially piloted in the sub-national areas within E4A, and NORAD funding enabled the programme to expand this to all E4A countries.

The expected outcome of E4A is more, and better, evidence based use of resources for maternal and neonatal health (MNH) services. Each country has a bespoke articulation of this general outcome statement. E4A is measuring this outcome through:

- The use of evidence by national and sub-national health managers and health facility managers in their decision-making (measured through repeated bespoke ‘data for decision-making’ (DDM) surveys).
- Improved political will to improve quality of care and the use of evidence for decision-making (measured through repeated bespoke ‘politics, power and perception’ (PPP) surveys).
- One or two country-specific indicators of MNH quality of care in each E4A country.

The expected impact of E4A is ‘accelerated reduction in maternal and neonatal mortality’. This has been indicatively modelled (the nature of the programme does not make direct attribution appropriate) as approximately 9690 maternal lives saved, 71,700 neonatal lives saved, and 47,640 stillbirths averted over the programme duration.

E4A will contribute to DFID’s Results Framework and Africa Regional’s Operational Plan indicator: number of people supported to have choice and control over their own development and to hold decision makers to account. These targets were set at 40 and 0.5 million respectively.

The end of 2015 marks the end of activities for the programme in three focus countries (Ghana, Sierra Leone and Tanzania) due to the reduction of £3m in the total budget over the final two years of the E4A programme. In addition to this, strategic changes were made to the overall programme in order to minimise the negative impact of the reduction of the budget. The priority was to retain the country teams ‘on the ground’ for as long as possible but the budget reduction does present two risks to the theory of change. The reduction in the geographical coverage and a shorter time frame in some countries may lead to lower level of sub-national to national impact and sustained political change may be less likely to occur due to early programme closures in 3 countries.

B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The overall outcome statement for E4A is ‘More, and better, evidence-based use of resources for MNH’. Each country has 2-4 outcome indicators. The mid-line data on outcome indicators was reported in 2014, and showed that most countries were on track to achieve the outcome on data for decision-making and improved political will, as reported in the 2014 Annual Report. No further measurement of the outcome indicators was due in 2015, with the endline due Q1, 2016. Final results on outcome indicators will be reported in the project completion report.

The midline PPP outcome indicator from Tanzania was lower than expected. Following the recommendation from the 2014 Annual review, E4A undertook in-depth qualitative assessment to better understand why the score had decreased because all other indicators demonstrated an improvement in political will and public perception on MNH. This qualitative work consisted of 7 key informants being re-interviewed in depth (July-August 2015, 2 national-level respondents and 5 in the Mara Region).

One key informant clarified that the lower score assigned at midline was not meant to be interpreted negatively, but was a reflection of him being more ‘realistic’ that there was still “room for improvement”. The lower scores at midline thus seemed to be due to respondents better scrutinising the sector and its performance.

Overall output score and description

A – Outputs met expectations

Key lessons

A prerequisite for working on a multi country programme like E4A is the need to have a shared Theory of Change. This ensures that all stakeholders have a consistent understanding on the approach to delivering change and can ensure their efforts are mutually reinforcing.

To deliver change it is important to recognise that different approaches work in different contexts and finding what resonates in a local context is crucial for impact. Advocacy work which is sensitive to the local context is more likely to promote ownership and therefore to be sustainable.

Key actions

Given the short time frame of the programme left, E4A should consider what further analysis can be carried out to substantiate the outcome statement if future low scores emerge from the endline data.

Has the logframe been updated since the last review?

The log-frame underwent a significant change during the 2014 Strategic Review, in order to make country targets more focused and aligned to what was possible to achieve within each country.

In May 2015, there have only been a couple of small changes, namely:
- Some Sierra Leone indicators, all accepted by the Monitoring & Evaluation Advisory Committee (MEAC) in May 2015
- Changes to the Malawi outcome indicator on quality of care due to new evidence on corticosteroids, accepted by the MEAC in May 2015.
- Changes to Malawi indicators 1.1, 1.2, and 3.1 were proposed and discussed with the MEAC. They were partially accepted, in recognition of difficulties of the Malawi programme during the re-budgeting / re-strategising exercise.
- PPP and DDM suggested changes in Tanzania and Nigeria – qualitative research commissioned by Options in both cases to fully understand low scores.

C: DETAILED OUTPUT SCORING

Output Title	Better information for better results: realising key parts of Commission on Information and Accountability (CoIA) recommendations in 6 countries.
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	31%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones 3 (2015)	Progress
1.1 / Ethiopia: Maternal death surveillance and response (MDSR) system coverage: the number of focal regions and woredas implementing MDSR per national guidelines, with meetings occurring as stipulated in the guidelines / Ghana: Use of MNH data for forward planning and resource allocation at district level. / Malawi: Coverage of community maternal death reviews (c-MDRs). / Nigeria,: Coverage of maternal death reviews (MDRs) / Sierra Leone: Coverage of maternal death reviews (MDRs) / Tanzania: Coverage of maternal and perinatal death reviews (MPDRs)	Ethiopia: 2 (regional level and 23 focal woredas in Oromiya and Tigray) / Ghana: District Health Management Team (DHMT)s in 9 focal districts have considered new MNH evidence at a management meeting, and used it for forward planning/resource allocation / Malawi: c-MDRs conducted in 8 Group Villages, according to the official guideline / Nigeria: MDR data collected in all secondary facilities in 1 focal state, following standardised MDR guidelines and tools / Sierra Leone: All designated Comprehensive Emergency Obstetric and Newborn Care (CEmONC) facilities in 2 focal districts (Koinadugu and Bonthe) conduct MDRs according to the national guideline / Tanzania: All 8 hospitals in Mara region review maternal deaths according to the nationally-approved MPDR guidelines / .	Ethiopia: Over-achieved / Ghana: Over-achieved / Malawi: Over-achieved (12 committees trained in c-MDR, so progress towards 2016 milestone) / Nigeria: Over-achieved (MDR data collected in all secondary facilities in 2 focal districts instead of 1) / Sierra Leone: Achieved / Tanzania: Achieved (including a post-training assessment in Sept 2015 which showed significant improvements in the quality of thereviews, and demonstrated thatavailable national guidelines werebeing followed by all hospitals)

1.2 / Ethiopia: % of health facilities visited in the last quarter of the project year which are implementing MDSR according to the national guideline / Ghana: Use of maternal death review (MDR) findings to identify and report problems in the system / Malawi, Nigeria, Sierra Leone: Use of maternal death review (MDR) findings. / Tanzania: Use of maternal death review (MPDR) findings	Ethiopia: target 33% / Ghana: E4A-supported training on MDR feedback delivered to GHS staff in 9 focal districts. MDR findings inform and are discussed by DHMTs during their quarterly meetings / Malawi: Data on factors contributing to maternal death in 6 districts disseminated to key stakeholders / Nigeria: State review teams in 1 focal state track progress on implementation of MDR recommendations through bi-annual state-level scorecards / Sierra Leone: National guideline on strengthening MDR response to the main 3 causes of death developed / Tanzania: Milestone due in October 2014 - Training of hospital staff from 8 hospitals in Mara region on how to use MPDR findings (action and response). Milestone due October 2015 – All MPDR Committees in Mara region (1 regional and 6 district) use MPDR data from health facilities to inform their decision-making, including resource allocation	Ethiopia: Over-achieved (46/57 health facilities, i.e. 81%) / Ghana: On track to be achieved by Q1, 2016. Report in PCR / Malawi: Achieved / Nigeria: Over-achieved / Sierra Leone: Achieved / Tanzania: October 2014 milestone now achieved. October 2015 milestone on track to be achieved by Q1, 2016. Report in PCR
1.3 / Ethiopia: Use by regional MDSR committees of MDSR data disaggregated by geography / Ghana: Use of disaggregated maternal and newborn data (including indicators from the CoIA list) in progress and performance reviews / Malawi: Use of disaggregated maternal and newborn indicators in progress and performance reviews at district level / Nigeria, Tanzania: Use of disaggregated maternal and newborn indicators from the CoIA list in progress and performance reviews. / Sierra Leone: Availability of disaggregated data on maternal and newborn indicators from the CoIA list	Ethiopia: Regional MDSR committees in all 4 regions/cities have discussed disaggregated MDSR data at least once / Ghana: Data on EmONC signal functions and health facility infrastructure disaggregated to health facility level disseminated and shared with Government of Ghana for use in progress and performance reviews / Malawi: District Dashboard data collected at least twice a year in 4 focal districts / Nigeria: MNH scorecards populated bi-annually, and results discussed by State review teams in 2 focal states / Tanzania: Disaggregated data from the national RMNCH scorecard are discussed by decision-makers at regional and district levels in 6 districts in Mara region at their regular meetings / Sierra Leone: Concept note jointly developed with the MoHS and other key partners, outlining next steps to enable national level access / reporting on COIA-related indicators disaggregated by age group and district	Ethiopia: Achieved / Ghana: Achieved / Malawi: On track to be achieved Dec 2015 / Nigeria: Achieved / Tanzania: Achieved / Sierra Leone: On track to be achieved by Dec 2015. Report in PCR
1.4 / Ethiopia: Development of a database integrating data for IDSR (Integrated Disease Surveillance and Response) and MDSR (Maternal Death Surveillance and Response) / Ghana: Coverage of mobile phone data capture system to monitor health facility readiness and ability to perform signal functions / Malawi: Coverage of mobile phone data capture system to monitor health facility readiness and ability to perform signal functions (QuIC) / Nigeria: Use of MNH evidence to support the development of annual state health sector plan and budgets / Sierra Leone: Availability and accessibility of data on key MNH outcomes / Tanzania: Coverage of QuIC data collection system to monitor health facility readiness and ability to perform signal functions	Ethiopia: Database is populated with up-to-date MDSR data from 4 regions / Ghana: At least two rounds of QuIC data capture completed in 16 districts / Malawi: At least two rounds of QuIC data capture completed in 4 districts / Nigeria: MNH data used by MTSS review teams in 1 focal state to develop annual state health sector strategies and budgets / Sierra Leone: National MDR database established. District dashboard mechanism established (populated with baseline data) in 2 focal districts, containing data from DHIS, QuIC / QuIC-FIT and MDR database / Tanzania: National stakeholder meeting convened to review QuIC pilot and discuss scaling up of the system beyond pilot districts	Ethiopia: Achieved / Ghana: Achieved / Malawi: Over-achieved (more than 2 rounds of data capture in the 4 districts) / Nigeria: Achieved / Sierra Leone: On track to be achieved Dec 2015. Report in PCR / Tanzania: Not achieved, sharing of QuIC routine data has taken place at regional, district and facility level. Need to also then have review of QuIC pilot at regional level first. Report in PCR

Key Points

E4A uses four main approaches to achieve Output 1: Better information for better results – improving the coverage of MDSR data, ensuring that MDSR data is used, ensuring the MNH data is disaggregated, packaging MNH data into scorecards to facilitate data for decision-making and piloting a new system of real-time quality of care data collection from facilities by telephone (QuIC).These approaches are used differently across the six E4A countries, depending on the specific country context.

Most milestones have been achieved; the handful that were not achieved are on track to do so in Q4 2015 or early 2016, and these results should be followed up in the PCR as noted above.

Summary of responses to issues raised in previous annual reviews (where relevant)

Ghana
The 2014 Annual Report recommended that the Ghana monitoring trip consider whether the data was actually reaching and influencing DHMT and other decision-making bodies. Along similar lines, the 2014 Annual Report also recommended that close monitoring of whether the QUIC approach was being adopted long-term by stakeholders, and whether results were being actively used to improve quality of care at facilities.
E4A is in discussions with the Ghana Health Service (Family Health Division) on how to embed the scorecard process within the DHMIS and routine DHMT assessments. E4A has built the capacity of health information officers and health managers to analyse and use data for local-decision-making, and also worked with the GHS and DHMTs to ensure MNH data is routinely available to review and discuss during management meetings to inform decision-making.

The independent policy study has reported that the facility scorecard has been used to influence improvements in staffing and availability of equipment, drugs and infrastructure.

The E4A Annual Report 2015 describes that good progress has been made in terms of building bridges and partnerships with various partners for various country specific asks; however, it seems that the Ghana programme needed more time to fully build the capacity and skills amongst local organisations and government counterparts to ensure sustainability. To quote the recent independent policy study (October 2015): “E4A/Mamaye has demonstrated that monitoring and supervision can be done better, with better health system performance, at little additional cost. Partners and staff are concerned that E4A/Mamaye initiatives will not be adopted nationally or regionally without more evidence of impact (longer demonstration) and the resources to implement them.”

Tanzania
In Tanzania, E4A established strong links with the White Ribbon Alliance Tanzania (WRATZ). To quote the recent independent policy study: “the role of E4A in strengthening and repositioning the White Ribbon Alliance (WRA) as a key advocacy body for MNH in Tanzania is increasingly appreciated by interviewees. The restructuring process is seen as inclusive and well managed, and all interviewees who mentioned the WRA consider this evolution as positive and promising.” WRATZ has now received funding from the Gates Foundation to implement its new five-year strategy, which in turn had been developed through an in-depth strategic planning and partnership engagement with E4A. The aspiration is for the MDSR system to continue to be strengthened under the guidance and leadership of the WRATZ members, following on from the work of E4A as the programme has ended.

QUiC
QuIC data has been used by a range of health system stakeholders to drive tangible improvements in quality of care in human resources, provision of care 24/7, the availability of drugs and supplies, referrals and infrastructure e.g.
- One district used QuIC data to make a case for more skilled staff and was able to recruit 35 additional skilled staff (Tanzania)
- QuIC demonstrated a consistent red scoring for elbow gloves in one facility. This resulted in timely ordering of supplies. (Nigeria)

Recommendations

E4A to follow up on the independent policy finding to establish what contributes to more evidence of impact (longer demonstration). This will assure partners and staff that E4A/Mamaye initiatives will be adopted nationally and regionally.

Output Title	Political leadership and public momentum
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	28%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones 3 (2015)	Progress
2.1 / Ethiopia: Integration of national MDSR guidelines in training and strategic plans / Ghana: Percentage of MamaYe! press releases that lead to a published article or are featured on radio/TV, without incentive / Malawi: Number of national TV programmes covering MNH issues, and number of district-level broadcasts/ publications covering MNH issues / Nigeria: Number of news articles in a 3-month period making reference to MNH, in newspapers (including online) / Sierra Leone: Percentage of MamaYe! press releases that lead to a published article in at least one newspaper, without incentive / Tanzania: Local media coverage of MNH issues	Ethiopia: Training schools in 4 focal regions/cities have had orientation sessions on the MDSR system / Ghana: 50% of MamaYE press releases lead to a published article or are feature on radio/TV (at least 2 media outlets) / Malawi: 6 programmes aired on national TV, which cover MNH issues. District-level journalists publish or broadcast at least 2 MNH stories per quarter / Nigeria: 100% increase since 2012 in the number of news articles. Plans in place for launch of investigative MNH media fellowship. / 50% of MamaYe press releases lead to a published article in at least one newspaper without incentive / Tanzania: Community radio stations in at least 19 regions feature MNH stories generated by local journalists who are Mama Ye! Advocates / activists	Ethiopia: Achieved / Ghana: Over-achieved (100%) / (37 articles published online, 9 in printed media, 11 on radio and 4 on TV) / Malawi: Achieved / Nigeria: Achieved / Sierra Leone: Achieved / (10 blogs, 3 newsletters, 3 pieces covered on radio/TV about MamaYe / Tanzania: Achieved

2.2 / Ethiopia: Number of community/religious leaders, local politicians, media representatives and CSOs engaged via E4A activities. / Ghana, Malawi, Nigeria, Sierra Leone, Tanzania: Number of advocates and activists engaged through E4A-supported national advocacy campaign. / Note: ‘engaged’ is defined as committed to E4A goals, and empowered by E4A with the power (evidence, information and/or strategy) to make change (real outcomes)	Ethiopia: 300 / Ghana: 200 / Malawi: 100 / Nigeria: 400 / Sierra Leone: 60 / Tanzania: 500	Ethiopia: Over-achieved (711) / Ghana: Over-achieved (1059, 50% female) / Malawi: Over-achieved (1834, 41% female) / Nigeria: Over-achieved (2332, 39% female) / Sierra Leone: Over-achieved (95, 37% female) / Tanzania: Over-achieved (2850, 46% female)
2.3 / Accessibility of relevant MNH information and resources for stakeholders.	Ethiopia: MDSR documentation available on WHO website: guidance, training materials, policy briefs, case studies (including use of data and actions taken) / Ghana, Sierra Leone, Tanzania: Website is contributing to raised awareness of MNH by regular updates to the content, including technical updates, new evidence added at least quarterly, and links to other relevant websites	Ethiopia: Achieved / Ghana: Achieved / Sierra Leone: Achieved / Tanzania: Achieved
2.4 / Website visits per month	Ghana: 950 / Malawi: 650 / Nigeria: 1,200 / Sierra Leone: 800 / Tanzania: 900	Ghana: Achieved (1061) / Malawi: Over-achieved (1095) / Nigeria: Over-achieved (1984) / Sierra Leone: Achieved (809) / Tanzania: Achieved (907)

2.5 (Not Ethiopia) / Ghana, Nigeria, Sierra Leone: Adoption of MamaYe! campaign by key engaged advocates/activists / Malawi: Number of MamaYe! clubs trained in 6 focal districts, and number of MNH seminars at the Kamuzu College of Nursing / Tanzania: White Ribbon Alliance (Tanzania)’s capacity to influence MNH policy at national level	Ghana: Advocacy Coalition partners and other stakeholders use MamaYe! branding for their own activities / Nigeria: MamaYe! activists advocate for E4A ask in Kano and Jigawa / Sierra Leone: 20 individual activists participate in at least 3 events since April 2015 where they deliver an address with MamaYe ask/sub-ask as the main theme, and 2 CSOs/other partner organisations have adopted at least one MamaYe ask/sub-ask into their annual workplan / mission statement / Malawi: 10 KCN seminars over the period November 2014 – October 2015 / Tanzania: E4A supported evidence-based strategic planning process complete, resulting in draft 5-year strategy for WRA Tanzania which is aligned with national commitments	Ghana: Achieved / Nigeria: Over-achieved (also in Ondo State) / Sierra Leone: On track to be achieved Q4 2015. Report in PCR / Malawi: Achieved / Tanzania: On track to be achieved Q4 2015. Report in PCR

Key Points

E4A’s approach to achieving Output 2 (Political leadership and public momentum) has included: engaging and mobilising communities to be more aware of MNH issues, empowering CSOs and citizens to advocate for, and take action on MNH, activities related to MNH resources being available and used from the national MamaYe websites, as well as engaging traditional media. This acknowledges that there are a range of ways to reach people in both cities and rural areas in five African countries. The difference in Ethiopia (indicator 2.4 and 2.5) also acknowledges how best to function as advocates within that political context.

The reduced milestones adopted during the Strategic Review in 2014 for indicator 2.4 seem to have been much more realistic as they have all been achieved, with a couple of countries over-achieving for 2015.

Summary of responses to issues raised in previous annual reviews

The 2014 Annual Review raised the point of sustainability of the MamaYe websites, with a question of who was going to host the MamaYe websites, update content, upload evidence etc.

The Nigeria, Malawi, Ethiopia and the regional site MamaYe/E4A will be maintained through the ongoing Gates investment. In Tanzania, Ghana and Sierra Leone, local activists have been engaged in continuing to provide stories for the websites, ensuring the sites remain fresh and responsive to local activist priorities. E4A is using the close-out of the Tanzania, Ghana and Sierra Leone programmes to test different models of continuing engagement, with the continuation of the Ghana site being supported through local partner ARHR, web-content from Sierra Leone being provided by a local journalist and a potential tender to local partners for continuing the Tanzania E4A site.

In the 2014 Annual Report, the point was also raised that 2015 saw elections in 3/6 E4A countries (Nigeria, Tanzania and Ethiopia) and questioned how the E4A programme would capitalise on upcoming opportunities. In Nigeria E4A advocated to different candidates on MHN issues and after the election engaged with the transition committee and the new government at state level to uphold commitments made on health. E4A has strong links with the Union of Tanzania Press Clubs (UTPC) where all their members received press packs on MNH and the MNH commitments made during the election campaign. This resulted in local journalist covering the issues raised in local radio and in local newspapers in the run up to the election.

In Ethiopia, E4A has a strong relationship with FMOH to strengthen MDSR as a key accountability mechanism for maternal outcomes. To minimise the risk of doing harm, E4A have not pursued a public facing campaign on MNH as the Ethiopian government has very tight regulations relating to the engagement of NGO’s in advocacy activities.

Recommendations

Whilst the funding to maintain the MamaYe websites across all countries until 2017 (from the Gates Foundation) is helpful in the short term, E4A should plan for a long-term solution on how to embed the need for an MNH evidence hub within local governments or local professional associations/institutions.

E4A Nigeria should build on their engagement with the new state government. Before the programme closes the team should brief relevant stakeholders on follow up to ensure further foundations are laid on this important breakthrough.

Output Title	Accountability & transparency mechanisms: Better oversight and transparency of the provision of maternal and neonatal health (MNH) services, for better accountability for mothers and their babies.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	31%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones 3 (2015)	Progress
3.1 / Ghana: Use of national accountability mechanisms to hold district health managers to account for the status of MNH services in E4A focal districts / Malawi: Multi-sectoral, evidence-based community level accountability mechanisms in place, which include District health sub-committees / Nigeria: National- and State-level accountability mechanism for service delivery / Sierra Leone: Transparency of RCH budget / Tanzania: RMNCH budget advocacy forms key activity for civil society coalition	Ghana: In 8 focal districts, data are collected every 6 months using the MNH scorecard mechanism, and results are reviewed by district authorities / Malawi: At least one District Health sub-committee meeting in 3 more focal districts to produce action plans with use of evidence / Nigeria: Accountability mechanism to track progress against MNH commitments is multi-sectoral and meeting quarterly, both nationally and at State level in 1 focal state / Sierra Leone: Status of national MNCH financing is made publically available on MamaYe website, and used by members from the budget tracking consortium to hold decision-makers to account / Tanzania: RMNCH financing is a key strategic objective for White Ribbon Alliance Tanzania in its strategic plan 2015-20	Ghana: On track to be achieved Q4, 2015. Report in PCR / Malawi: Achieved / Nigeria: Achieved / Sierra Leone: Achieved / Tanzania: Achieved

3.2 / Number of people supported to hold decision-makers to account in relation to MNH.	Ethiopia: 3,500 / Ghana: 30,000 / Malawi: 15,000 / Nigeria: 25,000 / Sierra Leone: 10,000 / Tanzania: 26,000	Ethiopia: Over-achieved (44,963 – primarily due to number (38,000) of health extension workers trained and providing support to E4A) / Ghana: Over-achieved (48,047) / Malawi: 19,646 / Nigeria Over-achieved (50,253) / Sierra Leone: Over-achieved (12,779) / Tanzania: Over-achieved (264,564)
3.3 / Ethiopia: Number of regions and health facilities producing MDSR action plans / Ghana: Mechanism to encourage service providers to report their training and resource needs	Ethiopia: All 4 focal regions produce an action plan based on data from that region’s MDSR system. At least 3 hospitals or health centres in each focal zone/city produce an action plan based on that facility’s MDSR data. / Ghana: in 2 regions (8 districts), teams are allocated to support supervision in districts. They visit at least once every 6 months and make a record of needs. One supervision partner adopts the supportive supervision system and commits to continuing with it post-E4A	Ethiopia: Over-achieved / Ghana: Partially on track to be achieved Q4, 2016 – Supportive supervision continues in Greater Accra and the Upper West regions in January 2016, partially-funded by SPH, E4A and the Greater Accra government. Discussions also continue with the Ghana Health Service and the MNH professional society on the subject.
3.4 / Ethiopia: Percentage of MDSR recommendations from 2014 action plans which have been implemented	30%	Ethiopia: Achieved

Key Points

In order to achieve Output 3, E4A has set up MNH budget tracking, action plans, scorecards and sub-national MNH accountability platforms. In Ethiopia, the approach is different to adapt to the local context, and establishing MDSR action plans are the key approach. In all countries except for Ghana, E4A has over-achieved or achieved its milestones under this output. In Ghana, they are on track to achieve the milestone by the time of the PCR.

Indicator 3.2 shows significant over-achievement by all countries. This is mostly due to the teams’ success in engaging with media outlets and creating spin-offs from MamaYe clubs and launch events. Tanzania in particular has had significant success engaging with journalists through the Union of Tanzania Press Clubs.

Summary of responses to issues raised in previous annual reviews (where relevant)

Three main recommendations in the 2014 Annual Review:
- E4A should continue working with local champions who can hold decision-makers to account even when the E4A programme ends.
- E4A should institutionalise accountability mechanisms within sustainable structures to ensure responsible exit strategies
- In Ethiopia where MDSR is the approach, need to continue to work closely with the host institution (WHO) to ensure systems are institutionalised before programme completion.

E4A has made progress in identifying local champions. The MamaYe campaign has been spearheaded in Sierra Leone by a local hero who has mobilised communities and activists to give blood and in Malawi national figures have associated themselves to the campaign. Coalitions have been built with ARHR in (Ghana) and UTPC and WRA in Tanzania, while support for accountability mechanisms will continue into 2017 in Malawi, Nigeria and Ethiopia through Gates Funding.

In Ethiopia E4A is embedded within WHO as the host agency where all activities are implemented in association with regional and federal ministries and therefore fully- integrated into government systems. The MDSR system will continue with funding from the Gates Foundation until October 2017.

Recommendations

E4A/MamaYe has gained visibility at both national and sub-national level, played its role in building coalitions and strengthened accountability mechanisms at country level. However as the programme draws to a close E4A should apply lessons from their innovative model in Nigeria and Tanzania on building political leadership to help other E4A countries find suitable ways to bolster their accountability & transparency mechanisms.

Sports personalities can act as great local champions, breaking down barriers and upholding transparency mechanisms for better accountability. In this context E4A could consider approaching international footballers who play for their national country.

Output Title	Better alignment between national and regional MNH initiatives, including the realisation of Commission on Information and Accountability (CoIA) goals.
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones 3 (2015)	Progress
4.1 / E4A countries' contribution to the CoIA learning process at the global level	Africa Health Budget Network has produced at least two quarterly newsletters and contributed to at least one regional event	Over-achieved
4.2 / Influence of CARMMA on MNH-relevant decisions made by heads of state and relevant ministries	Representatives of all E4A countries attend regional meetings/ conferences to raise the profile of MNH as an issue and share learning about the impact of the use of scorecards and best practice examples in national campaigns	Achieved
4.3 / Regional and national capacity for implementation of maternal death surveillance and response (MDSR)	National MDSR networks in the six E4A focus countries are set up such that they function nationally as well as members being connected to the global MDSR network. In at least 3 countries, teams convene a virtual network of interested stakeholders	Partially-met (achieved in Sierra Leone then on hold due to ebola, recently partially revitalised; and various stages of discussions on MDSR networks in other countries)

Key Points

E4A’s fourth output focuses on ‘Better alignment between national and regional MNH initiatives, including the realisation of CoIA goals. Three indicators are used to measure E4A influence and impact on communicating and strengthening regional and country level interactions in furthering efforts on MHN accountability and holding decision makers to account.

Indicator 4.1 on CoIA has been over-achieved, with a total of three quarterly newsletters with evidence and resources, and a catalogue of dedicated health budget advocacy materials including scorecards and factsheets produced for the Financing for Development conference in July 2015.

Indicator 4.2 milestones on CARMMA have been achieved, with E4A-MamaYe representatives attending events and conferences to showcase E4A-MamaYe’s use of scorecards and best practice to accelerate progress on MNH throughout 2015.

Indicator 4.3 has been partially achieved and may not be fully achieved by the end of the programme. The global MDSR network continues to bring together expertise and practitioners to strengthen the implementation of MDSR. Whilst good progress has been made in laying the foundations for an MDSR virtual network across each country the rollout of MDSR is at an early stage. A national MDSR network has been officially established in Sierra Leone and discussions for a virtual network have been taken forward in Nigeria. Discussions have taken place with country teams in Ethiopia, and Malawi in thinking through how to develop national level and/or virtual in-country MDSR networks, but these have not yet become firmly established.

Summary of responses to issues raised in previous annual reviews (where relevant)

The main recommendations in the 2014 Annual Review:

- Bring more to the fore the experiences of MDSR networks from country-level E4A teams to international fora.
- Inspire non-E4A countries who are part of the MDSR network to take positive experiences and create MDSR coalitions.
- Develop sustainable solutions to maintain/use statistics on African Health Stats. E.g. could try continuing linkages with UNFPA, WHO, USAID as key partners to institutionalise these changes. Bring African Union staff into the equation.
- Involve Tim Stern (DFID’s representation to the AU) on health discussions
- Work with Chair of International Federation of Gynaecology and Obstetrics (FIGO) Advisory Group to institutionalise MDRs, with community involvement as key part of that

The status of MDSR networks in other E4A countries varies according to context and need. In Nigeria a fledgling virtual network was recently launched on facebook and in Ethiopia, the MDSR Newsletter already represents a forum for sharing experiences and resources. The most established network is the Sierra Leone’s Maternal Survival Action Network, and its experiences have been shared through other platforms like WHO’s MDSR website.

Non-E4A countries who are part of the MDSR network have created coalitions at platforms such as the FIGO conference where E4A shared positive experiences from MDSR implementation and through the network’s newsletters and on the website where case studies and news updates on MDSR is presented. E4A sees FIGO as a key partner alongside WHO in their quest for sharing of knowledge and resources through the MDSR network. Ongoing support from Gates will help support continued efforts to inspire non E4A countries who are not part of the network.

The process for building sustainable solutions has begun with E4A coordinating capacity building inputs to the AU including Carmma and African Health Stats with UNFPA and USAID funded partners to ensure support is strategically aligned. This joint approach to strengthening AU processes will continue into 2017 under the Gates Survive & Thrive grant. There has been good engagement, with active players directly supporting AHS and CARMMA including USAID, Africa Strategies for Health and UNFPA. Plans are in place to hold a meeting in February to discuss a way forward for updating the platforms and increasing their utility and impact. This will be an opportunity to ensure that AU representation occurs including DFID representation to the AU.

Recommendations

E4A should consolidate their findings into a “How to Note” on achieving better alignment between national and regional MNH initiatives.

As the rollout of the virtual MDSR network has just started, early engagement by E4A in the form of a survey/questionnaire on how the network can best support its users in their everyday work would help make it fit for purpose and build ownership.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key cost drivers identified in the original business case remain unchanged and are as follows:

- Staff: National staff within the selected implementing partner institution to implement activities. International staff, mostly short term, technically supporting implementation, providing guidance, overseeing capacity building, collaborating with international organisations.
- Partner organisations: Civil society organisations and academic institutions implementing programme activities such as advocacy and accountability events, capacity building, data analysis and dissemination, as well as equipment, overhead costs
- Travel and subsistence: International and local travel to, and within, the six countries, as well as key regional and international events
E4A is managed as a milestone-based contract, with key deliverables and milestones agreed by DFID and Options for each of the financial years.

VfM performance compared to the original VfM proposition in the business case

## There are five VfM indicators: (1) management and administration costs per pound invested (as measured by unit costs of flights and per diems), (2) extra resources leveraged per pound invested, (3) use of evidence by national and sub-national health managers in their decision-making, (4) lives saved per pound invested and (5) economic cost of maternal lives saved per pound invested.
This review reports on the first two indicators. Indicator 3 was reported at midline in the last annual review and its endline reporting will be carried out in the final project completion report. Indicators 4 and 5 will be assessed at the end of the programme due to data availability and the nature of their relationship with cost benefit analysis agenda and the premise that the project will enhance the efficiency of pre-existing spend on MNH.

Progress against indicator 1 resulted in a significant saving of £78,153.00

All Flight Costs	No of Return Flights	Unit Cost	Total Cost
Budget for October 2014 to September 2015	72	£1576	£113,451
Actual cost for the same period	77	£829	£63,800

Accommodation – African City	No of Days	Unit Cost	Total Cost
Budget for October 2014 to September 2015	640	£186	£118,854
Actual cost for the same period	1,027	£88	£90,352

New resources (US $4,778,982) were leveraged from BMGF to build directly on the DFID contract work, in particular in Ethiopia, Nigeria, and Malawi. Since then further funding (US $999,110) has been leveraged to sustain the MamaYe’s regional portfolio work and widen MDSR coverage in Ethiopia. In addition WHO has also provided £25,000 for an in-depth assessment on the implications of MDSR legislation and US $19,989 to support the Malawi’s countdown dissemination on child and newborn health.

Assessment of whether the programme continues to represent value for money

Overall the programme continues to represent value for money given the progress made in all the outputs and VfM indicators. In addition capacity development is an important theme that is recurrent through all aspects of evidence, advocacy and accountability of E4A. Initial efforts focused on ensuring that E4A teams and host agencies were well equipped and well placed to implement the programme. This year the programme focussed on dissemination and communication of results and impact at high profile conferences e.g.

- Countdown to 2015 Country Case Study meeting (London, February 2015)
- African Union Meeting to Validate Draft Reports for the Review of Expiring Health Policy Documents (Nairobi, February 2015)
- MA4Health: Measurement and Accountability for Results in Health Summit (World Bank, Washington DC, June 2015)
- Financing for Development conference (Ethiopia, September 2015)
- FIGO World Congress (Vancouver, October 2015)
- Global Maternal and Newborn Child Health (MNCH) Conference (Mexico, October 2015)

Quality of financial management

Financial management has been effective within the E4A programme. Payments are based on performance on a quarterly basis against key performance indicators (KPI). The contract with managing agent - Options Consultancy is constructed such that 45% of costs are invoiced quarterly according to achievement of actual expenditure milestones and 55% invoiced based on delivery of KPIs.

Year 5 (April 2015 to March 2016) budget forecast of £1,987,231 was approved at the beginning of the financial year. To date 50% of the budget has been utilised against 11 KPIs. The remainder of the budget is on track to be spent by March 2016. The narrative reports for Quarter 2 (July to September 2015) showed that current spent and forecast are in line with budget forecast.

Options financial statements were audited in accordance with the requirements of the Companies Act 2006 by independent auditors. In their opinion the financial statements give a true and fair view of the state of the company’s affairs as at December 2014 and of its profits for the year then ended.

Date of last narrative financial report	12 October 2015 (5273500)
Date of last audited annual statement	31 December 2014 (5263498)

E: RISK (½ page)

Overall risk rating:

Medium

Overview of programme risk

Risks were assessed as part of the business case process and fall under the headings of political, institutional, social, economic and conflict. Under all five of these headings, risk was assessed as medium. For this reporting period the operating environment was stable and the Ebola epidemic abated in Sierra Leone, after significant effect in the previous reporting period. In Nigeria where security remains a challenge E4A works through local host agencies with only local staff and consultants. E4A Country Director is a member of the DFID Suppliers Risk Management Group and E4A follows DFID and FCO guidance for any travel to the north.

As acknowledged in the 2014 Annual Report, the budget cuts of 2014 added risk to the programme reaching its planned outcomes, because activities associated with the theory of change have had to be cut or reduced. This includes ending the programme early in Ghana, Sierra Leone and Tanzania.

In Ghana, it has been difficult to embed many of the E4A interventions within the Ghana Health System; E4A have reported that this is due to the early closure. It could also be however due to the choice of interventions from the start of the programme, and due to the context within the country regarding prioritisation of health and MNH in particular. However within the time frame E4A has worked with two host agencies – School of Public Health and Alliance for Reproductive Health Rights (ARHR) to integrate components of the programme that were in good position to be integrated into existing systems and institutions.

In Sierra Leone, the E4A programme has leveraged its connections with other programmes including the DFID ‘sister’ programme PMEL. This programme has been able to take on some critical elements that required further support, in particular FIT and QuIC FIT. District level activists will be supported by the E4A website, and one CBO in Koinadugu is seeking to register as MamaYe Sierra Leone to continue the MamaYe campaign with partners across the country.

Despite the Ebola outbreak the E4A team in Sierra Leone were able to focus on maternal and newborn messaging. They took the opportunity to participate in the Ebola social mobilisation committees to continue raising citizens’ expectations on safe clinics and encourage trust in health services. E4A also adapted our EmONC assessment tools (FIT and QuIC FIT) to the Ebola outbreak collecting information on infection prevention and control.

In Tanzania, there is extremely positive country context towards MNH, due to the strengthening of the host institution – White Ribbon Alliance Tanzania (WRATZ) – with whom E4A has been closely linked. WRA members are driving advocacy for MNH in Tanzania, in association with the Union of Tanzania Press Clubs (UTPC) which has been central to expanding awareness of MNH issues among the media and sharing MNH evidence and stories through local level media networks. In addition, the MDSR system is now embedded in national policy.

To mitigate the risk of key elements of E4A not being sustained E4A has developed sustainability plans for all programmes which have been incorporated into operational plans for the final months of the programme. Sustainability strategies identify the elements of the programme which will be sustained through institutionalising within the health system, strengthened advocacy coalitions developed through E4A, documenting and disseminating learning, and leveraging additional external resources. As described above Ghana, Sierra Leone and Tanzania are working to consolidate and embed those components of the programme that are in good position to do so while exploring alternative investments where it is considered essential to achieve the greatest long term impact. In contrast Nigeria, Ethiopia and Malawi has attracted investment from Gates Foundation to cement these programmes and transfer the learning and model to new parts of the country. Gates funding will also is also supporting the regional components of E4A’s work (AHBN, MDSR Network, support to AU/Carmma) and providing additional funding to expand E4A’s work in Ethiopia.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

There has been no underspend and as per business case the overall E4A programme is expected to end in March 2016The funding cuts of 2014 resulted in programme activities ending in December 2015 inGhana, Sierra Leone and Tanzania.

Performance of partnership (s)

DFID and E4A partner teams including the evaluation team have developed constructive working relationships. DFID provides oversight and technical/strategic guidance when needed, with a team that is committed though subject to staff turnover. Whilst E4A has had some leadership and management changes including in their country teams, they still possess high calibre teams and together with DFID the programme is effectively managed.

The programme contract was awarded to the E4A consortium following a competitive tender process. Options, the lead organisation in the consortium, are involved in DFID’s ‘Key Supplier Management’ (KSM) programme. The most recent KSM assessment confirmed Options’ good performance on contract management.

Asset monitoring and control

For this reporting period, the programme implementers together with their country offices have provided an updated list of assets purchased with the grant. These assets have not been monitored in the field by DFID.

G: CONDITIONALITY

Update on partnership principles (if relevant)

Not applicable

H: MONITORING & EVALUATION

Evidence and evaluation

2015 has seen the implementation of the Independent Evaluation in earnest, following the end of the Inception Period in mid-April 2014, adaptation of the Inception Report as per SEQAS comments, and then revision of the evaluation framework due to re-budgeting. The final evaluation framework was resubmitted and accepted by DFID in January 2015.
- The first progress report was submitted by the Independent Evaluators in May 2015, and the second progress report was submitted in October 2015. The quality of the progress reports is very good, and the independent evaluation team is very responsive to suggestions and changes made by DFID following review of these reports at the Monitoring & Evaluation Advisory Committee meetings (MEACs). A period of intensive data collection with country visits to Ghana, Malawi and Tanzania for the independent evaluation began in earnest in Q4 2015, as per the work-plan. Results will be reported on in 2016, as agreed.
- The policy studies component is ongoing under the management of E4A, with technical oversight from the Independent M&E Quality Assurer. This is a prospective study with both national and sub-national components. Progress reports have been submitted to Options, and reviewed by the Independent M&E Quality Assurer, on time throughout and mostly of excellent quality. Results have been disseminated to E4A country programmes, and used to adapt programming in a very positive way. One exception is the quality of the national study from Ghana – as reported in the 2014 Annual Report, there were concerns by both Options and the Independent M&E Quality Assurer of lack of contextual understanding and detail. In 2015, various discussions have taken place with the lead national investigator, and the quality has improved.
- Due to the ebola crisis in Sierra Leone, the nature of that country’s E4A programme’s involvement as part of the independent evaluation has changed. Firstly, the independent evaluation team and DFID selected Malawi as the third country to replace Sierra Leone. Secondly, the policy study in Sierra Leone has now changed to collect data as a retrospective case-study on how E4A responded and adapted to the ebola crisis, working through an independent researchers in Sierra Leone under the guidance of the principal investigator. Results are due with the final report in March 2016.
- The Independent M&E Quality Assurer undertook a monitoring visit to Ghana in July 2015. The main purpose was to accompany the policy studies team at sub-national level to monitor the process and results. Other aims of the monitoring visit were to reflect on how best to represent the policy study findings within the overall evaluation, and to explore sustainability issues as the programme ends. A trip report was submitted to DFID, and discussed with both DFID and Options. Follow-up meetings were held with the policy studies team and the evaluation team to implement the main recommendations. The findings on the policy study were overall very positive in terms of process – concluding that the policy study team was using sound data collection tools, and the process was independent, and the results from the policy study were being disseminated and used well by the E4A team. There was, however, a lack of coordination between the policy studies and the overall evaluation. This had always been stated as a risk due to separate management arrangements for each. Since the trip, there has been a significant increase in coordination between both teams, and agreement on how to represent policy study findings properly within the overall evaluation report (using DAC criteria as a guiding structure for content). Therefore, the risk has been mitigated, and should result in a better quality final overall evaluation which integrates the policy study fully within its findings and structure.

Monitoring progress throughout the review period

The programme receives feedback on implementation and progress through quarterly Key Performance Indicators (KPI)’s which are discussed in person with the E4A technical and leadership management team. This provides regular platform for feedback and to identify programme opportunities, challenges and risks. In addition DFID’s programme manager attended the E4A regional team meeting held in London in October 2015. The three day regional meeting with E4A Country Directors and Technical Support Unit (TSU) partners was an opportunity to discuss their experience to better understand results and issues of the programme.

As mentioned above the E4A programme is managed through a performance based (delivery of KPI’s) contract. This acts as a conduit for monitoring and discussing programme activities every quarterly ensuring that the programme is delivering on its objectives. Progress was also reviewed through other documentation e.g. E4A 2015 annual report, evaluation progress report, the independent M&E quality assurer’s trip to Ghana (July 2015) with the policy study coordinator and engagement at the E4A regional meeting.

As the programme is due to end in April 2016 when the full E4A programme closure report including the final independent evaluation report will be available, an internal desk based assessment was appropriate for this annual review. The review was informed by the above documentation and also had input from Independent M&E quality assurer. The review process took place during December 2015 and January 2016.