## Sheet1
Policy Research Fund - LogFrame
PROJECT NAME | Policy Research Fund
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (12/13) | Milestone 2 (13/14) | Milestone 3 (14/15) | Milestone 4 (15/16) | Milestone 5 (16/17) | Target (Sept 2017)
More effective evidence based policies in DFID | Quality of Evidence. | Planned | Portfolio Quality (PQ) score as at project start date. TBC. | Graduation to PQ score of 100 or above 0.5 increase. | Graduation to PQ score of 100 or above 0.5 increase. | Graduation to PQ score of 100 or above 0.5 increase. | Graduation to PQ score of 100 or above 0.5 increase. | Graduation to PQ score of 100 or above 0.5 increase. | PQ Score of 100 or above in line with EMC target.
Achieved
Source
Portfolio Quality score as provided to the Executive Management Committee from Aries.
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017)
| Impact of Evidence. | Planned | Portfolio Quality (PQ) score as at project start date. TBC. | Graduation to PQ score of 100 or above 0.5 increase. | Graduation to PQ score of 100 or above 0.5 increase. | Graduation to PQ score of 100 or above 0.5 increase. | Graduation to PQ score of 100 or above 0.5 increase. | Graduation to PQ score of 100 or above 0.5 increase. | PQ Score of 100 or above in line with EMC target.
Achieved
Source
Portfolio Quality score as provided to the Executive Management Committee from Aries.
| Impact Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017)
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017) | Assumptions
Increased use of evidence in formulating policy recommendations and programme design | Advisers gaining experience in commissioning and using research in policy. | Planned | 10 Advisers using PRF to produce evidence. | 12 advisers using PRF to produce evidence. | 15 advisers using PRF to produce evidence. | 20 advisers using PRF to produce evidence. | 23 advisers using PRF to produce evidence. | 25 advisers using PRF to produce evidence. | 25 advisers using PRF to produce evidence.
Achieved
Source
Through regular PRF rounds for applications and ensuring the PRF is communicated and promoted within advisory cadres.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
| 10.630m |  |  |  | 10.630m |  |  |  | 100
INPUTS (HR) | DFID (FTEs)
0.75 B1 Programme Manager 0.60 B2 Deputy Programme Manager
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017) | Assumptions
Quality of evidence on policy relevant issues | A suite of up to 100 quality research papers to be used by wider research community. | Planned | 50% of outputs of sufficient quality to be published. | 55% of outputs of sufficient quality to be published | 60% of outputs of sufficient quality to be published. | 65% of outputs of sufficient quality to be published. | 70% of outputs of sufficient quality to be published. | 75% of outputs of sufficient quality to be published. | 75% of outputs of sufficient quality to be published.
Achieved
Source
Policy Makers. Baseline figures obtained from PRF review which looked at transparency, rigour, validity, reliability and cogency. PRF commissioners and those using the evidence. Impact evaluation forms include this information which is mandatory for all commissioners to complete.
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017)
| Internal clients satisfaction with the above products and services. | Planned | 60% of outputs judged to be very good or excellent. | 65% of outputs judged to be very good or excellent. | 70% of outputs judged to be very good or excellent. | 75% of outputs judged to be very good or excellent. | 77% of outputs judged to be very good or excellent. | 80% of outputs judged to be very good or excellent. | 80% of outputs judged to be very good or excellent.
Achieved
| NOTE: Satisfaction Is the foundation measure and is a function of the timeliness and quality of the product delivered. | Source
PRF commissioners and those using the evidence. Impact evaluation forms include this information which is mandatory for all commissioners to complete.
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017)
| Evidence of sufficient quality to be published on R4D. | Planned | 70% of products judged to be of sufficient quality to be published. | 75% of products judged to be of sufficient quality to be published. | 80% of products judged to be of sufficient quality to be published. | 85% of products judged to be of sufficient quality to be published. | 87% of products judged to be of sufficient quality to be published. | 90% of products judged to be of sufficient quality to be published | 90% of products judged to be of sufficient quality to be published.
Achieved
Source
R4D and PRF commissioners impact evaluation forms.
IMPACT WEIGHTING (%)
40 | [9 empty] | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
0.3 B1 Programme Manager 0.3 B2 Deputy Programme Manager
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017) | Assumptions
Policy Impact | Research linked to clear policy objective. | Planned | 60% judged as having clear policy objective | 65% judged as having clear policy objective | 70% judged as having clear policy objective | 75% judged as having clear policy objective | 77% judged as having clear policy objective | 80% judged as having clear policy objective | 80% judged as having clear policy objective
Achieved
Source
Baseline figures from annual review of PRF. Impact evaluations to be completed 3-6 months after research to measure policy objective. Additional board members to help judge policy significance.
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017)
| Specified mechanisms for achieving policy impact. | Planned | 60% judged to have specific mechanisms for achieving policy impact | 65% judged to have specific mechanisms for achieving policy impact | 70% judged to have specific mechanisms for achieving policy impact | 75% judged to have specific mechanisms for achieving policy impact | 77% judged to have specific mechanisms for achieving policy impact | 80% judged to have specific mechanisms for achieving policy impact | 80% judged to have specific mechanisms for achieving policy impact
Achieved
Source
Baseline figures from annual review of PRF. PRF applciations will be judged on this element and impact evaluations will allow us to check this after project completion.
| Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017)
IMPACT WEIGHTING (%) | Convincing and clear evidence of policy impact. | Planned | 60% judged to have convincing and clear evidence of policy impact | 65% judged to have convincing and clear evidence for policy impact | 70% judged to have convincing and clear evidence of policy impact | 75% judged to have convincing and clear evidence of policy impact | 77% judged to have convincing and clear evidence of policy impact | 80% judged to have convincing and clear evidence of policy impact | 80% judged to have convincing and clear evidence of policy impact
40 |  | Achieved
Source
|  | Baseline figures from annual review of PRF. PRF applications will be judged on this element and impact evaluations will allow us to check this after project completion. | [7 empty] | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
0.3 B1 Programme Manager 0.2 B2 Deputy Programme Manager
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Target (Sept 2017) | Assumptions
Achieve savings on original quotes | Value of savings achieved | Planned | 2% of PRF budget savings in total to be recycled back to programme funds. | 4% of PRF budget savings in total to be recycled back to programme funds. | 8% of PRF budget savings in total to be recycled back to programme funds. | 9% of PRF budget savings in total to be recycled back to programme funds. | 10% of PRF budget savings in total to be recycled back to programme funds. | 11% of PRF budget savings in total to be recycled back to programme funds. | 11% of PRF budget savings in total to be recycled back to programme funds.
Achieved
Source
Record of savings achieved held centrally on DoR teamsite. Suppliers commercial proposals will be negotiated as will commissioners PRF applications.
IMPACT WEIGHTING (%)
20 | [9 empty] | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
0.15 B1 Programme Manager 0.10 Deputy Programme Manager