Business Case

Summary Sheet

Title: / Pitcairn Financial Aid Settlement 2016-17
Project Purpose: / To support the provision of public services to meet the reasonable assistance needs of the people of Pitcairn (including health, education and securing sea access), given self-sufficiency is currently not a viable option for this UK Overseas Territory. This is in line with the 2012 Overseas Territories White Paper and consistent with relevant elements of UK’s Aid Strategy and DFID’s 2015-2020 Single Departmental Plan.
Programme Value: £3.00m		Country/ Region: Pitcairn
Project Code: 204709	Start Date: 01/04/2016	End Date: 31/03/2017
Overall programme risk rating:	MODERATE
Quest Number:	5319452

Intervention Summary

What support will the UK provide?

This programme will support the government of Pitcairn Island to deliver essential services. Our financial aid will promote accountability, transparency and overall good governance of the Territory. It will also ensure that the remaining children on the island have high standards of child safeguarding. As such, to the extent practicable, our financial aid to Pitcairn is in line with DFID’s Single Departmental Plan and the strategic objectives of the 2015 UK Aid strategy[1] in particular on:
[1] UK aid: tackling global challenges in the national interest, 2015: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/478834/ODA_strategy_final_web_0905.pdf
- Strengthening global peace, security and governance
- Tackling extreme poverty and helping the world’s most vulnerable
- Delivering Value for Money

The UK government will provide up to £3.00 million (net) in financial aid to Pitcairn for the financial year 2016/17. This compares to a net settlement of £2.910m in 2015/16. This year’s settlement comprises:

£1,504,980 to cover the recurrent budget deficit. This includes £923,642 for the running of Pitcairn Islands Office (PIO) in Auckland, New Zealand, which provides a treasury role as well as logistical and management support to the island, plus government of Pitcairn Island salaries of £92,544 and pensions/child benefit of £18,614.

£1,217,370 to maintain maritime access to the island through the dedicated freight and passenger ship the MV Claymore II.

£560,090 to fill critical capacity gaps essential to provide health, welfare, education, judicial and legal services including ensuring continued child and adult safeguarding on the island. This also includes provision for flexible access to short-term TC/TA (technical cooperation/assistance) where there is adequate justification.

Expected revenue of approximately £282,440 will be offset against the figures quoted in (i) and (ii) above.

What are the main programme activities?

The project will support the Pitcairn Islanders by meeting their reasonable assistance needs through:
- maintenance of essential public service provision; and
- maintenance of regular and reliable sea access to Pitcairn

The main programme activity for DFID staff will be regular dialogue with the Pitcairn Governor’s office, including the island based administrator, the PIO, Island Council and FCO, focussing on: budget implementation; service delivery; and management of risk throughout the lifetime of the project.

Why is UK support required?

The UK Government is responsible for meeting Pitcairn’s reasonable assistance needs. With the exception of the European Union (EU), the UK Government is the only source of significant external financing available to Pitcairn. Without financial aid from the UK,the Pitcairn Island government would be unable to provide most essential public services. Public services would collapse and the islanders would have to return to basic subsistence or leave the island.

HMG recognises that the prospect of economic self-sufficiency for Pitcairn is very low, given its small population (42 resident islanders[2]), its small size (47 sq km/18.1 sq miles covering all 4 islands) and extremely remote location. The level of financial aid provided to Pitcairn is a reflection of this remoteness, and the lack of social and economic opportunities for its inhabitants. These factors raise two key challenges: how to provide (i) an appropriate level of essential public services; and (ii) a regular shipping service. How to meet these challenges cost-effectively is made doubly difficult by the need to guarantee adequate protection of children at all times and the very limited opportunity to raise revenues or pay for the public services required. Providing an adequate range of services and safe access to the island in the context of an aging population will also be an increasing challenge.
[2] Pitcairn Island Census December 2015

Tourism is a potential growth area and efforts are being made to market Pitcairn as a tourist destination. This includes support from the EU to improve tourism facilities through a new landing site to encourage more passing cruise ships and yachts to land passengers, the provision of transportation to bring people in from the ships, as well as refurbishment of the Adamstown Square. Part of this finanicial aid settlement will be used to fund the Tourism Department’s activities.

An independent socio-economic review conducted in late 2013, reviewed the financial and economic conditions on the Island and introducing import duties and income tax. Preparations for these developments have been underway for a number of years e.g. (i) improvements in the import regime and financial records of the Island Store; and (ii) implementation of the Land Court. The review concluded that while the introduction of income tax would raise revenue, the impact would be small. It would not be sufficient to reduce the budget deficit as government salaries would need to be increased to reflect the introduction of tax. With an ageing and declining population the opportunity to increase revenues will diminish further over time. The costs associated with continued child safeguarding (which includes international technical assistance) provide little opportunity to reduce the deficit.

There is no basis in the existing law of Pitcairn which requires a declaration of private earnings. Nor is there a requirement to contribute to governmental services (proportionate to income). The current constitution also does not allow a cap on the ability to claim legal aid, as exists in the UK, which has resulted in, and could continue to incur, considerable costs as residents pursue legal cases through the courts. The same provision does not allow assets outside Pitcairn to be taken into account when determining eligibility for legal aid.

What are the expected results?

The expected results of DFID’s support is that the Pitcairn population’s reasonable assistance needs will be met, cost effectively, through efficient management and delivery of essential public services (including the continued provision of child safeguarding measures) and the maintenance of regular access to the island.

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

OTD’s Operational Plan is in the process of being drafted with anticipated publication in May 2016. However DFID’s responsibilities for the UK’s Overseas Territories (OTs) continue to be framed by UN Charter obligations, UK legislation and long-standing Government policy. The 2012 White Paper reaffirms the UK commitment to meet the reasonable assistance needs of the aided-OTs (including Pitcairn) and ‘where conditions are right’ to invest in stimulating growth and reducing financial dependency. Where this is achieved, in the long-run this will reduce the reliance of aided OTs on UK financial aid.

OTD will continue to help meet the reasonable assistance needs of aided OTs by contributing to the cost of essential public services such as health (including health promotion and prevention) and education, and ensuring physical access to the islands. We will also work with OT partner governments to grow their economies and increase their own revenue base so that their aid dependency is reduced over time.

While recognising the significant difficulties of promoting increased levels of self-sufficiency among the Pitcairn Island community, DFID will nevertheless look to achieve value for money in meeting the UK’s obligations to the people of Pitcairn and to reduce the level of financial aid required from the UK where it is feasible and appropriate to do so.

What are the key risks to the success of the programme?

15.	The key risks to the success of the programme are regarded as moderate as outlined in the following tables. These risks do not have an impact on the achievement of DFID’s strategic objectives:
	Gross risk			Net risk
Risk Factor	Impact	Likelihood	Mitigating Measures	Impact	Likelihood
1. Exchange rate fluctuation Falls in the £ against NZ$ means value of UK budget support in local currency falls below amount in estimates	Moderate	Possible	There is no currency hedging in place and DFID has no separate contingency amount set aside to increase the £ value of the 2016/17 Pitcairn budget The ER will be closely monitored throughout the year and discussions held where additional savings within the agreed settlement could be made in the event of a significant fall in the £ against NZ$. (However £ continues to be strong against the NZ$)	Moderate	Unlikely
2. Failing standards of public service delivery due to lack of available workforce as a result of a declining population or serious injury	Major	Possible	The small workforce carries out 73 different part-time roles. As the population ages and declines so does the ability to carry out work required to maintain standards of public service. / Historically there has been a reluctance to supplement the workforce from the region, although a recent EU funded project successfully brought 3 Tahitians to work alongside the Pitkerners for a few months. Up to 20 migrant workers will be contracted to the island to support delivery of EDF10 work / The Administrator line manages divisional managers to ensure standards maintained. / If required the Governor will be asked to sanction introduction of workers in addition to those being funded through EDF from the region to ensure effect delivery of public services / .	Moderate	possible
3. Ability to attract and retain suitably qualified professionals	Major	Possible	Posts advertised more widely (currently in New Zealand, Australia with UK being considered if necessary)	moderate	unlikely
4. Lapse in child safeguarding measures with less children on island	Major	Possible	Off-island professionals continue to be deployed to implement all child safeguarding procedures and protocols, with oversight by HMG. / Regular child safeguarding reviews in place. / Island Council is making child safeguarding a priority.	minor	unlikely
5. Unsuccessful tender exercise for replacement freight and passenger service	moderate	Possible	Potential interest will likely be small as evidenced in 2008 tender exercise. It is an extremely difficulty route to operate commercially. / Prospective suppliers will be contacted to bring attention to process / If necessary consideration will be given to extending current supplier contract.	Moderate	possible

Strategic Case

The UK’s relationship with Overseas Territories (OTs) is different from that with independent developing countries. The International Development Act 2002 specifically exempts aid to the OTs from the poverty reduction criteria that apply to the rest of the DFID aid budget. The UK’s obligation to the OTs derives from the UN Charter: “to promote to the utmost, within the system of international peace and security established by the present Charter, the well-being of the inhabitants of these territories [whose peoples have not yet attained a full measure of self-government]”.

The level of aid to the Pitcairn Islands reflects its extremely isolated location in the South Pacific; a very small and ageing population; and the lack of social and economic opportunities for its inhabitants. These factors raise two key challenges: how to provide (i) an appropriate level of essential public services; and (ii) a regular shipping service. How to meet these challenges cost-effectively is made doubly difficult by the need to guarantee adequate protection of children at all times and the very limited opportunity to raise revenues or pay for the public services required. Pitcairn’s remote location and extremely small population inflates the per capita cost of providing even a very limited range of basic public services, including access to the island.

Pitcairn’s economy is tiny. There is limited economic activity including a tourism market (mostly based on homestays, visiting yachts and passing cruise ships), craft sales, basic agriculture and fishing. Off-island economic activities consist of international sale of postage stamps and coins and internet domain registration. GDP measures are largely irrelevant in this small, isolated community that currently has no tax base, though New Zealand inflation plays a part in the context of imported consumer goods and professional services.

Three key challenges to socio-economic development require consideration in all aid and/or development planning are:

The legacy of the child sexual abuse history and the continuing need to maintain stringent child protection procedures: HMG has put in place interventions to create a substantial child safeguarding framework; independent reviews have taken place in 2009, 2011, 2013 and again in 2015 (desk based). The 2015 review concluded there had been significant improvement with all 21 recommendations from the 2013 review having been implemented. It also noted an increase in the overall capacity of Pitcairn Islanders to work in partnership with HMG regarding child safety; mainly due to the current Mayor’s continued engagement and leadership on this, with the Island Council making child safeguarding a priority. The Council have demonstrated this commitment by issuing a notice on the official repopulation website [3] stating “Child safety on Pitcairn Island is paramount for every Pitcairn Islander ….”. However the report also concluded that continuation of child safeguarding controls by HMG, including the continued deployment of professionals to the island, was crucial. An on island review will take place during 2016/17.
[3] http://www.immigration.gov.pn/community/safeguarding_children/index.html

The ageing population and the declining economically active proportion of that population: Physical fitness is a requirement for many of the labours (paid and unpaid) required on Pitcairn, from working the long-boats, to building maintenance, craft making and subsistence agriculture. Of the resident population of 42[4], there are only 26 in paid employment[5], with only 8 of this group under 50, of whom only 2 are in the 20-30 age group. There are currently 28 people on the island over 50, 11 of whom are over 65. By 2025 the age dependency ratio (those under 18 and over 65 compared to the productive population) will be over 100 percent in comparison to the 2014 ratio of 58%[6]. The following table shows the current demographics.
[4] At 31/12//2015 a total of 42 Pitkerners were recorded as resident on the island, with 10 Pitkerners having been off island for some time. Data taken from Island Population Census at 31/12/15
[5] Those who are able to contribute to economic production through work (in government, working the long-boats, fishing, growing produce and so on). Pensionable age on Pitcairn is 65.
[6] Solomon R and K Burnett, 2014. Pitcairn Island Economic Review. Solomon Leonard Ltd, Wellington.

Resident Pitcairn Population 31/12/15

Even taking into account those Pitkerners currently residing elsewhere, there has been a steady decline in the population in recent years as highlighted in the following graph, with this trend expected to continue without repopulation. There are only three options of increasing the population – children being born to islanders, the return of some of the Diaspora and/or immigration to the island:

The able bodied population has declined to a critical level. The natural growth rate of the population is already far below a sustainable replacement rate. Altogether, there are 9 children between two families, four of whom attend secondary school in New Zealand and there have been only 8 births in the period 2001-12. Currently only 4 women of child bearing age reside on the island.

In the short term, maintaining and preventing non-communicable diseases (diabetes, hypertension, coronary heart disease) in the ageing population will be vital for islanders to keep an active workforce as well as to minimise the need for care in later life.

Increasing funds will be required in the medium-term to assist the ageing population.

In the longer term, this seriously calls into question the sustainability of the island: who will do the work, who will look after the increasingly ageing population and how; who will operate the long-boats, critical to the island’s economic and social opportunities? The island is belatedly promoting immigration[7] and investing in tourism promotion in an effort to reverse population decline. In reality the likelihood of a significant increase in population is low and the prognosis is very pessimistic.
[7] http://www.immigration.gov.pn/ .

The 2012 health and social welfare review[8] included population projections that show high dependency ratios[9] if the island population does not grow:
[8] Weil, Oliver and Janet Gardiner, 2013. Review of the Quality and Cost Effectiveness of Health Care and Social Welfare Provision for Pitcairn Island (31/1/2013), HSLP.
[9] The age-population ratio of those typically not working.

	2013	2015	2020	2025	2030	2035	2045
65+	10	13	15	19	22	23	20
Under 18	8	7	4	1	0	0	0
Dependents	18	20	19	20	22	23	20
Productive	31	28	22	19	14	10	3
Total	49	48	41	39	36	33	23
Age dependency ratio (under 18s and over 65s compared to the productive population)	58%	71%	86%	105%	157%	230%	666%

Dependency on HMG will undoubtedly increase if there is not a positive change in population numbers and a reduction in dependency ratio; with an increasing risk that the elderly will no longer be able to get off the Island to meet their increasing health care needs. Even if such change were to occur dependency will remain high. The island currently faces a very uncertain future and the HMG faces continuing financial aid support.

iii. Lack of migration to the island
A Survey of the Diaspora[10] was undertaken in late 2013, to inform the Pitcairn Island Council (PIC) and HMG of the potential for Diaspora migration to Pitcairn. Three barriers were identified to Diaspora returning to Pitcairn, specifically the issues around the history of widespread child sex abuse, resistance to outsiders and new ideas, and island inaccessibility.
[10] Solomon R and K Burnett, 2014. Pitcairn Island Diaspora Survey. Solomon Leonard Ltd, Wellington.
- Diaspora recognised that offender and victim programmes had been undertaken, with varying degrees of success. The survey concluded that until the community functions cohesively, and takes responsibility for a viable reconciliation process, immigration and/or increased investment are highly unlikely (as noted above the Island Council have taken steps to publicly acknowledge the past).
- The acceptance of outsiders and associated issues are recognised as complex and manifest in differing forms. The Diaspora Survey highlighted a strong belief that outsiders are not welcome and will not be able to integrate into the community. This was borne out by a successful settlement applicant withdrawing in early 2015 due to due to a perceived lack of engagement by the islanders to requests for information. The Governor’s office is currently liaising with two successful applicants who plan to move to Pitcairn in late 2016.
- Accessibility was repeatedly mentioned as a barrier to immigration, especially as it relates to other factors such as health and education

The Island Council have recognised these barriers and have publicly acknowledged this in the Strategic Development Plan and on the Immigration website.

GENDER EQUALITY
In the design of this intervention, we have considered the likely impact on gender inequality and whether it will make sustained improvements in gender equality. The small resident adult population of 37 is split between men (18) and women (19). Of these 3 men and 8 women are over 65. The remaining adults are employed in government posts or the island store. Of the key posts in managing the affairs of the Island 2 are held by women, and 4 by men. Given the small size of the population it is hard to draw meaningful inferences from these numbers – however, over the past 10 years, women have held fewer positions of authority than have men, though women have been ‘elected’ to 5 of the 7 positions in the Island Council, including deputy mayor.

In general, limited public services are provided to meet basic needs in health, social care, education and community policing, according to existing island policies and the core international conventions which apply to Pitcairn[11], the exception being CEDAW[12]. Pitcairn Island Council continues to consider making a request for extension of CEDAW to Pitcairn in consultation with the FCO.
[11] European Convention on Human Rights (ECHR), the International Covenant on Civil and Political Rights (ICCPR), the International Covenant on Economic, Social and Cultural Rights (ICESCR), the International Convention on Elimination of all forms of Racial Discrimination (ICERD), the Convention Against Torture and Other Cruel, Inhuman and Degrading Treatment or Punishment (UNCAT), and the Convention on the Rights of the Child (CRC).
[12] The Convention on the Elimination of All Forms of Discrimination against Women (CEDAW)

This intervention provides for services equally for all islanders, with specific attention for the needs of children and the elderly. Service delivery professionals will address vulnerabilities on an individualised and family basis, including safeguarding and development of the island’s children, support and care of the elderly (the majority of whom are women), and support and care for those with mental health issues

Child Safeguarding:

Whilst the Partnership Pinciples do not apply for development assistance to the Overseas Territories, we actively manage the key gender issue on Pitcairn which is the legacy of child abuse, outlined in 16 (ii) above. Abuse of girls and boys has taken place and DFID ensures that robust child safeguarding mechanisms are in place on the island through this intervention and through a separate child safeguarding project which provides access to professional backstopping and support on managing all aspects of identification of abuse and management of offenders. There are, currently, five children on island (one boy and four girls).

PITCAIRN BUDGET
Strategic Development Plan

The Pitcairn Island Council (PIC) has made some progress in developing a five-year Strategic Development Plan 2014 – 18 (SDP) which sets out a vision for developing a more sustainable and secure future for Pitcairn. The 2013 socio economic review echoed DFID concerns that the SDP was an aspirational document that was over ambitious, not adequately prioritised or fully costed, and did not account for implementation capacity and capability. The Mayor recognised the shortfalls of the SDP and with the PIC reviewed the plan with more realistic timelines and expected outputs. The revised SDP (2014-18) has been published.[13] However progress needs to be monitored and the document updated to reflect this.
[13] http://www.government.pn/policies/SDP%202014-2018%20-%209-7-2015.pdf

HMG’s contribution to the budget
Since Pitcairn has required development assistance (90-95% of its budget requirements from 2004 onwards – see graph below), HMG’s financial support has been critical to the island in terms of: (i) the maintenance of basic public services at reasonable levels for a small and isolated population; (ii) appropriate child protection and security; (iii) the provision of adequate shipping services; (iv) improved social cohesion, albeit fragile, following the adverse impact of the trial related to the landmark child abuse cases and imprisonment of a number of male islanders, as well as the recent trial of the former Mayor for possessing indecent images of children; and (v) a firmer organisational structure on the island based on the 2010 Constitution, which continues to be embedded. This is unlikely to change in the near future.
Financial Aid to Pitcairn 2003/04 -2015/16 (£'000)
HMG will provide up to £3.00 million (net) in financial aid to cover the shortfall between revenue and recurrent expenditure for the financial year 2016/17. The financial aid required is broken down as follows with a comparison to 2015/16:

	15/16	16/17
To meet the reasonable assistance needs on island, including the operational costs of PIO	£1.204m	£1.504
Shipping subsidy,	£1.28m	£1.217
Long and short term TC	£0.592m	£0.561
Capital expenditure	nil	nil
Expected Revenue		(£0.282)

Expected Revenue
Domestic revenue performance remains weak, providing less than 10% of the Island’s finances, with little opportunity to increase revenue. Previously revenue was generated by trade with passing ships and the production and marketing of stamps and commemorative coins, through agents in New Zealand. However changes to trade routes in the last 20-30 years meant a marked reduction in the number of ships passing Pitcairn. Similarly sales of stamps have been declining since the 1990s. Revenue from the production of coins has also continued to fall. As a consequence of these declines in revenue, the accumulated reserves of the island were consumed by 2004, requiring the island government to seek budgetary assistance in order to meet its reasonable assistance needs.

Tourism is a potential growth area and efforts are being made to market Pitcairn as a tourist destination. Visitor numbers, travelling from Mangareva on the Claymore have increased significantly from 28 in 12/13 to 58 in 13/14. Demand has increased and currently PIO is taking bookings up to a year in advance. During 14/15 the ship’s operator provided a third rotation, and this will be reintroduced during 16/17. While PIO did not receive full fares for these extra trips, NZ$500 commission was collected for each ticketed sale and this will continue in 16/17. The additional service provided options for more flexible and longer stays on Pitcairn, thus improving tourism options.

The shipping contract ends in March 2017 and a call for expressions of interest was made in February 2016, including a more frequent passenger service. It should also be noted that (i) transport costs to Mangareva (French Polynesia), in order to meet the Claymore, are significant (NZ$3,000 for round trip per islander; NZ$4,000 for islanders’ family members, NZ$5,000 for everyone else plus international airfares); and (ii) berths are used each year for islanders to obtain medical care in Tahiti or New Zealand.

Other key revenue strands recorded during 2015/16 showed a mix of results with a projected net income of $564,700
Stamps and Commemorative Coins: collectively these recorded a net loss of NZ$4,800 as the number of philatetists and coin collectors, globally, diminishes.

Landing fees: The decision to increase landing fees to US$50 resulted in revenue of NZ$90,000 in 15/16, with the expectation this will be maintained again in 16/17. As in previous years a number of cruise ships are expected to visit Pitcairn during the austral summer[14]. Whether passengers are able to land remains weather dependent and is at the discretion of the ships’ captains. Between April 2015 and February 2016, some 700 passengers landed on Pitcairn from 10 cruise ships, 14 yachts and 15 other vessels (including the Claymore). The islanders continue to hope for an increase in passing cruise ships and yachts through actively promoting Pitcairn. However there are concerns that cruise ship routes are also changing. Of the five ships scheduled to visit Pitcairn between January and March 2016, only one landed passengers. The situation will be monitored.
[14] http://www.visitpitcairn.pn/cruise_ships/cruise_ship_schedule/index.html

Conversely, internet domain registration has continued to flourish (mainly due to The Hunger Games film anthology, which uses the .pn domain as the “official” country code of the nation of Panem) with sales maintaining their expected target of NZ$65,000 in 2015/16 and expected to increase in 16/17.

Islanders pay contributions for two utilities (electricity and phone/internet access). Small revenues are generated from: (i) hiring of government equipment; (ii) nursery sales; and (iii) prescription charges and other medical fees. There are 11 homeowners who provide home stay facilities pay an annual fee of US$50 to the Tourism Department.

Employment

Salaries and pensions continue to account for a high proportion of annual on-island expenditure. HMG has raised concerns in recent years about capacity of the small island workforce given the tendency to create new posts, rather than rationalise the existing job structure and improve employment planning and prioritisation. The problem had increased with the development of alternative landing facilities (Alternative Harbour Project – AHP) being funded through EDF9, which has created a number of new posts, out with the government structure. Despite the Mayor, on his appointment in early 2014, publicly commenting that the project was an opportunity to bring in labourers, skilled or non-skilled, as the current Pitcairn workforce is not enough to sustain the community and run the project, no external recruitment was carried out.

In 2014/15 the Mayor commissioned a comprehensive review of all Government of Pitcairn posts. Consequently the number of roles has reduced to 73, of which 13 being carried out on a casual basis. This still equates to 10 FTE and there is scope to rationalise the posts further. The Mayor is being encouraged to do so by the Administrator. It is worth noting that during 2015 three Tahitians were successfully deployed through an EU funded regional project, to work on Pitcairn over a 3 month period. Over the course of 2016/17 a further 20 migrant workers are expected to come to the island to support work being carried out under EDF10.

Taxation

Residents are reluctant to declare income they make from the sales of local crafts and this is impossible to track – bar through the few ships that share the records of credit card transactions with the Islanders. These amounts are not insignificant, with some curios (eg large scale models of the HMS Bounty selling for up to £250). PIO advises it banks around US$100,000 a year from money deposited with the Government Treasurer. This is a critical gap in knowledge about islanders’ incomes, especially as there is no tax base on Pitcairn.

The socio-economic review conducted in late 2013 considered the potential to introduce an income tax threshold for island residents. The review concluded that the introduction of income tax would further raise the issue of the government wage, which may have to be increased to reflect the introduction of the tax. The net impact on the fiscal deficit was judged to be neutral. The review suggested that if in the future there was a need to raise government revenue it would be a better option to remove or adjust the subsidies, such as those on freight, electricity, and telecoms, rather than introduce a new tax.

There is no basis in the existing law of Pitcairn requiring a declaration of private earnings. Nor is there a requirement to contribute to governmental services (proportionate to income). On other islands with economies similar to Pitcairn’s (where earning information is hard to come by without a system of employment and PAYE, and where there is lot of subsistence living and self-employment), VAT or General Sales Tax (GST) is often used for raising revenue. In reality, on Pitcairn GST would not solve the problem as:
- It could only be collected from a limited number of payments such as the shop receipts, and possibly charges made for homestays.
- This could encourage direct orders from New Zealand, in an attempt to avoid being taxed.
- The cost of implementing GST laws and processes will likely outweigh the revenue for such a small community.

37.	A breakdown of the proposed budget is detailed in the Financial Case.

## Appraisal Case

38.	The Strategic Case sets out the financing requirements to deliver public services in Pitcairn. As an aided OT, HMG has a responsibility to ensure that reasonable assistance needs are met. Therefore feasible options to address this need are limited. Available options are:
- Option 1: Do nothing
- Option 2: Take control of Pitcairn’s budget and adopt a projectised approach
- Option 3: Devolve Financial Control to PIO
- Option 4: Devolve control to PIC
- Option 5: Provide Financial aid

39.	Option 1: Do Nothing
The counterfactual “do nothing” option would consist of DFID not providing any support for the recurrent budget. Without financial aid residence on the island would quickly become untenable. Public services would collapse and the islanders would have to return to basic subsistence or leave the island. This option is ruled out because it would not meet the reasonable assistance needs of the population and would contravene the UK’s legal responsibility to Pitcairn as set out in the UN Charter.

40. Option 2: Take direct control of Pitcairn’s budget and adopt a projectised approach
HMG could take full control of the Island’s public finances, assuming direct responsibility for setting Pitcairn’s recurrent budget and delivering its public services. This could include effectively establishing a series of projects to deliver specific services, funded by HMG and delivered by management agents appointed by DFID. It would require a readjustment in HMG’s relationship with Pitcairn with a significant reduction in the current level of delegation. This option is excluded because (i) DFID would be required to devote substantially increased levels of administrative resource to ensure effective delivery; ii) DFID would hold all of the political and reputational risk without adequate control of implementation in the local context; and iii) it would not deliver value for money for the UK tax payer in terms of the cost of public service provision.

41. Option 3: Devolve financial control to Pitcairn Island Office (PIO)
Financial control could be devolved in full to PIO in Auckland. This would effectively reinstate the old system which was in operation prior to 2009, and reverse the general increase in responsibility expected of the PIC, under the authority of the Governor, set through the new Constitution and organisational structure. The PIO would almost certainly need strengthened to take on additional responsibility, at a cost to DFID. Although DFID would have competent admininstrators in the PIO on which it could rely, on balance we think this option would provide an approximately equivalent value for money while leaving DFID still holding most of the political and reputational risk.

42. Option 4: Devolve control to Pitcairn Island Council (PIC):
This option would involve devolving all responsibility to PIC, reducing HMG’s level of control and oversight. Given the weak capacity of the island workforce and uncertainties over governance and effective financial control, this option is discarded as carrying too high a risk for DFID and HMG.

43. Option 5: Financial Aid (FA) – preferred option:
This involves the UK providing FA directly to PIO which is then re-allocated based on agreed divisional and TA programme budgets and workplans which are prepared in close consultation with the relevant divisional manager and Council. This approach allows money to be ring-fenced for specific activities if required. In Pitcairn, this would mean setting specific amounts for the subsidy for sea access and an amount for technical cooperation to improve local capacity and provide the necessary child safeguarding measures. This approach does not preclude the use of additional resources for targeted projects if deemed necessary.

44. The provision of financial aid is the only acceptable option as it provides the correct balance between direct engagement with PIO and PIC and HMG oversight to ensure value for money.
Theory of Change for Preferred Option: Financial Aid

Processes
Annual financial aid review agrees budget settlement and monitors performance against previous budget settlement, as well as mid-year reviews of financial, policy progress and review of progress against log frame targets.
PIO on behalf of PIC manages budget efficiently and effectively to deliver public services on island.
TC officers in critical posts to ensure continued child safeguarding and provision of basic services
Shipping subsidy covers annual operational costs of the supply ship

Outcome
Efficient and effective management and delivery of public services provision.
Assumptions
The main assumptions are:
- No major incidents which impact on government expenditure. This includes diverse exchange rate fluctuations. Evidence - medium
- No major unexpected increase in direct and associated costs pertaining to current island trial. Evidence - medium
- No more than one emergency medivac per year and/or no more than average costs of routine referrals. Evidence - medium
- Ability to attract and retain suitably qualified professionals. Evidence – medium/high
- Stability in fuel prices Evidence - medium
- Vessels able to land in poor weather. Evidence – medium/high
Outputs
1. Sustained budget management, in line with best practice
2. Public Service Provision maintained.
3. Regular, safe and reliable sea access to Pitcairn.

Impact
HMG's obligation to maintain Pitcairn's reasonable assistance needs cost-effectively is met.

Inputs
Finance – DFID funding of up to £3.00m. gPI revenues of £0.282m
HR – DFID advisory and programme management.
TA - on island to ensure continued child safeguarding and public service provision. Other TA as required

Value for money

45. Financial Aid (the preferred approach) is the best Value for Money (VfM) option, providing the most efficient method for meeting Pitcairn’s reasonable needs. Our approach to VfM is based on the 3Es: Economy, Efficiency and Effectiveness.

Economy: The “off-islander” professional posts (policeman, Family and Community Adviser, teacher and doctor) are all recruited from the New Zealand or Australia employment market by PIO on behalf of the government of Pitcairn, and supported externally through professional backstopping via the SCOT programme. The costs of recruitment are lower than would be in the UK as are the remuneration packages paid to successful applicants. The shipping subsidy contract was issued in 2009, following a tender exercise and will end in 2017. A tender exercise for the service was started in late 2015 with a call for expressions of interest made in late February 2016. It is expected that a limited number of suppliers will bid for the route and other options may need to be considered, including exploring options for route sharing with NZ shipping lines and if necessary, extending the contract of the current service provider. Provision and maintenance of a range of basic public services (e.g. electricity, telecommunications, etc.) and provision of part-time public sector employment is also based on New Zealand costs.

Efficiency: Over the years there has been a tendency to create new posts, rather than rationalise the existing job structure and improve employment planning and prioritisation. In 2014/15 government salary costs funded 98 positions (excluding 5 positions in the Island Store), which provide part-time employment for 31 Islanders – with almost everyone having more than one job. In 2014/15 the Mayor commissioned a comprehensive review of all gPI post. Consequently the number of roles has reduced to 73, of which 13 being carried out on a casual basis. This still equates to 10 FTE and there is scope to rationalise the posts further. The Mayor is being encouraged to do so by the Administrator. It should be noted this has not reduced the salary bill for the island. The costs of PIO represent a quarter of the financial aid costs. Two staff operate the PIO, which is responsible for all off island logistics, including for example liaising with suppliers and monitoring medical and legal expenditure. PIO also acts as the Treasury for Pitcairn, supporting banking services for the island, producing monthly financial reports. Support costs provided through PIO represent around 68% of PIO’s total costs. In 2014 the Governor’s office upgraded the on island representation to an Administrator, who has management oversight of all divisional managers, thus improving performance monitoring.

Effectiveness: This intervention is critical to ensure the reasonable assistance needs of Pitcairn continue to be met, including a strong and continuing focus on maintaining child safeguarding.

Commercial Case

46. The proposed funding mechanism is Non Budget Support Financial Aid (Financial Aid). In line with DFID’s Smart Rules, a Memorandum of Understanding (MoU) between DFID and Governor of Pitcairn will be used. As HMG provides 90% to 95% of Pitcairn’s budget requirements, funds will be paid quarterly in advance to PIO on receipt of call down requests for funds against the MOU, countersigned by the Governor’s Office.

47. Government posts being funded through Financial Aid are open to fair and transparent competition with oversight of the process being provided by the Governor’s Office and the Administrator on island, including interviewing prospective candidates. Proposals for any new posts in the government structure must be approved by DFID before competition takes place. Procurement of goods and services is managed by PIO in line with the agreement reached in 2010 when the new Constitution and new governance structure came into play.

48. To recruit long term technical assistance, PIO advertises in national New Zealand media as well as with key New Zealand Government departments (for police posts). If necessary the teacher, doctor and FCA posts will be advertised across a wider geographic region, including Australia and UK. DFID and the FCO play a key role in the recruitment of the off-islanders; commenting on terms of reference and the selection of applicants (the Deputy Governor is a member of the interview panel). Remuneration packages being offered are on a par with those in New Zealand, and are lower than would be paid in the UK. The terms and conditions offer VFM and are no more generous than DFID’s own.

49. The current island workforce, together with the TC professionals, is able to deliver the range of basic services required for the island. The PIO is responsible for the administration of all financial transactions undertaken of behalf of the government of the Pitcairn Islands and will maintain oversight of the budgets and manage the logistics in getting goods and services to the island.

## Financial Case

50.	The 2016/17 Financial Aid settlement for Pitcairn is £3.00million, provision for which is made in OTD’s programme (RDEL) budget. The table below provides a breakdown and shows the upper limit proposed for each area. There may be in year re-profiling of the budget and this will be done by PIO on agreement from DFID:

Expenditure 2016/17		Nz$	£ ER 2.13	rounded

PIO Running and Support costs		1,967,356.49	923,641.54	923,642

Council		74,500.00	34,976.53	34,977
Community Division		76,333.00	35,837.09	35,837
Finance & Economics Division		154,997.00	72,768.54	72,769
Natural Resources Division		44,538.00	20,909.86	20,910
Operation Division		373,788.00	175,487.32	175,487
Power Generation		39,200.00	18,403.76	18,404
Telecommunications		236,000.00	110,798.12	110,798
total On island costs		999,356.00	469,181.22	469,181

gPI Salaries		197,119.72	92,544.47	92,544
Benefits (Pensions/Child Benefit)		39,647.79	18,613.99	18,614
Total Salaries/Benefits		236,767.51	111,158.46	111,158

Recurrent budget deficit		3,203,480.00	1,503,981.22	1,503,981

Shipping		2,593,000.00	1,217,370.89	1,217,371

Technical Assistance		1,193,000.00	560,093.90	560,094

Total expenditure		6,989,480.00	3,281,446.01	3,281,446

Revenue expected		599,480.00	281,446.01	281,446

Financial Aid requirement		6,390,000.00	3,000,000.00	3,000,000

51.	PIO produces monthly expenditure reports as well as quarterly estimates of projected costs. Exchange rate fluctuations between sterling and NZ dollars will be closely monitored throughout the year to ensure reasonable assistance needs continue to be met. Should there be savings (in NZ$) as a result of sterling appreciation, DFID, gPI and PIO will discuss how this should be ultilised or whether it should be returned to DFID. The final decision will rest with DFID.

52.	Running costs include running of Pitcairn Islands Office (PIO) in Auckland, New Zealand, which provides a treasury role as well as logistical and management support to the island, plus on island costs such as government of Pitcairn Island salaries and pensions and public services. The support costs account for around 68% of PIO’s costs and include boarding school fees, IT support, medical costs (including supplies and off island costs) and legal costs.

53.	The cost of the shipping subsidy has been agreed as part of a contract which expires in 2017 and is not negotiable at this stage.

54. The Financial risk and fraud is assessed as low. Approved recurrent expenditure will be monitored, reported and accounted for as follows:

- The Administrator conducts monthly reviews of the Treasurer’s Office and Post Office with the Island Auditor (or with Policeman in Auditor’s absence).
- PIO produces monthly progress reports, comparing actual expenditure against the budget and providing explanations of variances. A more detailed report is provided in October. DFID provides feedback.
- An annual audit, including an island visit is carried out by External Auditors (an independent firm of chartered accountants based in Auckland). The audits are carried out according to NZ and international standards. The External Auditors will be expected to add their own comments and qualifications. The draft audited accounts are subject to review and counter signed by the Governor and the Head of the PIO. DFID provides comments on the audit reports.
- The PIO is located within the office of the Deputy Governor (in the British Consulate in Auckland). All funding requests made by PIO are countersigned by the either the Governor or his deputy Governor’s Office maintains general monitoring and supervisory overview

Management Case

55. The daily management of the intervention will be undertaken by PIO with inputs on progress being received from the relevant Divisional Manager and the Pitcairn Island Council. The Deputy Governor, the Administrator on island and FCO’s OTD colleagues will also contribute to the control of the quality and quantity of the outputs for this intervention. The Administrator has management oversight of all divisional managers, thus improving performance monitoring. As outlined above, there are regular reviews of expenditure and DFID monitors progress throughout the year.

56.	The Pitcairn Programme Manager will be Senior Responsible Owner (SRO) for the implementation of the programme. The SRO and Programme Team can call on the support of OTD’s Management and Advisory Team including:

- Head and Deputy Head of Department
- Senior Economist and Economist
- Senior Social Development Adviser
- Health Adviser

57. This project will not be delivered under a Partnership Agreement or modality arrangement. However funds are expected to be used for their intended purposes as laid out in the MOU that will be signed between DFID and the Governor of the Pitcairn Islands

58. The provision of financial aid in itself does not facilitate a fundamental improvement in the quality or efficiency of service provision. Instead, it is expected to support “business, as usual”, in meeting reasonable assistance needs. Evaluation of this will be carried out at the end of the 12 month project and findings will be recorded in the Project Completion report.

59. The Delivery Plan, which includes a Risk Register, and Logframe will be updated as necessary throughout the year. They are stored in DFID’s electronic filing system, references 5350688 and 5319456 respectively. The reference for this Business Case is 5319452.