## Template
PROJECT NAME | Pitcairn Financial Aid 16/17
IMPACT | Impact Indicator 1 |  | Baseline (2015/16) | Milestone 1 (2015/16) |  | Target (2016/17)
| Basic public services delivered within budget to expected standards. | Planned | Forecasted expenditure $NZD 5.755m. |  |  | NZ$6.989m
Pitcairn’s reasonable assistance needs will be met cost effectively. |  | Achieved | Expected Expenditure $NZD6.373m. | diff due to ER fluctuations
Source
Government of Pitcairn accounts and reports, annual external audit report and annual Budget aid Mission.
OUTCOME | Outcome Indicator 1 |  | Baseline (May 2016) | Milestone 1 (March 2017) | Milestone 2 (March 2018) | Target (March 2019) | Assumptions
| Percentage of children and adults that show excess weight (overweight or obese) as per their Body Mass Index, disaggregated by adult/child and gender. | Planned |  | Percentage of people with excess weight maintained or reduced. | Percentage of people with excess weight maintained or reduced. | Percentage of people with excess weight reduced. | No major incidents which impact on government expenditure. This includes diverse exchange rate fluctuations. No more than one emergency medivac per year and/or more than average annual costs of routine referrals
|  | Achieved | TBD
Source
Annual progress reports from Medical Officer
| Outcome Indicator 2 |  | Baseline (2009) | Milestone 1 (2016/17) | Milestone 2 (December 2016) | Target (March 2017
| Maintenance of child safeguarding oversight. | Planned |  | Continued implementation of “Partnership for Children” initiative Council and community continue with CS training as appropriate Continued safeguarding by off island professionals and Administrator | CSR 2016 undertaken on island and recommendations shared with HMG | CSR 2016 on island recommendations implemented and progress monitored
Pitcairn’s public services are managed and delivered efficiently. |  | Achieved | CSR Review (Desk based) 2015 CSR Review 2013 CSR 2011 CSR Review 2009 | CSR Review 2013 completed. Action plan developed.
Source
Government of Pitcairn accounts and reports
Quarterly and Bi-annual Child Safeguarding Reports. 2015 CSR outcomes
| Outcome Indicator 3 |  | Baseline 2013 | Milestone 1 | Milestone 2 | Target March 2016
| GPI headcount target numbers | Planned |  |  | 10 local FTEs | 10 local FTEs
|  | Achieved | 10 local FTEs | 10 FTEs
|  | Planned |  |  | Review of government jobs completed by December 2015.
|  | Achieved | Functional Analysis completed, Dec 2013. Further work required. |  | Restructure finalised March 2015, 60 permanent and 13 casual posts confirmed. = 10 FTEs
Source
PIO reports. Government of Pitcairn reports, Annual external audit report, PIC Mayor restructure proposal
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  | 3 | £0.283m |  | £3.283m | 91.38%
INPUTS (HR) | DFID (FTEs)
SRO and Programme Managers (0.7)
Economic Adviser (0.05)
SDA (0.2)
Governance Adviser (0.02)
Health Advisers (0.05)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline April 2013 | Milestone 1, 2014 | Milestone 2, 2015 | Target March 2016 | Assumption
Sustained budget management, in line with best practice | Percentage variance between actual expenditure and budgeted expenditure | Planned | 2% | No more than 5% (bringing in line with PEFA Indictaor 1, score A) | No more than 5% (bringing in line with PEFA Indictaor 1, score A) | No more than 5% (bringing in line with PEFA Indictaor 1, score A) | Accurate forecasting. No unforseen major incidents which impact on government expenditure. This includes diverse exchange rate fluctuations and more than budgeted expenditure for routine and emergency medical treatment
|  | Achieved | Expenditure $33k less than budget. Variance of 0.63% in 12/13 |  | Expenditure $
Source
Government of Pitcairn accounts and reports
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 2016 | Target March 2017
| Implementation of audit recommendations | Planned | Agreement on recommendations and implementation timing. | Implementation progress as per agreed target dates | "Unqualified" annual audit | "Unqualified" annual audit
|  | Achieved |  | All recommendations implemented or ongoing. 2013 audit taking place June-Sept | Report forwarded to new council for implementation. Recommendations are ongoing. Next review due as part of 2016 external audit due Sept.
Source
Government of Pitcairn accounts and reports. Annual audit report
| Output Indicator 1.3 |  | Baseline March 2012 | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target March 2016
| Percentage variance between actual local revenue and budgeted local revenue | Planned |  | Actual local revenue between 94% and 112% of budgeted local revenue (PEFA Indicator 3, Score B) | Actual local revenue between 94% and 112% of budgeted local revenue (PEFA Indicator 3, Score B) | Actual local revenue between 94% and 112% of budgeted local revenue (PEFA Indicator 3, Score B)
|  | Achieved | 9% under budgeted target | Expenses $53.7k over budget. Variance of >1% | Actual domestic revenue was projected amount
Source
Government of Pitcairn accounts and reports
IMPACT WEIGHTING (%)
20%
RISK RATING
moderate/unlikely
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2012/13) | Milestone 1 (Mar 2014) | Milestone 2 (March 2015) | Target (March 2016) | Ability to attract and retain suitably qualified professionals.
Public Service Provision Maintained. | Number and field of expatriate experts deliver basic services in line with job descriptions | Planned |  | All contracts include Code of Practice and Child Safeguarding for the Off Island Professional group ToRs. | 4 (education, health, social work and police) deliver in line with job descriptions | 4 (education, health, social work and police) deliver in line with job descriptions
|  | Achieved | 4 (education, health, social work and police) | Achieved. | Achieved.
Source
Annual education, health, child welfare and policing/immigration reports; School parent reports. Routine progress & performance
| Output Indicator 2.2 |  | Baseline (2012) | Milestone 1 (March 2014) | Milestone 2 (March 2015) | Target (March 2016)
| Percentage of children receiving full-time education appropriate to age and needs. | Planned | 100% | All children receiving appropriate full-time education, including two children in senior boarding school in NZ. | 100% (5 children in school on Pitcairn, 5 in NZ) | 100% (5 child in school on Pitcairn, 4 in NZ at boarding school)
|  | Achieved | 100% | 100% | Eldest child (17) left NZ boarding school during 2014 Further 3 children in NZ boarding schools 4 children in NZ with mother - but returned to island June 2015 October 2015 5 children on island and being educated in school
IMPACT WEIGHTING (%) |  | Source |  |  |  |  | RISK RATING
40% |  | regualar education reports |  |  |  |  | moderate/unlikely
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2011/12 | Milestone 1, 2014 | Milestone 2 | Target (March 2015) | Stability in fuel prices Vessels able to land in poor weather. Sufficient berths available for passengers Potential bidders identified during tender exercise
Regular and reliable sea access to Pitcairn supports reasonable needs. | Number of times the Claymore runs to/from NZ/Pitcairn carrying freight. | Planned |  | 4 |  | 4
|  | Achieved | 4 | 4
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline 2011/12 | Milestone 1, 2014 | Milestone 2 December 2016 | Target (March 2017)
40% | Number of times the Claymore runs to/from Mangareva/Pitcairn carrying passengers. | Planned |  | 8 | Tender process for access subsidy concluded by December 2016 | 8 New contract in place
|  | Achieved | 8 | 8
RISK RATING
|  | Government of Pitcairn and PIO reports |  |  |  |  | moderate/possible

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.