Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to International Agricultural Research Centres that benefits Poor People
Programme Value: £50,293,715		Review Date: 12/03/2016
Programme Code: 202748	Start Date: 01/04/2012	End Date: 31/03/2016

Summary of Programme Performance
Year	2015	2014	2013	2012
Programme Score	A	A	A	A+
Risk Rating	Low	Low	Low	Low

Summary of progress and lessons learnt since last review

Overall progress is on track, and the programme scores an A. The four international agricultural research centres which receive funding under this programme currently are largely meeting expectations against the main indicators relating to research delivery and scaling of technologies. Three of the four funded centres, received a performance bonus due to having fully met or exceeded the milestones for the key deliverables with an excellent performance against organisational and quality of research. The other centre (icipe) was largely on track against agreed deliverables and milestones, but progress on specific areas particularly impact evaluation had been slow. Performance against organisational behaviours (i.e. financial management, environmental management systems, gender sensitive HR systems and policies) was good.

During the year a new approach to assessing quality was piloted, stimulated by centre’s concerns that the former system, using the use of publications metrics in combination with the assessment of other research outputs, was insufficient. This was a useful exercise and has been incorporated into the 2016 performance review process.

DFID commissioned an external evaluation of the programme which is now completed. The evaluation is of wider interest within DFID Research and Evidence, and amongst other donors agricultural research. Lessons will be shared across DFID via the Evaluation Department Learning Seminars.

Summary of recommendations for the next year
Recommendations #1 and #2 are rolled over from last year’s Annual Review, as they continue to be relevant.

Where research centres have a strong presence and are scaling up technologies in specific countries, they should approach the Agriculture Research team to discuss how this overlaps with bilateral programme priorities, and where appropriate facilitate an introduction to Country Offices (Research Centres, ongoing).

Research Centres are encouraged to initiate a discussion with the DFID Agriculture Research team on the partnership or aspects of their performance as required (Research Centres, on-going).

DFID should share the evaluation findings and proposals for a new phase of funding with other core donors, with a view to discussing the proposed mechanism and exploring options for closer coordination and collaboration (by mid 2016).

Centres should from 2016 onwards include only publications which are undertaken by their own researchers and own funds, and where publications recognise the affiliation of the author with the research institution.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202748/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-3719418/

Outline of the programme

The UK is investing up to £50.2 million in international agricultural research over five years from 2011-2016. In 2011, a business case was approved to provide £30m to scale up our core funding to four international research centres, i.e. Centre for Agriculture and Biosciences International (CABI), International Centre of Insect Physiology and Ecology (icipe), the World Vegetable Center (AVRDC) and the Global Forum on Agricultural Research (GFAR), who were all pre-assessed as providing good or very good value for money to DFID. Funding to Crops for the Future (CFF) was discontinued as it could not demonstrate that it continued to provide value for money to DFID. However, one final allocation was approved, apportioned over 2012/13 and 2013/14 financial years to allow them time to attract alternative sources of funding.

Each of the selected research centres identified three or four key objectives, e.g. new improved vegetables lines with good nutritional and/or disease resistant properties, roll out of new national plant health systems in 30 countries, scaling up of “push-pull” control of striga in cereals in Africa and an integrated pest management technology for control of African fruit fly and mechanisms for tracking investments in AR4D and for building user feedback into international agricultural research systems. Based on their performance against the agreed key objectives and good governance measures, i.e. robust financial systems, an environmental management system with targets for reducing carbon footprint, metrics on energy use, etc, and HR policy and operational plans for ensuring gender balance in organisational structures and research processes implemented. DFID undertakes a review of each centre’s performance annually against the key objectives and organisational behaviours. On the basis of the performance review, a decision is made whether or not to award a 20% performance bonus for demonstrating good performance.

In November 2012, a business case was agreed to provide additional funding of £10m to two centres, CABI and icipe, which had demonstrated evidence of excellent research quality with development impact and value for money for DFID during the inaugural performance review. These centres also showed that they could scale up their work to meet strong Ministerial interest in the use of science and innovation in tackling poverty and in new forms of partnership with the private sector to deliver development outcomes. During 2012, a new funding arrangement was finalised with ICIMOD, following an assessment of the value for money they present to DFID’s agricultural research programme. Funding to GFAR ceased from 1 April 2014. In July 2015, an Addendum to the Business Case was approved which provided additional funding of £10.2m for one year.

An external evaluation of the performance management system has been completed by Landell Mills. The final draft was received in January 2016. The budget for this evaluation was £96,750.

Table 1 shows expected total expenditure for the programme.

Table 1

Centre	2011/12	2012/13	2013/14	2014/15	2015/16	2016/17	Total
AVRDC	340,000	1,440,000	1,520,000	1,520,000	1,900,000	380,000*	7,100,000
CABI	900,000	4,403,600	4,970,000	4,962,000	4,960,000	992,000*	21,187,600
icpe	353,033	3,515,367	4,070,000	3,248,000	3,248,000	812,000*	15,246,400
GFAR	90,000	240,000	240,000	-	-	-	570,000
ICIMOD	-	1,098,000	1,098,000	1,113,270	1,237,697	278,500*	4,825,467
CFF	-	217,500	82,500	-	-	-	300,000
Project Evaluation	-			72,563	24,187	-	96,750
	1,683,033	10,914,467	11,980,500	10,940,020	11,369,884	2,462,500	49,326,217

* 15/16 bonus: decision on whether bonuses are paid will be taken after 2016 performance review in June/July 2016.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Previous Annual Reviews assessed performance in the Outcome Assessment based on two components. Firstly, are the centres performing as expected, meeting deliverables and is the assessment against outcomes on track? Against this criteria, the annual outcome assessment is an A. Both outputs scored an A, with centres largely meeting expectations against the main indicators relating to research delivery. Three of the four funded centres received a performance bonus. The fourth centre performed satisfactorily.

For all centres, in order to leverage improved performance, specific recommendations for follow up action were made following the mid 2015 performance review. These recommendations identify areas where further work is required if the centre is to obtain a bonus in the following year. The main areas identified in the performance reviews for follow-up relate to impact evaluation, strategies and partnerships for scaling technologies, and gender analysis and mainstreaming work.

The second aspect of the assessment looks more broadly at the introduction of a new performance based management systems. An External evaluation was commissioned (see section H Monitoring and Evaluation ). This was broadly positive about the system, drew lessons and made recommendations for improved performance. The review team felt that since the data collection was undertaken for the evaluation (in late 2014), there is new evidence which indicates that centres do respond well to the combination of the bonus incentives with the partnership dialogue. There is good evidence in particular that centres are responding now to the challenge of introducing more robust impact evaluations, and gender analysis and mainstreaming.

Overall output score and description

Four centres were reviewed in mid 2015 as part of the Performance Funding system. CABI, AVRDC and ICIMOD showed good performance, and received bonuses. icipe demonstrated satisfactory performance but did not obtain a performance bonus.

All the centres delivered well against the core deliverables that they committed to at the beginning of the partnership, primarily around development and upscaling of new technologies. This output scored an A. Notable achievements including further development of Plantwise health clinic model at country office level, supported by the global Knowledge Bank facility, delivery of new vegetable varieties and technologies, upscaling of striga control technologies in East Africa, and generating of knowledge on the impact of climate change on agriculture in the mountain regions of South Asia.

Measured against the specific output indicators in the logframe, all centres have shown good performance in the number of research publications and those published in peer reviewed journals (see Table 2). On an aggregate level, we assess progress against outputs as meeting expectations.

The purpose of the performance management funding system is to leverage improved performance in particular areas. The review team felt that there was stronger evidence of the performance management system as a whole (i.e. the bonus plus performance review plus dialogue) as having delivered changes in specific areas captured under the outputs and indicators. For example, AVRDC had made significant progress on gender and impact evaluation. ICIMOD has demonstrated a continued commitment to mainstream gender in its research work.

In terms of performance against organisational behaviours (financial management, implementation of Environmental Management systems, gender sensitive HR policies), centres better understood expectations than in previous reviews, and were largely able to demonstrate good performance. This output scored an A.

Key lessons

The External Evaluation of the Performance Management Funding Mechanism, completed in 2016, sets out a number of clear lessons (Quest No 5332933). These will be shared via an Evaluation Brief, a presentation to DFID and interested donors and via social media.

Summary of responses from previous Annual Review

The Annual Review and its recommendations from 2015 was shared with all centres. Recommendaiton 1 encouraged research centres to work with the DFID Agriculture Research team to facilitate closer engagement with DFID Country Offices where appropriate. There has been some progress in this area. The second recommendation related to lesson sharing on the performance funding mechanism, drawing on feedback from the centres. The evaluation documents useful lessons, and over 2016 these will be proactively disseminated by DFID. The third recommendation related to the availability of DFID to the centres for follow up discussions on partnership or aspects of performance. The evaluation has reitereated the importance of the dialogue with centres, and will continue to encourage centres to proactively contact DFID to request discussion as needed. This is carried forward as a recommendation for this year.

Has the logframe been updated since the last review?

No.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Centres generating high quality research outputs.
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	70%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestones
Centres on track with agreed deliverables.	The milestones are centre specific and too many to list here. However, the summary below of the performance review demonstrates that the centres were broadly on track in terms of delivery of core deliverables.

Four centres were assessed in this year’s performance review in mid 2015. Overall the centres are all on track in terms of delivery against their core deliverables, as determined by each centre at the start of the programme. Where a centre has exceeded targets or is off track, these are captured in the response from DFID to each centre following the performance review. This output is therefore judged to score an A.

The section below draws on the formal response from DFID to each centre, following the performance review held in June/July 2015. The review Panel for each centre involved DFID Agriculture Research team members, a Senior Research Fellow, and advisers from other parts of DFID (DFID India for ICIMOD). The performance review challenges the centres to strengthen their work in specific areas, particularly in strategies and partnerships for technology scaling, impact evaluation, gender analysis. The section below extracts a summary and recommendations only from the performance review letters. For more detail, see the relevant letter to each centre.

The World Vegetable Centre (AVRDC) (awarded bonus – Quest No 5190725)
Last year, the Panel recommended three areas where AVRDC needed to strengthen its performance if it was to demonstrate a case for good or very good value for money for DFID research: gender integration, impact evaluation and scaling up. This year, the Panel commended AVRDC for its work in addressing the first two of these. Further work is recommended on developing an approach to scaling which is consistent with AVRDC’s role as a research and development centre. Overall the Panel’s view is that taking into account progress against milestones and on gender and impact assessment, AVRDC represents good value for money for DFID.
Recommendations made:
1. Demonstrate a clear approach to uptake of key technologies such as home gardening and grafting, making it clear what success would look like, which partnerships will be required to deliver impact, what the operational research agenda is around impact, cost-effectiveness, scaling strategies, and how these will be undertaken.
2. Make further progress in producing research outputs that have a strong focus on gender.

CABI (awarded bonus – Quest No 5190714)
The Panel agreed that CABI has demonstrated another year of strong delivery and represents very good value for money for DFID. CABI has continued to perform well against its main programmatic milestones as well as demonstrating continued good performance on organisational behaviours.
Recommendations made:
1. Over the next year, continue to make progress on producing research outputs that have a strong focus on gender.
2. Further development of the research agenda around quality, coverage, adoption, impact, cost-effectiveness, and sustainability of Plantwise and associated mobile advisory services, and measures to ensure the skills required to address these are available.

ICIMOD (awarded bonus – Quest No 5190783)
ICIMOD maintains a strong reputation for delivering good science and policy outputs, particularly around its contributions to the scientific debate on issues related to glaciers, snow and permafrost that has captured global attention. The Panel noted ICIMOD’s responsiveness to the recent earthquake using remote sensing to identify areas at risk of landslide, as well as ongoing work on flood early warning and mapping.

The Panel observed a much improved report from last year setting out clearly ICIMOD’s agriculture offer, and incorporating responses to last year’s recommendations. There was good demonstration of ICIMOD’s relevance in the region, and engagement with its stakeholders particularly on policy, although metrics and methods for measuring this require further strengthening. Overall ICIMOD represents good value for money for DFID.

Recommendations made:
1. The Panel would encourage ICIMOD to be clearer on its approach to developing technologies as well as its knowledge products, using its operational research and impact assessment to identify “game-changers” and identify effective partnerships to bring these to scale.
2. Continue to demonstrate that ICIMOD is delivering results in relation to agriculture and food security, both through its publications and through measurable impacts on the livelihoods of poor people.
3. ICIMOD should be more explicit about how it uses its transformative approach to gender in practice, including on how it is being used to identify strategic research priorities that will have a significant impact on women and girls.
icipe – Quest No 5190732

icipe has made good progress on its technology deliverables. icipe is on track with its major deliverables and targets for striga push-pull technology, fruit-fly and bioacaricide development, with milestones for the most part achieved or exceeded. icipe’s work on the development of a new fungal based tickicide (bio-acaricide) is very promising. Eco- and mammalian toxicity testing is now required and plans for this are in place. Livestock fodder production is a neglected area and vital for building livestock farmer resilience to droughts and other shocks. icipe’s work on improved drought tolerant fodder production (brachiara and Greenleaf desmodium) as part of the push/pull approach has developed well. Work on producing Napier Grass stunting disease resistant cultivars also is relevant to farmer needs. icipe’s work in these areas could potentially have significant impact on production and livelihoods.

For the last two years, the Panel made specific recommendations in 3 areas (gender analysis, uptake of new technologies and impact evaluation). The Panel noted some improvement of performance on gender issues but no evidence of action taken in response to the Panel’s recommendations from last year. In the view of the Panel, the action points set out in the 2013 letter from DFID to icipe remain highly pertinent.

The Panel would again like to draw the attention of icipe to the full text of the 2013 and 2014 letters, which included specific actions with respect to monitoring and evaluation and uptake and gender:
1. icipe further developing its strategy for monitoring and for impact evaluation, including strengthening of the skills sets available to it both in-house and through partnership with other organisations;
2. improved gender analysis across the portfolio, including more gender disaggregated data, and more explicit focus on gender in future publications; and
3. more in depth analysis on the constraints to uptake of new technologies leading to a more strategic approach to selection of partners best-placed to overcome those constraints and which are well-positioned to scale up the dissemination of the technologies and knowledge across Africa.
In particular, the Panel expects to see the following reflected in the 2016 report:
- gender disaggregation reflected in the output reporting;
- continued evidence of gender analysis in research outputs;
- clear articulation of scaling and delivery plans for fruit fly and climate adapted push pull technology for the next 3 years; and
- evidence of a strategic approach to selecting interventions to be evaluated, designing evaluations that are able robustly to identify the impact of selected interventions, and strengthening capacity either internally or with strong mutually-supportive collaborations. (See also Annex 1 to last year’s performance assessment letter specifically on DFID’s expectations on impact evaluation).

Indicator	Milestone
Research publications including in peer reviewed journals.	Ratio of peer reviewed publications to total publications is stable or increases.

Overall, the centres have continued to show good performance in the number of research publications and those published in peer reviewed journals – see Table 2 below.

Metrics for quality of research

In response to several centres commenting on the shortcomings of the metrics of quality of research that are used in the performance review, a pilot exercise to assess the quality of research, alongside the existing quantitative metrics was trialled. Centres were asked to provide:

- 3-7 best research publications (depending on the size of the research output of each centre), judged by the centre to represent high quality research and development relevance; and
- 2 Impact case studies which demonstrate the impact of research conducted with funds drawn wholly or partially from DFID and in areas in which the centre is still active.

The Centres were asked to provide a statement as to why these were important papers. These outputs were peer reviewed by DFID internally and the results, which are noted below, fed into the overall assessment at the performance review. Following this exercise, general guidance on research quality review procedures of centre publications were produced and shared with the centres. A copy is listed at Annex 1.

The World Vegetable Centre (AVRDC)

It was stated in their report that good progress had been achieved within AVRDC in incentivising high quality research publications. However a major driver for this increase would appear to the inclusion of a new researcher’s publications from their earlier research institution. AVRDC should revisit its strategy on publications to ensure greater clarity on research affiliations, bringing it into alignment with similar research centres under AIRCA. Excluding the new researcher’s publications from their earlier research institution, reduces the number of peer reviewed publications from 86 to 70.

Feedback on 2014-15 pilot - AVRDC selected six papers that were all broadly related to agriculture. While the three non-systematic desk-based review papers were all interesting, it was suggested that AVRDC included a greater balance of primary research in its portfolio in future years to demonstrate that it is conducting research of originality, significance and rigour. The genetic papers were particularly valued, although for highly collaborative papers with multiple partners it was not possible to identify the exact role of AVRDC and we would like this more clearly specified in future years.

CABI

CABI reported an increase in the number of research publications, a slight increase in the number of peer reviewed publications and and significant increase in the number published in a journal with an impact factor >2.

Feedback on 2014-15 pilot - CABI were congratulated for demonstrating, through its selection of publications, that it is involved in large amounts of high quality research. The range of research being conducted by CABI was impressive and the balance between descriptive, analytic and experimental studies was considered as very good. All papers were strongly relevant to agriculture in its broadest sense although further relevance to livelihoods and development outcomes was quite theoretical in a few cases.

ICIMOD

ICIMOD has continued to exceed its own target of more than doubling its number of peer reviewed publications, with those published in a journal with an impact factor >2 also increasing.

Feedback on 2014-15 pilot - ICIMOD were congratulated for the publication of an important report on water run-off from high Asia’s river basins. However, given the small number of papers requested, it had been difficult to make a convincing case that ICIMOD is conducting large amounts of high quality research. In future, we would request that all Centres, including ICIMOD, submit a portfolio of 5 research publications. It will be important for ICIMOD to ensure that selected papers clearly demonstrate that high quality and innovative research is being conducted.

icipe

icipe has shown a significant increase in the total number of publications and those published in peer reviewed publications. Despite the increase in peer reviewed publications, it has continued to have 50% of these appearing in a journal with an impact factor >2.

Feedback on 2014-15 pilot – icipe’s selection of publications demonstrated clearly that it was involved in high quality research and icipe were congratulated for the scientifically important work it was producing. Given our focus on agriculture, it was felt however that the selection was rather biased towards health and that some of the selections had little relevance to agriculture. The strong collaborations icipe had built with world leading research centres was welcomed, but for some of the selected collaborative publications it was not possible to identify the exact role of icipe and this should be more clearly specified in future years.

Table 2: Publications by centre

Centre	Baseline		2012-13		2013-14		2014-15
	No of Research Pub’tns	No in Peer Reviewed journals	No of Research Pub’tns	No in Peer Reviewed journals	No of Research Pub’tns	No in Peer Reviewed journals	No of Research Pub’tns	No in Peer Reviewed journals
AVRDC	186	40	286	96 (8 in a journal with an impact factor >2)	242	81 (12 in a journal with an impact factor >2)	185	86 (23 in a journal with an impact factor >2)
CABI	148	122 (26 in a journal with an impact factor >2)	100	93 (37 in a journal with an impact factor >2)	121	102 (18* in a journal with an impact factor >2)	105	88 (32 in a journal with an impact factor >2)
ICIMOD	89	19	19	11 (5 in a journal with an impact factor >2)	65	38 (28 in journals using an impact factor >2)	185	95 (40 in a journal with an impact factor >2)
icipe	86	80	123	96 (48 in a journal with an impact factor >2)	125	88 (40 in a journal with an impact factor >2)	205	136 (68 in a journal with an impact factor >2)

An anomaly in measurement was highlighted by this year’s review of publications. AVRDC figures included publications from a newly joined staff member, based on their work with another research institution. This significantly increases their impact factor publications and peer review publications. A review of centre approaches to the metric by DFID indicated that this was an anomaly and not common place across all centres.

Recommendation #4 Centres should from 2016 onwards include only publications which are undertaken by their own researchers and own funds, and where publications recognise the affiliation of the author with the research institution.

Indicator	Milestone
High quality case studies.	At least 1 case study a year published on R4D and the centre’s website.

The purpose of setting this indicator was to incentivise centres to provide DFID with impact case studies on a regular basis to assist DFID with briefing and communicating agricultural research. At least one case study per centre has been achieved. The case studies have helped to raise the profile and publicise the work done by the centres through DFID’s support. However, the quality of the case studies was variable, and not all of these were able to put forward to the main DFID government website as high quality case studies demonstrating impact at scale, and underpinned by robust evidence.

Indicator	Milestones
Gender specific research outputs.	1. At least two outputs with a gender focus. / 2. At least one peer reviewed publication with a gender focus published.

Whilst ICIMOD has made excellent progress on integrating a stronger gender analysis into their research work, this remains work in progress for the other centres.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Organisational behaviours which underpin effectiveness and value for money for DFID are strengthened.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

There are three indicators.

1. Robust financial systems and sources measured by:

a) Indirect/direct cost ratio, i.e. this ratio seeks to measure how much research programme activity a centre is able to support on its institutional cost base.
b) Audit opinion, i.e. an external auditor’s opinion on the centre’s financial statements indicates whether the centre’s financial accounting and reporting processes meet required standards. Depending on the nature of any qualification made, it may indicate financial “going concern” issues, the ability of the centre to account for its financial or physical assets, or the appropriateness of computations and estimates used in preparing the financial statements. Although an unqualified opinion does not provide absolute assurance about the reliability of the financial statements, a qualified opinion indicates an increase in the risk that the statements do not fairly present the true financial picture of a centre.
c) DFID costs as % of total funds, i.e. the ratio of DFID costs to total costs gives us an indicator of how dependent a centre is on DFID and how diversified its funding source. However, we note that these figures can vary considerably year to year and so 40% is set out as an indicative threshold and basis for discussion rather than an absolute figure over which we should not go.

2. A clear plan and strategy (Environmental management system) in place that incorporates:

a) specific targets for reducing the carbon footprint and wider environmental impact
b) metrics on energy use, waste, travel and transport
c) Processes for regular reporting to the Senior Management team

3. HR policy and operational plans for ensuring gender balance in organisational structures and research processes implemented

All centres were able to demonstrate a positive trajectory on the organisational behaviours indicators (financial management, Environmental Management Systems, gender sensitive HR policies and behaviours), justifying an A score for the output, although the rate of progress is variable across centres. This was analysed further by the external evaluation, as well as part of the mid 2015 performance review. The evaluation concluded that the dual attention paid to both institutional and development gender and women’s empowerment indicators by the performance management system was effective. However, commitment and progress has been variable across the centres, with ICIMOD demonstrating in the mid 2015 review strongest progress. This is still work in progress and one which requires greater focus particularly in CABI, AVRDC and icipe.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

DFID is providing multi-year core contributions to the centres with an annual performance payment based upon their achievements against some key deliverables and generic organisational behaviours set out in the logframe. DFID will continue to fund these centres for the period of the business case providing that there is satisfactory performance against these indicators.

Table 3: VfM performance compared to the original VfM proposition in the business case

Centre	Centres meet internal targets for cost ratio / Baseline 13/14 14/15			Unqualified opinion from external auditors on financial statements	DFID funding no more than 40% of centre’s overall funding / 12/13 13/14 14/15
AVRDC	0.23	0.19	0.18	Yes	13%	13.5%	12.5%
CABI	0.14	0.13	0.11	Yes	<25%	25%	19%
ICIMOD	0.17	0.14	0.14	Yes	7%	9%	5.7%
icipe	0.23	0.16	0.19	Yes	14.9%	29.5%	16.5%

All of the centres have continued to demonstrate good financial management and value for money with the current ratio of their indirect/direct costs below the baseline figure. The proportion of DFID funding to all centres is significantly less than 40%, which shows that they have a wide funding base and not overly dependent on DFID financial support.

Assessment of whether the programme continues to represent value for money

The External Evaluation found that the performance management mechanism established by DFID, such as setting the key deliverables at the outset of the funding, and the annual performance review, provide the international research centres with a clear focus on the agreed outputs and outcomes. It has also been effective in facilitating the delivery of high quality research, the agreed results, and value for money. Annex 6 of the Evaluation Report provides a detailed analysis of value for money for each centre. It also suggests some additional value for money metrics. These will be considered under a new phase of the programme.

Quality of financial management

All core payments to three out of four centres have been made as planned with the centres submitting six monthly invoices on time.

Following the identification of potential control weaknesses, payments to the fourth centre were delayed pending the outcome of an external audit of the robustness of the organisation’s openness, transparency, solidity in its governance and zero tolerance approach to fraud. The auditors’ found that in the areas of procurement and assets disposal management acted in the interests of the organisation. In the area of human resources they noted areas for improvement. Management have subsequently drawn up a timebound and monitorable action plan that has been accepted by the core donors. On this basis, DFID has released the outstanding payments.

All the centres provided a copy of their annual audited statements in time for the annual performance review. Payments from DFID were duly recorded and all the statements had been given an unqualified audit opinion by an internationally recognised accountancy firm. The annual performance reviews took place during June / early July and centres were notified by the end of July about our decision to award a performance payment. DFID determined that three centres met the qualifying criteria for a performance payment. These performance payment were made in August 2015. The unspent performance payment has not been re-allocated.

New Funding Support to the Centres

Currently, DFID is considering a new business case offering multi-year predictable funding to these centres plus some form of performance payment system. In deciding the latter, we will take into account the recommendations of the evaluators and our own experiences of the system over the last five years. We will also have to take cognisance of our budget settlement for 2016/17 onwards and DFID’s other research priorities.

Date of last narrative financial report	Various dates
Date of last audited annual statement	31 December 2015

E: RISK (½ page)

Overall risk rating:

Research and Evidence Division categorises risk within research programmes across management risk, output risk and intellectual risk. During this Annual Review, the risk profile of the programme was reassessed using this categorisation. Overall risk remains low.

Management risks are categorised as low overall. This is core funding (linked to specific performance measures) to well established organisations with good governance and strong finance and management systems. DFID works closely with other donors to these centres. In the case of one centre, a full management audit was undertaken by Sida, and donors have worked together closely to ensure a coordinated response, the implementation of an external audit and follow up to a number of potential control weaknesses.

Output risk is low. There is a high likelihood that the centres will all deliver on their core deliverables, structured around development of new technologies and scaling these up. However intellectual risk is identified as medium. This relates to the additional challenge given to the centres to make a step-change in impact measurement in particular, developing a coherent approach to monitoring and evaluation and delivering robust impact studies and evaluations of past or ongoing research and development programmes. The premise of the programme is that the performance funding management system will lead to higher performance in key areas. This is something that is currently being evaluated by a DFID commissioned external evaluation.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe and Performance of partnership(s)

The programme is delivering as planned, and performance of the partnership is good. Discussions are underway with centres on a potential new phase of support.

Asset monitoring and control

N/A. The partnership principles were not used as this is a global research programme which does not deliver funding through government systems.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

In 2014, using the Global Evaluation Framework Agreement, DFID commissioned an evaluation of the multi-year performance management arrangements introduced under this programme. The study has now been completed; the final draft was received in January 2016. The evaluation had two main objectives:
1. To assess the effectiveness of DFID’s performance management funding mechanism in delivering high quality research, delivery of results and value for money.
2. To make recommendations to DFID’s Research and Evidence Division on performance management funding of research, including metrics.
The evaluation’s main findings were that the PMFM processes that have been established by DFID, including setting the key deliverables at the outset of the funding and the annual performance review, provide the Centres with a clear focus on the agreed outputs and outcomes. It has also been effective in facilitating the delivery of high quality research, the agreed results, and value for money.

The results-based funding strengthened the centres activities in several key areas. For example, some centres are now building in appropriate impact assessment measures into the design of new research projects. Meanwhile, the attention paid to gender and women’s empowerment indicators by PMFM has had some success, supporting the efforts of the centres to produce more gender-focussed publications while helping to ensure that organisational structures and process were more gender-sensitive.

However, the evaluation also identified several areas for improvement. While the Centres were overwhelmingly positive about the multi-annual core funding, the evaluation did not find sufficient evidence to suggest that the bonus element was effective. Only two of the four Centres received bonuses throughout Phase 1, awarded for strengthening institutional capacity and promoting new research lines. The other recipient organisations were unclear about the criteria for awarding a bonus, and if and how some agreed-upon goals were weighted differently to other goals in DFID’s considerations for awarding bonuses.

Issues over clarity and communication were identified as the prime cause behind several other shortcomings. For example, Centres did not embrace robust impact assessment to the level that DFID had hoped for. Clearer communication between DFID and the Centres on what this would entail and understanding the limitations of impact measurement in relation to existing research projects would have helped manage expectations and establish realistic targets. More clarity on how to measure VfM and a closer collaboration on a more explicit theory of change, at an earlier stage, would also have helped make the PMFM more effective. Better communication and clarity over expectations would have helped the Centres develop a clearer idea of what they were aiming to achieve.

Monitoring progress throughout the review period

The main focus of monitoring is the annual performance reviews. However, DFID is available for additional dialogue and exchange with each centre between formal review periods. This is generally at the initiation of the individual centres. The extent to which different centres have taken up this opportunity has varied.

Research centres are encouraged to initiate a discussion with the DFID Agriculture Research team on the partnership or aspects of their performance as required (recommendation #2).

Review Process

This annual review draws upon the performance review of the four centres undertaken in mid 2015. It is also informed by a visit to CABI in Ghana made by Rachel Lambert in October 2015.

The annual performance review of each centre was led by an internal DFID team (Rachel Lambert, Alasdair Swift), supplemented by inputs from the two Senior Research Fellows, Maggie Gill and Alan Dangour and drawing on inputs from a Social Development Adviser (Andrew Clayton) and other Agriculture Research Team members. DFID India participated in the ICIMOD review meeting. The overall assessment for each centre was agreed by the performance review panel.

The performance review involved each of the five centres providing a written report of their progress against the key deliverables and milestones in the logframe. Each centre was invited to give a presentation to a DFID Panel based upon their report. This allowed each centre to elaborate on the information provided. The Panel asked questions to inform the discussion about how each centre had performed. Following the presentations held in July 2015, the Panel shared their findings and produced an agreed overall assessment. Each centre was notified of this assessment which included feedback. The performance review team decided which centres, merited a 2015 performance bonus.

Documentation (Quest No)
Business case (3717589)
Logical framework (3719418)
AVRDC 2014/15 Performance Report (5067741)
CABI 2014/15 Performance Report (5068322)
ICIMOD 2014/15 Performance Report (5068414)
icipe 2014/15 Performance Report (5068334)
AVRDC 2014 Annual Audited Accounts (5051031)
CABI 2014 Annual Audited Accounts (5008588)
ICIMOD 2014 Annual Audited Accounts (5097024)
icipe 2014 Annual Audited Accounts (5096922)
AVRDC 2014/15 Best Scientific Publications (5068434)
CABI 2014/15 Best Scientific Publications (5096
ICIMOD 2014/15 Best Scientific Publications (5068421)
icipe 2014/15 Best Scientific Publications (5068399)
Letter to AVRDC about Panel’s Assessment of 2014 Performance (5190725)
Letter to CABI about Panel’s Assessment of 2014 Performance (5190714)
Letter to ICIMOD about Panel’s Assessment of 2014 Performance (5190783)
Letter to icipe about Panel’s Assessment of 2014 Performance (51900732)
Terms of Reference and Checklist (5321146)
Annual Review Scoring Sheet (5321134)
Note of visit to CABI (Ghana) (5229142)
Evaluation Report of DFID’s Performance Management Funding of IARCs (5332933)
Team Leader’s Approval (5366821)

Annex 1

General guidance on research quality review procedures of Centre publications

We are grateful to you for taking part in the DFID Agriculture Research team pilot of a new mechanism for assessing the quality of research output from Centres. We requested that Centres provide a defined number of papers (between 3 and 7) published in the last 12 months that were your "best new research publications, judged by you to represent high quality research and development relevance". We then subsequently also asked you to provide a brief justification for your selections.

We have found the process instructive and we would like to formalise its use in future years with modifications as outlined below. We have not used the results of this year’s pilot test to grade the quality of research outputs from Centres. As the method for evaluating the quality of research outputs under this funding scheme is currently under review, we have also not used the number of journal publications/ peer-reviewed journal publications in making decisions about this year’s performance bonus. Next year we will use information from both the selected paper submissions and the total number of journal publications in evaluating the quality of research outputs from your Centre.

Next year we will request that you report, as before, on the number of research publications including the number in peer-reviewed journals. We will in addition ask each Centre to submit a portfolio of 5 research outputs that represent what it considers to be its most important research contributions of relevance to the central agriculture and/or development mission of the Centre, and we will ask for a justification for each selection. We will then review selected publications against the following three primary criteria (although do let us know if you would like us to consider other criteria):

Quality of research – does the paper report high quality, innovative and/or definitive research that makes a clear research contribution to the central mission of the Centre? In this assessment we will be guided by the principles of the UK Research Excellence Framework that specifically grades research quality according to its “originality, significance and rigour”. We have a preference for primary research publications, i.e. those presenting newly collected data, or new analysis of existing data (including systematic reviews with meta-analysis), although non-systematic desk-based reviews and opinion pieces can be submitted.

Relevance for agriculture and/or development – does the report provide evidence that is relevant for agriculture and/or development within the context of the mission of the Centre? We recognise that some research findings will have more immediate relevance, while others may have more long-term relevance – both are acceptable. As the funds to your Centre come from the DFID Agriculture Research team, we are most interested in research outputs that relate broadly to agriculture.

Role of organisation – what role did the Centre play in the design, conduct and reporting of the research? We would in future like you to specify this clearly in your support statement for each research publication. We value both Centre-led research and research conducted in collaboration with other groups. In highly collaborative research papers we would like to understand more clearly the input of the Centres we are supporting.

Specific feedback on 2014-15 pilot

We congratulate CABI for demonstrating, through its selection of publications, that it is involved in large amounts of high quality research. We are impressed by the range of research being conducted by CABI and think the balance between descriptive, analytic and experimental studies is very good. We felt that all papers were strongly relevant to agriculture in its broadest sense although further relevance to livelihoods and development outcomes is quite theoretical in a few cases.

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to International Agricultural Research Centres that benefits Poor People
Programme Value: £40,093,715		Review Date: 12/03/2015
Programme Code: 202748	Start Date: 01/04/2012	End Date: 31/03/2015

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	A+	A	A
Risk Rating	Low	Low	Low

Summary of progress and lessons learnt since last review

Overall progress is on track, and the programme scores an A. The four international agricultural research centres which receive funding under this programme currently are largely meeting expectations against the main indicators relating to research delivery and scaling of technologies. One of the 4 funded centres (CABI), received a performance bonus due to having fully met or exceeded the milestones for the key deliverables with an excellent performance against organisational and quality of research. The three other centres were largely on track against agreed deliverables and milestones. The main recommendations to centres following the mid 2014 review related to impact evaluation, gender analysis and mainstreaming and strategies and partnerships for uptake of technologies. Performance against organisational behaviours (i.e. financial management, environmental management systems, gender sensitive HR systems and policies) was good.

This review is a light touch one, since DFID has commissioned an external evaluation of the programme which is currently underway. This evaluation is expected to feed into future decisions in DFID agriculture research programme on use of performance management systems.

Summary of recommendations for the next year

Where research centres have a strong presence and are scaling up technologies in specific countries, they should approach the Agriculture Research team to discuss how this overlaps with bilateral programme priorities, and where appropriate facilitate an introduction to Country Offices (DFID to follow up via communication to research centres in March 2015).

Lessons will be drawn during the next Annual Review (due February 2016) on the effectiveness of this new mechanism to assess quality of research by the DFID Review team, drawing on feedback from centres.

DFID Agriculture Research team should formally draw attention of the partners to their availability for follow up discussions on partnership or aspects of performance (recommendation #3) (March 2015).

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to International Agricultural Research Centres that benefits Poor People
Programme Value: £40m		Review Date: 4 September 2013
Programme Code: 202748	Start Date: 01/04/2012	End Date: 31/03/2015

Summary of Programme Performance
Year	2012	2013
Programme Score	A+	A
Risk Rating	Low	Low

Summary of progress and lessons

As was the case in the last Annual Review, this year’s Outcome Assessment is based on two components. Firstly, are the centres performing as expected, meeting deliverables and is the assessment against outcomes on track?

Against these criteria, the annual outcome assessment is an A – i.e. outputs largely met expectations. For two of the 4 original centres, they have received a performance bonus (CABI and icipe) due to having fully met or exceeded the milestones for the key deliverables with an excellent performance against organisational and quality of research. Two other centres were largely on track against agreed deliverables and milestones, but DFID has used the mid 2013 performance review process to send a clear message on performance, and in the case of GFAR, has proposed to end funding unless there is clear evidence of progress on 4 objectives. For all centres, in order to leverage improved performance, specific recommendations for follow up action were made following the mid 2013 performance review.

The second aspect of the assessment looks more broadly at the introduction of a new performance based management systems. Is the system performing effectively, and meeting the objectives set out in the Business Case of using multi-year performance related funding to leverage higher performance, value for money, and closer alignment with DFID values and priorities? In relation to these criteria, the programme would appear to the review team to be meeting or exceeding expectations. However, this needs to be assessed independently of DFID. It should also be noted that there are no logframe indicators relating to this specifically, although it should be a major focus of the external evaluation planned for 2014.

In addition, the feedback from the centres, as well as the DFID Review Panel, indicates that the system is performing well. Standard reporting format was helpful, expectations clearer, and generally the review process and dialogue positively received. The centres commented favourably about the benefits arising from DFID funding, particularly the flexibility of unrestricted core funding over several years is vital for longer-term planning enabling more strategic funding decisions and leveraging new investments. Whilst benefits have been seen in several centres on gendered research and improved impact evaluation, more work is still required. Of the four centres who responded, three centres agreed that progress on their flagship programmes would not have moved as quickly as it has done without DFID’s support. ICIMOD made a valid point in that it was too early to establish the counterfactual and provide concrete evidence on this question.

Summary of recommendations for the next year

There are a specific set of recommendations for each centre recorded in the section 1 above on progress against outputs. These have been communicated to each centre earlier in the year. This section records additional recommendations arising from the review process itself, and from feedback from each of the centres as part of this review.

Recommendations

1. For all centres there is still much scope for improving gender analysis across the portfolio, including more gender disaggregated data, and for more explicit focus on gender in future publications. This is reflected in the centre specific recommendations in the earlier section of this report.
2. AVRDC still does not have a clear gender strategy; this needs to be developed next year in order to demonstrate how it will operationalise gender across its research programme. It also needs to identify the training needs for staff on gender research and gender champions to push gender integration across the research programme.
3. DFID undertook a field visit to icipe in 2013, which helped ground truth findings from the performance reviews and strengthen mutual understanding between DFID and the centre. DFID should aim to complete field visits to AVRDC, ICIMOD and CABI during 2014.
4. DFID should proactively share the results of the Performance management system with donor representatives involved in each of the centres, and best practice on organisational behaviours from each centre with the others.
5. The 2014 External Evaluation should look not just at the log frame indicators for this programme but also at the added value of the performance funding mechanism as a whole.
6. There may also be value in stimulating a discussion within AIRCA on how to strengthen impact evaluation across the international agriculture research centres and setting out and benchmarking direct/indirect costs.

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to International Agricultural Research Centres that benefits Poor People
Programme Value: £40m		Review Date: 12/03/2012
Programme Code: 202748	Start Date: 01/04/2012	End Date: 31/03/2015

Summary of Programme Performance
Year	2012
Programme Score	A+
Risk Rating	Low

Summary of progress

The Annual Outcome Assessment is based on two components. Firstly, are the centres performing as expected, meeting deliverables and is the assessment against outcomes on track? Against these criteria, the annual outcome assessment is an A+ – i.e. outputs moderately exceeded expectation. The assessment and the Performance Review undertaken in mid 2012 demonstrated that this is the case. Centres are on track to meet deliverables. Two out of 4 centres received a performance bonus (CABI and icipe) due to having fully met or exceeded the milestones for the key deliverables with an excellent performance against organisational and quality of research. The other two centres were largely on track against agreed deliverables and milestones. Where centres have performed less strongly, specific recommendations for follow up action were made following the mid 2012 performance review.

The second aspect of the assessment looks more broadly at the introduction of a new performance based management systems. Is the system performing effectively, and meeting the objectives set out in the Business Case of using multi-year performance related funding to leverage higher performance, value for money, and closer alignment with DFID values and priorities? In relation to these criteria, the programme is moderately exceeding expectations, (i.e. scoring an A+, although there are no log frame indicators explicitly relating to this). One new international centre (ICIMOD) was assessed and a new funding agreement established. Additional funding has been provided to high performing centres (CABI and icipe) meeting emerging priorities and building on their strong performance in the first year. Both DFID’s and the Centres’ assessment against the approach set out in Section 1.4 has been largely very positive, particularly in terms of the benefits of multi-year funding, leveraging performance on evaluation and cross cutting issues and a stronger technical dialogue with DFID. A number of areas have been identified to further strengthen the partnership and effectiveness of the model. Whilst the management approach introduced is not transaction cost neutral for DFID, overall the assessment is that the outputs obtained more than justify the transaction costs.

In summary, a score of A+ is justified. The centres were pre-assessed on the basis of representing value for money to DFID before this project commenced and funding was allocated to four centres on the basis of this assessment. The bulk of DFID funds (97%) goes to the three highest performing centres with 81% to two centres (CABI and icipe) that have fully met or exceeded the milestones for their key deliverables and demonstrated excellent performance against organisation behaviours and quality of research. This is further supported by the Secretary of State approving a business case last year increasing our support to CABI and icipe. The performance management system is working effectively, enabling DFID to scale up its work through this mechanism, and enabling delivery of significant research outputs.

Summary of recommendations for the next year

There is a need to draw centres attention to the need to strengthen the documentation and dissemination of gender research outputs. RED’s own gender stocktake could be shared with centres as part of lesson sharing and transparency.

A discussion on how to incentivise the right balance of scientific publications for scientists within Centres needs to be had as part of the 2013 Performance Review, with a view to setting clearer targets and being able to track progress by each centre of publications and quality of science.

Further work on value for money measures and benchmarking across programmes should be developed over 2013. The centres themselves could be asked to collaborate on benchmarking and good practice under AIRCA (Association for International Research and Development Centres for Agriculture). In particular, standard metrics and benchmark levels for things such as Admin/Corporate costs would be helpful and should be developed.

The Performance Review in mid-2013 should be used to communicate expectations and good practice on gender and environment in more detail. In particular, centres should be encouraged to share examples of best practice and to plan for gender specific knowledge outputs.

DFID should be proactive in highlighting and sharing best practice between centres (e.g. on gender mainstreaming, environment mainstreaming, VfM, evaluations).

DFID should explore with donor partners whether there is scope to use this to leverage greater impact, either through sharing of best practice, or through identifying strategic areas for collaboration.

DFID to consider making some funding available to support /stimulate broader involvement of the international agricultural centres in the CRPs.

The independent assessment, originally planned for 2013, should be put back to 2014, when the new performance based system.

GFAR to ensure that VfM measures are covered in the forthcoming governance review.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process