Project Completion Review - Top Sheet

Review Date:	May 2016

Title: Somalia Monitoring Programme (SMP)
Programme Code: 202984	Start Date: Dec 2012	End Date: April 2016
If programme was closed >1 month early please describe in a few words why.	Not applicable

Summary of Programme Performance

Year	2013	2014	2015	PCR
Programme Score	A	A	Deferred	A+
Risk Rating	Moderate	Moderate		Moderate

Financial Position

Original Programme Value	£6,500,000
Extensions/ amendments	Cost extension in November 2012 of £1,200,000 within same time-duration for project / Total cost = £7,700,000
Log-frame revisions (with dates)	Quest number 5228337. Revised in October 2015.
Total programme spend	£7,441,206
Total balance / (See financial table under section D)	£257,409

Follow up actions required following closure

- The team will ensure refunds from UNDP and UNFPA of the funds which were not utilised (£129,072 and 128,337 respectively). Details provided at the financial section.
- The recommendations in this PCR will be considered during the 1st year of implementation of the follow-on programme to SMP.
Acronyms
BBC	British Broadcasting Corporation
CSD	Central Statistics Department (in the Ministry of Planning – Somaliland)
CSFP	Core State Functions Programme
DCSA	District-level Conflict and Security Assessments
DFIDS	DFID Somalia
FAO	Food and Agriculture Organisation
FSNAU	The Food Security and Nutrition Analysis Unit
HCS	The Health Consortium Somalia
IBTCI	International Business and Technical Consultants Incorporated ‘the monitor’ responsible for delivering Outputs 1 and 3 (verifications and technical assistance)
IM	Independent Monitoring (or Third Party Monitoring)
IP	Implementing Partner
JHNP	Joint Health and Nutrition Programme
M&E	Monitoring and Evaluation
MoP	Ministry of Planning
NDP	National Development Plan
OCVP	Observatory of Conflict and Violence Prevention – Implementer of Output 2.1
PESS	Population Estimation Survey Somalia
PIMS	Promoting Inclusive Markets in Somalia
PM	DFID Project Manager
SDF	Somaliland Development Fund
SEED	Sustainable Employment and Economic Development
SHINE	Somali Health and Nutrition Programme
SMP	Somalia Monitoring Programme
SSF	Somalia Stability Fund
SORADI	Social Research and Development Institute - Somali agency
SRO	DFID Senior Responsible Officer – accountable for the delivery of the (SMP) project
TA	Technical Assistance
TPM	Third Party Monitoring (or Independent Monitoring)
ToR	Terms of Reference
UNCT	United Nations Country Team
UNDP	United Nations Development Programme – Managing Agent for Output 2.1
UNFPA	United Nations Fund for Population Activities - Managing Agent for Output 2.2
UNICEF	United Nations International Children's Emergency Fund
UNOPS	United Nations Office for Project Services
UNV	United Nations Volunteers
USAID	United States Agency for International Development
VFM	Value for Money
WB	World Bank
WFP	World Food Programme

Terminology

Implementing partner (IP)	The agency implementing a DFID funded project
The monitor	The agency contracted to carry out independent monitoring activities
Delivery partner	The agencies delivering SMP (IBTCI, OCVP, SORADI, CSD)
Log frame	Logical framework – DFID’s primary results framework tool for tracking the progress of project outputs and outcomes

Third Party monitoring:	a process whereby an organisation that is not involved in delivering a DFID funded programme conducts monitoring activities to assess the existence and effect of the project activities
Verifications:	a specific process to check a set of pre-agreed activities or results

A. Introduction and Context (1 page)

Dev Tracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202984/documents
Dev Tracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202984/documents

Context
Somalia is among the world’s most fragile states. The causes of the conflict are deep and complex and the effects are far reaching. DFID is funding programmes across Somalia but finds it challenging to effectively monitor and evaluate the delivery and impact of these investments due to the high levels of insecurity and threat. The Somalia Monitoring Programme (SMP) was designed to improve the production, quality and use of statistics and evidence on Somalia and to provide assurance on the actual delivery of UK-supported activities and results in inaccessible regions of the country.

The availability of data on Somalia is very limited. In 2012/13 there was little or no reliable population, income, economic, social or governance data, and what data was available was not well known, was based on inconsistent methodologies and was often not well packaged or made accessible for national-level decision-makers to use. In addition, several implementing partners, particularly those working on governance and security, were weak at determining and reporting results. Over the life of the programme, DFID Somalia’s portfolio expanded financially, technically and geographically as clearer political governance arrangements took shape and AMISOM helped extended security across the country.

Outline of programme and what it has achieved
The SMP was designed to provide better monitoring, evaluation and evidence for DFID-Somalia (DFID-S) funded programmes in order to improve effectiveness. The programme was delivered through the following implementing partners:
- International Business and Technical Consultants Incorporated (IBTCI) – Managing the verification of DFID’s portfolio and providing capacity building on Monitoring and Evaluation to DFID-Somalia (DFID-S) and project implementing partners (IP). IBTCI worked with three local Somali monitoring organisations which included: Social Research and Development Institute (SORADI) based in Hargeisa, Somaliland; Alliance for Development Solutions (ADS) Puntland monitors, Eagle Consulting based in Mogadishu.
- United Nations Development Programme (UNDP) through Observatory of Conflict
  and Violence Prevention (OCVP). OCVP conducted and produced District-level Conflict and Security Assessments across Somalia. OCVP is a local Somali non-governmental organisation with a mission to contribute to peace building and state-building across all regions of Somalia through research, education and dissemination of information that promotes social cohesion, security, safety, and sustainable development.
- United Nations Fund for Population Activities (UNFPA) in collaboration with the Ministries of Planning for the Federal Government of Somalia, Somaliland and Puntland: The	Ministries of Planning conducted the Population Estimation Survey Somalia (PESS) with oversight and capacity building support from UNFPA.
- The programme has exceeded its objectives with an overall score of A+.

Key achievements of the programme include:
1. The programme was able to execute independent and credible monitoring of all projects in DFID’s governance, economic development and health pillars. This entailed over 380+ specific assessments of projects across all regions of Somalia without threat or loss of life to monitors. Hard data confirming performance, results and risks were delivered and incorporate into DFID-S’s programme management and corporate reporting.
2. The programme was an important part of DFID Somalia Enhanced Risk Management Strategy, providing assurance that a significant and representative proportion of all DFID-S activities are being monitored in the field and providing hard intra- and inter-programme intelligence to manage risks, avoid doing harm and ensure programmes are continuously improving.
3. The strengthening of implementing partners’ and DFID’s monitoring and evaluation systems in order to strengthen programme accountability and the ability to monitor and improve results, particularly in key programmes to DFID’s strategic objectives, such as the Joint programme for Local Governance and the Somaliland Development Fund.
4. Completion of the first population enumeration for 40 years in Somalia, providing Somali authorities and the international community with national and regional estimates of Somalia’s population and the populations education, employment, asset ownership and wider human development situation. The internationally quality-assured statistics are now being used to determine priorities within the National Development Plan and the emergent Interim Poverty Reduction Strategic Plan.
5. A sample frame that is being used in the design of surveys & evaluations by a broad range of users, such as the Somalia High-Frequency Household Survey, the planned Demographic and Health Survey and the Multiple Indicators Cluster Survey, which are key instruments for Somalia to be able to track and increasingly report against the development priorities and globally agreed Sustainable Development Goals. In addition, a significant cadre of more and better skilled Somali enumerators, data-cleaners and statisticians was built through a series of increasingly demanding trainings that were applied to delivering the Population Estimation Survey for Somalia (PESS)
6. District-level Conflict and Security Assessments covering all of Somalia, including the cities of Mogadishu, Hargeisa and Garowe. These assessments have been used by Somali authorities and the UN both as baselines to track changes in personal safety, provision of security, satisfaction with justice providers and to inform Somali authorities’ priorities for action, in areas such as Baidoa, Kismayo, Bakool and Mogadishu where demand for better governance is most strong.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

Outcome	Better monitoring, evaluation and evidence for DFID-funded governance and peacebuilding programmes in Somalia.
Indicator(s)	2014 target	2015 target	PCR target	Achieved
Number of DFID Somalia governance, human and economic development projects that are monitored at least once per year (including field visits) (cumulative)	3	7	10	Exceeded expectation. 11 comprising of: / 4 governance & security programmes[1], / 2 health programmes[2], / 3 economic development[3], / 1 conflict pool & 1 aid enablers. / 1st year the programme verified governance programmes, the 2nd and 3rd year the programme progressively expanded to cover other pillars.
Level of Somali administration use of data generated by Somalia Monitoring Programme	Somaliland, Puntland & Federal governments using data from the intervention			Met expectation / Good progress See below for details
Number of DFID Somalia Governance, human and economic development projects that have been adapted in light of evidence and support emerging from this programme. (cumulative)	3	5	9	Exceeded expectation / Evidence from verifications enabled projects to strengthen implementation of programmes (e.g. SDF and JHNP) and ensure final delivery of outputs were concluded (e.g. CSFP SEED and JHNP). / 15 DFID Somalia programmes and projects reviewed and revised their log frame correctly to capture results.[4]
[1] DFID-Somalia Governance and Security programmes include: i) Core State Functions Programme, ii) Somalia Stability Programme, iii) Accountability Programme, iv) Somalia Monitoring Programme.
[2] DFID-Somalia Health programmes include: 1) The Health Consortium for the Somali people; and 2) Joint Health and Nutrition Programme.
[3] DFID Somalia Economic Development programmes include i) Somaliland Development Fund ii) Promoting Inclusive Markets (PIMS) in Somalia iii) SEED
[4] The 15 log frames: 10 in the Governance and Security portfolio (UNDP's Parliamentary Strengthening, OCVP's, UNDP's-A2J, UNDP's-CPP, KCC's CDNA, UN's JPLG, DDG's CSP, DDG/HI's SJSP, ASI's-SSF (Results Framework), UNOPs/Sahan's Police Stipends, Internews' Somaliland Elections). 3 in the Economic Growth portfolio (DAI’s PIMS, Mott MacDonald’s SDF, and Mott MacDonald’s ESRES). 2 DFID Business Cases (the Rule of Law and SHINE business cases).

The project has achieved its intended outcome.

Independent Monitoring and M&E Support (Outcomes 1 and 3)
- This project has been significant in shifting attitudes of DFID-S staff and programme implementers towards greater recognition of the benefits of independent monitoring. There has been positive engagement with stakeholders and greater transparency in delivery of the programme.[5] The Fund Manager for the Somalia Stability Programme, for example, was initially defensive of the verification findings but with time and consistent engagement by the DFID-S programme team they were able to understand the benefits and positively engaged with and acted on the findings.
  [5] 77% of IP reported improved consultation and engagement with stakeholders as a result of verifications. 74% of IPs reported that the verifications had improved their decision making processes. 84% of IPs reported that the verifications had contributed to increased transparency. Again increased transparency on what?”
- DFID-S staff have responded to the verification reports and used findings to engage with project implementers to improve the quality of project delivery. This has improved accountability and the quality of dialogue between DFID, Implementing Partners and sub-contracted delivery partners. Implementing partners have found the verifications to be useful tools for strengthening their projects. Actions were taken in response to over 100 verification reports which received orange or red flags[6] The health team, for example, used the findings to have productive dialogue with implementing partners on a range of issues raised by the verifications (e.g. the operation and maintenance of medical equipment, attendance of health personnel, citizens’ satisfaction with health services and health staff morale). In the case of the Health Consortium of Somalia, for example, the implementing partner Trocaire agreed that a complex set of issues would be revisited by a different set of monitors to verify to what degree the problems had been resolved.
  [6] Source: SMP Submissions All Key Summary Findings and Feedback (DFIDS Team site DFID-S Team site) Orange indicates there are issues to be noted and addressed while Red indicates there are issues which require immediate addressing
- There is a range of examples where poor delivery and suspected under-performance were confirmed by the monitoring evidence and action was taken to redress the identified shortcomings. In addition, positive findings from the verifications have been used to identify good practice for advocacy purposes. The verification of the Young Graduates project[7] under the DFID-funded UNDP Accountability Programme identified clear gaps in the results and sustainability of the programmes. The DFID-S programme team used these findings to have conversations with the UN and Somalia authorities on options to enhance the sustainability of the programme which resulted to the young graduates being integrated into the civil service.
  [7] M-210 - Young graduates programme - Mogadishu

Somali Administration Use of Data (Outcome 2)

Use of Data 1: Population Estimation Survey Somalia (PESS)
- The Statistics Department/directorates in the Ministry of Planning (MoP) have taken full ownership of the PESS data. The departments’ capacity has significantly increased due to this programme as has MoP staff’s active commitment to capacity building activities. Statistics Department staff have a good understanding of the PESS and are able to communicate it to policy makers. Senior managers at the Statistics Department/directorates have taken the initiative to promote these data and cascade PESS evidence and learning to other government departments. There is a genuine enthusiasm over these data as they are seen as being the most credible, important and available set of statistics on Somalia for many years.
- The PESS dataset is an invaluable source of evidence for planning, monitoring and policy formulation. The PESS headline and thematic reports are being drawn on in the evolving National Development Plan (NDP) for Somalia and Somaliland. This has raised demand, for example, by the Minister of Planning asking the World Bank to accelerate and add its poverty analysis to the PESS work in time to also be included in NDP planning. The data has been endorsed by the Federal Government of Somalia and the Somaliland authorities, a considerable achievement given the political challenges in Somalia. Furthermore, the PESS is being used by donor partners, including the UN which has endorsed its findings for use by all UN agencies[8]. It is highly likely that the data will feature in the final NDP.
  [8] UNICEF has already used the PESS as population denominator for calculating ‘rates’ in education (e.g. Proportion of children in school)
- The Ministries of Health, Education, Labour and Finance and the Office of the Prime Minister are using PESS data in their planning.
- A key success of the PESS is that there is now a robust sampling frame covering the entire country. This has already been used by the World Bank (poverty estimation), UN Food & Agriculture Organisation (FAO), British Broadcasting Corporation (BBC), UN World Food Programme (WFP), UN International Children's Emergency Fund (UNICEF) and United States Agency for International Development (USAID) to design and conduct surveys and evaluations. The MoP is using the sampling frame to revise its plans for conducting the Consumer Price Index (CPI) survey and calculations. This broad up-take of the sampling frame should lead to the availability of a range of new, better quality statistics over the next few years.
Use of Data 2: District-level Conflict and Security Assessments (DCSAs)
- The DCSA data has been openly received by district level stakeholders and high level political representatives at workshops and roundtable discussions respectively. There appears to be an acceptance of the data which is encouraging.
- There is limited evidence of the hard use in planning of this data by senior decision-makers. All reports, however, are available online (at www.ocvp.org ) and there were 8,981 downloads by March 2015, of which about 32% were returning visitors, with an increasing proportion being from within Somalia. Other major downloads were from Kenya, UK, USA, Australia and Belgium.

Use of Data 3: Verification Reports
Somali authorities have drawn on the verification reports to adapt programmes in which they are a main stakeholder for example:
1. Under the Sustainable Employment and Economic Development (SEED) programme, verifications indicated some unfinished construction projects though the project had closed. DFID-S acted to get the FAO team to meet Somaliland stakeholders to review and recommend remedial action on issues raised by verification reports and to complete all outstanding work.
2. The verification of work on Qudhacdeer Market under the Joint Programme for Local Governance (JPLG) programme raised concerns around forced relocation, perceived lack of consultation, lack of visibility on when and how the new market will open, traders working in difficult and unsafe working conditions whilst the market upgrade was being undertaken and uncertainty over the allocations and operation of the market. The team engaged with UNDP and the relevant District Council, with these partners taking action to redress these concerns. A repeat verification assessment 6 months later confirmed most problems were fully resolved.

Overall Output Score and Description:	A+	Outputs moderately exceeded expectation

Output	Output Indicators	Impact Weight	Risk	Score	Progress against Target
Results reported by partners verified	1.1 Number of DFID Somalia Governance, human and economic development projects whose results have been at least partially independently verified. / 1.2 Number of verification field visits undertaken	40%	Moderate	A+	1.1–Met / 1.2-exceeded expectation
Baselines, results and impacts of interventions determined	2.1 District-level Conflict and Security Assessments (DCSAs): Number of districts subject to UNDP governance and security surveys over the period of support. / 2.2 Population Estimation Survey for Somalia: Number of statistical analysis/data collection exercises supported in Somalia that produce valid results (e.g. population calculation)	30%	Moderate	A++	2.1-exceeded expectation / 2.2-exceeded expectation
Implementing partners capable of monitoring results and impact	3.1- Number of DFID Somalia governance, human and economic development implementing partners that have completed monitoring and evaluation capacity-building exercises / 3.2 Number of DFID Somalia governance, human and economic development projects that have log frames that meet DFID corporate guidance without substantial input from DFID staff (cumulative) / 3.3 Number of DFID Somalia governance, human and economic development projects that report fully on outcomes and outputs.	20%	Moderate	A	3.1 – Exceeded expectation / 3.2- Exceeded expectation / 3.3-not met
Governance and peacebuilding information collated, analysed, packaged and presented	4.1 Number of analytical and lesson-learned reports produced and presented to the DFID Governance and Peacebuilding team	10%	Moderate	A+	Exceeded expectation

The SMP has met all of its output milestones and exceeded expectations in a number of areas. Key achievements at the output level include:
- 389 verifications ( against a target of 290) carried out across the entire DFID-S portfolio with the pace of completion increasing across the lifetime of SMP. They included 227 verifications under Governance and Security programmes, 111 verifications under Human Development programmes, 37 under Economic Development Programmes, 11 verifications Conflict Pool programme and 4 verifications under Aid Enablers Programme.
- A large range of capacity building activities carried out for implementing partners and DFID-S which has led to log frame strengthening across the DFID-S portfolio and revision of the theories of change and planned activities in some specific programmes.
- A range of lesson learning products disseminated and used across the DFID-S portfolio to better manage project delivery.
- 47 high quality District-level Conflict and Security Assessments (DCSAs) and 15 comparative reports covering all of Somalia including 16 districts in Mogadishu that have been drawn on by Somali authorities, donors and UN development agencies to better monitor citizens’ experience of security, basic services and governance conditions on the ground.
- Completion, government endorsement, publication and use of the Population Estimation Survey of Somalia (PESS) results and thematic reports.
- A sampling frame which can be used in the design of household surveys covering all of Somalia.
- Significant capacity building of downstream partners including MoP- Statistics Department (both Federal & Somaliland government) and evidence that this learning is being put to good use.

Lessons and how these have been shared
The lessons learnt during the implementation of this programme have been applied to the design of the next phase of the SMP, including those recorded in the previous annual reviews. The theory of change for the next phase is much more explicit about underlying assumptions regarding the incentives and behaviour of Somali authorities and implementing partners in using verification evidence and better statistics. To date, SMP has shown an ability to adapt and improve to meet user needs. This approach should be continued in order to maximise the utility of its products. Furthermore, lessons will be shared through DFID’s internal virtual Independent Monitoring Group which consists of staff from across DFID’s country-offices and headquarters with experience and/or interest in independent monitoring.

Programme Delivery
A movement towards more results-focused contracts should be pursued in a manner that reinforces implementing partners’ willingness to experiment with flexible approaches, and incentives them to exceed agreed desired results. SROs should make clear through contracts, MoUs and working discussions that flexibility, innovation and increased pace are expected through the course of the programme as learning increases.

The continuity of UN staff has been less than that of private suppliers, therefore, it should be regularly checked and, where faltering, early agreement on managing the replacement of key staff should be pursued.

Verifications
A monitoring project (like the SMP) can provide far greater insight into the quality of programme delivery than the standard approach of field visits. This is due to (a) both the quantity and quality of information collected; (b) the quality assurance process undertaken before the final report is produced which involves and produces greater transparency with implementing partners and (c) the increasing analytical power of a growing set of synthesised qualitative data that allows identification of systematic factors affecting programme performance, as well as highlighting partners or geographies that are proving problematic. Such an independent monitoring approach can be executed in more stable country settings and would potentially unlock greater value from improved programme performance in such settings, where the monitoring findings can be triangulated with other evidence and followed through subsequently by in-situ visits and discussion with DFID staff.

The institutional objective(s) and scope of third party monitoring (TPM) should be clearly articulated. The TPM project can be designed to provide programme management tools at the micro level, lesson learning at the sector or thematic levels and as an accountability tool at the macro country office level. Clarity, however, about the primary purpose in design should be made clear as that would allow for transparent and calculated consideration of when greater scope may need to be given to secondary objectives. The SMP model initially focused at micro, project level but evolved overtime to accommodate broader needs of the portfolio. This model worked well for DFID-S and IPs.
A strategic approach to planning verifications is highly beneficial. A clear strategy should be developed from the start. The strategy should consider the pros and cons of verifying the entire portfolio, bearing in mind that for monitors to provide high quality verifications they need to understand the programmes and this understanding will take time and therefore adds to the cost. It should also consider the need for a certain volume of verifications per project in order to provide a rounded picture of project performance especially since the verifications are based on small, non-random samples. The strategy should build in flexibility to respond to evolving priorities and risks.
The verifications component of the programme would be more efficient if clear protocols were put in place which outlined the purpose, required engagement of different stakeholders and processes involved in the third party monitoring. This programme experienced back and forth between the monitor and IP’s being verified, but as leant during implementation, an introductory letter to the IP leadership made it easy to access field offices.
The development of a DFID-S monitoring and evaluation plan would help DFID users to understand the objectives of the verification reports vis-a-vis other complementary M&E tools (e.g. evaluations and project reviews). This would help to manage user expectations and to make clear where evidence from verification reports can most appropriately be used and where its contribution is ancillary.

Capacity Building of DFID-S and Implementing Partners on M&E
An earlier strategic ( and less demand-led) approach to providing technical support on M&E may have been more beneficial. This would have identified from DFID’s perspective the priority implementing partners and their M&E issues that needed to be addressed, as well as collective approaches to addressing them, as opposed to an entirely tailored approach to IPs who were conscious of their M&E capability-deficit. A clear strategy should be developed from the start of the next phase. This strategy should be based on the evidence of the need for support and key opportunities for influence. Therefore, an assessment of the strengths and weaknesses in DFID-S and IP M&E systems and the convergence between the two would be beneficial. Capacity building should be designed to go beyond log frame and theory-of-change strengthening to consider the actual tools and practical processes for monitoring that need to be employed within the programmes. DFID-S staff should be provided with training opportunities to strengthen their understanding and competence to discuss and work with partners in improving M&E systems and practices.

Population Estimation Survey Somalia (PESS)
Supporting government to produce, analyse and disseminate data with ongoing capacity building support which is specific to the product being produced is highly beneficial. It may be a slower process (than the implementing partner agent taking full control) but the benefits of government ownership and the knowledge gained by government staff far outweigh potential delays. This programme has shown that this approach need not compromise the quality of the final product. The likelihood that policy makers will use the data is far higher when government officials have ownership, as the officials are not only knowledgeable about the data, they are also have an enthusiasm which make them great promotors of the product.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Results reported by partners verified
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	40
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes – previously 25%

Indicator	Target	Achieved
1.1 Number of DFID Somalia Governance, human and economic development projects whose results have been at least partially independently verified.	10	10[9]. SMP initially verified only governance pillar project in 2013 and early 2014 but the utility of the process and findings encouraged an upgrade in ambition to provide verification across the economic development and health pillars also. By end of programme 74 implementing partners were verified.
1.2 Number of verification field visits undertaken	290	389 verification reports / 227 Governance & Security, / 111 Human Development, / 37 Economic Development, / 11 Conflict Pool, / 4 Aid Enablers.
[9] All programmes under governance, health and economic development were verified apart from stipends programme and World Bank aspects of other programmes. Programmes include: HCS, JHNP, SMP, Accountability, CSFP, SEED, SDF, PIMS, SSF, ESRES & Conflict Pool

This output significantly exceeded expectations. The SMP developed a strategic approach to planning verifications. As such the entire development portfolio was covered by verifications, with the number of verifications for any given programme weighted according to programme value. The number of verification field visits far exceeded the expected level. As the programme progressed, engagement increased, with users finding the verifications increasingly useful. Expectations of what the SMP could deliver increased as demand increased, including demand from implementing partners who were initially wary and in some cases reluctant to engage. The programme has continued to deliver beyond expectations.

Key Points
- The success of the verifications has been due to professional delivery, DFID’s approach to strengthening project implementation through continual lesson learning and good engagement from IPs. This was because teams realised TPM was an extra programme management tool which both DFID-S teams and IP leadership would use to have a constructive conversation with their field offices on issues raised and to find solutions or improvements to project delivery.
- Verification reports provide much more robust oversight of project delivery than the traditional field visit approach due to the depths of observations. The verification report gave detailed findings as collated from the beneficiaries, government administrations, IP and other interested stakeholders. Nonbiased reports increased the acceptance of the findings.
- Reports are clear, accessible and relevant to DFID-S project management team needs. IBTCI has assisted DFID-S staff to identify needs and has been flexible to meeting user needs within the parameters of the verification model used.
- Verification reports are based on a sound systematic methodology. Findings are deeply rooted in qualitative evidence from field observations and interviews with beneficiaries, project implementers and local government officials.
- The use of photographs and interview transcripts provides DFID-S and other users with an immediate connection with the reality on the ground in areas where DFID access is not possible. The transcripts can be particularly powerful as they are based on interviews with beneficiaries who have been chosen at random, thus reducing biased messaging.
- Involvement of implementing partners to fact check the report and incorporate their feedback before it’s shared with DFID-S increased IP acceptance of findings.
- The verifications considered gender issues (e.g. benefits to men/women), interviewed men and women and used male and female data collectors.
- In addition to identifying performance issues that required strengthening, the SMP also identified areas where performance had exceeded expectations. These examples have been useful for providing positive advocacy materials for DFID-S use, and because they are openly available to key stakeholders, provide inspiration and ideas to others on how to improve delivery.
- Information turn-around between DFID-S and IBTCI took longer than anticipated resulting in delayed compilation of the portfolio outlook (e.g. project documents, staff contacts) outputs and activities which subsequently affected the deployment process. Time was wasted in trying to obtain DFID information, resulting in inefficiencies.

Summary of responses to main issues raised[10] in previous annual reviews (where relevant)
[10] Full list of Annual Review Dec 2014 recommendations can be found in Annex 1
Working with IBTCI, DFID-S developed an annual verification plan representative of DFID’s investment by programme. This new approach was a very positive development resulting in better prioritisation of verifications, predictability of timetables and a confidence at the top of the office that the full portfolio had sufficient oversight.
IBTCI designed an engineering tool and hired a consultant engineer for the technical review of infrastructure projects. The tool was piloted for four verifications. This is an area that could be developed further in future.
DFID-S to actively disseminate findings with other donors, NGOs and government as appropriate.
For the SDF, UN JPLG and the SSF programmes that have multiple stakeholders, DFID-S ensured that all partners were involved through the full cycle of the verification process and this strengthened the ownership, utility and action with respect to verifications finding.
DFID-S and IBTCI to better communicate to multilateral organisations the objectives of the third party monitoring emphasising the mutual benefit to both parties.
DFID-S shared their approach and headline finding with the Risk Management Group (which multilateral, bilaterals and NGOs attend), the UN-Somalia’s Risk Management Unit and the UN country team’s monitoring and evaluation working group. DFID-S successfully influenced the World Bank to embrace and procure independent monitoring to verify programmes being supported within its Multi-Donor Fund.

Recommendations for future programmes
Cross portfolio lesson learning - The project performed well at meeting micro-programming needs but was not initially designed to provide systematic lesson learning over the broad portfolio. The ambition for and analytical power from the consolidated findings verifications, however, increased through the life of the project.
- The future project should explore how to strengthen cross portfolio lesson learning.
- Clarifying roles and responsibilities in the obligations and communications between implementing partners and the monitoring agent contracted by DFID-S. It would be worth to consider the following: (a) MoUs/contracts/introductory letter containing reference to the requirement to engage with independent monitors, outlining the purpose and processes.[11] (b) Clear protocol outlining expectations of DFID-S programme managers, the team managing the monitoring project and IPs (e.g. providing timely project info to monitors, outlining how PMs communicate with IP and monitors, how the monitor works with IPs and downstream sub-contractors and timetables for monitoring).
  [11] Processes would include ways of working in order to avoid issues such as IPs contacting monitoring interviewees in an attempt to influence them.

Expanded use of sectoral experts (as piloted in the engineering tool) could strengthen the quality of the verifications. A VFM assessment could assess the added value of such an approach.

Output Title	Baselines, results and impacts of interventions determined
Output number per LF		2	Output Score	A++
Risk:		Moderate	Impact weighting (%):	30
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes – previously 40%

Indicator	Target	Achieved
2.1 District-level Conflict and Security Assessments (DCSAs): Number of districts subject to UNDP governance and security surveys over the period of support.	50	62
2.2 Population Estimation Survey for Somalia: Number of statistical analysis/data collection exercises supported in Somalia that produce valid results (e.g. population calculation)	13	22[12]
[12] See annex 3 with complete list. This included: i) Nomadic data collection – population counted at water collection points; ii) Data entry, processing and analysis for the PESS top level results; iii) Publication of “Data for Better Tomorrow” including data on the population size and distribution, population distribution by sex and age, households and household size and a methodology section; iv) sampling frame developed v) analytical reports Methodology and assessment of data vi) Population composition vii) Housing and Household assets viii) Education characteristics ix)Population mobility x)economic xi) analytical reports from Somaliland and Puntland which will make the products to 22

This output significantly exceeded expectations.
Key Points
- OCVP significantly exceeded expectations by producing 47[13] District-level Conflict and Security Assessments (DCSAs) covering 47 districts and 15 comparative reports over the period Sept 2013 to March 2016.
  [13] Of the 47 DCSAs, 16 covered the 16 districts of Mogadishu
- The achievement of this target is impressive given the political, logistical and security challenges that data collectors face in the challenging context of Somalia. A further, unexpected challenge was the delays caused by UNDP which resulted in OCVP effectively losing five months of implementation time over the 30 month period (see section F).
- OCVP expanded its capacity to carry out DCSAs, including setting up offices in Garowe and Mogadishu. This enabled OCVP to easily deploy to any district across Somalia, prior to this, OCVP were only conducting DCSAs in Somaliland.
- The DCSAs gather community perceptions regarding service providers as well as accessibility and effectiveness of the services they provide. The reports cover service provision in four sectors: justice, governance, security and conflict.
- The reports are of high quality using survey methodology best practice to provide representative quantitative surveys of the district populations complemented by qualitative interviews. The well-presented, user friendly reports are all available online in PDF format ( at www.ocvp.org )
- In order to promote the use of this data (outcome 2) OCVP undertook 22 data dissemination workshops and 9 high level round table discussions with Somali government officials and civil society at district level.
- The capacity of OCVP has been strengthened by this project. The coverage and quality of DCSAs has significantly improved. Key contributing factors include: a UNDP contracted specialist based in Hargeisa for 12 months, the 5 in-house capacity building workshops[14] and the strong push for continual improvement from OCVP management.
  [14] Topics: Research, Organisational Management, Finance and Human Resources, Peacebuilding and Security Reforms, Qualitative Research
- IBTCI third party verifications on OCVP activities have been largely positive. They have scored well against a recent UNDP Capacity Assessment. In response to sustainability concerns, OCVP recruited a resource mobilisation manager and developed a funding mobilisation strategy.
- This review obtained limited direct feedback from users. Feedback received from DFID users included that the DCSAs may gain more use within DFID-S if they were shorter and more frequent. However, it is not clear whether the same view would be held by other users. That said, OCVP have piloted a much more rapid and subjective assessments of security and political conditions on the ground, which could be consolidated with the stronger aspects of its statistical approaches to the DCSAs.
- The Population Estimation Survey for Somalia (output indicator 2.2) exceeded expectations in terms of quality, number of products and associated capacity building.
- The PESS (in which DFID was the lead-donor) was completed and endorsed by the Federal Government and officially launched in 2015. This is a major achievement for Somalia given the politics of undertaking a survey and agreeing population figures across the administrations. The data has been disseminated within 12 months of data collection which compares well to other countries.
- Six survey publications[15] are available in hard copy and online http://analyticalreports.org/ . The publications are of high quality, presenting the data in a clear, user friendly format. The methodology constraints (e.g. sampling errors) are clearly presented, which aids users and can be used to respond to critique that this is not a census. These reports are providing much-need statistics against internationally agreed human development indicators.
  [15] Full Report, 6 thematic reports: Methodology, Demographics, Housing/Assets, Education, Mobility
- The project has been instrumental in strengthening the statistical capacity of national and regional government staff. PESS trained over 4,500 Somali women and men in mapping, validation, data collection, data entry and analysis.
- Data collection was a challenge due to insecurity, some selected areas were inaccessible. Where this was the case, satellite images were used to count the number of structures within the boundaries of the inaccessible areas. Satellite imagery was also used for validation and quality control. This represents an innovative use of technology to strengthen data quality.

Summary of responses to main issues raised[16] in previous annual reviews (where relevant)
[16] Full list of Annual Review Dec 2014 recommendations can be found in Annex 1
- PESS: DFID-S held direct discussions through the course of 2015/16 with the Ministry of Planning in both the Federal Government and Somaliland government on the priorities and processes for elaborating a national strategy for the development of statistics. In addition, DFID supported a wider discussion of statistical coordination and priorities among donors and Ministers of Planning.
- DCSA: DFID-UNDP-OCVP agreed a list of districts that would be priority for DCSAs in 2015/16 and comparative reports to ensure that DCSAs covered districts which had governance and security programmes being implemented.

Recommendations for future programmes
The dissemination of the Population Estimation Survey for Somalia could be further strengthened through innovative use of web based tools. UNFPA are exploring the use of DevInfo to disseminate summary data for users to manipulate. UNFPA are also exploring the use of the World Bank’s microdata cataloguing tool ‘NADA’ to make meta-data and micro-data available to researchers. These are both positive moves.

OCVP should continue to seek user feedback on their products and on user needs. It will be important that they maintain consistency and it is essential that they maintain comparability across districts. However, they should consider whether the current in-depth but low frequency approach is most suited to the analysis needs across a range programmes by DFID, other donors and the Somali authorities.

Output Title	Implementing partners capable of monitoring results and impact
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes – previously 25%

Indicator(s)	Target	Progress
3.1 Number of DFID Somalia governance, human and economic development implementing partners that have completed monitoring and evaluation capacity-building exercises	15	25[17]
3.2 Number of DFID Somalia governance, human and economic development projects that have log frames that meet DFID corporate guidance without substantial input from DFID staff (cumulative)	9	10[18]
3.3 Number of DFID Somalia governance, human and economic development projects that report fully on outcomes and outputs.	20	19[19]
[17] These are: UNDP Parliamentary Strengthening, UNDP’s Community Safety Programme, OCVP’s DCSA, UNDP’s A2J, UNDP’s CPP, KCC’s CDNA, UNDP JPLG, UNCDF JPLG, UNICEF JPLG, ILO JPLG, DDG’s GPC, DRC’s GPC, CARE’s GPC, CARE’s GPC, IRC’s GPC, DDG’s CSP, DDG SJSP, Horizons Institute SJSP, ASI’s SSF, ASI’s PRPD, RAADE (SSF), UNOPS Police Stipends, Sahan Police Stipends, Handicap International Promoting Inclusive Elections, Internews Somaliland Elections.
[18] The 15 log frames, supported by IBTCI, which meet DFID corporate guidance includes: 10 in the Governance and Peacebuilding portfolio (UNDP's Parliamentary Strengthening, OCVP's DCSA, UNDP's A2J, UNDP's CPP, KCC's CDNA, UN's JPLG, DDG's CSP, DDG/HI's SJSP, ASI's SSF (Results Framework), UNOPs/Sahan's Police Stipends, Internews' Somaliland Elections). 3 in the Economic Growth portfolio (DAI’s PIMS, Mott MacDonald’s SDF, and Mott MacDonald’s ESRES). 2 DFID Business Cases (the Rule of Law and SHINE business cases).
[19] DFID Somalia have gone through 2 rounds of annual reviews and PCRs with most scoring an overall score of A or A+ since October 2013. PCRs and/or ARs completed include, i) Core State Functions Programme (3); ii) Somalia Stability Programme (3); iii) Accountability Programme (2); iv) Somalia Monitoring Programme (2); v) The Health Consortium for the Somali people (2); vi) Joint Health and Nutrition Programme(2); vii) Somaliland Development Fund (1); viii) Promoting Inclusive Markets (PIMS) in Somalia (1); ix) SEED (1); x) Somaliland election support (1); and xi)Engagement in National Processes from State and Effective State Administrations (1).

This output met expectations. IBTCI provided technical assistance (TA) to implementing partners to strengthen their log frames and monitoring and evaluation systems. The majority of TA was provided to programmes within the Governance and Security team portfolio. In the final 18 months the TA expanded to support Human and Economic Development pillars. Given that this was a new approach to strengthening M&E across the DFID-S portfolio, the targets that were set for the project were realistic rather than stretching. Despite exceeding the target on 3.1 the output has been scored an A because the TA support was mainly focused on log frame strengthening with limited support to theory-of-change reassessments.

Key Points
Technical assistance was provided to IPs on a demand-led basis. There was limited demand from the majority of DFID-S partners. It is not clear whether this was due to lack of awareness (of the assistance available or of the potential for improvement), or a reluctance to engage. Hence it was predominantly reliant on DFID advisors/programme managers to encourage IPs to engage. Significant examples of this work support included support to both the Somaliland Development Fund and the UN Joint Programme for Local Governance to re-examine the intended results and assumptions of their programme, to deliver updated results-frameworks and to agree practical tools and processes to collect evidence of results, with all implementing agencies and donors participating in the process and approving final products. Since the overall technical assistance offer was demand-led, its promotion and up-take was constrained among some implementing partners. Despite low demand initially, demand did increase significantly over the course of the project.

- IBTCI provided various types of M&E support to DFID-S Business Cases, Programmes and teams, as well as to primary implementing partners and sub-partners. After DFID-S portfolio and log frame mapping was completed (May 2015) IBTCI gained a more accurate understanding of where and how its technical assistance was being used, both in the DFID-S structure and in the DFID programme management cycle.
- This mapping activity provided a clear understanding of how all levels of DFID-S portfolio M&E frameworks/log frames align with IP frameworks. This should form an integral part of the planning in phase 2 to ensure alignment across the portfolio at all levels.
- Partners that did engage with TA provided positive feedback. Most of the TA was provided to strengthen log frames[20]. There is clear evidence that log frames across the portfolio have been significantly strengthened which should lead to improved assessments of progress at annual reviews and improved programme delivery (the latter being an intended impact of the programme).
  [20] Exceptions included: a comprehensive, annual capacity assessment (OCVP); In-depth M&E “assessment” of OCVP project and organization; UNOPS and Sahan’s preparation for 2015 Annual Review; and development of M&E Officer ToRs, and a Capacity Assessment tool and methodology for Horizons Institute.

Summary of responses to issues raised in previous annual reviews (where relevant)
Extending support beyond log frames was a recommendation in the previous annual review. IBTCI developed an M&E technical assistance menu but very few partners requested support on any aspect of M&E outside of log frame development or revision. The next phase of the programme would benefit from strengthening M&E support overall.

The previous annual review highlighted the need for further log frame guidance. IBTCI shared log frame best practices with DFID-S teams that requested technical assistance as well as providing support to teams and key implementing partners in applying best practices within specific projects. The best practices are also included in the final Lessons Learnt report (March 2016) submitted by IBTCI.

Recommendations for future programmes
The next phase of SMP (DFID-S working with our contracted monitoring agent) should create a log-frame quality assessment tool and use it to assess the quality of selected log frames in the DFIDS portfolio and structure the support from just being demand-driven but need identified as well. This would help build on the alignment mapping activity (see above).

DFID-S should explore ways in which teams can be incentivised to engage with TA, in order to strengthen M&E across the portfolio. It is likely that engaging all projects may result in less effective TA, as resources may be spread too thinly. An alternative approach could be to target TA at projects based on a range of criteria such as performance, delivery mechanism, log frame quality (see above), level of investment, project risk, results expected and geographical scope.

Output Title	Governance and peacebuilding information collated, analysed, packaged and presented
Output number per LF		4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Target	Achieved
4.1 Number of analytical and lesson-learned reports produced and presented to the DFID-S Governance and Peacebuilding team	6	10[21]
[21] They include: 3 meta-analysis presentations, fiduciary risk, lessons learnt document, nomination strategy paper, how to note, deep dive to specific programmes i.e. 2 for SSF and Health

The delivery of results against this output naturally increased over time as more data, more pointed questions and more robust analysis emerged from the programme. Increasing amounts of data and DFID-S’s ability to analyse robustly these big data-sets from TPM allowed for the clearer identification of systemic performance issues and options to redress them. With repeat surveying of district conflict and security assessments, officials and civil society actors were able to discuss more objectively peacebuilding progress and challenges, particularly paying attention how differing experiences of distinct groups through time in terms of access to justice, security and human development could be better addressed.

Key Points
- The development of a set of data collection tools and templates for different types of verification (construction/rehabilitation/procurement, event, tender, technical assistance, engineering) increased efficiencies of project design and allowed for cross portfolio meta-analysis (see output 4).
- Cross-portfolio lesson learning is viewed as highly useful for the office. This project was initially limited in what it could provide as this was not identified as a primary objective of the project; as time progressed, however, the project highlighted the additional value that could be leveraged from data, analysis and discussions across the portfolio. The fiduciary risk analysis based on TPM, for example, helped to focus more objectively on specific risks that needed to be gripped in the portfolio.
- Thematic and sector learning is important in order to take the project beyond the simple verifications which tend to focus on ‘fixing’ singular issues. Lessons could potentially be transformative to the delivery of programmes.

Summary of responses to issues raised in previous annual reviews (where relevant)
None

Recommendations for future programmes
Whilst the project delivered what was expected, the demand for cross portfolio lesson learning is high and the future programme should capitalise on this.

The strengthening of the lesson learning component could be used as a means to bring IPs together to share lessons and to learn from others’ experiences.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance - UNFPA
Cost driver	Action taken
Staff	UNFPA used locally available expertise, from both Kenya and Somalia. International experts were only considered in very limited cases and for short durations particularly to act as quality control for the process.
Training & forum	Forums for discussing pertinent issues were held within Somalia except in cases that they required senior officials from the three authorities to agree on a common standard. In such situations meetings were held in one of neighbouring countries (Uganda, Ethiopia or Djibouti) which grants easy access to nationals from Somalia in addition reasonable conference costs.

Economy: PESS was delivered at a low cost per household ($35 per household) and represented exceptional value for money. Typical household surveys can range for $300 per household (as in the case of Young Lives Research Study) to $460 (the average unit cost per household of 13 surveys conducted by the World Bank at 2013 prices).Costs were managed down by using a simplified survey instrument, procuring enumerators via local networks and at rates that did not distort the local market, and by setting-up effective data-entry and cleansing processes that reduced costs from poor data management.

Efficiency: The model UNFPA used to deliver both PESS and the analytical report involved hands-on coaching, leveraging the local statistics staff, training them and deploying them to accomplish a task. This meant UNFPA did not recruit many expensive international experts to collate and analyse data but worked with the locally available resources to undertake the task. In addition, this enhanced the capacity of the statistics departments in Somaliland, Puntland and the federal Government without necessarily having a project solely devoted to capacity building.

Effectiveness: Delivering PESS was a major achievement. The PESS data is being drawn on to make development plans and investment decisions by the Somali authorities and international donor community more evidence-driven and hence enhancing the likely value for money of the $1.3bn in development and humanitarian aid that Somalia receives annually. Whilst it is it difficult at this stage to quantify, it is clear that there will be a long-term benefit stream from the PESS in terms of: (a) improvement in resource allocations by better links to demographic information; (b) improved targeted and more appropriately designed development interventions; and (c) enhanced accuracy of future demographic, economic and poverty surveys that are built on the PESS sample frame.

Key cost drivers and performance – UNDP
Cost driver	Action taken
Data collection	Due to security challenges even local Somali staffs require security to move to parts of the country that is not their resident area/region. OCVP opened offices in Garowe and Mogadishu and recruited staff who would easily access these areas with less cost and less security threats.
Data Analysis and dissemination	UNDP recruited UNV who built the capacity of OCVP staff in-house and quality assured the DCSA products before they were published.

Economy: UNDP contracted OCVP (a local organisation) to undertake the District Conflict and Security Assessment). By the end of the programme OCVP had utilised $1,491,385 (about £ 932,116 at an exchange rate of 1.6) to deliver 62 DCSA’s (47 DCSA’s and 15 comparative), including their management and operational cost. Savings on the administrative cost were modest, with UNDP management of the programme and relationship with OCVP accounting for 32% of the total value of this project component. Whilst this level of administrative overhead is less than other UN joint programmes (such as the JPLG), future options for supporting data-collection and analysis of local security and governance conditions should consider private sector options.

Efficiency: Employment of staff that would easily access various regions allowed for speedier completion of DCSAs and the QA process. Although there was several months’ delay during implementation, OCVP was able to recover time through concurrent deployment of research and survey teams.

Effectiveness: Policy briefs were developed from striking research findings and key issues identified by the district assessment reports and shared with policy makers in Hargeisa, Garowe, Baidao, and Mogadishu among other districts. 35 round tables, dissemination workshops and policy briefing sessions were held (including police and justice participation). Government officials were receptive to the information shared with them.
Key cost drivers and performance - IBTCI
Cost drivers	Actions
staff costs	DFID had a contract with IBTCI that limited DFID’s ability to negotiate post-contract on staff fees. Emphasis was put on pressing to obtain maximum productivity from the supplier’s staff over the course of the contract.
Verifications and assessments/reviews	IBTCI managed the cost drivers associated with verifications by geographically clustering verifications (only deploying to remote areas if there were sufficient number of verifications to share costs). IBTCI also worked with three different local organisations across regions. This helped reduce travel, operational and security costs as these organisations are familiar with local context. Over time they generated a standard rate per verification for different locations.
Office costs	Remote management of Somali sub-contracted verification partners. IBTCI did not establish an office in Somalia; they work through subcontracted Somali partners who have lower operational costs.

Economy: Clustering verification visits; outsourcing functions which could be done more cheaply externally, for example data collection delivered by local organisations. This resulted in a speedy and affordable process with final verifications totally 389 (33% ahead of the agreed logframe target). IBTCI utilised about 53% on staff costs (salaries) and 47% on delivering the project (verification and TA support).

Efficiency: Investing in cross-regional learning and training with Somali field monitors in order to strengthen the quality of verification reports; and ensuring the increasing quality of reports through quality assurance and monitoring by its Nairobi and International offices.

Effectiveness: Conducting meta-analysis of verifications across the DFID-S portfolio which in turn supported identification of strategic issues to improve DFID-S’s wider portfolio.

VFM performance compared to the original VFM proposition in the business case

Overall VFM performance is considered to be very good across the programme.
A number of the outputs exceeded expectations. The quantity of the outputs was often above target and the quality (verifications, PESS and DCSA) was high. Implementing partners approached the programme with a proactive attitude of improving quality and better meeting user needs.

The programme is effective. Data and evidence produced by this programme is being used by DFID-S, implementing partners, other donors and government. The PESS technical products and statistics have been used for government development planning (particularly the draft National Development Plan and also in the development of more specific statistical surveys (such as the World Bank’s high frequency survey which has now delivered poverty headcount figures for the country). This programme has shown great potential to inform policy and programming. A follow up programme should build on these foundations to have greater impact as there is scope for improved effectiveness going forward.

Assessment of whether the programme represented value for money
The programme represented value for money. The theory of change held well for this programme and as such a second phase should build on the strengths of the design used in this phase.

Quality of financial management during programme

In overall the £7.7 million was allocated and disbursed as follows:
Component	Component (T)	Budget – / £	Disbursed / £	Balance / £	To be refunded $	£ (ex. rate 0.7[22])
202984-101	Third Party Verification for Somalia -IBTCI	2,623,405	2,623,405	0	0	0
202984-102	Somalia Population Estimation Survey Project - UNFPA	1,400,000	1,400,000	0		0
202984-103	Third Party Monitoring and Evaluation -IBTCI through USAID	923,174	923,174	0	0	0
202984-104	Observatory: Measuring Peacebuilding and Governance in the Somali Regions	1,500,000	1,500,000	0	172,787	129,072
202984-105	Results Adviser Programme Funded	142,421	141,037	1,385
202984-106	UNFPA - Post-PESS Capacity Development for Statistics in Somalia	1,111,000	1,111,000		171,803	128,337
	Total	7,700,000	7,698,615	1,385	344590	257,409
	Total balance				258,794
[22] https://www.oanda.com/ see screenshot attached as annex 4

Spend by output	As per business case	Actual spend £
TPM and M&E (output 1,3 &4)	3,890,000	3,546,578
District Conflict & Security Assessment (output 2)	1,500,000	1,404,083.4
PESS(output 2)	2,310,000	2,389,263
Results Adviser Programme funded	0	141,037

IBTCI: £3,546,578.5 was contracted as a result based contract. This ensured the implementing partner delivered as per the deliverable schedule because payments were tied to specific milestones. It was an efficient way of delivering.

UNFPA: £2,512,000 MOU’s major milestones were (i) delivering the PESS headlines (ii) in-depth thematic analysis reports. This ensured we did not disburse funds which would not be needed immediately. Due to the project’s technical and political complexity, some milestones were delayed, e.g. the first launch of the PESS headline figures. Some ancillary activities were not fully finalised resulting in an unspent balance of $171,802.88 (0.7 ex. Rate £128,337) that will now be refunded to DFID.

UNDP through OCVP: £1,500,000 MOU was to facilitate district level surveys on governance. £1,404,083.4 ($2,190,458) was spent on district data collection, analysis and publishing the findings and capacity building. 62 district conflict and security assessments and comparative reports were produced. Due to UNDP staffing gaps, their administrative budget was not exhausted, hence $ 172,787 (0.7 ex. rate £129,072) will be refunded to DFID.

IBTCI / Date of last narrative financial report	This was an output based contract no progress reports. milestones were received
Date of last audited annual statement	5518087 month– 01/05/ 2016
UNFPA / Date of last narrative financial report	5392287 / July-December 2015
Date of last audited annual statement	5479216 - 30/04/2015[23]
UNDP / Date of last narrative financial report	5480420 / 31/03/2016
Date of last audited annual statement	5361069 – 2015 & 5345853 30/11/ 2015
[23] The Quest number has audits for ministries of planning for FGS, SL & Puntland

E: RISK (½ page)

Quality of risk management over the life of the programme

The overall programme risk rating is moderate.

Management of risk during the life of the programme has been active and effective. Security risks were mitigated by preparing and working with Somali authorities for field surveying and using robust analysis of satellite imagery for inaccessible areas. DFID and UNFPA’s emphasis on open cooperation and joint data-analysis among technical experts on PESS related data has ensured its visibility, use and ultimate acceptance (both formally and tacitly by the Federal Government and regional authorities in Somaliland and Puntland).

Risks around independent monitoring steadily decreased as the programme became more strategic, transparent and cooperative in pursuing verifications. The overwhelming majority of partners participated in an increasingly cooperative manner in submitting to scrutiny, resolving identified problems and adjusting their project management practice as appropriate. DFID-S advisers and programme staff were increasingly able to understand, use and influence change from the verification reports, and participated fully in lesson-learning events on the collective monitoring findings. Support to M&E and independent monitoring did not displace implementing partners’ focus on broader results. In fact the M&E support increasingly helped partners to think more critically about their desired results and the theories of change upon which they were built.

The programme increased the frequency of programme management meetings with the key implementing partners in the last 18 months of the programme to ensure that all intended outputs were delivered and that partners’ reporting was more regular and thorough. In addition, due diligence on each implementing partner was undertaken by DFID-S and an organisational and financial management review of OCVP was conducted by UNDP, with the findings being shared with DFID-S. The recommendations from the due diligence were followed-up either through the quarterly meetings and through the partner updates.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

- IBTCI (verifications and M&E support). Initially IBTCI was contracted through USAID under their Monitoring and Evaluation Programme for Somalia (MEPS). DFID-S signed an arrangement with USAID which enabled DFID to benefit from the existing USAID infrastructure and share costs. One year after the arrangement MEPS closed and therefore USAID formally communicated their intention to discontinue the arrangement. DFID-S requested a waiver to directly contract IBTCI on the basis of ensuring continuity of service. Despite the change of contractual arrangement, IBTCI remained on track. The contract with IBTCI was output based with a high degree of technical collaboration with DFID-S enabling them to exceed the output targets and producing some helpful analyses that were not envisaged in the original contract ( such as an fiduciary risk exposure assessment based on an analysis of over 2,200 interviews with beneficiaries).
- UNDP/OCVP (District Conflict & Security Assessments -DCSAs). OCVP conducted DCSAs across Somalia and exceeded expectation irrespective of the very difficult environment. UNDP did not fully meet its obligation of supporting OCVP both administratively and through implementation. There were delays in implementation due to several contract lapses between UNDP and OCVP. A lot of time was lost due to these lapses and the recruitment of inexperienced consultants during the 1st year of implementation. Staff continuity was a significant issue for UNDP and DFID should note this as a potential risk for future programmes with UNDP (which continues to have workforce planning challenges).
- UNFPA (PESS). The sensitivities around population data resulted in a delayed political consensus on the headline figures. However, the official government launch of the PESS report paved way for various stakeholders to use the data especially in important documents such as the National Development Plan. The subsequent thematic reports have been well-received, are being used by government and development partners, and are reducing the rhetoric of lack of data for Somalia. The team acknowledges there was a lot of capacity enhancement for the statistics department at the Federal government, Somaliland and Puntland which enabled a technically credible survey to be conducted.
- Overall. The DFID-S team responsible for SMP programme was able to ensure that targets in the log-frame were met, and in some cases exceeded the targets. The Delivery plan was used effectively to help track progress, monitor delivery with implementing partners and ensure compliance issues were not forgotten.

Performance of partnership(s)
- The relationship with IBTCI over the period has been very productive. There was close engagement between the SMP team and the IBTCI team in Nairobi. They met regularly as need arose and quarterly to take stock of progress. IBTCI would submit verification reports and M&E assistance matrices as agreed in the contract.
- UNDP: The finalising of annual agreements with IP was delayed every year, resulting in a total of five months where OCVP staff were unable to officially work on the project and staff were without pay. In the recruitment of the initial technical consultant, UNDP failed to consult with OCVP, which resulted in an inexperienced UN Volunteer on the project for twelve months. Continuous change of staff in the UNDP team resulted in inconsistent reporting and strained communication between UNDP and DFID-S. UNDP has been poor at providing reports of progress on-time to DFID-S who often had to go directly to the downstream partner for reliable information.
- The relationship with UNFPA has been good. For the PESS, which was jointly funded, formal coordination and reporting was done through a technical coordination group. DFID engaged directly with UNFPA and had an opportunity to input into post PESS activities which included the thematic reports. UNFPA have been a proactive, transparent and technically-competent partner.

Asset disposal and value obtained by DFID
The team maintained asset registers throughout the programme as required. The asset register was updated bi-annually. A spot check on OCVP’s assets was conducted before the transfer request was approved. The register included all assets worth over £1000 and with life of over one year

- UNDP: The assets were donated to OCVP through the formal process as required by the smart rules. UNDP sent a request for donation to DFID to be allowed to transfer the assets to OCVP (Document quest number: 5385997), DFID-S Head of Office approved the transfer of ownership (Document Quest number: 5382410)[24].
  [24] UNDP: Quest Number 5385997 and 5382410
- IBTCI: some assets were donated and transferred to downstream partners. The disposal proposal articulates what will remain with IBTCI and what will be transferred to downstream partner. Request for transfer of ownership from IBTCI is quest number 544687 and the approval by DFID-S Head of Office is quest number 5444657
- UNFPA: The assets will be used by UNFPA under SMP II. This has been agreed by both DFID Somalia and UNFPA to allow continuing benefits and increased Value for Money from these assets.

Both UNDP and IBTCI committed to abide with the disposal guidance where they assured DFID that the items will be used for development purpose and they will be disposed of as per the IT Equipment disposal policy and in-line with EU Waste Electrical and Electronic Equipment (WEEE) Regulations.

G: CONDITIONALITY (½ page)

Partnership principles assessment -
Partnership Principles Assessments were not used in the management of this programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
A cross cutting evaluation of “DFID’s Approach to Remote Management in Somalia and North-East Kenya” was conducted in 2014 and is published online https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/405263/remote-management-somalia1.pdf. The Theory of Change appears to hold for this project. The data produced is informing DFID’s project adaptation (verifications) and broader donor planning (e.g. PESS). It is beginning to filter into national policies though this will have to be monitored over a longer time period in order to assess its impact on government policy making.

Monitoring progress throughout the review period
Each project partner had its own logical framework which fed into the overarching log frame which was used to monitor the programme. Each partner had systems in place to monitor these frameworks. The Senior Responsible Owner for the project regularly met with project partners to review progress. Financial progress monitoring was done both at programme level and at the individual agency level.

Beneficiary feedback
Feedback was obtained from a wider selection of beneficiaries[14] and was predominantly positive. The downstream Somali partners (OCVP, SORADI and CSD) provided very positive feedback on the programme. They all described how their organisation’s capacity had been significantly increased and their enthusiasm for the programme provides a strong indication that it will have broader reaching results beyond the timeframe of this review.

Project Completion Report Methodology
This PCR was conducted by Philip Cockerill a Statistics and Evaluation Adviser for Middle East and North Africa (MENAD) supported by Leo Thomas DFID-S Results Advisor and the programme team Hannah Chira and Maimuna Abdalla. The findings are based on a review of project documents (annual reviews, quarterly reports), project products (verification reports, verifications meta–analysis, PESS publications, DCSAs), partner websites and interviews[25].
[25] Interviews were conducted with DFID programme staff, DFIDS staff benefiting from verifications and M&E support, UNDP, UNFPA, IBTCI, OCVP, SORADI, UNJPLG, Central Statistics Department in Ministry of Planning.