Business Case

Summary Sheet

Title: Programme for Strengthening State Capabilities in India
Programme Summary: The UK through DFID will invest up to £4.5 million as Technical Assistance over up to five years to diagnose and strengthen capacity and capabilities of select Indian states and sectors. This programme aims to strengthen their governance, institutional, implementation and policy formulation capacity for better policy, programme implementation and achieve inclusive growth. / The programme will use a two pronged approach: / Component 1: Research and diagnostics assessment of select state and sectoral institutions through technical assistance. Partner with multilateral and non-multilateral development institutions to undertake rigorous state and sectoral capabilities and relevant policy environment assessments. Commission strategic policy research to address evidence gaps that can help state and sectoral players to strengthen institutions, policies and delivery mechanisms. / Component 2: Training, capacity building, delivery/implementation and other related support to state and sectoral institutions through direct technical assistance. The programme will provide bespoke capacity building support in collaboration with non-multilateral development partners (including private sector firms, think tanks, other specialised bodies, civil society organizations (CSOs) etc.).
Programme Value: up to £4.5 m		Country/ Region: India
Programme Code:	Start Date: December 2018	End Date: December 2023
Overall programme risk rating:	Moderate
Vault Number:

Intervention Summary

Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver (1/2 page max)

India, though one of the fastest growing major economies of the world, is still burdened with inter-state disparity in institutional capacity and resulting governance and economic performance. State wise contribution to India’s growth story is vastly divergent. For example, five states account for around one-half of India’s GDP. There is also significant inter-state variance on poverty, with States plagued by bad governance and poor rule of law (like Uttar Pradesh, Bihar and Madhya Pradesh) accounting for highest levels of extreme poor. Pockets of extreme poverty also exist in more developed states such as Maharashtra.
[note] Maharashtra, Tamil Nadu, Uttar Pradesh, Karnataka and Gujarat
[note] RBI data

DFID in India has a number of programmes that are using the DevCap (returnable capital) instrument along with Technical Assistance (TA) to address market failures and growth barriers across India. DFID India is exploring the possibility of deploying further DevCap and TA to address barriers to growth and build markets for the poor across India. However, it understands the reality that states in India are extremely diverse in terms of their institutional capacities and resources. This affects the rate and extent of capital absorption as well as the effectiveness of the interventions. Therefore, developing state capacities, strengthening state and sectoral institutions and systems are of primary importance and may be an efficient and effective way to ensure better development outcomes and effective way of using UK taxpayers’ money.
[note] http://ams/Data/CountryDashboard.aspx?country=IN

To that purpose, the UK through DFID India will invest up to £4.5 million as Technical Assistance over up to five years to strengthen institutions, enhance governance, institutional, policy making and implementation capacity in select states and sectors. The programme will use a two pronged approach:
Component 1: Research and diagnostics assessment of select state and sectoral institutions through technical assistance.
Component 2: Training, capacity building, delivery/implementation and other related support to state and sectoral institutions through direct technical assistance.
The overall outcome envisaged is strengthened capacity of institutions in select states and sectors to develop and implement good policies and practices. The expected impact of the programme is strengthened overall governance, enhanced income and livelihood outcomes and inclusive growth in the selected states and sectors.

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
The programme is consistent with the UK’s International Development Act. The use of multilaterals as one of its key implementing partners for the programme would help ensure that UK’s (one of the largest donors to the multilateral system) core support to the multilateral system is more effectively and strategically spent in India. The programme would also engage with Indian and UK think tanks and Universities, CSOs, private sector firms and other specialized bodies to ensure a comprehensive support to bridge evidence gaps and enhance capacities of state and sectoral institutions. The programme does not involve financial aid to Government of India. It is in line with DFID India’s ongoing Country Development Diagnostics, the agreed strategy for DFID India and would contribute to the implementation of DFID India’s current and future Business Plans as well as development cooperation funded by other HMG departments in India.

What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
The programme directly contributes to the ‘Deliver value for money and efficiency’ target of the SDP by enhancing institutional capacity of states and key sectors and enabling them to better implement policies and programmes and bring in more transparency and accountability in their operations.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
Yes. The programme is coherent with the wider international community and partner government requirements. By strengthening state governments’ and sectoral institutions’ capability, the programme interventions aim to ensure that DFID India is more effective in its future engagement with Indian states.

Has the programme considered working with HMG Departments and accessing cross-HMG funds?
The programme will collaborate with other HMG departments (like Her Majesty’s Treasury (HMT), Foreign and Commonwealth Office (FCO), the National School of Government International (NSGI) etc.) and leverage their expertise.

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
The programme will complement existing and planned interventions across DFID India. It would particularly synergize with DFID India’s ongoing programmes like the Economic Policy and Prosperity Partnership and Global Partnerships Programmes.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
Demand from states and sectoral institutions will drive the choice of states and sectors. Other filtering criteria, as indicated in the ‘Management Case’ section, will help choose interventions funded by the programme. It does not commit to any particular state/sector/theme at the outset. The programme will have annual and mid-term reviews and would appropriately respond to changing priorities and contexts in discussion with the government counterparts, key partners and DFID India’s internal strategic focus.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
The key risks anticipated in this programme could be due to lack of demand from states and sector ministries/departments, lack of impact, sustainability and lack of DFID and UK gains. The following are the related mitigation measures:
- DFID will partner with multilaterals to ensure that the state and sectoral engagements are strategic and rigorous. DFID and the multilateral partner would engage in dialogues with the highest level of state and sectoral stakeholders. The resulting engagements will be in response to demand from states and sectors – addressing the risk of insufficient buy-in
- State and sectoral engagements will be demand driven, complemented by policy research, just-in-time implementation support and bespoke training and capacity building support. The three pronged approach will ensure that expected impact is maximised.
- To address the risk of inadequate DFID and UK gains, a set of criteria will determine which interventions receive funding under this programme. DFID India leadership will be part of the programme’s Steering Committee to ensure UK and DFID gains are part of the ‘line of sight’.
  [note] The Management Case lists out the set of criteria.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
The programme will be suitably branded to reflect the UK’s contribution. DFID India will be an equal partner in the engagement with the multilateral(s) with veto power on where and how to engage. A Communications Adviser from DFID will advise on the positioning and size of logo in the communication materials produced.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
The programme will be appropriately quality assured through annual and mid-term reviews.

Does the SRO and team have the capability and resources to deliver this programme?
Yes. An SRO, a programme manager and a team of senior advisers (as part of the Steering Committee), will manage the programme. DFID India will be accountable for delivery of the programme and has sufficient budget allocation for the same.
Strategic Case

While India has successfully halved the share of extreme poverty as share of the population (from 45.9% in 1993) in the last two decades, it is still a country with one of the largest absolute number of poor worldwide. Despite being one of the fastest growing economies of the world, it ranks 130 out of 189 countries on the UNDP’s Human Development Index (2018). A key characteristic of India’s unique growth story is the vastly varied growth and economic performance across its states. Significant disparities in institutional capacities across sectors and states exist and lead to disparity in the achievement of outcomes between and within states. While several parts of the country have made tremendous progress on socio-economic indicators, other regions are lagging behind.

For instance, a recent (2017) state level Ease of Doing Business survey by Niti Ayog on more than 3,000 Indian companies, reports that it takes an average of 156 days to get land allotted from the government in India. However, companies in Himachal Pradesh report that it takes only 28 days for them, while those in Chhattisgarh take 213 days. Similarly, the time it takes to get an electricity connection varies significantly at the national (52 days) and state levels (31 days in Karnataka and 95 days in Odisha).
[note] http://niti.gov.in/content/ease-doing-business-enterprise-survey-indian-states

As per the Public Affairs Institute’s Governance in States of India ranking, West Bengal ranks among the top 5 large states in terms of managing crime and violence, but secures the last position among the 18 large states in terms of fiscal management. Odisha ranks high in terms of implementation of Business Reforms Action Plan but secures the second lowest rank (only after Delhi) in terms of transparency and accountability.
[note] http://www.pai.pacindia.org/#/2018

As per the latest Social Progress Index (that analyses the social progress across Indian states for the period 2005–2016), Chhattisgarh attains a higher social progress score (56.69) than Rajasthan with a NSDP per capita (28,373) lower than the latter. Manipur and Maharashtra have a difference of two points on social progress when the former belongs to the category of low-income states while Maharashtra has one of the highest per capita incomes in the country. Despite not achieving highest NSDP levels, Kerala achieves the highest score on social progress, while Goa and Delhi, the richest states (measured by NSDP), perform worse.
[note] https://socialprogress.in/social-progress-initiative/

The World Bank’s latest Country Partnership Strategy in India (2018-22) reiterates that given the key role of government in India’s political economy and to strengthen India as a middle income nation, it is essential to make its public institutions more competitive. This will ensure that policy reforms and input investments better translate to last mile service delivery and development impact.

The UK’s development cooperation policy with India has shifted away from a focus on basic service delivery towards accelerating inclusive economic development. The guiding principles of leaving no one behind, providing support for economic, fiscal and financial market reform, improving access to finance, improving business environment, investment and innovation potential and value chain development have been some key features of this strategic shift. Post this transition, DFID in India has developed a portfolio of programmes that are using the DevCap instrument along with TA to address a host of market failures and growth barriers in some states in India. Until recently, DFID India has been focusing mainly on the poorest states, but has through its experience realized that limiting itself to particular states limits the scope of impact that DFID envisages in India. There is a need to choose states for strategic interventions taking into account their readiness and on-ground demand as well as potential for systemic impact.
[note] http://ams/Data/CountryDashboard.aspx?country=IN

1. In view of the significant institutional capacity constraints at the state and sectoral level leading to varying and often sub-optimal development outcomes, DFID India understands the need to support all tiers of government and the key sectors in strengthening institutions, improving transparency and accountability mechanism and enhancing effective programme and policy implementation capacity. To this effect, this programme will support interventions to systematically diagnose capacity constraints in selected state and sectoral institutions and providing bespoke capacity building and implementation strengthening support. DFID will leverage expertise of all major development stakeholders for this.
2. To achieve its goal, the programme will have a two pronged approach:
- Component 1: Research and diagnostics assessment of select state and sectoral institutions through technical assistance. Partner with multilateral and non-multilateral development institutions to undertake rigorous state and sectoral capabilities diagnostics and relevant policy environment assessments. Commission strategic policy research to address evidence gaps that can help state and sectoral players to strengthen institutions, policies and delivery mechanisms.
- Component 2: Training, capacity building, delivery/implementation and other related support to state and sectoral institutions through direct technical assistance. provide bespoke capacity building support in collaboration with non-multilateral development partners (including private sector firms, think tanks, other specialised bodies, civil society organizations (CSOs) etc.).

Learnings from these activities will inform DFID India’s current and future programmes as well as development cooperation funded by other HMG departments. The overall outcome envisaged by the programme is strengthened capacity in select states and sectors resulting in improved service delivery and better policy making and implementation. DFID will disseminate the findings and institutional strengthening approaches to other states to enhance shared learning and uptake. The expected impact of the programme is strengthened overall governance, enhanced income and livelihood outcomes and inclusive growth.

Component 1: Technical assistance for research and diagnostics assessment of capacity of select state and sectoral institutions
States in India are vastly diverse in terms of their economic status, wider dimensions of well-being and institutional capacity. Lack of capacity is holding India’s growth potential back. DFID India works with a mandate of economic development, poverty reduction, creation of jobs and that of shared prosperity between UK and India. Given the mandate, developing a deeper understanding of states’ and sectoral capacities, identifying state and sector specific barriers to growth, and providing bespoke institutional development and capacity building solutions will strengthen the development impact DFID India envisages to attain through its diverse set of financial instruments and in diverse set of states and across sectors. These benefits will also potentially accrue to other non-participating state authorities and development actors as the analysis will be available in public domain.

1. The component aims to identify key obstacles that hinder development in select states and sectors. It will cover three types of activities:
  [note] Namely – inadequate capacity for long term strategic planning and policy analysis; inadequate capability for economic and social policy making and delivery; poor human resource management capacity leading to sub-optimal work performance; poor financial and project management capacity, in particular procurement, which leads to weakness in delivering policies and poor monitoring and results framework for assessing impacts of policy implementation (in particular for measuring equitable benefits – inclusion impact).
  1. In-depth and demand driven institutional diagnostics
  2. Policy analysis, research and evaluation to fill evidence gaps and strengthen policy making capacity of state authorities and sectoral institutions
  3. Sharing of findings to ensure inter-state learning

Through these above activities the programme will enhance DFID’s understanding of state and sector level barriers to growth, develop capacity of select institutions to deepen our partnership with India. DFID India envisages collaboration with different types of development partners for different strands of work – to ensure leveraging the right scale of rigor and expertise.
[note] In particular, partnering with multilateral organisations will help strengthen a joint approach to address growth barriers and market failures in India –reduce duplication of efforts and enhance additionality. It will also help ensure that UK’s core support to the multilaterals (UK being one of the largest donors in the multilateral system) is effectively spent in India.

Apart from assessments of state and sectoral capacities, there will be demand driven research and evaluation to bridge evidence gaps on key growth obstacles. This will include (but will not be restricted to) policy and evidence gaps on cross sectoral issues like women’s economic and social empowerment, disability, norms etc. DFID India will therefore forge partnerships with Indian and UK Universities and influential think tanks to commission demand driven thematic research to bridge evidence gaps, undertake evaluations of policy reforms and enrich the overall evidence base. In addition, policy practitioners will provide advice on key state specific and sectoral challenges. The string of activities under Component 1 will support studies, analysis, discussions etc. for identifying opportunities for Devcap and technical assistance as part of DFID India’s future pipeline of programmes.

An indicative list of tasks covered by this component is:
- Analysis of state’s drivers of growth, poverty reduction measures and fiscal condition –These assessments will help to identify key priority sectors the state should focus on and related policy, investment and institutional constraints that should be addressed to accelerate inclusive growth.
- State capability assessments – These assessments will particularly focus on understanding a state’s barriers to effective implementation of programmes. This will happen through an extensive process of dialogue, assessments and analytical work in collaboration with the state government.
- Political economy assessments – This activity will support the continuous process of collecting insights and analysis of political economy assessments for promoting sector policy and institutional reforms in the state.
- Strengthen sectoral policy and institutional reforms – Based on the priority sectors identified in consultation with the state governments and line ministries, DFID intends to extend support to deepen the engagement in identified sectors. This will include sector specific assessments of policies, governance, institutions, investments, financing and service delivery issues in the selected states. There will be assessment of opportunities for leveraging private finance. Select states will receive support to develop sector strategies and action plans. There will be wide dissemination of good practices from other states and global experience.
Component 2: Provide bespoke training and related support to state and sectoral institutions to strengthen their capacity.
The goal of the component will be to address evidence based capacity gaps of state governments and sectoral institutions, helping enable the institutions to function optimally and maximize their effectiveness for achieving development goals.

Based on the state capability diagnostics, sectoral evidences and policy research under Component 1; Component 2 will respond to demand driven training, capacity development and implementation support needs of states and sectors. It will do so by leveraging UK expertise (for example in areas of governance reforms) as well as expertise of other resources commissioned from other stakeholders/key partners and convening high-quality international technical advice. DFID will partner with key think tanks and research institutes like Niti Ayog, UK Behavioural Insights Team, Centre for Policy Research, Jameel Abdul Lateef Poverty Action Lab (J-Pal) etc. and other specialized bodies like the UK’s National School of Government International (NSGI) for this strand of work.
[note] NITI Aayog in partnership with Prime Minister’s Office has emerged as a major policy innovation hub since 2015 - focusing on areas such as AI, Health delivery, delivery for aspirational districts, Ease of Doing Business.

Apart from providing capacity building support, DFID will also work with state authorities and sectoral institutions to improve resource utilisation, targeting, monitoring, and evidence based planning of their current commitments. Particular focus will be on departments responsible for the development of vulnerable population (women, minorities, disabled etc.). For example, this component will also pilot use of innovative behavioural change models like ‘nudge theory’ to enhance capabilities in state and sectoral institutions – notably with respect to effective implementation of policies. For this, the programme will leverage UK and global expertise on behavioural insights for institutional strengthening and policy implementation.

Gender Equality
The programme complies with the Gender Equality Act of 2014. When addressing barriers to economic growth in states and sectors, the programme will have a clear focus on strengthening capacity of institutions to identify and implement gender and disability responsive policies and practices. Gender and disability mainstreaming will gain support from the state and sector capacity assessments, policy research and capacity building activities. Appropriate indicators will also be included in the logframe to capture the effect of the programme on helping state authorities achieve greater gender equality in development outcomes.

Terrorism and Bribery
Like all other DFID intervention, this programme must comply with relevant legislation, including the Terrorism Acts 2000 & 2006, Proceeds of Crime Act 2002 (Part 7) Money Laundering Regulations 2007, Terrorist (Asset Freezing etc.) Act 2010, the Bribery Act 2010, and the Al-Qaida (Asset Freezing) Regulations 2011. This will require DFID, and its delivery partners, to: (a) identify our partners (including robust due diligence) and ensure they are aware of their responsibilities in relation to the legislation; (b) keep appropriate records; (c) establish internal procedures and controls to mitigate risks; (d) prepare guidance and training sessions to increase staff awareness; and (e) report any contra indicators to the relevant authorities.

Given the nature of the programme, there is low risk of misappropriation of funds for terrorist purposes. The partnership with the Multilateral(s) is a key mitigating factor, as it will facilitate the opportunity to work closely with the state and national governments, strengthen institutions and delivery – boosting transparency and accountability. For example, at the UK Anti-Corruption Summit in May 2016, the World Bank Group reaffirmed its commitment to confront corruption as a core development issue wherever it exists and to support integrity in public sector institutions. Diversification of partners further mitigates the risk.. For all non-multilateral partners, due diligence will be done as a key risk mitigating factor.

## Appraisal Case

The appraisal case considers three feasible options for the implementation of the programme.

Option 1: Undertake all two components through private sector firms

Mechanism: Under this arrangement, DFID India would engage with one or more private consulting firms and think tanks to help strengthen its outreach to states, engage in institutional capabilities diagnostics and deepen partnerships. It would also commission independent research and evaluations to understand barriers to growth in select states. Based on the analysis, DFID would fund bespoke training (either using UK expertise or commission from the market) to state and sectoral institutions.

Pros and Cons: This approach would allow DFID to choose private sector partners it would want to engage. However, limited multi-disciplinary capacity of private companies, lesser degree of credibility (than multilateral partners) with public sector and state authorities and potential delays because of DFID’s competitive procurement processes are some of the key factors that render this choice as sub-optimal.

Option 2: Undertake both kinds of interventions only through multilaterals

Mechanism: Under this arrangement, DFID India would collaborate with one (or more) multilateral organisations and strategically engage with states and sectors to diagnose and strengthen capacity of institutions. With the multilateral partner, DFID would engage in diagnostic assessments of growth barriers in states and key sectors therein. Based on the evidence, DFID and the multilateral partner would develop capacity development solutions, either for short term trainings or for the long term through a programmatic approach.

Pros and Cons: Collaborating with a multilateral organisation will ensure a greater buy-in from the states due to proven track record of DFID and multilateral agencies in providing expertise. However, the scale and volume of operations of multilateral organisations also poses a concern that the partnership will be driven by the multilateral’s strategic goals in the country and DFID India will remain the secondary partner. It might also restrict DFID’s ability to contract specialists for specific and follow up activities (like draw on expertise from UK’s Behavioural Insight Unit for strengthening institutional capacity and providing training).

Option 3: Engage with a host of development partners (multilateral organisation(s), Indian and UK Universities and think tanks, CSOs, specialized bodies and the private sector)

Mechanism: In this option, DFID India would collaborates with multilateral organisations, influential UK and Indian Universities and think tanks, CSOs, private sector firms and other specialist bodies to diagnose and strengthen state and sectoral institutional capabilities. Like option 2, along with the multilateral partner, DFID would engage in systematic diagnosis of partner states and sectors’ barriers to growth and identify areas of improvement. In addition, research and evaluation exercises will cover key thematic areas. Based on the evidence, DFID and the multilateral partner would develop capacity development solutions, either for short term trainings or for the long term through a programmatic approach.

Pros and Cons: Under this arrangement, DFID India would not only partnering with multilateral organisations to strengthen its strategic partnership with states, but would also address evidence gaps in policy and reforms by drawing from a wide pool of experts from Indian and UK academia, research institutes, CSOs, specialist bodies and private sector firms. This multi-pronged approach would enhance government buy-in and bolster DFID India’s position as an equal partner. It further allows for UK academia and think tanks to share knowledge and contribute to policy and institutional reforms in India, paving way for future stream of UK benefits.

The above options have been analysed and scored using the Multi-Criteria Analysis. The three options have been qualitatively evaluated for their ability to deliver Primary and Secondary benefits as per the indicators below.

Impact Area		Indicators
Primary Benefits	Partnership Impact	Better development partner coordination resulting in higher additionality / Strategic engagement with states leading to stronger, demand driven partnerships for DFID India
	Governance Impact	DFID's ability to respond to demand driven governance, institutional and policy reforms to influence and enhance state capability
	Programme Delivery Impact	DFID’s ability to implement programmes on ground with enhanced and sustainable development outcomes due to enhanced delivery capacity of state and sector institutions
	Sectoral and Policy Impact	DFID's ability to influence key sectoral reforms and demonstration through pilots
Secondary Benefit		Build the partnership between India and the UK by strengthening G2G engagements, institutional and business links and by building markets of interest to UK investors and businesses

The Primary Benefits are weighed 75% and the Secondary Benefit is weighed 25%. Based on qualitative assessment of each benefit vis-à-vis each option, a score has been provided on a scale of 1 to 5 (1 being the worst score) – as shown in the table below.
[note] ICAI report on Prosperity Fund

	Primary Benefits					Secondary Benefit
	Partnership Impact		Governance Impact	Programme Delivery Impact	Sectoral and Policy Impact
Benefits	Better donor coordination resulting in higher additionality	Strategic engagement with states leading to stronger partnership	DFID's ability to respond to demand driven governance and policy reforms to influence and enhance state capability	DFID’s ability to implement programmes on ground with enhanced and sustainable development outcomes due to enhanced delivery capacity of state and sector institutions	DFID's ability to influence key sectoral reforms and demonstration through pilots	Build the partnership between India and the UK through strong G2G engagements, build markets of interest to UK investors and businesses
Options
Private Sector Only	2.5	3	4	3	3.5	3.5
Multilaterals Only	4.5	4.5	4	4	4.5	4
Mix of development partners	4.5	4.5	5	5	5	5

Based on the above analysis, Option 3 with DFID partnering with multilateral agencies for strengthening state partnerships, commissioning thematic research from Indian and UK Universities, think tanks, private sector, CSOs and specialised bodies for policy influence, capacity development and knowledge sharing - represents the best way forward.

Theory of Change for Preferred Option
The programme focuses on strengthening capacity of select Indian states and enhances their effectiveness in policy making, implementation and achieving inclusive growth and development outcomes by strategically collaborating with key development partners. The chart below summarizes the Theory of Change of the programme:

Input	Interventions	Output	Outcome	Impact
Up to £4.5m TA / DFID Resource: / SRO / Sr. Advisers / Programme Manager	Engagement with states and sectors to understand drivers and barriers of inclusive growth, fiscal condition, governance readiness (meetings, diagnostic analysis, research, seminars)	Strategic engagement with states leading to stronger partnerships	Strengthened institutional systems and capabilities (planning, management, policy making, implementation capacity) in select states and sectors	Strengthened overall governance, enhanced income and livelihood outcomes and inclusive growth
		Identify key areas of governance, institutional and policy strengthening in states and across sectors
		Evidence driven and informed pipeline development for DFID India
	Commission demand driven research and evaluation to inform policy and institutional and implementation capacity strengthening	Enhance DFID's ability to respond to demand driven governance, institutional and policy reforms to influence and enhance state capability / Enhance DFID's ability to influence key reforms
	Provide capacity development trainings and associated activities to states and sector institutions	Enhance capacity of state administration based on gaps identified from the diagnostics and research

Commercial Case

Procurement/commercial requirements for the intervention
DFID proposes to provide up to £4.5million Technical Assistance over a period of up to five years through two delivery channels – i) up to £2.5m to partner with multilateral organisations; ii) up to £2.0m directly managed by DFID to partner with think tanks, Universities, CSOs, specialised organisations, private sector and other capacity development partners.

Partnership with multilateral
1. DFID’s partnership with a multilateral will amplify the UK’s reach and influence across states in India, help strengthen state capacity and ensure spending of UK taxpayers’ money more effectively. The multilateral organisations have their own area of expertise and the 2016 Multi-lateral Aid Review in 2016(MAR) confirmed that DFID’s multilateral partners add real value for the UK.
2. The global reach, technical capacity, breadth of funding instruments, and convening and influencing role of multilaterals make them central to UK development objectives. They are good at delivery against challenging objectives and manage risks well.
3. Engagement with multilaterals will use the Externally Financed Output (EFO) framework. The EFO(s) will be backed by detailed Concept Notes that will be screened using the list of criteria (as listed in the Management Case) to ensure the programme supports interventions that maximize DFID’s current and future work plan. There will be a robust governance structure in place for effective management of the EFO along with clearly defined deliverables. The EFOs will funded in two tranches and linked with delivery of agreed outputs.

Outputs delivered though third party contracting
1. DFID will manage the partnerships and award contracts through competitive processes. DFID will consider framework contracts for better value for money where appropriate.
2. Majority of contracts with non-multilateral development partners will likely fall under the OJEU limit. In these cases DFID India will undertake limited competition amongst at least three suppliers whose specialization and track record match the requirements of the task. DFID India will also review the possibility of contracting a managing agent to manage some or all of the contracts with non-multilateral suppliers. For interventions expected to cost above the OJEU limit, DFID India will follow OJEU procedures. In both cases, DFID India will liaise with and take advice from DFID’s PCD and the Commercial Adviser assigned to DFID India.
  [note] Particular attention will be paid to the supplier’s ability to comply with DFID’s safeguarding policy.
3. The programme will ensure effective financial systems and cost control measures are in place and transparent cost effective, competitive procurement processes for sub- contractors. Part of the funding will be linked to deliverables, aligned with logical framework output milestones.

How does the intervention design drive VfM for DFID?
1. EFO(s) with a multilateral organisation (MO) will include Concept Notes which will specify activity areas, expected deliverables and expected timelines.
2. Procurement by MO if any will be as per its principles of: best value for money; economy and efficiency; fair and open competition, transparency and accountability in the procurement process.
3. DFID will oversee the Technical Assistance partnerships with non-multilateral partners. DFID will run an open competition to allow leading international/UK organisations with niche expertise to partner with Indian counterparts for enriching the policy and governance evidence base to strengthen state capacity.
4. DFID will consider using one of its commercial framework agreements for the competition. The Terms of Reference will be in sync with the expected deliverables, focusing on the product or output required and encouraging suppliers to propose innovative and workable solutions. Following contract award, DFID will then develop an performance agreement (output based to the extent possible) to drive VfM.
5. The principal means by which DFID will seek to maximize the impact of each pound spent towards the cause of poverty reduction and shared prosperity is as follows:
- Good selection of interventions
- Focus on economy, efficiency and effectiveness. This includes ensuring VFM in inputs, improving the way inputs are converted to outputs and focusing on how outputs contribute towards the broader development objectives.
- Ensuring a focus on strategic issues and regularly reviewing performance and adjusting – to maximise the potential for impact.
- Using competitive processes to drive VFM in delivery of inputs by suppliers
The following indicative list of variables will measure the programme’s VfM:
- Economy: Estimate the main cost drivers of the programme and ensure costs and fees are well negotiated and within agreed frameworks.
  - Personnel-hours per £ per output
  - Cost per study
  - Cost per seminar/workshop
  - Cost per training provided
  - Daily cost of technical advisers contracted by DFID
- Efficiency: Estimate delivery of outcome vis-à-vis inputs
  - Cost per state or sector engagement/partnership developed/strengthened
  - Cost per stakeholder reached through programme interventions
- Effectiveness: Estimate delivery of impact vis-à-vis inputs
  - Cost per inclusive policy/programmes the programme supports/strengthens
- Equity:
  - Choice of sectoral and policy interventions will be driven by the goal of maximizing reach to and impact on the poor and vulnerable communities

1. The above list is indicative. The proposed VfM indicators will be modified and customised through the course of the programme’s inception and implementation phases to match actual interventions.
2. As a policy engagement, it is inherently difficult to quantify value for money at the effectiveness level. The key for the programme to be impactful and have robust value for money will be to choose the interventions well. Therefore choice of interventions will be based on the criteria proposed in the ‘Management Case’. Moreover, if the inputs purchased are cost effective, the programme should represent good value for money. In addition, the proposed strategic partnerships offer DFID India a set of platforms that have the potential to reduce costs overall.

How do we expect the market place will respond to this opportunity?
1. We expect a significant market response due to: a) overall TA availability and b) the nature of the assignment likely to provide successful bidders with significant additional business opportunities.
2. India has a strong supply of local consulting/policy research capacities. The intervention design will seek to engage local consultants with a demand for limited international/UK specialists where it is felt that local capacities would benefit from this.

How does the intervention design use competition to drive commercial advantage for DFID?
To draw in the best quality of supplier at competitive prices, DFID India will appropriately design the interventions. TA contract(s) will largely be output-based with payments to the supplier linked to achievement of agreed milestones to ensure effective supplier performance. Adoption of a quality and cost based selection (QCBS) system of evaluation will also ensure VfM.

What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?
1. Key cost drivers: Though the contracts will be Output based to enable DFID to minimise risk and incentivise the consultancy to perform efficiently a detailed breakup of the cost would be analysed to benchmark the cost. The key cost elements will be professional fees of consultants both technical and administrative; administrative costs such as travel, office rents, other office expenses and the costs of sub-grants or sub-contracts that the main contractor may have to issue to address emerging needs of the technical support.
2. To ensure competition, DFID India will use appropriate benchmarks against cost of each intervention. Contracts will embed applicable safeguards and sanctions to ensure satisfactory performance. Achievement of deliverables/outputs of the contract will enable release of payments. This will ensure sufficient management oversight including early sight of risks and other issues.

How will the contract be structured and how will supplier performance be managed through the life of the intervention?
1. Interventions with multilaterals, while managed through EFOs, set against detailed Concept Notes. The Concept Note will lay out clear deliverables. Periodic expenditure/utilisation reports will help monitor the expenditure. Payments under the EFO(s) will be released in two tranches – release of the second tranche being contingent on satisfactory spend of the first tranche.
2. Interventions by non-multilateral partners will be against a clear set of Terms of Reference, key deliverables and milestone will be developed, discussed and agreed with suppliers. Performance will be managed by reviewing the outputs delivered by the supplier against the output schedule agreed in the contract. Payments to supplier will be on reimbursable basis, subject to satisfactory delivery of agreed milestones. The work plan will include mutually agreed milestones; these will be monitored on a monthly or, preferably, quarterly basis.
3. The suppliers will submit reports on a quarterly basis providing summaries of progress against the work plan deliverables and Logframe outputs. Regular review meetings and interactions with the agency will ensure satisfactory performance.

## Financial Case

A total of up to £3 million will be allocated to Component 1 – ‘Address evidence gaps and undertake diagnostic assessment of the readiness of systems and policies across states and sectors by using expertise of multilateral organisations, Indian and UK think tanks and Universities’. A total of up to £1.5m will be allocated for Component 2, namely ‘Provide bespoke training to states to build capacity of their human capital and strengthen state and sectoral institutions’. The following is an indicative summary budget. The programme SRO (or their Line Manager) will have flexibility to reallocate funds among the components and between years based on state and sector demand and insights gained during programme implementation.

Component Description	Year 1 (2018-19)	Year 2 (2019-20)	Year 3 / (2020-21)	Year 4 / (2021-22)	Year 5 / (2022-23)	Total
Component 1 (up to)	£1.25m	£1.5m	£0.25m	0	0	£3.00m
Component 2 (up to)	£0.25m	£1m	£0.25m	0	0	£1.5m
Total (up to)	£1.5m	£2.5m	£0.5m	0	0	£4.5m

Adequate funds are available in DFID India’s Aid Framework, following the approval of DFID India’s Operational Plan 2016-2020. As the programme will be for up to five years –any funding beyond the current Operational Plan period will be subject to adequate funding being available in the subsequent DFID India Operational Plan.

Any capital assets procured under the TA support of this programme will be treated in accordance with DFID procedures and declared to DFID on an annual basis. Should assets remain at the end of the programme; a disposal strategy will be agreed with DFID.

Payments to multilaterals will be through EFOs. Funds under EFO mechanism will disburse in two tranches. The remaining funds will be disbursed to service provider(s) who will be procured in line with DFID’s procurement policies.

What is the assessment of financial risk and fraud?
As one of the implementing partners will be Multilateral organisation which already have robust governance policies in place including managing financial risks and fraud, the risk of financial or fraud risk associated with this kind of partnership is very limited. DFID will carry out Due Diligence for other service providers. DFID India will choose suppliers who can comply with DFID’s safeguarding policy. There will be stretching targets and support to encourage stronger compliance, closer to international standards.

How will expenditure will be monitored, reported and accounted for?
For the multilateral partner(s), an EFO agreement will be signed and the expenditure will be monitored based on the expenditure/utilisation reports received. An output based work plan, linked with payments to milestones/outputs will be agreed with other service providers on an annual basis and progress will be measured and monitored quarterly. Payment will be made against acceptance of milestones. These will include clear calculation of performance-based payments to against the agreed monitoring framework.

Management Case
Management Arrangements for Programme Interventions:
1. This section outlines the governance and management arrangements to strengthen the programme’s ability to deliver. The primary stakeholders for the programme will be DFID, state governments, national government ministries and departments, multilateral organisation(s), Indian and UK Universities, think tanks, other specialized bodies, CSOs and private sector firms. Within DFID, the team leader, senior advisers, policy manager and a programme manager will have oversight of the programme.
2. Given the multi-state, multi-sectoral and multi-thematic scope of the programme, it will be important for DFID to pool together its in-house expertise for market engagements, screening of proposals and overall oversight of the programme outcome and impact. The programme Senior Responsible Owner (SRO) will in the initial year spend approximately 20-30% of her/his time on ensuring the programme is effectively implemented. Senior Advisers will be drawn upon on to provide steer on specific aspects of the programme and will spend about 10-20% of their time in the initial year of implementation. The Programme Manager will be required to spend around 15-20% of her/his time in the first year of implementation. There will be a Steering Committee (consisting of members from DFID India Leadership Team) for this a Programme.
3. When working with multilaterals (under component 1), a three tier governance structure will be followed.
- Multilateral Steering Committee (SC): This will consist of the Country Heads (or Deputy Heads) of the two organisations. The role of the SC will be to provide overall strategic oversight and direction to the partnership and set out the guiding principles of the same.
- Coordination Committee: This will constitute of senior advisers/senior management from both organisations and DFID’s programme SRO. The committee will meet quarterly and provide general oversight on on-track delivery of the programme. The members will jointly liaise with government and other stakeholders and discuss broad sector trend, strategy, opportunities, challenges that will shape the programme activities and outcomes in the medium to long term.
- A Working Level Body: This will constitute of technical advisers/specialists from both organisations who will coordinate monthly to work together to undertake, commission, supervise and quality assure tasks under each strand and sign off on reporting and coordinate on joint missions, meetings and dissemination events.
Selection Criteria for Proposals funded through this Programme
The following evaluation criteria will ensure proposals funded under this programme align with DFID’s objectives:

Is this support driven by a demand from the state government or sectoral institutions? / The proposed engagement with any state or sectoral institution will be demand driven. A formal written request would be of particular preference. DFID will have a definite veto power on the choice of states and sectors to engage in, that will be funded by DFID money. DFID personnel will also decide on the nature of DFID’s engagement – driven by DFID’s comparative advantage, additionality and value for money.
Does the intervention fit with DFID and HMG priorities? / While DFID India would not be interested in only engaging in the poorest states, it would be keen on taking up states that have market failures and growth barriers that DFID India is well positioned to address. Activities with positive gender and disability benefits would be favoured, as would activities that, directly or indirectly, in the short, medium or long term, help build and strengthen the partnership between India and the UK.
Does the UK and DFID have a comparative advantage? / In addition to programme funds, the UK brings a host of expertise to the table- public finance management, public investment management, Public-private partnership (PPP) experience, use of innovative financial instruments for development, frameworks for appraisals and other international expertise. Areas of interventions that would allow for an optimal use of the UK comparative advantage would be favoured.
Is there a clear line of sight/theory of change? / The proposed intervention(s) seeking support through the programme should have a clear theory of change as to how the activity(ies) would enhance the effectiveness of implementation of an identified policy and/or programme.
Does the support have a focus on gender mainstreaming and/or disability focus? / Proposed interventions with a line of sight on gender mainstreaming and/or with a focus on addressing the needs of the disabled would be favoured.

Monitoring and Evaluation
The programme logframe would be the basis of performance monitoring. Programme progress would be monitored quarterly based on agreed work plans and on a bi-annual basis by the Programme Steering Committee. DFID would also undertake annual reviews in line with standard DFID requirements against the programme logframe.
Risks and Mitigation
The overall risk of the programme is ‘Moderate’, post mitigation. The key risks and mitigation approach are listed in the table below:
Risk Description [Risk Category]	Gross Risk			Mitigation Measure [Residual Risk]
	Likelihood	Impact	Gross Risk
Due to upcoming national and state elections, state governments may be reluctant to take on state capability assessments and other reforms [External]	Possible	Major	Major	DFID along with the multilateral partner would reach out to the highest level of government stakeholders in key states and seek a buy-in at the earliest. In state interventions would be agreed upon and would be a demand driven process. The engagements will be timed to avoid pre-election/election periods. [Moderate]
There is a risk that the programme supports small scale/ad-hoc initiatives that are not subsequently scaled up [Delivery]	Unlikely	Major	Major	By carefully screening sub-projects and through the governance arrangements, DFID would track progress and deliverables. Payments will be linked with agreed milestones. [Moderate]
Programme interventions do not lead to envisaged impact [Delivery, Reputational]	Unlikely	Major	Major	By carefully screening sub-projects and through the governance arrangements, DFID will systematically follow up with government counterparts and implementing partners on progress and uptake of interventions and recommendations. [Minor]
There is a risk that in the partnership with the multilaterals DFID is not engaged with as an equal partner, adversely impacting the goals for outcome and impact. [Delivery, Reputational]	Possible	Major	Major	DFID will set up a firm governance structure for engagement with the multilateral partners. Working collaboratively across the spread of the partnership will be non-negotiable. [Moderate]