Annual Review - Summary Sheet

Title: English In Action
Programme Value: £50,000,000.00		Review Date: 20th May 2015
Programme Code: 107480	Start Date: May 2008	End Date: March 2017

Summary of Programme Performance
Year	2009	2010	2011	2012	2013	2014	2015
Programme Score	2		2	A+	A+	A+	A+
Risk Rating	Low		Low	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

The EIA programme continues to achieve innovative and quality teacher education at scale, exceeding targets in terms of numbers of teachers trained and pupils reached. The programme is now scaling up training for schools and teachers in more socio-economically disadvantaged regions.

Recommendations made during the last annual review 2014 placed a particular emphasis on the need for the project to improve procedures for the gathering and dissemination of project data. This has been done with a view to better presenting evidence in national and international contexts of the impact of the project’s innovative approaches to teacher development, English language teaching, and educational broadcasting. Overall, the project has addressed 20 out of 22 recommendations made in 2014 review. The remaining two are in progress.

The project has put in place quasi-experimental research mechanisms to assist in gathering evidence relevant to the new batch of teachers studying as part of the scale-up process. EIA has developed strategy documents for Advocacy and Institutionalisation & Sustainability covering the final 18 months of delivery. Specifically, these look at approaches for ensuring the uptake and continued use of project outputs within the project lifetime and beyond.

Summary of recommendations for the next year

Teacher professional development and sustaining the approach
The Advocacy Strategy recognises that in order to embed the 5 key elements[1] of teacher professional development into the Government of Bangladesh (GoB) systems, each element may need to be dealt with separately because GoB may not be able to implement all at once. However international evidence[2] shows the importance of the 5 elements working together to create an effective professional development package, and the project should communicate this and support GoB to work towards that in the future. EIA should develop clear activity schedules by July 2015 to
[1] 1. Professional development aligned with classroom practices, with follow up support and monitoring. 2. Peer support (formal and informal peer support). 3. Head Teacher support. 4. Alignment with curriculum and assessment (school and external). 5. Offline AV materials and enabling technology. Curriculum expertise and lesson modelling is provided through the AV materials, used in teacher and facilitator development activities carried out with peer support at local meetings and in school.
[2] Pedagogy, Curriculum, Teaching Practices and Teacher Education in Developing Countries. DFID. Dec 2013.
  1. integrate the five elements into relevant department or units within the GoB system
  2. work to embed each component within existing or emerging GoB activities in the sector
  3. encourage the uptake of EIA methodologies and components by donors engaged in the sector, with a view to better ensuring the embedding and mainstreaming of these methodologies within the education system. Where required, EIA should also agree with DFID any mechanisms of support they can provide.
EIA to look at parallel strategies for potential placement of EIA materials and methodologies within the next primary sector programme (post PEDP3), in secondary sector design, and in other educational sectors including TVET and adult education.

Undertake a budgetary audit to help identify resources available for undertaking all tasks associated with institutionalisation, sustainability, and advocacy by August 2015.

Align Advocacy Strategy tasks and outputs with wider objectives across the Institutionalisation & Sustainability Strategy by August 2015.

In relation to each task associated with the I&S and Advocacy Strategies, develop a detailed framework for delivery of required services June 2015 to Dec 2016, specifying in each case:
        - Staged activities to undertake
        - Schedules and timetables for delivery
        - EIA implementing staff, including roles and responsibilities for co-ordinating activities and delivery of outputs
        - Required budget and resource allocation

Media and Adult learning component (BBC Media Action)
All EIA project partners (BMB Mott McDonald, Open University, BBC Media Action, DFID B, GoB) should ensure a clear mutual understanding of the future use of BBC Janala materials, both by private sector partners within Bangladesh and in other contexts.

Research, Monitoring and Evaluation
EIA to continue to consolidate available data, and prioritise existing research plans towards development of evidence that is key to supporting Phase IV objectives for the institutionalisation and sustainability of the programme, including the publication of evidence-based research briefings aligned with the Phase IV Advocacy Strategy.

Value for Money and asset management
- EIA to develop a plan to implement selected VfM enhancements, implement these over the first 3 to 6 months of the next review period and build capacity to monitor these so that performance can be assessed at the next review.
- EiA, DFID and GoB to agree a process to hand over the assets to the Government in an appropriate way, while ensuring/promoting that the equipment will remain available for the teachers.

A. Introduction and Context

Outline of the programme
English in Action works to improve levels of English language with the ultimate aim to aid economic growth. This has been implemented through two main components - a school based programme aimed at bringing about change in English teaching and learning in primary and secondary schools and an adult (15+) learning programme that uses electronic and print media e.g. television, website, mobile and newspaper to teach communicative English. In order to improve the quality of student learning in English, teachers have to find ways to improve the teaching and learning practices in their classrooms. EIA is designed to help teachers do this through a one-year programme of teacher professional development. EiA is a £50 million programme being implemented over nine years (2008-2017). It is a discrete project under a multi donor funded and government led sector-wide primary education programme i.e. Third Primary Education Development Programme (PEDP3).
Expected Results / EIA expects to increase social and economic inclusion for more than 25 million Bangladeshis by developing English language skills for school pupils and adult learners over the lifetime of the project. The project also expects to contribute to the economic growth of Bangladesh by providing English language as a tool for better access to the world economy. EIA has taken this forward through the development and delivery of inclusive national programmes. The beneficiaries are adults in urban and rural communities, teachers of English, and school-aged children. Progressive and innovative approaches to teaching and learning ensure that all beneficiaries have the opportunity to develop English as a practical skill. / By the end of the final year of the programme (2016/17), the following logframe outcomes are expected to be delivered: / Increase in the proficiency in communicative English among the population of Bangladesh measured objectively against recognised international frameworks. / Increase in employer satisfaction (with employees’ communicative English). / Increase in motivation for learning and using English among the population of Bangladesh / Increase in use of English language media products. / Bangladesh Context / English in Action was designed in response to a request from the Government of Bangladesh: English language skills are in short supply. This is as a result of two main factors -poor quality English teaching in schools and limited access to high quality English learning materials for students and adults. Few people under fifty are confident, fluent English speakers, and English is the most commonly failed examination subject at the secondary certificate level. Lack of English language skills is regarded as a constraint to economic development. For example, employers state that job applicants and employees lack English language skills necessary to work effectively. A pre-appraisal mission recommended that the problem be addressed at scale, through a project that would have substantial reach and impact. Previous shorter term, smaller scale interventions were not fully successful and results were not sustained. Reasons for this included the lack of scale, the lack of extended timeframes, and an absence of focus on adult learners. / The context has not changed significantly and the original activities and assumptions are still appropriate. Updated research carried out for EIA by Euromonitor (2013) found that candidates with good English skills were felt to have a 30-50% higher chance of being employed in the formal sector and were likely to receive an income premium of 25-30% compared to candidates without good English skills. / PEDP III is a successful mechanism of GoB and donors agreeing on objectives and pooling funds. However, the ‘quality impact’ is not convincing as far as it is known (very little is measured on outcome level, e.g. learning outcome of the large in-service training effort in PEDP3 are unknown). Therefore the synergies of EIA (which has proven a positive impact on classroom practice) with PEDP3 have great potential, primarily in in-service training, but also in classroom monitoring, quality assurance, availability of classroom materials, peer support, head teacher engagement, etc. This potential needs to be used to the fullest extent, spanning into ‘PEDP4’.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

Indicator	Milestone	Progress
1a. Increases in English language competence (ELC) among the population of Bangladesh (teachers & students) at Trinity GESE level[3]:	Primary students: / 5% increase over baseline at level 1 or above / 5% increase over baseline at level 2 or above / Secondary students: / 10% increase over baseline at level 2 or above / 5% increase over baseline at level 3 or above	Primary students / 34% increase over baseline at level 1 or above / 5% increase over baseline at level 2 or above / Secondary students: / 12% decrease from baseline at level 2 / 6% decrease from baseline at level 3
1b: Increases in ELC among the population of Bangladesh (adults)	N/a (no milestone and planned assessment this year)	N/a
2: Employer satisfaction (with applicants’ / employees’ communicative English)	Applicants not having necessary EL skills: 40% / Employees having necessary EL skills: 76%	38% / 92%
3: Motivation for learning and using English among school population of Bangladesh	N/a	N/a
4: Use of English Language news & media	N/a	N/a
[3] GESE: Trinity Grade Scale is developed based on the common European framework of language testing, developed to assess students’ English Language ability objectively. It is a 12-grade scale. Attainment levels for the first four grades on the scale is as follows: - Trinity Grade 1 – requires knowledge of greetings and some basic personal information - Trinity Grade 2 – speakers can offer and respond to short, simple questions, requests and statements relating to personal details and situations - Trinity Grade 3 – speakers can exchange basic everyday information, asking and answering questions using simple sentence patterns - Trinity Grade 4 – speakers can talk about a prepared topic, asking and answering questions about it

In accordance with logframe design, English language competence (ELC) testing of students in 2014 (post-EIA intervention) was compared with a pre-intervention baseline established in 2010, with particular focus on performance at two criterion grades for primary (students at or above grade 1 and at or above grade 2) and two criterion grades for secondary (students at or above grade 2 and at or above grade 3) on the Trinity GESE scale.
The results indicate that the English in Action (EIA) intervention has led to an improvement in primary students’ performance which substantially exceeded the annual milestone as laid down in the logframe.

That secondary students learning outcomes at criterion grades are well below baselines implies they are likely to have started substantially below baseline. Also EiA, as a result of its social inclusion strategy, targeted students and teachers in the poorest Upazilas and their baseline skills may have been lower than those included in the baseline. A pre-test / post-test methodology is necessary to avoid the problem of comparing post-test results to a baseline from a different population and time. A quasi-experimental study is being implemented in 2015-2016 to a design agreed with DFID Bangladesh and informed by review and guidance from South Asia Research Hub (SARH) and Specialist Evaluation and Quality Assurance Services (SEQAS).

A new quasi-experimental research will focus in particular on the socio-economic status of the target audience, their levels of access and exposure to English language through broadcast media and so on and will help provide further analysis on teachers and students’ classroom practices and English language competence, comparing EIA treatment schools with control schools.

The results of the Employer Satisfaction survey indicate positive outcomes in this indicator area for the review period. However, it is important to note that there has been no analysis of the specific English language skills required by employers in various sectors, and so available data is based on purely on employers’ perceptions. With this in mind, these results may be partly influenced by changing perceptions of English language usage and skills in Bangladesh, possibly as a result of the popularity of various BBC Janala media broadcasts. For instance, as English language competence is traditionally associated with both high status and high levels of education, there may be a greater general appreciation, including among employers, of English as a functional, context-specific set of skills attainable by the general population.

In light of EIA’s expanding involvement in TVET, research into the sector-specific English language skills required for particular work roles would be highly beneficial in informing ongoing initiatives for English language skills provision within the vocational education sector. Also, in light of EIA’s expansion of service provision to populations in more rural, isolated and economically-deprived regions across Bangladesh, it is also important to note an absence of data relating to the large informal employment sector in Bangladesh, where many of the poorest are employed or self-employed. Again, this would be a valuable area for future research within the context of ELT for employment in Bangladesh.

Overall output score and description

The overall output score is A+. Results have exceeded targets in all outputs. Output 2 has come to an end so there are no further targets.

	2015 Milestone	Achievement
OUTPUT 1 (Primary)
O1a: Reach	Teachers: 7,500 / Students: 540,000	8,463 teachers (12.5% additional) / 653,000 students (20.5% additional)
O1b: Implementation	Student talk: 20% / In English: 60%	27% student talk in a lesson / 94% of that talk is in English
OUTPUT 2 (Adult Learning)
O2a: Reach	N/a	N/a
O2b: Perception	N/a	N/a
OUTPUT 3 (Secondary)
O3a: Reach	Teachers: 5,000 / Students: 2.08M	5,455 teachers (8% additional) / 2.22M students (7% additional)
O3b: Implementation	Student talk: 20% / In English: 60%	24% student talk in a lesson / 92% of that talk is in English
OUTPUT 4 (RME)
O4a: Knowledge products	N/a (no milestone set for 2015)	N/a
O4b: Research dissemination	2 conferences	9 conferences, 2 papers, 2 chapters
OUTPUT 5 (I&S)
O5a: Strategic partnerships	Education partnerships: 3 or more / Existing media partnerships: continue	5 / Continued
O5b: Policy seminars	1	1 was planned. But not achieved due to political unrest.

Key lessons

A recent DFID-funded literature review[4] identified four key findings that characterise teacher development programmes[5], which have positive results in improving teaching practice and learning outcomes. EIA exemplifies how all the key elements can be implemented in a large-scale school-based teacher development programme. However, EIA adds a fifth key element – offline audio-visual materials and enabling technology; this fifth element is also consistent with the findings of a later DFID funded literature review of educational technology[6].
[4] Westbrook, J., Durrani, N., Brown, R., Orr, D., Pryor, J., Boddy, J., and Salvi, F. (2013). Pedagogy, Curriculum, Teaching Practices and Teacher Education in Developing Countries: Final Report. Education Rigorous Literature Review, EPPI-Centre, Social Science Research Unit, Institute of Education, University of London. p60-64
[5] Peer support from other teachers; follow-on support and monitoring; support from head teachers; alignment of teacher development with teachers’ needs and context, and with student curriculum and assessment.
[6] Power, T., Gater, R., Grant, C., and Winters, N. (2014). Educational technology topic guide. Technical report, Health and Education Advice and Resource Team (HEART), Department for International Development (DFID), London, UK.

As set out in its Institutionalisation and Sustainability (I&S) Framework (doc ref 8.1), EIA’s dialogue with government policymakers is now not about ‘how EIA can be sustained’, but rather, how these key elements of effective teacher development, as exemplified by EIA, can be incorporated within government programmes in order to maintain and build upon improvements in the quality and equity of classroom practice.

The evidence reviewed above suggests that the school-based, peer-supported approach, with enabling technology providing offline audio-visual materials for professional development and classroom use, is capable of improving classroom practices at large scale. Further, that improved classroom practices have been consistently translated into improved learning outcomes.

Has the logframe been updated since the last review? Yes

Based to the 2014 annual review recommendations the logframe was updated during reporting period.

Output 1
- Indicator O1a – Milestone 2016 changed to 17,500 teachers (from 37,000) and target 2017 changed to 41,000 teachers (from 67,500 teachers). Across primary and secondary, the logframe reach numbers now match the GoB Revised Development Project Performa for EIA. Milestone 2016 and target 2017 student reach have been changed to reflect the new teacher numbers.
- Indicator O1b – Target 2017 for ‘student talk that is in English’ changed to 60% (from 70%), which is consistent with previous milestones, and there is no reason to suppose that the % will increase when operating at the largest scale.

Output 3
- Indicator O3a – Target 2017 changed to 10,000 teachers (from 9,000 teachers). Across primary and secondary, the logframe reach numbers now match the GoB RDPP. Target 2017 student reach has been changed to reflect the new teacher numbers.
- Indicator O3b – Target 2017 for ‘student talk that is in English’ changed to 60% (from 70%) to be consistent with previous milestones.

Output 4
Indicator 04a - Target 2017 is reduced to 5 (from 7) research reports and to 4 (from 6) research briefs.  Following DFID B advice (as further emphasised in the 2014 Annual Review) to undertake a quasi-experimental study in 2015, the project will not carry out the classroom practice and ELC studies on Phase IV cohort 2 (previously planned). Milestone 2016 is changed from N/A to 4 research reports and 3 research briefs to reflect the planned publication dates of reports.

The 2015 annual review proposes the following review to the logframe
Indicator	Proposed Change	Reason
Outcome Indicator OM1a: / Increases in proficiency in communicative English among the population of Bangladesh (teachers & students)	Change milestones for 2017 / Measurement of teacher English language proficiency (ELP) is ‘not applicable’ for milestone 2016 and target 2017	EIA evidence has shown over the years no obvious correlation between teacher and student ELP / International evidence confirms EIA evidence / Measuring teacher classroom use of English is not possible due fund constraint
Output 4 Statement: / Increased information available around improving English language competency	Amend output statement to: ‘Increased knowledge available around improving English language competency and teacher practice’	Clearer expression of project output
Output 5 Statement: / Strengthened capability of key organisations and professionals in the education and media sectors to adopt EiA approaches	Amend output statement to: / ‘Collaboration with key organisations and professionals in the education and media sectors to adopt EiA approaches’	Clearer expression of project output
Output Indicator O5a: / Number and extent of strategic partnerships with key organisations in education and EL media sectors; and number of sector professionals (broadcast and ELT) taking part in ELT media capacity building initiatives	Add to source / ‘DFID PSC quarterly reports’	Adds data source for extent of strategic partnerships
Outcome Indicator OM1a: / Increases in proficiency in communicative English among the population of Bangladesh (teachers & students) / Output Indicator O1b: / Implementation: The numbers of teachers using Communicative Language Teaching (CLT) approaches in their classroom practice / Output Indicator O3b: / Implementation: The numbers of teachers using Communicative Language Teaching (CLT) approaches in their classroom practice	Amend the milestones for 2016 and 2017 / Include note that ‘milestone 2016’ is to report on pre-test results of quasi-experimental (QE) study’ and that ‘target 2017’ is to report on post-test results of quasi-experimental study	EIA resources enable two evaluation studies to take place in Phase IV. Originally, study was planned in 2015 and in 2016 which would have assessed improvement against baseline collected in 2009. / Instead, drawing on 2014 AR feedback, a QE study (involving pre-test evaluation and post-test evaluation) has been designed in consultation with DFID. This will provide robust evidence of improvement between post-test, pre-test, intervention and control group. / The pre-test study in 2015 will be reported for AR in 2016 and post-test in 2016 will be reported in late 2016 / early 2017.

Impact Weightings

AR2014 recommended reviewing the impact weighting to reflect the end of component Output 2 in this final phase.

	Previous	Now
Output 1	25%	25%
Output 2	25%	0%
Output 3	25%	25%
Output 4	10%	25%
Output 5	15%	25%

## C: DETAILED OUTPUT SCORING

Output Title	Greater access to and use of EIA English classroom methods for primary school teachers and students
Output number per LF	1	Output Score	A++
Risk:	Low	Impact weighting (%):	25%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Reach / The cumulative numbers of teachers and pupils participating in English in Actions primary intervention	Primary teachers / 7,500 (50%/50% M/F) / Primary pupils / 540,000 (49%/51% M/F)	Exceeded / Primary teachers / 8,463 (45%/55% M/F) / Primary pupils / 653,000 (49%/51% M/F)
Practice / The number of teachers incorporating EIA approaches in their classroom practice.	20% of student talk in a lesson / 60% of that talk is in English	Exceeded / 27% of student talk in a lesson / 94% of that talk is in English

Key Points
EIA is designed to enable teachers to improve the teaching and learning practices in their classrooms, through a one-year programme of teacher professional development.

During the review period, the project significantly exceeded the achievement of targets on coverage of students and teachers as well as attainment of desired classroom practices for use of English. The coverage of students and teachers continues to show an upward trend in maintaining good gender balance on participation. Overall, the number of students reached is well above the milestone for the review period. This is particularly noteworthy as, firstly, the project covered some of the most deprived sub-districts where quality of education is particularly low; and secondly, these numbers were achieved despite 3 months’ disruption to programme delivery as a result of political unrest during the review period.

The achievement of scale-up can be attributed to a large extent to the further extension of decentralised approaches adopted at the level of sub-districts, leading to effective peer support at the school/ cluster level and the provision of regular follow up meetings. In addition, the m-learning (mobile learning) based ‘trainer in your pocket’ approach, facilitated through use of mobile phones, continues to be central to the uptake of methods and approaches in schools and classrooms. This model has led to reduced levels of input from core–trainers and English learning experts, leading to better value for money and the re-affirmation of the value of decentralised approaches to teacher development practices.

Focus group discussions undertaken by the review team with teachers at primary and secondary levels corroborated the data findings, with comments suggesting more interaction and speaking time for children in the classroom, and the substantiation of data evidence for increases in both student talking time and student talking in English. Talking time is measured through classroom observation study by researchers from Institute of education and research (IER). This is commendable when compared to traditional classroom situations where children have neither the opportunity nor encouragement to speak.

According to teachers in the focus group discussions, as a result of EIA methodologies and materials, children are more articulate, confident in class, and look forward to classes with EIA-trained teachers. Teachers also describe their own confidence and articulation as having improved, and some are now used as ‘ subject trainers’ on the regular government system training programs. This shift is attributed to the participatory and interactive approach to teaching and learning modelled by EIA in its AV (audio visual) materials.

A brief review of the materials generated over a period of time also suggests EIAs success in utilising state-of-the-art teacher development practice techniques in the development of materials. The materials are of high quality and conform to global best practices for the development of EL skills. An additional noteworthy factor of materials, more specifically of the audio–visual materials, is their authenticity and contextuality. All videos are shot in real classroom situations with practicing teachers, thereby making the promoted techniques appear more reliable and practical. In addition, it is reported that this clear localised contextuality also enhances the acceptability of these teaching approaches among government counterparts in schools across Bangladesh.

In general terms, the approach and methodology adopted and practiced by EIA for teacher professional development is ‘universal’ and applicable across subjects. Several of teachers participating in the focus group discussions described using EIA techniques in other subjects. This indicates an awareness of the broader usability of EIA’s approaches for improvement of educational pedagogy. However, examples of the wider use of EIA techniques were largely limited to language subjects, and teachers said that it would not be possible to use these approaches when teaching science, maths or social science. Explanations given by teachers included a) because the EIA materials were not available for these subjects, and b) that the methodologies were seen to be appropriate for the teaching of language skills.

Regarding assessment within the EIA programme, all Output 1 testing is linked to the internationally recognised Trinity Grade Scale, developed to assess students’ English Language ability objectively, and conducted by independent assessors from Trinity. Discussions at various levels with project functionaries and other stakeholders establish the indpendence, objectivity and reliability of the tests to the satisfaction of the review team. However, following the recent levels of language acheivement identified among current cohorts of teachers,their appropriateness as a tool for the assessment of teachers’ language has been called into question.

Previous annual reviews have commented on the lack of a counterfactual or a quasi-experimental design for attribution of English language learning skills to the EIA intervention. In response, a quasi-experimental research tool has been developed, covering Students and Teacher’s Language attainment and also Classroom Practice. While this research will offer insight into EIAs attributive role in these areas, its contribution to inform ongoing EIA practice is likely to be minimal as, due to delays caused by political disturbances, it will only begin to yield results in time for the 2017 Annual Review.

A number of concerns were expressed by the EIA team to the reviewers regarding the implementation of key programme activities during Phase IV in light of funding and resource constraints – for example, the inability to deliver Head Teacher support, undertake field visits to support monitoring at proportionately reduced samples, or a full cycle of follow-up visits to existing cohorts. EIA has tried to respond to this by aligning some of these activities with GoB’s ongoing mechanisms for teacher professional support but there is risk of dilution in quality. However, on the positive front, this strategy of ‘dovetailing’ EIA practice with GoB mechanisms also provides a basis for further engagement and integration with existing GoB mechanisms for teacher training delivery during this Phase IV, as well as acting as a forum for implementing a well-staged and smooth handover process based on practical tasks.

Overall, progress on this Output is to be particularly highlighted for its exceeding targets across all milestones.

Summary of responses to issues raised in previous annual reviews (where relevant)

Three recommendations for this output came out of the 2014 Annual review
Explore reasons for underperformance in the improvements in teachers’ English language skills, using external expertise if possible.
Response:
A review and further analysis has taken place – see 2015 AR document 3.2 – which has ascertained that the assessment of teachers’ language skills focuses on assessing general English language competence while the EIA materials and content only deliver inputs designed to enhance teachers’ competence in the use of classroom language. Because of this, EIA evidence indicates that there was no link between student and teacher English language proficiency; this was similarly true of the international evidence reviewed. Teachers’ classroom English may be more relevant than general English.

Small scale, well-designed independent research using discourse analysis techniques could provide valuable information about the nature of student talk in EiA classrooms, and could provide useful knowledge about both the likely impact and sustainability of EiA’s teacher training approaches. This should be undertaken.
Response:
EIA welcomed this recommendation in principle, but the present staffing budget does not provide for this currently. Therefore no action is to be taken as agreed with DFID subsequent to the 2014 Annual review.

DFID should consider commissioning independent research into the role of m-learning and peer support within EiA; if strong evidence can be found for the success of this approach, it will be of great interest to the E4D field.
Response:
This research has not been commissioned, due in part to the limitations of funding within the EIA programme. However, OU are actively pursuing external funding to support a number of further research initiatives. It is proposed that this includes research analysing the role and impact of m-learning and peer support within the programme.

Recommendations

Recommendations for primary and secondary schools intervention (output 1 and output 3) are related to institutionalisation and sustainability. Hence all recommendations are placed under Output 5 (institutionalisation and sustainability).

Output 2 Title	Change people’s perceptions of English language learning, reduce barriers to English, and support the development of an English language media sector through the innovative use of television, mobile phones, and other media platforms
Output number per LF	2	Output Score	N/A
Risk:	Low	Impact weighting (%):	N/A
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Note that this output has completed delivery. Milestones shown here are targets for 2017 (end of project), and progress is final achievement as reported to the 2014 annual review.

Indicator(s)	Targets (2017)	Progress
Reach / The cumulative number of Bangladeshis regularly accessing BBC produced EIA media products	A cumulative total of 9 million people (60%/40% M/F)using BBC produced EIA media products	Exceeded / At least 28 million people have accessed at least one BBC Janala product. / 10.25m (46% M/54% F) are highly exposed.
Perception / The number of Bangladeshis accessing BBC produced EIA media products, who report reduced barriers and increased positivity towards learning communicative English	43% of people who have used BBC EIA products will report increased motivation to learn and /or increased confidence to use English in their everyday lives / (47% of men; 35% of women)	Exceeded / 60% of those who are exposed to BBC Janala products have reported increased motivation and/or confidence towards English (62% of men, 59% of women).

Key Points
Output 2 is now closed and has exited from DFID funding. All output indicators have exceeded their end-of-programme (2017) target. The priorities during this year have been to ensure a smooth administrative close-out of the output as well as attempting to ensure that learning content produced by the project can be kept available to audience beyond the end of DFID funding.

A number of local, private-sector partners have been identified who may be in a position to take over provision of some or all of the learning materials. The selection of partners has taken longer than expected, due to editorial, commercial, fair trading and copyright complexities, but BBC Media Action are in the process of finalising details for the private-sector tendering process, with the anticipation of commencing and concluding the selection and handover in the next few months. In the meantime, BBC Media Action have successfully negotiated with existing technical partners to ensure that mobile and web content remains accessible to audiences, at no cost to the project.

Under contracting arrangements developed as part of the EIA programme, all media, materials and content developed under EIA as part of BBC Janala belong to BBC Media Action. BBC Media Action have the right to re-use it worldwide. DFID also have the right to freely use this material worldwide. BMB MottMacdonald and OU have the right to freely use these materials within the context of the EIA programme.

Beyond this, BBC Media Action have indicated their willingness for the content to be re-used in other contexts by GoB or other interested parties on request, on the principle that their use will not affect any anticipated contractual arrangements between BBC Media Action and private sector partners. In addition, BBC Media Action have already developed mechanisms and platforms enabling the content to be publically available on an open-access basis.

Independent of the EIA programme but based on their experience within EIA, BBC Media Action continue to share evidence of best practice and advise the GoB and their partners in the development of public awareness and educational broadcast materials.

It is worth noting that BBC Media Action have continued to explore options and support initiatives for the further use of BBC Janala content beyond the end of their funding support as part of the EIA programme, and should be commended for doing so.

Summary of responses to issues raised in previous annual reviews (where relevant)

Four recommendations for this output came out of the Annual Review 2014:

      1. DFID to support BBC Janala as fully as possible and within necessary timescales to facilitate the transition to private sector delivery
Response:
BBC Media Action are working with DFID colleagues to ensure smooth transition for this component of the project, and in support of this, DFID have extended close out deadlines and approved revised budget. The transfer to the private sector is nearing completion.

      1. Wherever possible, continued informal contact between EiA and BBC Janala, including joint dissemination activities, should continue.
Response:
BBC Media Action presented at and participated in the EIA technology policy seminar, and syntheses reports of lessons learned for adult learning and schools components are pending final approvals for publication and dissemination. Prior to their exit from the EIA programme, BBC Media Action regularly took part in EIA meetings and events during 2014-15.

      1. BBC Media Action should continue capacity building work with BTV (including through other platforms funded by DFID HQ), if resources are available for this important work.
Response:
Capacity building work, particularly with BTV, continues to be part of BBC Media Action’s centrally funded programme of activities. BBC Media Action has continued to maintain links with BTV beyond the end of DFID funding for their work with EIA. Discussions are currently underway between BBC Media Action and BTV regarding production and broadcast of new health, agriculture and skills-based content, with BBC Media Action providing long-term, relatively intense capacity building support.

DFID and BBC Janala should consider the assessment and evaluation of capacity building work – this has been a major achievement of the project and it would be useful to develop qualitative and quantitative indicators which can measure achievement.
Response:
BBC Media Action, as part of its global work in capacity building, is currently reviewing the way in which capacity building activities are evaluated and their impact. However, it was not possible within current funding for BBC Media Action to undertake additional evaluation of BBC Janala capacity-building prior to their exit from the EIA programme in December 2014.

Recommendations

All EIA project partners (BMB Mott McDonald, Open University, BBC Media Action, DFID B, GoB) should ensure a clear mutual understanding of the future use of BBC Janala materials, both by private sector partners within Bangladesh and in other contexts.

Output 3Title	Greater access to and use of EIA English classroom methods for secondary school teachers and students
Output number per LF	3	Output Score	A++
Risk:	Low	Impact weighting (%):	25%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Reach / The cumulative numbers of teachers and pupils participating in English in Actions secondary intervention	Secondary teachers / 5000 (69%/31% M/F) / Secondary pupils / 2.08M (48%/52% M/F)	Exceeded / Secondary teachers / 5,455 (81%/19% M/F) / Secondary pupils / 2.2M (47%/53% M/F)
Practice / The number of teachers incorporating EIA approaches in their classroom practice.	20% of student talk in a lesson / 60% of that talk is in English	Exceeded / 24% of student talk in a lesson / 92% of that talk is in English

Key Points
EIA is designed to enable teachers to improve the teaching and learning practices in their classrooms, through a one-year programme of teacher professional development.

During the review period, EIA has exceeded targets by reaching 5,455 secondary teachers (target 5000). This was achieved in spite of programme disruption caused by sustained political unrest, and in spite of the programme delivering training to cohorts of learners from isolated and socio-economically deprived sub-districts – a result that is to be commended. Achievements in classroom practice in terms of both student talk time and talk in English have also exceeded targets. Reason why progress data of female teachers in secondary school is lower than the target is because 1. The number depends on available female teachers in the selected schools which is outside the control of the project and 2. overall national percentage of female teachers in secondary is low (24% BANBIES 2014) and of that English subject teacher is much lower.

The EIA model adopted at Secondary level is the same as at Primary level, using holistic, innovative approaches to teacher professional development. Reliance is placed on peer support and the ‘trainer in your pocket’ m-learning approach, utilising content provision through mobile phone and SD/memory cards. Tried and tested peer support mechanisms through teacher facilitators, local level cluster meetings, and peer support have contributed to reaching scale. The decentralised arrangements for programme delivery ensured that there was little negative impact resulting from the continuous 3 months of political disruption during the period under review.

In keeping with Output 1, materials produced are of high quality, with an appreciation of typical Bangladesh school context and involvement of practicing teachers contributing significantly to the authenticity, acceptability and applicability of the EIA advocated approach.

In terms of scaling up EIA’s activities in secondary schools, a key concern is lack of a secondary education teacher education framework into which EIA activities could be integrated. However, the secondary education sector program along the lines of PEDP3 in primary education, has identified EIA as a key advisor in the development of teachers’ guides, audio materials for listening activities, instructional manuals, and guidelines for assessing of listening and speaking skills.

EIA concerns have been expressed based on confusion over the mandate for primary and secondary education as set out in the Education Policy 2010, causing apparent overlaps in coverage for Years 5 and 6. However, the concerned government directorates and NCTB have taken this into account and have agreed clear lines of departmental responsibility during the transition phase.

EIA has been able to sign a MoU with the Dept of Technical Education under Ministry of Education for inclusion of an English learning component within its technical and vocational education program. At the moment this MoU is operational through a specific program run in 64 GoB TVET schools and colleges across the country. The present Project Director of Skills Development programme suggests that the initial but visible successes of the EIA model has enhanced its potential to be incorporated across all government TVET schools and colleges together with 400 plus private TVET institutes. Further evidence of the impact of EIA methodologies would strengthen its position in this regard.

Overall, progress on this output is excellent and the project is likely to continue on a similar trajectory over a period of next 2 years.

Summary of responses to issues raised in previous annual reviews (where relevant)

As for Output 1 responses.

Recommendations

Recommendations for primary and secondary schools intervention (Output 1 and output 3) are related to institutionalisation and sustainability. Hence all recommendations are placed under Output 5 (institutionalisation and sustainability).

Output 4 Title	Increased information available around improving English language competency
Output number per LF	4	Output Score	A+
Risk:	Medium	Impact weighting (%):	25%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number of knowledge products developed	No 2015 milestone	EIA will publish 4 knowledge products in 2015. / The project is likely to meet or exceed the 2017 target for research reports and research briefs
Amount of research disseminated via conferences/ book chapters/ presentations peer reviewed, journals chapters in academic books/ distribution of reports to key stakeholders in Bangladesh and to research databases	2 conferences	9 conferences / 2 papers / 2 chapters

Key Points

EIA research outputs continue to represent the project and its achievements at an international level. Externally, as a result of these and other research dissemination activities undertaken over the project lifetime, EIA is increasingly regarded as a key case study for innovative approaches to teacher education at scale. This status will contribute to the on-going dissemination and uptake of the programme’s approaches and methodologies at a wider level.

The M&E framework and programme management information system (PMIS) act as comprehensive tools for gathering project data. Strategic plans to establish these tools within key GoB departments and provide orientation and training to GoB staff are fully in keeping with the institutionalisation and sustainability goals for the project.

However, the project’s future capacity to undertake further wide-ranging research is uncertain, due primarily to limited availability of project funding for the remainder of the project lifetime. In order to address this, OU is pursing options for securing external funding for research support. The implications of this for EIA’s immediate research priorities are discussed below.

Bearing in mind the limited availability of funding resources within the project, it is proposed that current and future research plans should focus on utilising already-gathered data, rather than seeking to generate new data. In addition, any research plans should focus on supporting the Institutionalisation & Sustainability and Advocacy Strategies for Phase IV. Specifically, this would involve producing a series of thematic 1—2 page research briefings that:
- showcase the impact of EIA as an ‘approach’ rather than as a project
- provide evidence demonstrating the effectiveness of individual EIA components, methodologies and delivery mechanisms
- supplement research evidence with practitioner-orientated summaries of key approaches, delivery mechanisms, and audiences

In the first instance, the research briefings might cover a number of key aspects of EIA, for example:
- EIA as a teacher education methodology
- One each for EIA’s 5 ‘recipe’ components for teacher education (Follow-up support; Peer support; Head teacher support; Alignment between assessment and curriculum; Offline AV materials and portable technology)
- EIA’s model for language-learning
- EIA’s pedagogic approach
- EIA’s programme delivery structure at local levels

In addition, each set of research briefings might be developed and re-developed with a particular audience in mind, including, for example: GoB policy makers; donors; NGOs; Higher education institutes and colleges; regional and local education offices; teacher support staff ( Teacher Trainers, Local Education officers); Head teachers; Teachers. The function of this will be to help ensure the continued awareness of, engagement with and uptake of EIA products and practices within Bangladesh by GoB, donor programmes, and the education system at large.

The existing Research and Evaluation Plan for production and publication of findings during Phase IV is adequate in general terms. However, in light of the above, it would be appropriate to supplement this with a detailed schedule for development and production of evidence-based research briefings, co-ordinating staff, and budgetary and resource allocations.

In addition, it might be also appropriate for the duration of Phase IV to regard research monitoring and evaluation (RME) activities as a key element within the I&S strategies discussed under Output 5, and to align any RME production schedule with specific deliverables detailed within the I&S and Advocacy Strategies.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were two recommendations from this output:
OU should seek independent peer review of their main research products so that strength of evidence can inform and shape advocacy in Phase IV of EIA.
Response:
Independent peer review has taken place, producing research publications of a high standard and which are serving to disseminate EIA’s outcomes and practices to an international audience. OU have also put in place agreed peer-review mechanisms that will support any subsequent published research outputs for the remainder of the project lifetime.

For Phase IV, a revised and succinct research and evidence plan should be developed, in the light of timescales/ resources.
Response:
An updated Phase IV Research and Evidence plan has been prepared. This includes new quasi-experimental study that will act to gather data on both classroom practice of teachers and language acquisition among students and teachers from the first cohort of Phase IV. – see 2015 AR document 7.3.

Recommendations
EIA to continue to consolidate available data, and prioritise existing research plans towards development of evidence that are key to supporting Phase IV objectives for the institutionalisation and sustainability of the programme, including the publication of evidence-based research briefings aligned with the Phase IV Advocacy Strategy.

Output 5 Title	Strengthened capability of key organisations and professionals in the education and media sectors to adopt EiA approaches
Output number per LF		5	Output Score	A
Risk:		High	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number and extent of strategic partnerships with Key organisations in education and English language media sectors: number of sector professionals taking part in ELT media capacity initiatives	Education Partnerships / 3 or more / Existing media partnerships continue	5 education partnerships (DPE, DSHE,NCTB, SESIP,NAPE) / Media partnerships continued
Number of policy seminars with key decision makers on English language education policy reform to support communicative teaching and learning	1	1 planned but not completed due to political unrest.

Key points
Project activities to support the adoption and institutionalisation of EIA approaches have continued during the review period, although political unrest created challenges for meeting the target on policy seminars as this activity required the wider participation of various stakeholders.

EIA are making progress in encouraging the uptake of EIA methodologies at both GoB and school levels. The formation of the EIA Core Working Group is an appropriate forum for engaging directly with GoB counterparts in seeking to raise and address issues of institutionalisation, although the constraints of working within the rigidity of GoB organisational infrastructure, programmes and budgets is noted. In this regard, the role of a strong and supportive Project Management Unit within GoB is of particular importance.

In parallel to working at the central level, EIA have been responding to requests from various Upazila education offices seeking to utilise EIA materials and training approaches as part of their autonomous regional teacher training activities. Simultaneously, there are numerous examples of interest and uptake of EIA materials and methodologies among partners within Bangladesh who fall outside of the project’s specific remit. In both cases, this is a very positive development, and their potential should be explored further.

The simultaneous top-down and bottom-up approach illustrated above is potentially of great benefit to strategies for the institutionalisation and sustainability of the EIA programme. Through adopting this approach of working simultaneously with key stakeholders at all levels of the education system, EIA have the potential for creating a critical mass for educational reform in Bangladesh. It would be in the project’s interest to attempt to formalize this approach within the Advocacy strategy by mapping all partner institutions with whom the project is engaging.

During 2014 – 2015, key achievements for Output 5 include:

Primary
- In-service programme content integration during 2014 – EIA approaches and Audio Visual (AV) materials were embedded in the Subject-based Training (SBT) for English, administered by the Directorate for Primary Education (DPE).
- On-going activities for capacity building of the SBT Master Trainers and Teacher Trainers
- Upazila Resource Centre (URC) Instructors are involved as EIA Teacher Facilitators for Head Teachers. URCs are used as EIA teacher workshop venues.
- On-going work with the Monitoring and Evaluation Division of DPE to revise the classroom observation form. Currently, a pilot study, jointly with the M&E Division is being planned.
- EIA linkages with the Primary Education Development Programme III (PEDP III) were highlighted in the revised PEDP III document in 2015.
- EIA is experimenting with a demand-led approach in which clusters of schools not in the EIA programme can request minimum support to provide EIA methodology through the existing decentralised systems, which seem promising and can prove to be a model for use of decentralised funds and efforts for teaching quality

Secondary
- EIA contributed to the Second Teachers Quality Improvement (TQI2) programme by helping to develop ‘Secondary Teachers' Competency Standards’.
- EIA was invited to contribute to the development of the framework for the Secondary Education Sector Investment Programme during 2014.

NCTB
- Contribution to the Primary textbook revision process, administered by the National Curriculum and Textbook Board (NCTB) during 2012, conducted small-scale and large-scale try-out studies together with JICA during 2012 and 2013.
- Agreement to produce Secondary Audio contents for NCTB in 2014.
- Integrated EIA approaches/classroom activities in the Primary Teachers’ Editions for class 1, 2 and 3 during 2014.
- Integrated AV contents and activities in the Primary curriculum dissemination workshop materials for English during 2014 and 2015.

Technical and Further Education
- MPhil programme on English Language Teaching Learning and Research was developed together with Dhaka University. The third cohort of student researchers was recruited during 2014.
- First cohort of intervention completed with embedded approaches, activities, materials and capacity building input for the Secondary Skills Development Project (SDP) led by the Directorate of Technical Education (DTE) during 2014.
- On-going work with the Monitoring and Evaluation Wing of Directorate of Secondary and Higher Education (DSHE) to revise the classroom observation form.

Non – formal Primary Education (NFPE)
- EIA approaches and materials were adopted by UNICEF for their non-formal education programme during 2012 and 2013. During the reporting discussion started to expand that further in urban setting.
- English Reading Scheme (ERS) materials for Primary children that were developed together with Friends in Village Development Bangladesh (FIVDB) during 2012 and 2013 are currently being used and have been printed by Save the Children’s non-formal schools programme.

Local NGOs and the Telecommunication Sector
- BBC MA’s adult English learning clubs are supported by local NGOs.
- EIA is now transferring the multi-media English learning products to the local partners. In partnership with BBC MA, six local mobile operators, state and private TV companies, national newspapers are creating affordable learning materials accessed by millions of people.

In addition to the activities listed above, EIA have drafted two key documents providing oversight of their activities in facilitating the process of engaging stakeholders in the uptake and handover of EIA materials, content and methodologies: firstly, the EIA Institutionalisation & Sustainability Strategy Framework and, secondly, the EIA Advocacy Strategy for Phase IV.

(i) The EIA Institutionalisation & Sustainability Strategy Framework is recognised by EIA and approved by DFID as a working document, subject to ongoing review and amendment. There are a number of proposals that might strengthen it as a tool for co-ordinating the project’s delivery of I&S within Phase IV.

- Firstly, it is proposed that EIA undertake a budgetary audit of available funding to assist in the prioritisation of resources and their allocation in relation to I&S tasks – including Advocacy and RME - for the remainder of the programme from June 2015 to March 2017. Such information should be included in the I&S Strategy Framework document.
- Within the I&S Strategy Framework document, there is a reasonable breakdown and identification of key tasks and issues for consideration in relation to I&S. Specifically, Primary Education Table 1 acts as an example of this. It is suggested that a similar framework is developed for all other I&S task areas featured in the Strategy (e.g. Secondary Education).
- In relation to each task area associated with I&S, it is proposed that EIA develop a detailed framework for delivery of required services June 2015 to Dec 2016, detailing:
  - Staged activities to undertake
  - Schedules and timetables for delivery
  - EIA implementing staff, including roles and responsibilities
  - Required budget and resource allocation

(ii) The EIA Advocacy Strategy for Phase IV outlines the priority concerns for EIA during the final 2 years of the programme. Firstly, it proposes a ‘dual-level’ strategy that divides desired achievements into those for the remaining project lifetime (2015-2017) and those beyond the project lifetime (2017 onwards). Secondly, it summarizes the current advocacy ‘landscape’ for the project through various tools:
- Qualitative ‘Grading’ of the relationships between key stakeholders and EIA
- Summaries of partnerships and mechanisms currently in place for handover of different components of the EIA teaching programme to GoB (e.g. DPE, Core Working Group, SESIP, NCTB, M&E, Dip in Primary Education)
- Summary evidence to support advocacy of EIA achievements and practices
- An Advocacy Implementation Strategy for EIA and DFID

In the context of the institutionalisation and sustainability, the EIA Advocacy Strategy recognises the need to regard the key components of the EIA teacher education programme as ‘discrete’ elements, in order to a) pass them on to relevant counterpart departments and units within the GoB system, and b) work to embed them within existing or emerging GoB activities in the sector. It also acknowledges the potential for engagement with other donors in the sector as a means of facilitating the on-going uptake of EIA methodologies and practices across other education support programmes.

There are a number of proposals that might strengthen it as a coordinating tool for the advocacy process.

Firstly, the document would benefit from inclusion of more specific information to support the implementation process. This includes the following:

- A breakdown of key tasks to undertake or deliverables to produce in response to each Advocacy goal, including, where relevant, a procedure for collaboratively-agreed allocation of advocacy tasks between DFID and EIA
- A staged schedule of outputs in association with these tasks, including a timetable covering June 2015 – March 2017
- Identification of EIA roles and responsibilities for leading and co-ordinating activities in each case (for example, as currently present in Appendix 3)
- A breakdown of budgetary or resource allocations required to undertake each activity

Secondly, in two particular components, DFID is named as facilitator in relation to certain roles. It is proposed that, in these tables, EIA also include themselves in a parallel active role in relation to each of the tasks, and that a staged activity schedule is developed. In the case of activity areas where DFID plays a key advocacy role, EIA should develop a schedule of advocacy activities in consultation with DFID and agree institutional responsibility for undertaking each one.

Summary of responses to issues raised in previous annual reviews

      - Four (six) key areas of EIA should be prioritised for sustainability
Response
The Phase IV plan and work plan have been updated to reflect these priorities
      - The development of a clear and strong advocacy plan within next six months, which presents evidence from EIA and from the literature base; this should be accompanied by transparent costs.
Response
The advocacy plan has been developed in consultation with DFID – see 2015 AR document 8.2.

      - DFID to facilitate and advocate inclusion of TA from within EIA in the sector programme wherever possible. This should focus on teacher development models which have been proven to be best practice by evidence from systematic review and from within EIA
Response.
DFID facilitated the attendance of EIA at the Secondary Sector planning process, PEDP3Joint Sector Review and included EIA reference in revised PEDP3 document.

      - NCTB expressed willingness to include TA from EIA in the ongoing work of textbook / teachers’ guide refinement by June – EIA should follow this up as soon as possible since activities are ongoing. EIA’s contribution to the Teacher’s Guides (cross curricular) would be highly valued.
Response
In October 2014, NCTB decided to incorporate EIA AV materials in their new primary Teacher Editions and Curriculum Dissemination training from January 2015. EIA teacher professional development videos and classroom audios will therefore be distributed to all primary teachers. (NCTB have as yet not proceeded with proposal for English workbooks). In respect of secondary, in September 2014, SESIP and NCTB identified areas of collaboration. EIA is currently involved in production of new audio listening texts for Class 6-10, and will give input to three English Curriculum Guides for Class 6-8 and video support materials for teachers and facilitators.

      - EIA should consider how ‘bottom-up’ methods might be used to increase the likelihood of sustainability. For example, School Management Committees have influence at local level and might help disseminate the usefulness of EIA’s work.
Response
A report was produced on the Kishorgonj initiative which describes the process and initial findings of this demand led programme. Eleven Upazilas have asked to participate in EIA in 2015 on their own initiative (independent of any central Government steer).

      - For Secondary Schools, a MoU has been signed with the Teaching Quality Improvement project (phase 2). Bearing in mind the ‘recipe’ concept, activities should be revisited in the light of time and resource constraints. Cost options might be based on phasing/numbers of teachers trained.
Response
Following their Mid Term Review, TQI2 is now focusing on Classes 11 & 12, and therefore this is no longer appropriate

      - The Secondary Schools Improvement Project led by the Ministry of Education and funded by ADB is a key initiative and EiA should seek to influence as much as possible within time/ resource constraints.
Response
EIA has been identified in the sector-wide SESIP framework as being able to support the work in key areas such as the development of the teacher education policy. EIA have also been invited to a meeting with the MOE Secretary to discuss areas of collaboration. This is incorporated in their Phase IV plan and work plan – see 2015 AR documents 3.1 & 9.4.

      - The GoB led, ADB funded Skills Development Project is keen to implement EIA approaches once there is clear evidence of the success of the intervention – there is thus a need to gather high quality evidence to embed the work of the project in this sector.
Response
In light of budget constraints, it has been agreed with DFID that post-intervention testing will only take place if Government funds allow for this.

      - The schools components, at this stage of the project, need to develop phase-out plans as part of the institutionalisation strategy within next six months.
Response
OU phase-out plan has been prepared and shared with DFID. But the school phase out plan is yet to be produced – see 2015 AR document 3.4.

      - All activities undertaken to bring about sustainability should be accompanied by clear research evidence and clearly set out costs.
Response
Advocacy plan has been developed in consultation with DFID – see 2015 AR document 8.2.
Updated Phase IV research and evidence plan has been prepared – see 2015 AR document 7.2.

2015 AR Recommendations

In the context of institutionalisation and sustainability of the EIA programme, the Advocacy Strategy recognises that in order to embed the 5 key elements[7] of teacher professional development into GOB systems each element may need to be dealt with separately. Because GoB may not be able to implement all at once.  However it is also important to highlight that the 5 elements work together to create an effective professional development package, which is supported by international literature review[8], and advocacy should focus on communicating that message, and supporting GOB to understand that vision as something to work towards in future. In taking this further, EIA should develop clear activity schedules by July 2015 to
[7] 1. Professional development aligned with classroom practices, with follow up support and monitoring. 2. Peer support (formal and informal peer support). 3. Head Teacher support. 4. Alignment with curriculum and assessment (school and external). 5. Offline AV materials and enabling technology. Curriculum expertise and lesson modelling is provided through the AV materials, used in teacher and facilitator development activities carried out with peer support at local meetings and in school.
[8] Pedagogy, Curriculum, Teaching Practices and Teacher Education in Developing Countries. DFID. Dec 2013.
  1. integrate the five elements into relevant department or units within the GoB system
  2. work to embed each component within existing or emerging GoB activities in the sector
  3. encourage the uptake of EIA methodologies and components by donors engaged in the sector, with a view to better ensuring the embedding and mainstreaming of these methodologies within the education system. Where required, EIA should also agree with DFID any mechanisms of support they can provide.

EIA to look at parallel strategies for potential placement of EIA materials and methodologies within the next primary sector programme (post PEDP3), in Secondary sector design, and in other educational sectors including TVET and adult education.

Undertake a budgetary audit to help identify resources available for undertaking all tasks associated with institutionalisation, sustainability, and advocacy by August 2015.

Align Advocacy Strategy tasks and outputs with wider objectives across the Institutionalisation & Sustainability Strategy by August 2015.

In relation to each task associated with the I&S and Advocacy Strategies, develop a detailed framework for delivery of required services June 2015 to Dec 2016, specifying in each case:
  1. Staged activities to undertake
  2. Schedules and timetables for delivery
  3. EIA implementing staff, including roles and responsibilities for co-ordinating activities and delivery of outputs
  4. Required budget and resource allocation

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers associated with this programme are:

1. Teacher face to face meetings and support
2. Development and production of audio and video materials
3. Equipment (speakers, SD-cards and mobile phones)

Collectively these account for 75% of the total costs and individually face to face meetings and support to teachers is the most substantial cost incurred at 50% (in phase IV of the programme). In the past 7 years these costs have decreased and have remained within budgetary expectations. Utilisation rates (actual as a percentage of budget) on all key cost drivers except equipment show an under spend, which has been due to the political turmoil and delayed implementation of the phase IV cohort. The project expects a catch up in spend in the first quarter of FY8. The project will also ensure that these funds are spent efficiently to meet the programmes core deliverables.

VfM performance compared to the original VfM proposition in the business case

Value for money for English in Action has been assessed on three levels.[9] Firstly, whether the programme continues to produce additionality (positive net benefits) relative to DFID not intervening in this programme (do-nothing); Whether the programme continues to produce additionally relative to the next best alternative means of delivering the same strategic objective i.e. enhancing teachers professional development; And whether there are any lessons that can be incorporated into the English in Action programme that enhance elements of value for money – economy, efficiency and effectiveness – without compromising performance in any of the other VfM elements.[10]
[9] An important caveat to this analysis is that the additionality calculations focus only on the primary education sector. EIA provide support to teachers to impact teaching outcomes in the secondary sector but the nature of these interventions are difficult to model and monetise in the NPV calculations and so have been omitted. As a consequence, and in addition to other qualitative benefits that have been identified during the VfM assessment but not monetised the net benefits measured for EIA are a conservative estimate of the total. Also the nature of English tuition at secondary level is more reliant on private provision raising strong issues on the relevance of GoB SBT as a useful comparator. For example, the Teaching Quality Improvement Project 2 focuses on Classes 11 and 12 (which EIA does not cover) and the Secondary Education Sector Investment Programme is yet to start its teacher development programme.
[10] See Annex [x] for a full explanation of the VfM asasessment.

Taking each in turn:

English in action continues to produce additionality relative to doing nothing (government provision of English subject based training). That is, when assessed over a horizon of 19 years (the useful lifetime of the programme, EIA produces a net present value for net benefits of £11.7m.[11] Since a net present value was not produced in the original business case it is not possible to deduce whether EIA is delivering more or less net benefits than was expected then. However a benefit-cost ratio of 3.4 indicates strong multiplier effects are present that justify DFIDs continued involvement on additionality grounds. Moreover sensitivity analysis conducted to check the extent to which net benefits are affected by changes in key assumptions - changes in the discount rate and changes in learning gains both for EIA and SBT – underlines the robustness of these findings.
[11] Using a discount rate of 10%.

For whether EIA continues to produce additionality over and above a next best alternative means of delivery, BRAC Primary Education Programme (BEP) is chosen as the most suitable comparator to deliver similar outcomes.[12] Assessed over the same time horizon using the 10% discount rate shows that EIA produces additionality over and above its next best alternative of £3.7m. Moreover, there are a number of non-monetised benefits that are associated with EIA, which indicate that what has been monetised is a conservative estimate. Sensitivity analysis applied to both EIA and BEP show that these findings remain robust.
[12] While there are differences in the delivery channels used between EIA and BRAC for primary education there are elements within these delivery channels that are comparable. Also both serve to achieve very similar outcomes and impact and therefore on the basis for assessing EIA relative additionality, BRAC primary education programme is judged to be the most suitable comparator.

Finally, whether there are any lessons that EIA could adopt from the best practice of the next best alternative across the elements of value for money (economy, efficiency and effectiveness) the comparisons are shown in table [1]. For this exercise, delivery channels and processes are important, as well as data availability, and so taking into account both considerations it was judged that the 3e’s comparison as better suited to a comparison between the existing government models of English subject based training.

Table 1: Value for money comparison between EIA and Subject Based Training
Value for Money measures
	Phase II	Phase III	Phase IV	SBT
Economy
Unit cost per teacher for face to face support	270	176	42	42
Audio and Video materials	105	35	17	-
Equipment	225	81	2.5	-
Total	500	292	81.5	42
Efficiency
Reach	400	7,500	33,500	70,000
Student talk time	27%	27%	20%	5%
Student use of English in the classroom	81%	91%	60%	5%
Effectiveness
Proportion of students getting access to the income premium on English	40%	30%	15%	1%
Cost per learning outcome	17	13	7.78	58

Across economy indicators, EIA has been successful in reducing unit costs substantially since phase II across all areas of economy measured. However, EIA is shown to be only as good as GoB SBT in terms of teacher training and support unit costs and while no information could be obtained on audio and visual materials and equipment for SBT the local content of these may cause GoB SBT unit costs to be comparable or lower in some areas. As a result EIA has developed a set of recommendations to further reduce unit costs across economy indicators over the next year. On efficiency, while the alternative GoB SBT has greater reach, student talk time as well as use of English in the classroom is greatly superior for EIA. Finally on effectiveness and cost-effectiveness, EIA achieves a higher proportion of students with and increased competency grade in English than GoB SBT and in spite of higher unit costs in some areas of economy are able to achieve a higher impact more cost effectively than the governments SBT. Over the course of year 8 of the programme, actions taken to improve economy within EIA should enhance the programmes cost-effectiveness further.

Assessment of whether the programme continues to represent value for money

Overall, on the basis of the analysis undertaken to judge EIAs VfM performance, this review concludes that EIA continues to provide VfM for DFID. However, this exercise has revealed a few areas where VfM can be improved over the next year. These are mainly in the areas of economy and efficiency:

Economy: Reduce the unit cost of face to face meetings to current GoB levels (PEDP3 unit costs); use lower cost printed materials; reduce operating costs through greater use of GoB speakers and teacher’s mobile phone; and decentralise operations to assure quality of implementation and minimise cost of logistics; fuel, lodging, per diems, overtime, etc.

Efficiency: Explore opportunities for ensuring face to face support through GoB system.

In the first month of the next review period EIA will develop a plan to implement these VfM enhancements, implement these over the first 3 to 6 months and build capacity to monitor these for the next review.

VFM Recommendation EIA develop a plan to implement selected VfM enhancements, implement these over the first 3 to 6 months of the next review period and build capacity to monitor these so that performance can be assess at the next review.

Quality of financial management

Invoices are submitted on a monthly basis for DFID assessment and approval before submitting to DFID HQ for final processing. The invoices are accurate and submitted in a timely manner. Where DFID has queries the project team responds promptly.
The project also provides supporting narrative for any monthly budget variance, setting out how these have occurred, possible impact on future spend and also how they propose to minimise the impact of these variances to ensure that specific DFID financial commitments are met (ie December and March expenditure milestones).
EIA has ensured cost controls in line with the contract. The project has identified and delivered efficiency savings throughout the current project year.

Despite the turbulent year the project managed to keep the underspend limited to 7%, of which approx 3% is savings.

Forecasted spend was broadly in line with the programme activity plans taking into account adjustment to implementation of various activities  to the lengthy political /security situation in the programme year.
Risks in the flow of funds are considered to be low.  In the Project Memorandum a risk of corruption in the procurement of goods and services was identified but all procurement of goods and hardware has been undertaken through Crown Agents. Additionally BMB closely monitored all other procurement for risks of corruption.

The programme has been reminded of DFID reporting compliance requirements regarding Fraud and Corruption particularly in view of laptops registered as lost/stolen over the last 12 month. The project has also taken measures to minimize the risks related to misappropriation of funds and equipment, including:
- Sensitisation/Awareness building amongst the staff: EIA shared Anti-Fraud policies in all-staff meetings and discussed its Safety and Security Policy.
- Staff that has been victims of a robbery shared their experiences with other staff members.
- IT equipment forms have been introduced. These ‘contracts’ specify the user policy, rules and regulations in terms of the asset and consequences in case of loss, carelessness, theft, etc. Each employee receiving a laptop, phone or other IT equipment needs to sign this user contract.

Date of last narrative financial report	QPR Q4 FY7
Date of last audited annual statement	November ‘14

E: RISK (½ page)

Overall risk rating: Medium

In the Project Memorandum the key risks identified are:

1. Political/policy change – High level political commitment not maintained
2. Lack of training capacity developed
3. Sufficient human and physical resources are not made available
4. The design of the programme and its envisaged scale up leads to reduced quality and impact
5. Corruption in the procurement  of goods and services

Subsequent reviews of the risk management matrix have identified the main risk to the programme as sustainability and resulted in revisions at Impact and Outcome levels (a,b) and for Outputs 1 and 3 (c)  :

- Major political instability at national level: probability increased from Low to Medium, with some additional information on the upcoming elections and criminal court verdicts of the war criminals.
- Current political commitments to prioritise English learning for economic development not maintained: from Low to Low-Medium, related to the upcoming elections and possible change of power.
- Failure to gain timely and effective access to schools and teachers: increased from Low to Low-Medium.

Overview of programme risk
Under Phase IV of the programme, the main risk for EIA is ensuring the institutionalisation and sustainability of the EIA content, methodology and materials. In order for the project’s outputs to become sustainable, key elements need to become fully absorbed and utilised within government structures. The main challenges to achieving institutionalisation, and hence sustainability within the education system, are, at this stage of the project:
- Project resources – both human resources and finance
- Status of partnership activities with GoB and key stakeholders
- GoB capacity

In addressing these challenges, enhancing the Advocacy and Institutionalisation & Sustainability Strategy documents will help to rationalise activities, prioritise areas of primary interest and identify best ways to effectively and efficiently implement procedures over the coming 18 months to March 2017.

The project should continue to take a multiple-stakeholder approach to advocacy, which is already demonstrated by current activities. Specifically, this will involve engaging with the centralised GoB system and also with local and regional educational stakeholders and with ‘external’ partners – donors and NGOs – to raise awareness and encourage uptake and utilisation of EIA outputs.

The key challenges will continue to remain in place for the project, simply because both primary and secondary education sector operates a large multi-layer, multi-stakeholder system with more than 27 million students. Changing any system/processes within that would require long term on-going intensive engagement, for which the project has limited ability given the resource constraints.

Outstanding actions from risk assessment

1. Prioritisation of Phase IV Advocacy and I&S tasks
2. Identification of available resources for delivery of above
3. Development of project implementation plans for all Advocacy and I&S tasks

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The project is proceeding well against the planned timeframe.

Performance of partnerships

Partnerships between EIA consortium members are operating well. However, as OU are reducing their levels of involvement in the delivery of project activities, and BBC Media Action are no longer part of the project in a formal sense, there is an opportunity for the project partnership to reassess roles and responsibilities, particularly in planning for the implementation of key advocacy and I&S tasks during final 18 months of programme delivery under Phase IV.

Within this context, there has also been some discussion over collaboration between DFID Bangladesh and EIA in implementing advocacy initiatives associated with engagement with upcoming GoB and donor-led programmes. As recommended under Output 5, there is scope for further discussion and formalisation of roles and responsibilities in this regard.

Asset monitoring and control

The last EIA spot check took place in December 2014. DFID observed that the EIA team monitored and registered its assets is comprehensive and satisfactorily presented. However there were a few concerns about the number of laptops –4 laptops- which were registered as lost/stolen over the last 12 months. In response EIA provided a separate document with all items lost and stolen, brief description of the incident and relevant documents such as police reports and management decisions. The asset register as well as the list of lost and stolen are now available online and accessible for DFID. Both lists are updated on a monthly basis.
As per the recommendation of the DFID programme team, EIA prepared an Anti-Fraud Policy aiming to reduce any risks related to misappropriation of funds and equipment. The key issues around the policy have been shared amongst the EIA staff and beneficiaries.
The assets provided from EIA to teachers (speakers, phones) are still DfID-owned and managed as part of EIA’s asset management. EIA has proposed to DfID that these assets should be transferred to the GoB. The GoB, particularly DPE, is raising concerns that if the assets are not in the school’s asset lists, that the items may be misappropriated, and neither GoB nor EIA can do little to prevent or reverse that. EIA does not have the capacity to manage the assets in the present numbers (around 12,500 of each).

Recommendation It is a matter of some priority that a process is put in place to hand over the assets to the Government in an appropriate way, while ensuring/promoting that the equipment will remain available for the teachers. DFID have been in discussions with EIA about a possible process for handing over assets.  EIA are also in discussion with relevant Ministry about process. We anticipate that a plan for transfer will be agreed in the second half of 2015.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The Annual Review, conducted by an independent team, Education adviser and programme Manager, took place over an 8 day period, including 5 days in Dhaka and the remaining 3 days for preparation, review planning, documentary analysis and report writing. Information and data was gathered through reviews of project documentation, interviews and discussions with EIA project management and staff, GoB staff, DFID Bangladesh and teacher focus groups. Due to time limitations, there has been no independent verification of the data presented to the review team. In keeping with findings first identified in AR 2014, there is no strong evidence of substantial improvement of English language skills among teachers during the review period. Among the reasons given that may explain this are the following:
- Trinity examinations assess general English language competence, whereas EIA provides training designed to enhance teachers’ classroom language competence.
- At EIA programme scale-up, initiated in 2013-2014, the target areas covered those more rural regions with higher levels of socio-economic deprivation. In this context, the baseline information gathered from cohorts during the pilot programme is unrepresentative of the current cohorts of trainee teachers.

Monitoring progress throughout the review period
EIA have considered the implications of the evaluation findings for the project as a whole, and, in response to recommendations made in AR 2014, have put in place a Quasi-Experimental research tool that will better reflect the cohorts of teachers covered during the scale-up period. However, due to the disruption caused to programme activities by 3 months of strikes in early 2015, the new research tool will only be able to yield findings in time for AR 2017.

Annex 1: Additional observations by review team

Regarding EIA’s approaches to advocacy, there are a few general comments:

Firstly, in general terms, it is proposed that advocacy as an activity should be presented as one element of the I&S process, acting to a) raise awareness of EIA achievements among key stakeholders and b) encourage the uptake of EIA materials, methodologies and practices by both GoB and Upazila education institutions, and external stakeholders such as donors and NGOs. Within this, scheduled task outputs and deliverables described in the Advocacy Strategy should be closely aligned with wider objectives described in the I&S Strategy.

Secondly, as mentioned above, the advocacy strategy sees merit in presenting a two-phased approach to sustainability, covering, firstly, June 2015 - March 2017; and secondly, beyond March 2017. However it would also be useful to spell out the implications of this approach to the practical implementation of the advocacy strategy.

Thirdly, as discussed under Output 4, in support of general advocacy, and drawing on existing data gathered through the project’s existing research, monitoring and evaluation activities, EIA would benefit from developing clear and concise practice-orientated research briefings, covering key components of the EIA methodology and approach, summarising evidence of their key achievements and also outlining basic practical frameworks for delivery. These documents would be designed as a tool to engage with stakeholders at all levels of the education system, including GoB and donors, as well as practitioners at regional and local levels.

Fourthly, as part of the general approach to encouraging uptake and use of EIA materials and methodology across the education system in Bangladesh, the project should consider discreet use of EIA as a brand, particularly in terms of embedding its innovative approach to teacher professional development. In particular, this might involve starting to present EIA primarily as a clear methodology rather than as a project, and also as far as possible shifting away from the high-visibility interpretation of EIA as representing a set of AV materials and approach.

Fifthly, there is a case for recognition of importance of communications within GoB to help facilitate improvements in internal communications between key players at GoB. Poor internal communications present a major risk for the sustainability of the project during the wind-down of EIA-led activities in the next two years, and certainly beyond 2017.

Finally, as part of both advocacy and wider institutionalisation and sustainability, EIA should look at strategies for the potential placement of EIA materials and methodologies within post-PEDP . This would be in addition to providing on-going support to the implementation of PEDP III. Primarily, this strategy would be undertaken through a) advocating for EIA’s representation in initial strategic donor meeting June 2015, b) continuing to embed programme materials, tools and methodologies within key GoB departments in the run-up to these departments’ contribution to the post-PEDP planning process, c) continuing to work with key donors in raising awareness of EIA’s achievements, activities and resources, d) engaging with the post-PEDP planning process during the period commencing June 2016 until programme close March 2017.