Annual Review

Title: Infrastructure for Climate Resilient Growth in India
Programme Value £ (full life): £ 10m		Review Date: 20th December 2018
Programme Code: 204794	Start Date: 08 January 2016	End Date: 31 March 2024

Summary of Programme Performance
Year	2017	2018	2019	2020
Programme Score	B	A+	A+	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204794/documents
DevTracker Link to Log frame:	VAULT Ref. 23673791

A. Summary and Overview (1-2 pages)

Description of programme
Infrastructure for Climate Resilient Growth (ICRG) programme is a £10 million technical assistance (TA) provided over eight years to Ministry of Rural Development (MoRD), Government of India (GoI) and three states (Bihar, Odisha and Chhattisgarh). The ICRG programme is partnering with GoI to improve abilities of poor and vulnerable people to cope with climate change impacts. The programme aims to strengthen the quality and productivity of infrastructure built under Mahatma Gandhi National Rural Employment Guarantee Act (MGNREGA) to support resilient livelihoods through ground water recharge, micro-irrigation, soil and water conservation and plantation. This phase of the programme is in its last year of implementation and has delivered on the following objectives at the national and sub-national level:
[note] ICRG phase I will end in March 2020, the programme has been extended for four more years in this review period and the phase II will begin in April 2020 till 31st March 2024.
1. Building capacity of different tiers of government line departments to plan, converge, implement and monitor development programmes addressing climate change (CC)
2. Improve resilience through climate proofing of MGNREGA works
3. Fostering and demonstrating convergence for reducing CC vulnerabilities

The programme contributes to the UK’s climate commitment under the International Climate Fund (ICF) and demonstrates UK’s global expertise in building resilience of the poorest and most vulnerable people. Programme interventions directly support Indian government’s climate goals and commitments made in international climate negotiations by strengthening MGNREGA contribution on building resilience. The programme is currently delivering four tranches of activities under different contracts and agreements. These are:
[note] Nationally Determined Contributions (NDC) adopted by India in 2015 as part of Paris Agreement, list MGNREGA as one of the schemes that contribute towards adaptation actions and mitigation goal on carbon sinks with the help of plantation works.

Component 1: IPE Global and consortium partners – Ricardo Energy and Environment, University of Manchester and PwC, are the main TA partners, contracted to manage and deliver the programme over four years (till Feb 2020). In their final year of engagement on the programme the TA team has demonstrated how climate resilient considerations can be integrated into the planning processes of MGNREGA in the three states (103 blocks) by working closely with MGNREGA functionaries, state and national officials. The team has developed 1156 detailed project reports (DPRs) since inception which illustrates how combination of MGNREGA natural resource management (NRM) assets/infrastructure can effectively lead to enhanced climate resilience of the rural poor communities, through water and environmental conservation. (ongoing, till Feb 2020)

Component 2: International Institute for Environment and Development (IIED) was initially engaged to develop an analytical framework linking MGNREGA with climate resilience and recommended options to MoRD to integrate climate risks and opportunities in future MGNREGA investments. Post establishing a strong linkage between MGNREGA and climate resilience, IIED was engaged for an additional 18-month project, supporting the MoRD to develop innovative financing solutions to strengthen MGNREGA contribution to resilience at the level of the household and the local economy. A regional proposal to finance the additional costs to pilot the climate resilience interventions in selected states under India's national adaptation fund on climate change (NAFCC) is being developed. (ongoing)
Component 3: UNDP India, was engaged in the reporting period to build and sustain the successes of ICRG Phase I, supporting greater climate resilience for poor communities living in rural areas. UNDP is designing the contours of the extended programme activities and outputs with the objective of scaling up ICRG interventions, best practices through a focus approach on deepening the integration of climate change considerations through scientific projections (climate information services) into MGNREGA activities; building scientific and technical capacities of decision makers at various levels. (ongoing)

Component 4: Sambodhi Research and Communications Private Limited, was engaged to conduct a third-party independent performance evaluation of the ICRG Programme in November 2018. The evaluation team submitted the Midterm Evaluation in this reporting period – which helped DFID identify what has worked and what hasn’t, so far, in the programme implementation. Based on the recommendations presented in the mid-term report, the DFID ICRG programme team is exploring a possible time and cost extension. The end-term evaluation of the programme is due in March 2020 which will feed into the design of the proposed ICRG Phase II (ICRG+) activities and outputs. (Ongoing)

Summary supporting narrative for the overall score in this review
The programme has performed well against all milestones, scoring an A overall. While the programme previously focused on demonstrating the improvements possible through better planning of MGNREGA infrastructure and the associated impact on livelihoods, the focus of the final year of this phase was on institutionalizing the ICRG approach in the planning and design of MGNREGA works both at national level and states.
[note] ICRG Approach: Programme adopts a unique approach of downscaling and de-mystifying climate data, integrating it into India’s social protection scheme to strengthen and sustain the schemes contribution in building climate resilience of the rural community in the face of increasingly frequent and higher magnitude climate hazards. The approach also includes - Integration of multiple MGNREGA works that collectively build resilience as well as focuses on convergence with other departments for complementary support.

Following last year’s Annual Review (AR) recommendations, the programme delivery and management has been streamlined. The delivery plan, programme outputs and risk register were revised in the first quarter of 2019 to better reflect weighting, activities and measurable indicators of partner activities and their work plans, to effectively meet the overall objectives. To assess the programme’s contribution in building resilient MGNREGA structures and rural communities, an independent third party was appointed to conduct a mid-term and end-term evaluation. The midterm evaluation submitted in May 2019, assessed ICRG programme’s theory of change, and its performance to deliver the expected outcome. The mid-term evaluation identified programme’s successes and failures and areas that need attention or revision to meet its intended target, the results of the mid-term were then used to inform a possible time and cost extension on the programme and design the outline of a potential ICRG Phase II (ICRG+). The end-term evaluation (due in March 2020) will help document valuable lessons and generate evidence to inform future programming decisions in DFID India, across UK Government climate change programming and for the Government of India.
Some achievements of the programme in this year include:
1. Presentation of ICRG at the UN Climate Change Conference COP 25 in Madrid under both India and UK Pavilion. The presentation on ICRG was made by the Joint Secretary, MGNREGA, MORD at the India Pavilion during COP25 proceedings, reflecting the evolved relation between the ministry and the programme.
2. Two international publications documented the programme’s unique approach of downscaling climate data (i.e. regional climate model downscaled to block level) and integrating it into MGNREGA design and delivery at the local level. These include (i) India in a warming world, integrating climate change into development, by Navroz K. Dubash; (ii) Resilience Shift programme (funded by the Lloyds Register Foundation) that documents global innovative resilient infrastructure projects.
3. The Hon’ble Union Minister (Rural Development, Agriculture and Farmers Welfare & Panchayati Raj) recognised two of ICRG support areas as outstanding performers in the implementation of MGNREGA – (i) Mungeli District in Chhattisgarh for effective implementation of MGNREGA by District Team; and (ii) GP Podi, District Koriya, Chhattisgarh, as best performing GP for construction of structures augmenting water harvesting under MGNREGA.
4. Directives were issued by the state government to mainstream climate change into MGNREGA design and planning across all blocks of the 5 districts in Chhattisgarh, where ICRG is being implemented under the state’s flagship programme of ‘Naruwa, Garuwa, Ghurwa and Bari’ (NGGB).
  [note] Chhattisgarh has come up with an innovative vision to revive the agricultural economy by striking a golden mean between modernity and tradition at the grassroots ‘Naruwa, Garuwa, Ghurwa and Bari’. Chhattisgarh’s vision for reviving agriculture is collective action to ensure water conservation, livestock development, compost usage, and cultivation of vegetable and fruit.
5. In Odisha, the state government has issued notifications to mandate the scale up of the ICRG approach. The success shown in convergence in Badabil, Keonjhar, Odisha has led to it being designated as a ‘best practice’ by the state (Letter, Annexure 3). The convergence has led to leveraging INR 60 lakhs (£64,000) from other government programmes and schemes through the Odisha Livelihood Mission and the Odisha Agro-Industries Corporation for this site.
6. In Bihar, the ICRG programme has provided strategic support to the state government in the design and roll out of their state flagship program ‘Jal Jivan Hariyali’ (JJH) that focuses on ground water recharge and its conservation.
In the last year of Phase I implementation, the programme also continued to focus on increasing the number of natural resource management (NRM) infrastructure works under MGNREGA (at least upto 75-80%) to improve individual and community resilience. During the review year, the programme has made significant progress and has assisted MoRD and State Rural Development Department in achieving the following results:
[note] NRM structures help in flood protection, enhance net irrigated area and groundwater improvement.
Selection and design of climate resilient works (CRWs)
- While the TA team did not prepare new climate resilient works (CRW) in the 103 programme blocks under MGNREGA in the reporting period, it focused on completion of the CRWs already sanctioned in the detailed project reports (DPRs) prepared by the team. These include natural resource management structures which will lead to increased irrigated area by 7775 hectares and plantation of 366 hectares that should sequester ~34,000 tonnes of carbon over the next 30 years.(Detailed in Annexure 5)
  [note] Each climate resilient work (CRW) is a combination of a core work (for e.g., land development) and a few ancillary structures (for e.g., plantation on the bunds, dug wells to harvest sub-surface water, Nadep pits, etc.). Such clustering is done based on biophysical (drainage line, ground water, and forest), socio-economic features (production system, land use pattern), and/or expected outcomes (water availability, diversified livelihood). This approach ensures that CRWs are durable and productive. Further, a livelihood plan is developed for each CRW and its beneficiaries, and the plan is implemented by leveraging resources from other programmes/schemes operational in the area. This enhances the productivity of the CRWs and leads to more resilient communities.
  [note] Calculations: Cumulative carbon sequestration after 30 years is projected to be 93 tonnes of carbon (tC) per hectare (74 tC/h above ground and 19 tC/h below ground). Therefore, total potential of the plantations to sequester carbon over 30 years is projected to be = Total area under plantation (in Ha) x 93; Reference: Tiwari et al., EPW May 14, 2011, Vol XLVI No 20.
- Support was provided to the Department of Forests in Chhattisgarh, the nodal department for the implementation of the state government’s flagship programme - Naruwa, Garuwa, Ghurwa and Bari (NGGB). In the reporting period, 137 Naruwa (water conservation) DPRs in 24 Districts and 540 Naruwa DPRs were prepared by the Zila Panchayat team in 9 Districts of Chhattisgarh based on the capacities that were built on ICRG approach.

Scale up and institutionalization of ICRG approach
- The Annual Master Circular 2019-20 for MGNREGA issued by the Ministry of Rural Development (MoRD), Government of India, includes mention of climate adaptation under MGNREGA and a section on monitoring and evaluation (M&E) of the climate outcomes of MGNREGA assets through the inclusion of the indicators developed under the ICRG programme – this is the highest level of policy influencing possible as this Circular is the only document published by the Ministry offering strategic guidance to the state on effective implementation of MGNREGA every year.
  [note] https://nrega.nic.in/Netnrega/WriteReaddata/Circulars/2390Annual_Master_Circular_2019-20.pdf : Chapter 6: Entitlement IV – Right to Plan and Prepare a Shelf of Works; Section 6.3; pp 20
  [note] https://nrega.nic.in/Netnrega/WriteReaddata/Circulars/2390Annual_Master_Circular_2019-20.pdf : Chapter 7: Entitlement V – Works under MGNREA; Section 7.12.2, pp 57
- The ICRG approach which recommends integration of multiple NRM works (with improved engineering design) that collectively build resilience has been adopted by the Government of Chhattisgarh for its flagship programme, the NGGB. This NGGB programme covers all 33 districts of the state and ICRG provided training to Forest Department staff, prepared templates for the DPRs and supported quality assurance.
- In Odisha, the state government has issued directives for scaling up the ICRG approach in all the blocks of the 5 districts where the project has been implemented.
- In Bihar, the ICRG approach to planning water conservation and ground water recharge structures has been adopted under the state government’s Jal Jivan Hariyali (JJH) of the State Government.
- ICRG’s MoU with the Odisha Livelihoods Mission (OLM) has been renewed till the end of the programme. In the reporting period, OLM has issued directives for active integration with beneficiaries of MGNREGA assets as has been demonstrated in ICRG by developing livelihood plans for each CRW beneficiary. Further, OLM has directed that the convergence be monitored at district level every month by the District Rural Development Agencies (DRDA) and at state level.
- In Chhattisgarh, an MoU has been signed with the State Rural Livelihoods Mission (SRLM-Bihan) that will focus on convergence of livelihoods interventions around MGNREGA assets. As per the terms of the MoU, models for facilitating four livelihoods have been developed.

The key lessons learnt during the review period are:
- ICRG had a positive impact on – the MGNREGA-NRM structures (engineering design); capacities of functionaries; and awareness around climate change in the rural communities. The mid-term evaluation suggests that the DPRs highlight adequate additionality, in terms of design and approach towards the creation of structures. However, it was noted that it is important that MGNREGA structures using the ICRG approach are constructed as per the prescribed DPR so that results become visible.
- Beneficiary assessment, by the third party, validates the impact pathway that the ICRG has envisaged. At the impact level, it is seen that 29% and 23% of direct beneficiaries have very low and medium adaptive capacity, respectively. This suggests that access to CRWs has comparatively been able to improve the adaptive capacities of the direct beneficiaries by increasing their household income that is primarily dependent on agriculture productivity. Development of CRWs has resulted in improved access to irrigation for the direct beneficiaries, encouraging them to cultivate a larger share of crops for commercial purposes.
- Engaging with the decision makers, at political and bureaucratic levels is important for the scale up of any TA programme. ICRG’s engagement with the state governments has remained significant. The results accruing from the construction of assets like farm ponds and land development works in Chhattisgarh and Odisha respectively has been key to the institutionalization of the ICRG approach in the states.
- The engagement with MoRD in this reporting period has become regular, several meetings were conducted with the Joint Secretary (JS) and Director (MORD, MGNREGA) to (i) finalise the concept note on National Adaptation funds for climate change (NAFCC); (ii) integrating ICRG approach into training manual; (iii) finalising the annual master circular (especially the climate change section) and (iv) to firm up MORD’s participation in COP 25.
- ICRG also engaged with MoEFCC officials (Secretary, Additional Secretary and joint secretaries in different meetings) to disseminate the programme learnings and results. ICRG participated in the pre-planning of United Nations Convention to Combat Desertification (UNCCD) COP-14 on combating desertification, which was held in Delhi (in September’19) to help the ministry develop the legacy project (Mahatma Gandhi Green Path running across 3 states) to arrest conversion of semi-arid region to arid and address the global challenge posed by land degradation.
- In addition to the above, the programme was presented at the World Sustainable Development Summit 2019; the 8th Global Agri-Connect 2019; Community Based Adaptation Workshop 2019 – reiterating the novelty of the approach of mainstreaming climate considerations into a social protection programme of the scale of MGNREGA.
- Convergence with different government programmes and schemes (livelihood, agriculture, forest, etc.) help leverage additional funding towards social protection and establish institutional linkages leading significant spin offs and scale up. The success shown in Odisha is a point in case as the intervention in Badabil village of Saharpada Block in Keonjhar, has been designated as a ‘best practice’ by the government and directives issued to replicate this convergence model in other blocks and villages.
  [note] Resources have been leveraged from Odisha Livelihoods Mission; Integrated Tribal Development Agency and Odisha Agro Industries Corporation to strengthen the interventions.

Recommendations for the next phase of the programme
ICRG Programme has ambitious objective with the potential for greater impact. Subject to approval, ICRG+ proposes to build upon and take forward the work done in Phase I, with increased emphasis on:
1. Institutionalising the successful approaches of building climate resilience for wider reach and impact in Phase II (ICRG+).
2. Facilitating integration and convergence (at national and sub-national level) among the related Government of India programmes, global initiatives (such as Coalition for Disaster Resilient Infrastructure (CDRI)), policies and regulations and linking the programme outcomes to India’s national climate change targets and SDGs.
3. Promoting alignment and harmonisation with other development agency programmes.
More specifically -
Building and strengthening UK’s climate engagement with India
- Climate change and its potential to reverse development is increasingly being recognised by local actors and communities across India. Integrating climate risk management into large development programmes is being used as an effective tool to reduce the climate related losses across the globe. MGNREGA with its several key interventions and innovations targeted towards poverty alleviation, natural resource management make it an ideal platform for the integration of climate resilience. ICRG Phase II (ICRG+) proposes to continue the legacy created in the first phase and ensure greater internalisation of the ICRG approach within MGNREGA. (DFID will design ICRG Phase II and begin implementation by July 2020, subject to approval).
- ICRG+ proposes to deliver on the objectives of UK’s climate engagement strategy, which has kept resilience at the heart of its strategic partnership with India to accelerate actions in implementing the Paris Agreement on Climate Change. (DFID, ongoing)
- ICRG+ proposes to continue to engage with the Ministry of Rural Development (MoRD) and will build stronger channels of communications with Ministry of Environment Forest and Climate Change (MoEFCC) to achieve our engagement objectives with India, of which, one of them is to develop influencing pathways to reach opinion-formers and decision-makers. (throughout ICRG+ implementation till March 2024)
- ICRG+ proposes to offer a concrete opportunity to work across HMG on the resilience theme– bringing in UK’s expertise in research, climate science, technology, and evidence, to influence and build climate resilience into the world’s largest social protection scheme. (DFID, through out next year)
- The ICRG programme has focused consciously on initiating partnerships/linkages with local institutions in the state for strengthening livelihood resilience. This would be continued under ICRG+ and efforts made to operationalise convergence with other government programmes. (DFID with UNDP in 2020)

Scale up and institutionalisation of ICRG approach
ICRG+ proposes to focus on the following 5 principles of institutionalising ICRG approach:
1. Policy reforms – integrating climate resilience measures into various MGNREGA guidelines/modules; regional disaster risk planning and management to build resilient people, environment and economy.
2. Develop and embedding climate risk management approach and tools in MGNREGA processes at various levels (design, delivery and monitoring).
3. Influence - national and state actions plans on climate change to include MGNREGA as a delivery mechanism for climate adaptation action (through climate resilient rural infrastructure).
4. Promote convergence at all levels – to enhance climate resilience outcomes of MGNREGA.
5. Capacity building of administrative and technical staff on climate resilient infrastructure planning.
- The efforts made at initiating partnerships at the local level with government institutions has shown results. The institutionalization and scale up of the overall ICRG approach of downscaling climate data into effective MGNREGA village plans compatible to future climate scenarios, in all the three states is a case in point. One of the key reasons for this success has been the intensive nature of engagement and hand holding support provided by the ICRG state teams. The extension period will continue the support of embedding the approach within government systems and will keep the momentum going through state engagement. (DFID with UNDP, throughout the extended period)
- Engagement with MoEFCC was initiated in the last AR and continued this year by engaging with the ministry during several international and national climate events and meetings. Designing a strategic engagement with MoEFCC will be consistent with the increased emphasis in the proposed ICRG+ towards institutionalisation of tools and approaches and moving from the outputs to the outcomes. (DFID, 2020)
- Building capacity across all administrative levels (national and sub-national) of MGNREGA would remain a key focus of the proposed ICRG+. This will help ensure sustainability of climate and environment benefits of MGNREGA especially across the three ICRG states. In this regard, ICRG’s engagement with the National Institute of Rural Development (NIRD), responsible for building capacities of MGNERGA functionaries, will be strengthened. This engagement will contribute to scale up of the programme lessons and training on climate mainstreaming with MGNREGA. (DFID with UNDP)
- DFID India will work closely with the Asia Regional Team (ART) to explore the case and scope to scale up ICRG further through the proposed Asia Pacific Climate Resilience Platform (APCRP). (DFID)

List of Abbreviations
Acronym	Full Form
AR	Annual Review
BTRT	Block Technical Resource Team
CAMPA	Compensatory Afforestation Fund Management and Planning Authority
CFT	Cluster Facilitation Training
COP	Conference of Parties
CRW	Climate Resilient Works
CSO	Civil Society Organisation
DTRT	District Technical Resource Team
GoI	Government of India
IAD	Internal Audit Department
ICF	International Climate Fund
ICRG	Infrastructure for Climate Resilient Growth
IIED	International Institute for Environment Development
IISC	Indian Institute of Science
ITDA	Integrated Tribal Development Agency
MGNREGA	Mahatma Gandhi National Rural Employment Guarantee Act (MGNREGA)
MoEFCC	Ministry of Environment, Forest and Climate Change
MoRD	Ministry of Rural Development
NABARD	National Bank for Agriculture and Rural Development
NAFCC	National Adaptation Fund on Climate Change
NDC	Nationally Determined Contribution
NGGB	Naruwa, Garuwa, Ghurwa and Bari
NRM	Natural Resource Management
OLM	Odisha Livelihood Mission
PMU	Project Management Unit
PRI	Panchayati Raj Institute
PSC	Programme Steering Committee
PwD	Persons living with Disability
QPR	Quarterly Progress Reports
RIF	Research and Innovation Funds
RF	Resource Funds
SARH	South Asia Research Hub
SIRD	State Institute of Rural Development
SRLM	State Rural Livelihood Mission
TA	Technical Assistance
TAST	Technical Assistance Support Team
VFM	Value for Money

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Increased capacity of implementing agencies and communities to plan and implement climate resilient works
Output number per LF		1	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s)	Progress
1.1 Governance structures for programme implementation established	Project Review Meetings at National and State Government levels held, and Minutes issued	Achieved / One formal review of the programme progress was carried in June 2019 at the national level. / In Bihar, the Secretary Rural Development Department and the MGNREGA Commissioner have conducted monthly progress review meetings. In the reporting period, the Secretary chaired 3 review meetings and the MGNREGA Commissioner -12 meetings. / In Chhattisgarh, / the Empowered Committee for MGNREGA State Council, reviewed progress in October 2019. The meeting was chaired by the Chief Secretary and attended by Secretaries of 10 Departments. / The MGNREGA Commissioner reviewed progress in March 2019 and the meeting was attended by State level officers of MGNREGA; Mission Director of State Rural Livelihood; Joint Director of SIRD. / The Minister, P&RD, Government of Chhattisgarh met with the ICRG team in August 2019 to discuss the possibility of extending ICRG approach across the state. / Regular meetings were held with the Secretary Rural Development and MGNREGA Commissioners. / In pursuance of the convergence agenda, meeting was conducted with the IG of Agriculture University; the CEO of CAMPA; SIRD and MD SRLM for planning and collaboration. / In Odisha, the Project Steering Committee has reviewed the programme periodically. The programme is also reviewed by the Project Directors of the District Rural Development Authorities every alternate month at state level. The Odisha Livelihood Mission has issued letters to the Project Directors to review the progress of the OLM-ICRG partnership on promoting climate resilient agriculture every month at district level and on a fixed date with the ICRG team at state level. At the district level, the programme is reviewed by the District Programme Committee in their regular monthly meetings.
1.2 Number of modules and guidebooks developed for capacity building, training and awareness generation about climate resilient infrastructure planning and implementation	cumulative 17	Exceeded / 2016-17 2017-18 2018-19 2019-20 / 12 10 12 / Total: 34 / In Bihar; (i) Design of recharge pit for districts in North and South Bihar for MGNREGA Technical Assistants (ii) Module for Q-GIS planning (iii) User Manual for Google Earth Planning and Design for Jal Jivan Hariyali initiative. / In Chhattisgarh; (i) Approach Paper for Rivulet Restoration for the NGGB programme of the state; (ii) 3 Case Studies on CRWs developed were selected by MoRD for publication of Best Practices under MGNREGA; (iii) Case Studies of CRWs implemented in 9 districts released at the Central India Workshop; Manual on Community Level Processes i.e. strengthening the Jankar Dals was documented and released at the Central India Workshop. / In Odisha; (i) Training Manual for MGNREGA Society and ICRG districts to use for Labour Budget trainings (ii) Guidelines for Preparation of Labour Budgets in the context of climate change in 2019 – these have been approved by the district administrations of all the ICRG districts and issued for use by all blocks (iii) Training modules & kits to SIRD to be used as resource material for their trainings (iv) Disaster Management Plan for PR&DW Department for 2019 (v) An Standard Operating Procedure (SOP) on Distress Migration for districts in Western Odisha was prepared. Based on this, the Department has been implementing a migration strategy in 20 migration prone blocks of Western Odisha on a Mission mode (vi) Livelihood Strategy for households in Puri & Khurda districts affected by cyclone Fani.
1.3 Number of MGNREGA plans developed with climate resilient infrastructure perspectives in 103 blocks	cumulative 500	Achieved / 1,813 gram panchayats influenced since programme inception – to integrate climate consideration in MGNREGA plans. No DPRs were developed in this year as the focus was on integration. / The state wise break up of GPs is - 129 in Bihar; 165 in Chhattisgarh and 214 in Odisha. / In Chhattisgarh additional support in reporting year was given for preparation of 4 Gram Panchayat plans on saturation mode based on NRM works; Forest Department was assisted to develop 137 Naruwa (water conservation) DPRs in 24 districts and 540 DPRs in 9 districts by the Zila Panchayat under NGGB programme. / In Odisha additional support in the reporting year for 12 GP plans in 6 migration prone districts of Balangir; technical support to MGNREGA Society to prepare 628 GP level GIS based plans in 314 blocks of the state.
1.4 Number of functionaries trained on climate resilient works planning, execution and monitoring	cumulative 1500	Exceeded / 11,138 functionaries trained in the reporting year across the three states. / In Bihar, 1132 functionaries trained (802 MGNREGA and 330 Line Department functionaries where 776 participants were from non-ICRG districts). / In Chhattisgarh 7236 functionaries trained (4838 community level resource persons; 332 Forest Department Officials for Naruwa restoration; 66 CSO members; 2000 technical & administrative officials of the 9 programme districts. / In Odisha 2770 functionaries trained at state and district level for MGNREGA & Line Department Officials.

Provide supporting narrative for the score
- The programme continued its focus on embedding ICRG approaches at the state level and with the MoRD at national level. The ICRG Resource Persons have been deployed by MoRD to train MGNREGA functionaries across the country on GIS based planning mandated for developing Gram Panchayat Development Plans (GPDP).
- The ICRG Team was invited by the National Institute of Rural Development (NIRD), Hyderabad to present the project at a national training workshop, organized in September 2019. There were participants from 20 states at the training.
- The local ICRG Teams are strategic advisors to state and district administrations of Chhattisgarh and play a key role in training and capacity building of NRM planning under MGNREGA. Lead roles were played in supporting the Forest Department in Chhattisgarh to roll out the government’s flagship programme – the NGGB. Support includes training, development of templates for preparation of DPRs and quality assurance of DPRs prepared.
- In Chhattisgarh ICRG support has succeeded in approval of Compensatory Afforestation Management Planning Authority (CAMPA) funds to the tune of INR 150 crores (£ 16m) for the Forest Department.
  [note] CAMPA Act or Compensatory Afforestation Fund Act is an Indian legislation that seeks to provide an appropriate institutional mechanism, both at the Centre and in each State and Union Territory, to ensure expeditious utilization in efficient and transparent manner of amounts released in lieu of forest land diverted for non-forest purpose which would mitigate impact of diversion of such forest land.
- In Bihar, the Team is supporting the state government to design and roll out their flagship programme – the Jal Jivan Hariyali (Water, Life, Greenery) that focuses on ground water conservation. Support has included orientation on the ICRG approach, the sharing of templates for DPR preparation and developing the institutional structure for the Authority (institution) that the state is creating for oversight of implementation of Jal Jivan Hariyali.
- In Odisha, directives have been issued in all 5 districts to scale up ICRG across all blocks. Similar embedding has been demonstrated in the partnership with the Odisha Livelihood Mission (OLM) with regular monitoring and support to convergence with MGNREGA works across the state.
Lessons identified
- Awareness around climate change and therefore the need to build resilience is well recognised across all ICRG villages, blocks and districts. The strategic positioning of the ICRG programme within the project states has been leveraged to converge with other departments for complementary interventions.
- MGNREGA is one of the key schemes of GOI which reports its contribution towards adaptation and mitigation targets of India’s NDCs. Climate and Environmental benefits created through water conservation, drought and flood proofing measures under MGNRES are recognised and reported against local adaptation actions and climate sink target of India’s NDC. ICRG has worked with MoRD and 3 States Government to strengthen and enhance MGNREGA contributions towards NDC by using climate science to better inform selection and design of the drought proofing and water management structures. The study conducted by Indian Institute of Science (IISc) under ICRG on carbon sequestration potential of MGNREGA was also used to address the parliamentary queries this year, which states:
‘According to estimates made by IIS, ‘The mean carbon sequestration achieved in 2017-18 for drought proofing activity under MGNREGA is estimated to be 25 MtCO2 (tree biomass and soil carbon) and is projected to increase to 85 MtCO2 annually, by 2030. Further during the period 2020-2030, the total carbon sequestration potential of MGNREGA drought proofing works, that could be reported under NDC is estimated to be 101 MtCO2 or 4% for the reporting period of NDC’.
[note] Drought proofing’ is the NRM activity (recognised under MGNREGA) that largely includes tree planting, horticulture and afforestation.
- The interventions on the ground have led to adoption of ICRG strategies for the roll out of state level flagship programmes in Chhattisgarh and Bihar. In Odisha, the approach has been made mandatory through government directives in all 5 districts – based on the results generated by the work carried at the district and block level.
- The ICRG programme was selected for presentation in the India pavilion at the COP25 and COP24 in the last 2 years – these are the first time ever that MoRD has participated in the COP. MORD’s participation in COP has ensured their sustained commitment towards integrating climate change into MGNREGA design and implementation.
- State governments and MoRD acknowledges the value of the trainings provided by the ICRG state teams and the PMU appointed at the ministry. The trainings are carried by using the modules developed for preparation of Labour Budgets that internalises climate information. There is a strong notional value of a PMU being established but the actual technical support is limited as they become fairly entrenched within the host entity’s targets and actions. A partially embedded support system may be of greater value to the programme itself, however, deeper analysis needs to be conducted on how PMU’s can be made more effective than their current statuses.

Output Title	Enhanced capacity of technical organisations such as academic institutions, technical engineering institutions, training organisations, CSOs
Output number per LF		2	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s)	Progress
2.1 Total number of supporting institutions trained on design, implementation and management of climate resilient infrastructure	cumulative 24	Achieved / 2016-17 2017-18 2018-19 2019-20 / 11 3 11 9 / Total: 34 / In Bihar (i) KVK Muraol, Sakra, Nalanda, Banka (ii) JEEVIKA / In Chhattisgarh (i) Forest Department (ii) ToT for 17 CSOs working in different agro-ecological zones of the state (iii) Chhattisgarh Centre for Climate Change for revision of SAPCC & inclusion of PR&RD in list of core departments for SAPCC / In Odisha (i) SIRD (ii) OLM (iii) 30 districts of Odisha trained on GIS & Remote Sensing planning of NRM works (iv) All 71 blocks of 5 ICRG districts on preparation of climate sensitive labour budgets. / Trainings have been conducted across institutions in the state – these trainings however need to be translated into improved capacities at all levels to convert the learnings into application in design climate resilient infrastructure.
2.2 Number of institutional mechanisms developed/strengthened for improved planning and measurement and implementation of works	cumulative 9	Achieved / 2016-17 2017-18 2018-19 2019-20 / 3 8 11 / Total: 22 / Parentships forged between MGNREGA and different institutions to leverage funds, resources and expertise to improve rural livelihoods. / In Bihar; (i) Department of Agriculture (ii) JEEVIKA (iii) PRADAN (iv) Chetna Foundation, Banka (v) Facilitation of farmers to link with mandi developed by Kaushalya Foundation. / In Chhattisgarh; (i) MoU with CEO CAMPA (ii) MoU with State Rural Livelihood Mission / In Odisha; (i) Partnership with ICAR-Central Institute of Women in Agriculture extended (ii) MoU with OLM extended (iii) Facilitation of partnership with ITDA (iv) Institutional partnership with Odisha Agro Industries Corporation. / The extension phase will focus on institutionalising the convergence model demonstrated in this phase to sustain the impacts and ensure long term benefits.
2.3 Number of training modules and guidebooks on climate resilient planning and implementation developed	cumulative 11	Exceeded / 2016-17 2017-18 2018-19 2019-20 / 1 5 7 14 / Total: 27 / In Bihar; (i) Module on NRM and GIS based design of NRM structures for engineering staff of MGNREGA (ii) Module for Planning and Implementation of better infrastructure in CFT Blocks in Bihar through JEEVIKA (iii) Module for water security through NRM works with ICRG concept / In Chhattisgarh; (i) As per MoU with SRLM, plan sheet for 4 livelihood activities in convergence with MGNREGA assets prepared with User Manual (ii) Manual for community level members on climate resilient perspective and use of MGNREGA for addressing climate risks (Hindi) / In Odisha; (i) Directive on 30x40 model in Mayurbhanj (ii) Directive on construction of check dam in Mayurbhanj (iii) Directive on increasing productivity of MGNREGA works through convergence issued in Keonjhar (iv) Directive on construction of rain water harvesting structure in Keonjhar (v) Directive on construction of check dam with land development in Kalahandi (vi) Directive on renovation of check dam with deepening of tank in Kalahandi (vii) Strategy to address environment induced distress migration in Balangir (viii) Directives to take up model village interventions issued to all Blocks in Balangir (ix) Directive on preparation of Labour Budget in the context of climate change issued in 5 districts.
[note] Linkage with the Department of Agriculture led to access to seeds, fertilizers and equipment for CRW beneficiaries; linkage with JEEVIKA led to CRWs beneficiaries being linked to Farmer Producer Companies of JEEVIKA; linkage with PRADAN led to CRW beneficiaries being linked with distribution centres and them being used as resource persons for capacity building; linkage with Chetna Foundation helped individual CRW beneficiaries to plantation.

Provide supporting narrative for the score
- Output 2 focuses on developing capacity of institutions which support MGNREGA implementation agencies. The programme has strategically positioned itself in the 4 years of implementation by forging partnerships/linkages with several institutions (such as livelihood mission, Krishi Vigyan (agriculture department), environment and forest department etc.) at the state level. The merit of such partnerships has the potential to trigger mainstreaming and scale up of interventions leading to climate resilience and strengthened livelihoods.
- In Bihar, linkages established with the Agriculture Department to facilitate inputs for the beneficiaries of CRWs. The ICRG programme has worked closely with the concerned Krishi Vigyan Kendra (KVKs) building capacities of farmers on seed replacement, soil management and front-line demonstration. ICRG has also worked actively with JEEVIKA to promote and strengthen livelihoods of CRW beneficiaries through Farmer Producer Societies (FPS) and with Cluster Facilitation Team (CFT) blocks on planning and implementation of better infrastructure in line with ICRG. The ICRG programme has provided strategic support in the design of the state government’s flagship programme – Jal Jivan Hariyali – and provided training on use of GIS for design of water conservation structures.
- In Chhattisgarh, the programme’s approach to planning and design of MGNREGA assets has been dovetailed into the state governments flagship NGGB. Extensive capacity building of the Forest Department staff has been conducted for the preparation of DPRs for rivulet restoration. The programme has also succeeded in inclusion of the PR&RD Department in the SAPCC and is part of the core advisory group that is revising the State Action Plan on Climate Change (SAPCC). Under the MoU with the State Rural Livelihood Mission, the programme has developed strategies for convergence of four types of livelihoods with MGNREGA structures and prepared a User Manual.
- In Odisha, 9 directives were issued by the state government to replicate NRM works as designed under ICRG. The MOU with the Odisha Livelihood Mission (OLM) has been extended as has the partnership with the Integrated Tribal Development Agency (ITDA). The programme has also facilitated partnership with the Odisha Agro Industries Corporation Limited (OAIC). These agreements and convergences with other available schemes/project funding, have contributed in strengthening livelihoods of CRW beneficiaries.
- Interactions took place with the National Institute of Rural Development, Hyderabad and the ICRG approach was presented at a training that had participation from 20 states.
Lessons identified
- National level platforms such as NIRD mandated to build capacities across MGNREGA organisation structure play an important role in promoting ICRG approach and its scale-up across the country. Initiative led by NIRD helped document four of ICRG’s case studies - showcasing best practise on water conservation which can be adopted by other states and districts experiencing water stress. Further, by inviting ICRG trainers in two national level trainings of MGNREGA functionaries and officials, NIRD supported dissemination of integrating climate risk management into selection and design of NRM assets under MGNREGA.
- The programme has been instrumental in establishing partnerships between schemes, programmes and departments at the district, block and village level to strengthen livelihoods. The linkage with horticulture department in Odisha has helped CRW beneficiary in getting free seeds to take second crop – demonstrating how MGNREGA convergence model can be applied to build climate resilience of the vulnerable poor.

Output Title	Innovative tools (e.g. IT based) and effective processes to strengthen MGNREGA systems
Output number per LF		3	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s)	Progress
3.1 Number of decision-making tools developed for planning, execution and monitoring of assets and tested in pilot blocks	5 (in 2019) / cumulative 10	Not achieved (overall) / Climate App (integrated with CLART - Composite Land Assessment and Restoration Tool for CRW-DPR preparation) – in progress / Design of a Plan Sheet for livelihood activities based on convergence with MGNREGA assets & User Manual under the MoU with SRLM in Chhattisgarh and Policy Brief on Convergence under ICRG / Excel based sheet for assessing the water efficiency of water harvesting assets of MGNREGA in Chhattisgarh (In progress) / Excel based tool for design of typical NRM structures under MGNREGA. / *see Annexure 1 for all decision-making tools.
3.2 Improved geo-tagging of MGNREGA infrastructure	Monthly data analytics report produced	Achieved / 3,212,148 MGNREGA assets have been geotagged as on 4.12.2019. / Information used by MoRD for review of progress and reporting to the Prime Minister’s office; reports also used during Labour Budget and Mid-term review meetings of states. / ‘GeoMGNREGA Watch’ a 24x7 service for trouble shooting continued to be maintained.

Provide supporting narrative for the score
The support provided to the MoRD at the national level through the PMU is acknowledged by the department. The PMU supported geotagging of 32.1 million assets completed under MGNREGA, helping MORD for regular monitoring and reporting to the Prime Minister’s Office. Extensive support has been provided for training staff across India on GIS based planning of MGNREGA assets. The M&E Framework designed under ICRG, measures the environmental benefits of MGNREGA assets in the 103 blocks. The trend analysis of the M&E results shows positive impact on the bio-physical and socio-economic indicators due to improved designs.

Lessons learnt
- There has been significant success in training of MGNREGA functionaries on GIS based planning for designing NRM assets. ICRG’s district engineers from all three states, due to their proficiency in planning tools have been appointed as resource persons by MORD for conducting trainings under MGNREGA. Using this as an opportunity, ICRG team takes one session during these national level trainings on climate proofing of MGNREGA-NRM structures.
- The MoRD’s publication on Water Conservation includes four case studies covering ICRG interventions that have been duly vetted by a 3rd Party appointed by the National Institute of Rural Development, (NIRD), Hyderabad. These 4 case studies highlight the ICRG process adopted to build overall climate resilience of the community and people – which can easily be replicated by other states and district.
- The use of tools like card games, climate kunji, short films by Civil Society Organisation (CSO) working at the community level, has built awareness amongst farmers (especially women farmers) on climate change which in turn has influenced the choices they make in selecting NRM assets under MGNREGA.

Output Title	Evidence generated and shared nationally, regionally and more widely to inform policy and wider investments in design and implementation of public works-based programmes by building climate resilient livelihoods and physical assets
Output number per LF		4	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s)	Progress
4.1 Number of knowledge products, policy and strategy briefs, video documentaries and peer reviewed papers developed and disseminated (including video documentaries)	cumulative 20	Achieved / Around 20 new evidence papers were developed in this review period, some of these are listed below / Concept notes on climate risk management framework delivered to the Rural Development Departments of Karnataka and Andhra Pradesh / National Adaptation Fund for Climate Change (NAFCC) Concept Note / Social protection background paper for the Global Commission on Adaptation - IIED presented key concepts and evidence from MGNREGA’s current and potential strengthened role for adaptive social protection (and examples from ICRG). / Background paper: implications of climate variability on the Mahatma Gandhi National Rural Employment Guarantee Act (MGNREGA) / Cross state paper including the synthesis paper: on role of MGNREGA in enhancing adaptive social protection. / In Bihar; (i) Documentary on use of IEC in planning MGNREGA (ii) Case Studies (5) and Snippets (iii) Case Study on Gender & MGNREGA / In Chhattisgarh; (i) Case Studies (9) and Snippets (19) (ii) Policy brief on Vulnerable Group Study by TISS Hyderabad (iii) Power Point presentation on INRM approach; GIS assisted Model Plan / In Odisha; (i) Case Studies (5) and Snippets (35) (ii) Policy Brief on environment induced migration in Odisha (iii) Document on institutionalization of best interventions in Odisha (iv) Disaster Management Plan for PR&RD for 2019 (v) Video documentation of 2 best ICRG CRWs of Kalahandi & Mayurbhanj prepared by IIT Kharagpur for MoRD (vi) Strategy for preparation of labour budgets in the context of climate change prepared for ICRG districts and issued as directives in all 5 districts (vii) A concept note on ‘Setting up a Climate Change Resource Cell’ prepared and submitted to PR&RD / A film on preparation of Labour Budgets / 4 films for MoRD of which 3 are yet to be released (http://www.youtube.com/watch?v=cJ4WPSEFSlo&t=5s) / 117 blogs – a web page designed to collate all the success stories on water conservation work done under MGNREGA (https://nrega.nic.in/netnrega/JalShakti/MGNrega waterconservation.aspx) / 450 success stories on water conservation under MGNREGA have been collated from across the country. 117 of these stories have been verified a 3rd Party and compiled for a publication called ‘Jal Sangrah’. This publication includes 4 case studies of ICRG interventions. These stories will be visible on the above links as blogs after the release of the publication. / 3 new publications for MoRD – the Annual Master Circular English 2019-20 (https://rural.nic.in/sites/default/files/nrega/Library/Books/FINALBookAnnualMaterCircular(11.07.19).pdf); the Annual Master Circular Hindi 2019-20. This is the first time that a Hindi edition has been released (https://drive.google.com/file/d/17l3TDfqlgwgtjKPaPVMahFLKVWPzR1A/view?usp=sharing); the publication titled ‘Jal Sangrah’ is yet to be released / 17 presentations were prepared for MoRD on various topics (https://drive.google.com/drive/folders/1OGBmmbukQ-5j9hkezlF12HSexay5gi78?usp=sharing) / Note: ICRG was also cited in a publication as the only programme which is helping MGNREGA to mainstream climate change. Publication: India in a warming world, integrating climate change into development, by Navroz K. Dubash (2019); Resilience Shift programme (funded by the Lloyds Register Foundation) selected ICRG programme and documented it as part of the global innovative resilient infrastructure projects.
4.2 Number of knowledge exchange events/forums organized	cumulative 15	Achieved / While the national workshop wasn’t conducted, the programme carried several state level events to disseminate ICRG results. / In Bihar; (i) NRM & use of Google Earth for planning climate resilient structures under Jal Jivan Hariyali programme (ii) Workshop on Water Security & design of structured (ii) Gender & NRM and Vision workshop in JEEVIKA as partner agency (iv) Land based livelihoods and climate change with CSO partners / In Chhattisgarh; (i) Central India workshop on Building Climate Resilience of Central Indian Drylands with participation in collaboration with the PR&RD; Centre for Climate Change, Forest Department, Government of Chhattisgarh. Participation from Maharashtra and Madhya Pradesh and national institutions. Participation by Chief Minister, Minister PR&RD and Minister Environment & Forests (ii) 2 ToT workshops for 66 members from 15 CSOs participated in the workshop. / In Odisha; (i) Water Resource Management- Desalination” at the International Conference on Climate Change, Water & Food Security” (CCWFS-2019) in Bhubaneswar (ii) “Our Actions are Our Future”- Healthy Diets for #Zerohunger World” organized by ICRG and Central Institute for Women in Agriculture (iii) Workshop on ‘Strategy to Reduce Distress Migration in Western Odisha’ in MGNREGA Society (iv) District level sharing workshop on ‘Migration Package to arrest Distress Migration’ in 4 districts (v) Workshop on “Strategy to reduce climate induced distressed Migration” was held at Balangir district. / At national level presentation on Convergence for Improved livelihoods at the 8th Global Agri-Connect. DFID’s other programmes such as Bihar AGRI project and Climate Proofing for Growth and Development were also showcased. / ICRG were resource persons at a national training organized by NIRD, Hyderabad. / ICRG was presented at the World Sustainable Development Summit (WSDS) in February 2019 (on Mobilising Finance for Adaptation in South Asia). / ICRG was presented at the Community Based Adaption, April 2019 in Addis Ababa, Ethiopia. / ICRG Programme presented at a side event in the India pavilion at COP 25 in Madrid, Spain. / Meetings/interactions with GoI / The studies conducted under ICRG were presented to ministry officials at several occasions. The Indian Institute of Science (IISC) study on carbon sequestration potential of MGNREGA (supported under ICRG) was used to respond to parliamentary queries raised in December 2019. The IISC has demonstrated that MGNREGA has led to increasing Soil Carbon Capture, reducing land/soil erosion and reduction of vulnerability to Climate risks.
4.3 Number of demonstrable prototypes of climate resilient infrastructure supported and documented	cumulative 600	Exceeded / 1156 DPRs (i.e. 792 CRWs) facilitated since inception; 624 DPRs in the reporting period / In Bihar 35 were facilitated / In Chhattisgarh 338 DPRs were facilitated / In Odisha 251 DPRs were facilitated

Provide supporting narrative for the score
The methodology used by ICRG team in preparing the designs of the CRW’s has been embedded in MGNREGA planning in the 103 programme intervention blocks and recognised as a standard operating procedure. In Odisha, all 5 district administrations under ICRG have issued directives to follow the approach demonstrated under ICRG for planning and design of MGNREGA infrastructure. In Chhattisgarh, the approach has been adopted under the NGGB programme for the Naruwa (water conservation) component. Knowledge sharing between the states has shown significant improvement due to efforts made by MORD in documenting and disseminating best practices on water conservation, drought proofing and integration of climate risk management, with help from the PMU. Also, creating a presence of MGNREGA in social media, made possible through the support provided by the PMU has helped disseminate knowledge created under ICRG. In the last reporting period the following social media platforms were created and are being maintained in this reporting period:
1. Youtube channel – https://www.youtube.com/channel/UCIicGPL5tTD23FvCDFOhrOA/videos
2. Wordpress Blog of MGNREGA – https://mgnregasuccess.wordpress.com/

Lessons learnt
- Global and national discourse on social protection and climate resilience is growing – practices adopted by ICRG for effective climate mainstreaming can be developed into standard approaches/methods which can be shared with other countries. (Feb 2020)
- Documenting best practises and case studies act as a powerful tool scale-up and replication – this is evident from the embedding of the ICRG approach (on water conservation, drought proofing, integration of NRM works across small watershed area) in state government flagship programmes in Bihar and Chhattisgarh and in multiple platforms in Odisha.
- To increase dissemination of ICRG studies and researches, technical papers/products need to be peer reviewed by Government officials from MORD and MOEFCC. (ongoing)
- Knowledge products such as training manuals and climate tools to be adopted by the ministry to maximise outreach. Programme to engage closely with MoRD to ensure integration of climate interventions in standard guidelines and manuals of MGNREGA.
- While, the ICRG programme produced several DPRs and designed CRWs the knowledge needs to be transferred to the MGNREGS functionaries at the district and block level, so that they are able to execute the design independently to sustain and scale-up the ICRG impacts.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)
At the Impact level, ICRG seeks to improve the ability of the poorest and most vulnerable people in the focus states (Bihar, Chhattisgarh, Odisha) to tackle impact of climate extremes. At the outcome level, ICRG focuses on improving the quality and creation of climate resilient assets under MGNREGA and other convergence schemes. To achieve the above, inputs are designed to address the identified and agreed requirements to enhance state, technical, systemic and learning capacity.

While there have been no major changes with regards to the programme’s theory of change in the past year, the target on certain output indicators have been revised to reflect the changing context of programme delivery as illustrated in the table below. ICRG+ proposes to refine the current TOC and make it more robust by using learnings from the end term evaluation and Phase I implementation.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead.

In the last 4 years of implementation, interventions across all input areas have collectively worked at outcome level. Some of the principles demonstrated under ICRG have been noted by the respective state governments as well as the MoRD and reflected in the various directives issued for adoption of ICRG practices.

Progress against the outcome level indicators is as given below.
Outcome	Outcome Indicator 1	Milestone (s)	Progress
Improved quality of the physical assets under MGNREGA	Increase in number of MGNREGA infrastructure which will lead to climate resilience improvement (flood protection, net irrigated area and ground water improvement)	Positive change in choice, budgetary allocation and infrastructure options at block level for improved climate resilience	The programme has facilitated selection and design of 792 Climate resilient works. since inception. (details in Annexure 7) / In addition to prototype CRWs, 92 DPRs with 282 CRWs consisting 1146 MGNREGA works have been prepared and submitted in 33 blocks of Chhattisgarh. / The programme has supported preparation of 785 DPRs for Nala restoration and Saturation based NRM plan. / The programme has also influenced the labour budget (LB) preparation of 604-gram panchayats (Odisha – 214 GPs, Bihar -225 GPs and Chhattisgarh – 165 GPs). In addition, in Odisha, programme indirectly influenced LB preparation in 628 GPs. In total LB influenced 1233 GPs. / In Chhattisgarh, the ICRG approach for water conservation has been adopted under the state government’s flagship NGGB programme. ICRG has provided strategic guidance for programme implementation; training across the entire state; development of templates for preparation of DPRs and quality assurance of DPRs. / In Odisha, the district administration has issued directives to all blocks in the 5 districts under the programme to scale up the ICRG approach. / In Bihar, the ICRG has provided strategic support in the design and roll out of the state governments Jal Jivan Hariyali programme that focuses on ground water conservation and recharge.
	Outcome Indicator 2
	Volume of public finance mainstreaming climate change (including additional climate finance) (in million GBP)	cumulative £ 40 million	£ 22.67 million of public finance mainstreaming climate change because of ICRG support in the reporting period - / £ 45.34 million cumulative in project period. / (details in Annexure 4)
	Outcome Indicator 3
	Climate change integrated in MGNREGA policy and planning (using ICF KPI methodology for “level (1-10) of climate change integration in national planning.”)	10	10 directives issued under ICRG / Inclusion of climate change considerations in the Annual Master Circular 2019-2020 by MoRD, GoI. / 9 directives in Odisha. / (details in Annexure 2 and 3)
[note] The amount is calculated based on the costs of the individual MGNREGA structures proposed as part of the 1156 DPRs (which include 2552 works). These DPR’s have already been accepted under the labour budgets and the money allocated to the villages for the development of these assets.

Compliance to the Gender Equality Act:
The programme has a strong focus on inclusion (reducing gender inequality, mainstreaming persons living with disability (PWD) and particularly vulnerable tribal groups (PVTGs) /marginalised) and empowerment of women belonging to the poorest households. Women headed households are prioritised in all ICRG blocks during selection and development of CRW’s. The skill development and training programmes have also been developed with special focus on women beneficiaries. During the process of labour budgeting and GP levels decisions on the assets to be created, facilitated by the TA, have ensured special focus on inclusion of women in both consultation and decision-making capacities. In Addition, the Civil Society Organisation working at the community level, uses card games, climate kunji and other tools to build awareness amongst farmers (especially women farmers) on climate change and how it should be reflected in the choices and demand under MGNREGA plans.

Contribution to International Climate Fund (ICF) objectives:
The programme fully contributes to International Climate Fund (ICF) objectives and therefore the entire spend is reported under ICF budget head. The programme is focused on the most climate vulnerable states and districts in India and it delivers on four key performance indicators of ICF pertaining to climate resilience and adaptation. Out of these, two ICRG Logframe indicators directly measure ICF KPIs whereas two indirectly contribute to ICF KPIs. A summary of these indicators is shown below:
Sl No.	ICRG Logframe Indicator	ICF KPI	Contribution
1	Number of households with improved resilience in 3 states – with disaggregation of women and social groups. (Impact Indicator)	Number of people with improved resilience as a result of ICF support (ICF KPI 4)	Direct: 2635 beneficiaries
2	Volume of public finance mobilized for mainstreaming climate change (Outcome indicator)	Volume of public finance mobilised for climate change purposes as a result of ICF funding (ICF KPI 11).	Direct: 42631.04 / Lakh INR / (45,207,634.48 GBP) / *labour budget in Bihar not yet finalized so that figure is not included.
3	Number of functionaries trained on climate resilient works planning, execution and monitoring (Output indicator)	Level of institutional knowledge of climate change issues as a result of ICF support. (ICF KPI 14)	Indirect: 35,340 people
4	Outcome indicator: Percentage increase in number of MGNREGS infrastructure which will lead to climate resilience improvement (plantation, flood protection, net irrigated area, etc.) that has potential for carbon sequestration in tCO2 equivalent	Greenhouse gas emissions reduced or avoided (tCO2). (ICF KPI6)	34009.17 (tCO2) / (details in Annexure 5)
5	Number of Knowledge products and policy briefs developed and shared publicly to contribute to the global efforts on addressing poverty and environmental issues simultaneously. (Output indicator) / Labour Budget policy brief / Saksham Training module / Policy Brief on Convergence / Policy paper on MIS for MGNREGA / Policy paper on Rights based ACT for Climate Resilience / Paper on Water Resources in a changing climate: Is MGNREGA able to address insecurity in rural India? / Paper on Climate responsive social protection: challenges and opportunities for mainstreaming climate change in MGNREGA in India. / Paper on Climate awareness and behavioural change in rural India.	Extent to which ICF intervention is likely to have a transformational impact (ICF KPI 15)	Indirect: 8
[note] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/253682/ICF-KPI-summary.pdf

Note: ‘Direct Beneficiary’: Beneficiaries which are directly covered under the DPRs developed by the ICRG team in the 103 blocks of 3 states; Indirect Beneficiary’: Beneficiaries of the villages in which the ICRG team has influenced the labour budgets (as well as the decision-making process regarding the selection and design of the NRM structures) through their partner NGOs and capacity building of MGNREGA functionaries.

Describe any planned changes to the logframe as a result of this review (1/2 page)
After substantive review in the last review period, no major changes were undertaken in the Logframe milestones for the last year of Phase I implementation. The activities and their corresponding outputs in this reporting period focused on scale up of ICRG interventions and embedding of climate risk management into MGNREGA design and implementation (at national, sub-national and district levels). If and when the programme enters its proposed new phase (ICRG+), a more robust Logframe will be designed which takes into account the learnings from Phase I and aligns the milestones of each indicator based on the ambition set for phase II.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

IPE Global, the main TA partner for the programme implementation was selected through OJEU contracting process and is responsible to provide technical assistance to MoRD and three State governments towards achieving the programme outputs. Their resources deployed for this programme includes a central level team, three state level teams, an IT support unit within MoRD and pool of experts drawn when needed, along with an Advisory Board comprising of experts for whose time, no fee is charged. The contract includes a Research and Innovation Fund to support innovation, evidence generation and commission research in issues emerging from the programme. The cost of personnel deployed by the main contract partner IPE Global is the main cost driver of ICRG. Resource spent on creating knowledge portals has also been kept tight and legitimate to use the existing resource people to collate and write and bring in external consultants only for the last bits of work.

In the reporting year, focus on building a constituency through Global AGri Connect and by showcasing ICRG’s impact through Communities of Practice has also led to better uptake of elements. Odisha DRDA Guidelines and GO for Keonjhar & Balangir, Samarthya  Manual incorporating climate  resilient  designs has ensured that components developed under the programme will continue to deliver development and adaptation benefits even after the investment has long been stopped. Such institutionalising and scale-up elements are the most substantial value for money benefits.

Assessment of whether the programme continues to represent value for money
Some of the indicative priority areas which will offer VfM include:
S. No.	Priority areas for the year	VfM approach
	Capacity development of Administrative and Technical Staff engaged in MGNREGA implementation	The costs pertaining to hosting the capacity development programmes and the participation costs of the government personnel were covered by the respective state governments.
	Demonstrate climate proofing of MGNREGA assets (~600) in 103 blocks	100% of the costs pertaining to the wage and material cost for all demonstration structure were covered through fiscal allocations under MGNREGA to the three ICRG states.
	Revision and institutionalization of the training materials for BFT and District and Block Level Technical Resource Teams	The institutionalization of revised Samarthya Manual and BFT Training manual to have pan-India implication on climate resilient design of MGNREGA assets. / The inclusion in AMC would mean sustainability in allocation of resources to climate resilience as well as use of techniques and tools developed by ICRG.
	Climate specific studies such as modelling and carbon sequestration	One-time investments in the Block adaptation packages are being considered as a sure proof way of converting complicated climate information into feasible development plans. This approach has seen value in National Action Plan (NAP) Global network, Climate Action Network South Asia, and is being replicated by Development Alternatives and WWF for Climate Smart villages work in the Sunderbans.

Economy:
The programme has made enough economic gains in terms of the inputs invested into the technical support provided by different delivery partners. These economic gains are illustrated below:
- The programme approach ensures value added support to MoRD by complementing their existing systems rather than creating parallel systems.
- International expertise on social protection and climate resilience is leveraged (from Ricardo Energy and Environment, University of Manchester – consortium members of the main TA partner) to design easy to use climate tools, training materials, and prototypes of climate resilient works are developed under the programme which can be adopted by other states at no additional costs.
- Around £ 45.34 million of public finance has mainstreamed climate change priorities in MGNREGA planning and execution. This amount corresponds to 2552 MGNREGA structures as part of the 1156 DPRs developed, with climate compatible design and location of NRM structures, which are accepted under the labour budget thus far.
- The cost saved by virtue of hosting workshops in government premises, was beneficial to the programme. The Raipur state workshop spent 40% less than what could have been the expense if hosted at a hotel premise.
- The programme team works closely with the state governments and has been successful in scaling up ICRG’s best practices in Odisha with the state government adding a new district.

Efficiency:
- Efficiency is achieved by exceeding the output milestones in this reporting period. The efficiency gains have also been realized through faster achievement of targets in comparison with the programme milestone.
- Efficiency gains have been enhanced by ensuring sustainability of use and implementation of tools and techniques produced by ICRG as well as by integration of the guidelines into the Annual Master Circular – in essence the investment made once will continue to accrue returns even after the TA is completed.
- The district level Government Order (GO) in Odisha would ensure that the climate integration and development of CRWs continues as the focus of MGNREGA in the districts and the adaptation of the ICRG approach into the Government of Chhattisgarh’s flagship programme, NGGB – this would accrue multiple climate benefits for a longer time for the same investment.
- The CSO training and engagement and orientation to integrate Climate resilience into MNREGA schemes has cascading effect on wider application and enhancement in the number of beneficiaries (Direct: 24618; Indirect beneficiaries: 151752).
- Over 35,000 people were trained under the programme by training of trainers, and trainings provided through local partners and government training system.
- The ICRG approach on developing adaptation package has been shared with communities of practice that are supporting several governments in their respective work during state and national workshops this year. ICRG has built synergies with other practitioners (such as GIZ, UNDP< USAID, World Bank, etc.) which will increase coverage and scale of benefits of the programme. The team will develop this relationship further in the coming year.

Effectiveness:
- The programme has proven to be highly effective in it’s on the ground delivery across the 103 blocks by ensuring adoption of CRW approach across the board. Improved structural designs of NRM assets have accrued environmental benefits that improve ecosystem services overall (water conservation, soil moisture enhancement, etc.).
- This phase of the programme has achieved its targets on leveraging finance (~£40 Million) through convergence with other schemes/departmental funds; scale up and mainstreaming into the state level policies such as NGGB in Chhattisgarh, adoption in non-ICRG blocks and districts in Odisha and integration with the Jal Jivan Hariyali Mission in Bihar.
- Inclusion of the Climate Resilience and convergence methodologies and guidelines provided by ICRG into the AMC and the announcement by the Joint Secretary at COP 25 in Madrid on adoption of ICRG best practices (and approach to integrate climate risk management into MGNREGA) have been larger strategic achievements that fulfils the sustainability criteria effectively.

Equity:
- ICRG interventions are inclusive from the beginning and this year the focus remained on women headed households and persons living with disability (PwD) during selection of asset creation. The number of PWD who were included in the design of CRW increased by over 50% from last year reaching to a total of 89 beneficiaries.
- In the reporting period, of the 2881 households that will benefit from climate resilient works, 884 are SC, 455 are ST and 1018 are OBC and/or Minority communities.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

As explained above, the programme has demonstrated Value for Money on all 4 counts of Economy, Efficiency, Effectiveness and Equity. Thus, it should continue on its own merits. This programme sits in the Urban, Energy and Green Growth portfolio of DFID India. This is an important (with 100% ICF) programme that directly addresses adaptation to climate change and builds climate resilient rural communities, livelihoods and infrastructure in DFID India’s portfolio. The Programme is designed with a focus to have a transformational effect on the world’s largest labour-based social safety net programme. The programme’s technical support is improving quality of assets built under MGNREGA, thus delivering direct benefits to approximately 5 million people, as well as avoiding the loss of £15 million of public money and enhancing the effectiveness of the £7 billion spent annually by the Government of India on MGNREGA as estimated during the business case.

India plays a major role in global efforts to address climate change with 60% of its population at high risk from climate, with most comprising of poor living in rural areas, thus the success of this programme in terms of ensuring Value for Money is integral in the DFID India narrative. While the funds are going towards Technical Assistance only, social impact stories have documented tangible benefits in increasing the productivity of the most vulnerable rural households in the project areas.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
A risk register of the programme has been developed and modified following the last Annual Review using the latest risk management guidelines of DFID. Overall the risk level remains at moderate. The Government of India remains committed to provide necessary budgetary support to MGNREGA. Continuous engagement with the MoRD at national level and with the state governments has not only helped align with the government priorities, it has also led to scale up in additional districts and blocks in Odisha, Chhattisgarh and Bihar. The training conducted by the ICRG Teams is delivered at state level and this contributes to ensuring continuity in case there are personnel changes. The programme needs to build more inroads in MoEFCC in the final year of implementation and henceforth will be an area of focus.

Overall risk rating: Moderate
Key Risks (and Residual Risk Rating post Mitigation)	Mitigation measures
Delivery: Proposed policy and institutional reforms may be delayed due to long drawn government processes [Major]	The team closely engages with key stakeholders and decision makers to speed up the process of approval. This is further ensured via a 6 member PMU support provided to MoRD and progress meetings conducted by Programme Steering Committee Meeting (Biannually) at the national level and monthly review meetings at the state level.
Delivery: Frequent transfer of senior government officials involved in project may delay interventions that require government approvals [Moderate]	The TAST regularly monitors government counterpart movements and takes measures for smooth handover process for such transitions. Focus on strengthening systems and policies to avoid risk related to individuals (such as inclusion of climate change in the schedule of MGNREGA)
Delivery: Risk of programme deliverables not achieving intended impact. [Moderate]	The team works in close consultation with MoRD at the national level and State Rural Development Departments (Bihar, Chhattisgarh, Odisha). All activities are formally agreed and tracked with partner department at the annual Programme Steering Committee (PSC) and monthly state review meetings. There is scope for the PSC to deliberate on priority areas and change deliverables, if the latter does not have the desired impact. The programme has also contracted a third party to conduct a Mid Term (which was submitted in May 2019) and End Term Review (due by March 2020) which will capture the extent of impact of the programme’s activities systematically feeding into the design of ICRG Phase II.
Delivery: Capacities created through the programme fail to be sustainable after the programme ends. [Major]	In the last year of implementation of Phase I, the programme had a strong focus on ensuring sustainability of the institutions created. This included extensive discussions with MoRD and MoEFCC and other development partners on – embedding climate change objectives within MGNREGA delivery with sustainable sources of climate finance. To ensure that capacities on climate adaptation are built within line departments, communities, CSO partners and state governments to effortlessly deliver climate objectives through MGNREGA – the programme team developed training modules which can continue to be rolled out with MGNREGA regular trainings. In addition, IIED is developing a regional and state specific proposal in consultation with MoRD to leverage additional climate funds to sustain the climate resilience interventions demonstrated under ICRG.
Delivery: State elections and code of conduct for one to three months impacting the delivery of the programme. [Moderate]	In the reporting period, centre and state elections (Bihar and Odisha) were held of which the programme team was aware. The team worked closely with line departments and officials to ensure approvals are given before the election dates were announced. Also, to ensure early buy-in from government officials, newly appointed at both centre and state, the programme team organised a state workshop and a presentation for new officials/minister and presented the progress on ICRG and its design.
Operational: Delays in release of funds for MGNREGA by GoI &/or state governments. [Moderate]	The team will closely work with line departments and MGNREGA functionaries at the block and district level to ensure spend and accurate measures taken to estimate budgets.
Safeguards: The programme might not reach persons with disability and women beneficiaries, leading to unintended exclusion. [Moderate]	The programme explicitly captures inclusion as one of the impacts by targeting 50% women beneficiaries. In this reporting period, the programme developed two evidence papers one on ‘how disability is addressed in MGNREGA and other social protection programmes’ and other on 'How can social protection programmes like MGNREGA enhance the ability of women to respond to climate change?' to help track MGNREGA benefits PwD and women and inform related policy on inclusion. These case studies and specific recommendation will be shared with GoI as policy briefs.
Safeguards: Risks of unreported sexual exploitation, abuse and harassment of children, young people and vulnerable adults who work with delivery partners, as well as their own staff and volunteers. / [Moderate]	Delivery partners work with CSOs and community mobilizers in the field and have been instructed by DFID to follow its enhanced safeguarding standards. During selection of a suitable vendor DFID conducts a due-diligence and reviews the organisations policies. First tier partners are reminded of their responsibility every six months to ensure appropriate safeguarding standards have been cascaded down the delivery chain. SRO shares new enhanced standards and emphasise its application throughout their delivery chains. Evidence that the standards have been shared and that partners are clear about the expectations were recorded and reported duly in the reporting period. This practice will continue till the end of project.
Reputational: Failure to deliver intended development objectives as per GoI expectations. [Moderate]	Review with GoI to ensure programme and expectations are on track - once every two months. Quarterly review of project progress with supplier – not only in terms of money disbursed against milestones but also in terms of development impact assessment. In addition, recommendations from mid-term evaluation will be fed into the programme delivery.

Update on partnership principles
DFID India’s Partnership Principles state that DFID India’s support is based on a shared commitment to the following four principles:
  1. Helping India reduce poverty and leave no one behind
  2. A commitment to respecting human rights and other international obligations
  3. A commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption
  4. A commitment to strengthening domestic accountability
In line with the above, ICRG complies with the partnership principles and where funding is channelled through partner organizations, this is done in accordance with these principles. Compliance to these principles is ensured through stocktaking against IAD and Annual Review recommendation, Due Diligence, Financial Audits, Mid-Term and End Term Reviews and sharing results with MoRD and state officials.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)
Programme progress is on track (in most cases exceeding) for all four outputs. Delivery against the agreed outputs is monitored and reported on a quarterly basis. In the reporting period, the programme team resolved the programme delivery and finance issues observed in the last review in collaboration with the main implementing partner and established a management framework.

Financial Performance:
Overall the programme is delivering against its financial targets, however there have been cases of variance in monthly expenditure against forecast due to unforeseen delays in approvals by Government officials on workshop, standard guidelines, and manuals. The main TA service provider (IPE), have been made aware of DFID compliances in terms of quality, cost and transparency requirements and have discussed in detail the recommendations on programme’s financial management made by PCD.

The PMU support to MoRD has been extended in the reporting period with budgetary provisions made in the main TA contract. Utilisation with respect to research and innovation funds (RIF) and resource funds (RF) will be monitored to keep them below contractual provisions. Invoicing and financial statements will be monitored closely by the DFID Task team to observe compliances, any profit variance and use of open book accounting.

Date of last narrative financial report(s)	10 Oct 2017
Date of last audited annual statement (s)	01 Sep 2017

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
Logframe and M&E framework developed in the reporting period are the two main basis of programme monitoring. In addition, the monitoring of the programme in the review period was undertaken as follows:
- A National Steering Committee meeting chaired by MoRD was held in June 2019. Regular meetings at state level and district level in the three project states.
- Field visits by DFID Team along with TA partners in Bihar, Chhattisgarh and Odisha.
- Monthly meetings with IPE Global and monthly progress reports and payment-based deliverables.
- Quarterly Progress Reports (QPR) with output wise information update, key achievements and challenges faced.
Evidence (1/2 page)
The evidence supporting the programme’s theory of change has strengthened. The policy directions of the GOI with regard to MGNREGA such as increased budget allocation for natural resource management and focus on quality of infrastructure reconfirm the evidence base further. Research conducted by IIED and University of Manchester builds evidence on MGNREGA contribution in building resilience and highlights the need to integrate climate risk management into the provision of services provided under MGNREGA and planning natural resource management structures.

A set of eleven interventions are identified in the reporting period collated from literature, programme experience and evidence generated from studies conducted by MoRD, GIZ, UNDP and the DFID funded ICRG programme. The recommendations are assessed individually using IIED’s ‘Pathway to Resilience’ analytical framework that unpacks the theory of change for each intervention’s impact on strengthening resilience. The M&E framework which has collected data in the pre and post monsoon period this year will establish programmes impact against specific socio-economic indicators. The mid-term evaluation results also validate the programme’s theory of change and highlight that the programme beneficiaries are positively impacted by the ICRG interventions that builds climate resilience.

The ICRG programme has an inclusive approach and is tracking disaggregated data as evidence of this approach. The table below shows the details in the project states.
Bihar	1931 SC/ST/OBC benefiting from climate resilient works (SC+ST+OBC) / 35 women-headed households benefiting either directly through wage earnings under MGNREGA or through improved livelihood opportunities
Chhattisgarh	426 SC/ST/OBC benefiting from climate resilient works (SC+ST+OBC) / 8 women-headed households benefiting either directly through wage earnings under MGNREGA or through improved livelihood opportunities
Odisha	491 SC/ST/OBC benefiting from climate resilient works (SC+ST+OBC) / 28 women headed households benefiting either directly through wage earnings under MGNREGA or through improved livelihood opportunities
Consolidated	2848 SC/ST/OBC benefiting from climate resilient works (SC+ST+OBC) / 71 women-headed households benefiting either directly through wage earnings under MGNREGA or through improved livelihood opportunities

Refer to Annexure 6

Learning (1/2 page)
The third-party end term evaluation of ICRG will draw lessons from programme’s design and implementation – these will be documented and presented to key stakeholders in March 2020. ICRG has developed case studies; worked with MoRD to create a presence for MGNREGA on social media and has participated in several workshops at national and state level. These are contributing to the overall knowledge management under the programme and documentation of the learnings emerging from project implementation and discussion on climate resilience.

Progress on recommendations from previous reviews (1/2 page)
The table below provides an update on the recommendations from the previous reviews.

Recommendation	Progress
Building and strengthening partnerships: develop and implement a strategic dissemination strategy	Dissemination strategy was developed for the final year of phase-I implementation and several state and district level workshops were conducted for dissemination. In Addition, the team created a compendium of case studies and designed policy briefs and guidelines which presents the ICRG approach and process to help scale-up in other blocks and states.
Ensure sustainability of the intervention	Research and evidence papers developed under ICRG were modified into short policy briefs and designed as impactful case studies for both internal and external stakeholders. The programme focused on the capacity building of MGNREGA functionaries by creating standard guidelines on CRM, training manuals and climate tools that were presented to the ministry to maximise outreach.
Engagement with the Ministry of Environment, Forests and Climate Change	This is ongoing – Several meetings were held in the reporting period to introduce the key interventions of the programme and present the outline of the NAFCC proposal. The programme was also selected under the India pavilion in COP-25 due to this engagement with MoEFCC.
Continue strong engagement with MoRD to ensure alignment with GoI priorities under MGNREGA and mitigate emerging risks	This is continuous. MoRD has a new Joint Secretary in charge of MGNREGA from October 2019. The MoRD has requested DFID for extending the support of the PMU demonstrating the perceived value of the support.
Development of a value for money strategy	A framework for this has been developed stating the indicators to be monitored across the 4 ‘E’s’.
Special focus on disability inclusion in infrastructure planning and design for the programme approach	This has been done. Recommendations from the paper on disability are being incorporated in the designs of the climate resilient works.
Two key delivery partners IPE Global and IIED to work together in the last year of phase I implementation.	This was ensured by identifying and laying out specific time inputs from experts of both organisation in their respective work plan and outputs. There was joint participation by IIED and IPE in COP25 and the event was designed in consultation.

Annexure 1: Number of decision-making tools developed for planning, execution and monitoring of assets and tested in pilot blocks (Cumulative)

S.No	AR year	Tools Title
1	17/18	A climate change impact assessment study for all 103 ICRG Blocks have been completed and a tool for conducting the climate impact assessment in other Blocks prepared.
2	17/18	State specific climate change adaptation packages have been developed for Odisha, Chhattisgarh, and Bihar to help decide the choice and design of works that are most appropriate to reduce vulnerabilities and enhance climate resilience. The Block Adaptation Packages are based on the Climate Modelling Study and Vulnerability Assessment carried in 2018. The Adaptation Package lists the most appropriate works (both community and individual) to address risks of drought and flood in the Block. This is a decision-making aid for the MGNREGA functionaries while choosing works for inclusion in the Labour Budget. The adaptation packages were revised post field surveys in 2018-19.
3	18/19	Climate App
4	18/19	Block level decision-making toolkit
5	18/19	Addressing disability in design and access of MGNREGA assets
6	18/19	Monitoring and Evaluation framework
7	19/20	Design of a Plan Sheet for livelihood activities based on convergence with MGNREGA assets & User Manual under the MoU with SRLM in Chhattisgarh (Submitted to SRLM) and Policy Brief on Convergence under ICRG
8	19/20	Excel based tool for design of typical NRM structures under MGNREGA.

Annexure 2: List of Directives issued by the Odisha ICRG districts

in 2019 in Odisha, the ICRG districts have identified the best interventions in every district and issued directives to all blocks to institutionalise those interventions. A total of 9 directives have been issued.
1. Directives on Climate Resilient Structure of 30*40 model has been issued by Mayurbhanj district
2. Directives on Construction of Check dam in the context of climate change has been issued by Mayurbhanj district.
3. Directives on making MGNREGA works productive through Convergence has been issued by Keonjhar district.
4. Directives on Construction of Rain Water Harvesting Structure taken up under ICRG has been issued in Keonjhar district.
5. Directives on Construction of Check dam with Land Development has been issued in Kalahandi district.
6. Directives on Renovation of Check Dam with Deeping of tank has been issued in Kalahandi district.
7. Directives to address environment induced distress migration has been issued in Balangir district.
8. Directives to take up the model village interventions also approved and issued to all the Blocks of Balangir district.
9. Directive of preparation of labour budget in the context of climate change has been issued across the 5 districts.

Annexure 3: Directive by Odisha state government to adopt ICRG

Annexure 4: Calculations for leveraging public finance

Year	INR (crores)	GBP (million)
2017-18	75.12	8.35
2018-19	128.89	14.32
2019-20	204.01	22.67
TOTAL	408.02	45.34

Note: 1 GBP = INR 90

The figures for previous years are as reported in the AR’s.

Annexure 5: Greenhouse gas emissions reduced or avoided (tCO2) – ICF KPI 6

State	Area under plantation (in hectares)	Potential increase in area under irrigation (in hectares)	Potential for carbon sequestration in tCO2 equivalent
Bihar	68.02	4485.80	6325.86
Odisha	204.22	2640.39	18992.46
Chhattisgarh	93.45	648.73	8690.85
TOTAL	365.69	7774.92	34009.17

Annexure 6: Number of direct beneficiaries HHs

Parameters	Cumulative (Since Inception)	2019-20
Chhattisgarh
Total direct beneficiary	3260	446
Scheduled Tribe	1673	187
Schedule Caste	661	172
Other Backward class	866	67
Women headed HHs	45	8
Disabled headed HHs	8	4
Women	128	15
Bihar
Total direct beneficiaries	14914	2435
Scheduled Tribe	684	268
Scheduled Caste	3357	712
Other Backward Class	7198	951
Women headed HHs	526	35
Differently abled HHs	487	80
Women (From Plantation)	5	2
Odisha
Total direct beneficiaries	7875	491
Scheduled Tribe	4842	187
Scheduled Caste	883	130
Other Backward class	1531	174
Women Headed HHs	564	28
Differently abled HHs	89	6
Women (From Plantation)	1724	20
Consolidated
Total direct beneficiaries	26049	3372
Scheduled Tribe	7199	642
Scheduled Caste	4901	1014
Other Backward class	9595	1192
Women Headed HHs	1135	71
Differently abled HHs	584	90
Women (From Plantation)	1857	37

Annexure 7: Progress against CRWs in Bihar, Odisha and Chhattisgarh

Parameters	Bihar		Total		Chhattisgarh		Total		Odisha		Total
	2016-17	2017-18	2018-19	Total	2016-17	2017-18	2018-19	Total	2016-17	2017-18	2018-19	Total
CRWs selected	9	143	104	256	9	147	104	260	5	142	129	276
Total MGNREGA work in the selected CRWs	18	282	241	541	7	390	325	722	13	664	612	1289
Total HH/Direct Beneficiaries for these NRM works	457	7880	5146	13483	305	1646	1309	3260	439	4030	3406	7875
Total number of MGNREGA works sanctioned (w.r.t CRWs)	12	123	42	177	7	341	315	663	9	640	590	1239
Total HH/Direct Beneficiaries	342	5162	1388	6892	305	1364	1134	2803	289	3995	2713	6997
Total MGNREGA works Commenced (w.r.t CRWs)	1	65	12	78	7	309	312	628	8	498	363	869
Total HH/Direct Beneficiaries	80	1775	385	2240	305	1236	1092	2633	265	3569	1699	5533
Total MGNREGA works completed (w.r.t CRWs)	11	13	1	25	7	253	176	436	8	427	222	657
Total HH/ Direct Beneficiaries	262	372	18	652	305	1012	616	1933	265	2367	995	3627
Total MGNREGA works completed in the ICRG Blocks (irrespective of the CRWs) since April 2017*.		6226	9327	15553		114822	134038	248860		68939	36436	105375
Total MGNREGA – NRM works completed in the ICRG Blocks (irrespective of the CRWs) since April 2017*.		259	1882	2141		21187	24998	46185		5965	3985	9950
Total MGNREGA – NRM works influenced by CSOs in ICRG blocks		315	511	826		1078	2288	3366		1026	2214	3240
Total HH/Indirect Beneficiaries		8820	15638	24458		22681	18163	40844		40746	45704	86450

*the figures recorded on 2nd December 2019.