Annual Review - Summary Sheet
Title: STRENGTHENING TRANSPARENCY ACCOUNTABILITY AND RESPONSIVENESS PHASE 2
Programme Value: £22.87 million (DFID Contribution is £15m and the rest is contributed by the EU (£2.92m) and DANIDA (£4.95m) )		Review Date: 1-5 February 2016
Programme Code: 204657	Start Date: 19/02/2015	End Date: 30/09/2020

Summary of Programme Performance
Year	2016
Programme Score	A
Risk Rating	Medium

Summary of progress and lessons learnt since last review: This is the first annual review.

Summary of recommendations for the next year
- Review the capacities of all Steering Committee (SC) Members and take a decision on remuneration, as their willingness and ability to manage increasing demands will be critical to the well running of the programme. It is a potential risk to the programme to expect the current and planned level of responsibility and decision making for the programme to be undertaken on a voluntary basis – Action by April 2016;
- Outputs from the PEA and the GESI Strategy should be practical and user friendly to ensure SC and PMT Members make effective use of these valuable technical inputs;
- The proposed Strategic Framework for Continuous Learning should dovetail with M&E functions and have well-established feedback loops to ensure learning is actually utilised as part of programme implementation;
- The PMT should start to define the framework for managing grants and how it will interlink with other Inception Phase deliverables;
- The M&E Framework should incorporate the requirement for the SC to connect directly to grant funded programmes and beneficiaries through field visits to assess first hand the effectiveness and impact of their decision-making on grant proposals. This should be seen as a critical part of the feedback loop;
- The next Annual Review should review the extent to which SC/PMT decision-making is informed by technical expertise provided by consortium partners;
- The SC to set clear timelines to consider, decide and test options for the national entity.
- The risk assessment and mitigation strategy should be completed by end February 2016 to support the programme in navigating the high risk operating environment around elections. This should be presented to the FC to consider their risk appetite as donors, to avoid any “knee-jerk” reactions. A process for dealing with concerns including managing political and reputational risks to funders should be agreed as part of this strategy.
- The proposed M&E System should be subjected to an independent review, commissioned by DFID, at the end of the Inception Phase to ensure gender and social inclusion considerations are properly taken into account.

Strategic Points for consideration:
- The SC should develop a credible and convincing vision as a first step towards establishing a national entity which a wide range of stakeholders (including investors) will want to be part of. This should be prioritised alongside technical and legal considerations.
- The programme govenance structure is in place, but relationships are still “forming” and “norming”. The settling down of the SC/PMT and CA roles and how they interact should be kept under close review. Whilst still at an early stage of Inception, it is important not to underestimate the effort, commitment and accountability needed by all parties to build trust and confidence. This will be critical to the health, success and sustainability of the Programme.
- There will be on-going tensions between the quality and quantity of grants as the SC are pressured to respond to a demanding and resource starved CSO sector. Strong pragmatic leadership and decision-making will be key, in order to maintain the overall quality and strategic coherence of the grant portolio.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	4844405
DevTracker Link to Log frame:	5316752

Strengthening Transparency Accountability and Responsiveness Programme (STAR Ghana) is expected to run for five years with a total budget of £22.87 milliion. The Programme is expected to deliver the following results:

- Contribute to improved governance in a deteriorating context;
- Innovate ways to enable citizens to engage actively and constructively on policy; service delivery and accountability issues piloted and tested.
- More effective civil society in Ghana, including better analysis, communication, engagement and collaboration between policy/think tanks civil society, citizens and Parliament;
- A Ghanian owned, credible, strategic and fundable organisation in place by the end of Year 3, and managing the programme during years 4 and 5.

 A Steering Committee (SC) has been constituted to lead on strategic programme development and management oversight. DFID Ghana has contracted Christian Aid on behalf of other donor contributers to provide technical expertise; administration and grant management. Christian Aid leads a consortium comprising: MANGO, Social Development Direct; On Our Radar; Overseas Development Institute and Nkum Associates. Christian Aid is represented in country by a Programme Management Team (PMT).

At the end of this second Phase in 2020, donor contributers would have provided a full decade of support to strengthening the demand side of governance in Ghana. Therefore, the STAR Ghana approach has a strong focus on sustainability, including establishing a more diverse resource base by attracting private sector investment.

The procurement and contracting process was extremely lengthy due to the fact that the tender process has to go through a presentation stage before the preferred bidder could be selected. This was not envisaged in the procurement time which is a lesson to inform future tendering process.Staff changes in DFID’s Procurement and Commecial Department led to further delays. The contract with the successful implementing partner was only signed 10 months after the Business Case was approved, and as such there has been little time for implementation before this Annual Review. The programme includes a 6-month inception phase. STAR Ghana commenced its six month Inception Phase on 19 October 2015. This Annual Review is being conducted after only four months of operations, the bulk of which has been consumed by the urgent call for elections proposals within a very tight timeframe.This review therefore seeks both to make an objective assessment of progress against the agreed logframe, recognising the limited time since implementation began

The operating context is currently dominated by forthcoming Presidential and Parliamentary elections scheduled to take place in November 2016. Therefore, normal start-up challenges include pressure to support civil society organisations to play their part effectively in the electoral process. There is signficiant stakeholder expectation, that STAR Ghana will live up to the standard set during the award winning first Phase[1]. There is increasing evidence to indicate that 2016 may be an unsafe year for Ghana, with some observers predicting higher then usual levels of electoral violence. Civil society organisations (including the media and faith-based organisations) will therefore form an important part of risk management and mitigation, including civic and voter education; domestic elections observation and parallel voter tabulation.
[1] The World Bank awarded STAR Ghana the Global Partnership for Social Accountability Award for Leadership in Social Accountability for the African Region

The UK has established a niche area for democratic governance work in Ghana, through support to STAR Ghana, which has proven itself as an effective channel for supporting interventions which target the most vulnerable and marginalised, upholding the UK’s commitment to leaving no one behind. STAR Ghana has also enabled the UK to respond to strategic priorities relating to gender equality and Persons with Disabilities.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Whilst the Programme is on track, it is too early to provide a meaningful outcome assessment.

Overall output score and description A – Output Met Expectation.

STAR Ghana has made an impressive start in the 4 months since the inception phase began. Key achievements:
- Office set up and mobilisation;
- Management Team in place;
- Consortium members starting to produce critical technical analysis to inform the Inception Phase, including approach to Political Economy Analysis; Gender Inclusion and options for the national entity;
- SC re-constituted and orientated;
- Monthly Steering Committee Meetings held and documented;
- Monthly Progress Meetings between the PMT and DFID held and documented;
- Website activated;
- Election Roundtable held with a wide range of key stakeholders to identify priority areas of support;
- Outreach to potential grant partners in three locations outside of Accra;
- First call for proposals (Elections) yielding 219 proposals. Grants will be awarded by 1 March;

Key lessons

- Relationship management will continue to be a major challenge for the SC, PMT, Christian Aid and DFID/Funders Committee and will require continuous investment and effective communication.
- The importance of realism about the capacity of the SC whose members juggle a range of other commitments. This should remain under close review with a proper stocktake at the end of the Inception Phase.
- An appropriate information and knowledge management system is required which responds to the SC’s absorptive capacity, to ensure effective utility of technical advice provided;
- Key lessons learnt on financial management weaknesses from Phase 1 will inform the Grants Management Framework.

Key actions

Key Inception Phase Actions which the Programme must deliver include:
- Political Economy Analysis (PEA)
- Communication Strategy
- Women’s Empowerment Strategy
- Monitoring and Evaluation Framework
- Baseline collection and review of logframe in the first six months of the Inception Phase
- Update the Risk Assessment and Mitigation Strategy

Has the logframe been updated since the last review? Yes. This is the first Annual Review. However, the logframe presented in the Business Case was reviewed in October 2015 to reflect initial Inception Phase activities. Year 1 milestones are in line with the revised Inception Phase Plan agreed with the Service Provider. The logframe will be finalised during the Inception Phase.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	STAR2 providing effective Convener, Catalyst and Coordinator (CCC) role
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		First Review	Impact weighting % revised since last AR?	First Review

Indicator(s)	Milestones	Progress
Quality of policy, strategic and thought leadership (score 1-5; one best)	Programme Management Team (PMT) mobilised and office set-up. Steering Committee (SC) appointed and oriented.Terms of Reference developed and agreed. Regular Steering Committee meetings taking place. Monthly meetings between DFID and SP established.	A - All key senior management positions in the PMT have been filled. The Office set-up is almost complete. All SC Members have been appointed and following an initial Orientation Workshop in November, regular monthly meetings are taking place. Terms of Reference have been developed, but not yet finalised and agreed. Monthly meetings between DFID Ghana and the Service Provider/PMT have also been established.
% stakeholders stating STAR is playing a strong/very strong Convener, Coordinator and Catalyst role.	Initial stakeholder mapping completed. Communications Strategy under development. 1 Thematic session convened with stakeholders. At least 2 outreach events outside of Accra	A - Initial stakeholder mapping completed. Communications Strategy for Programme Start-up developed. 1 session with election stakeholders held. 3 outreach sessions held in Takoradi, Sunyani and Tamale.

Key Points
The SC has reviewed and approved the new PMT structure. Christian Aid has establised working groups involving the PMT and Consortium Partners to help strengthen coordination at all levels of programme implementation. Rapid office set up was made possible by the retention of office, furniture and equipment used for Phase 1, which also represented good value for money.

The same Steering Committee Members were brought forward from Phase 1 and continue to show strong interest and commitment with good attendance and engagement at Committee meetings. However, the SC will be required to take on additional decision-making/oversight responsibilities under Phase 2, which may strain already stretched capacities. Increasing pressures will need to be closely monitored and a decision taken on remuneration to ensure proper stewardship of STAR-Ghana is not compromised.

Information sessions have proved crucial in reducing misunderstanding in the grant cycle and helped potential applicants to engage more in the process. This forms part of a more systematic and transparent process of grant-making aimed at improving the quality of proposals and delivering better outcomes.

Summary of responses to issues raised in previous annual reviews: N/A. This is the first annual review.

Recommendations
Review the capacities of all SC Members and take a decision on remuneration, as their willingness and ability to manage increasing demands will be critical to the well running of the programme. It is a risk to the programme to expect this level of responsibility to be undertaken on a voluntary basis. – Action by April 2016.

Output Title	Effective strategic partnerships in place with policy level organisations and parliament
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		First Review	Impact weighting % revised since last AR?	First Review

Indicator(s)	Milestones	Progress
Measure on effectiveness of high-level policy engagement, citizens’ engagement and innovation (to be agreed during inception)	Discussions to Political Economy Analysis (PEA) and Gender Equality and Social Equality (GESI) Strategy approach underway. Monitoring and Evaluation (M&E) framework under development. Communications Stategy under development. Website reactivated.	A – Oversae Development Institute (ODI) completed one country visit and presented the PEA approach to the SC. GESI Strategy approach is under implementation with the TORs for the GESI Technical Advisory Group (GTAG) approved and members identified. The GESI Strategy validation meeting is scheduled for 22 February. The Communications Strategy is under development and the Website has been reactivtated
Quality of Parliamentary oversight and engagement with the public (score 1-5; one best)	Discussions to PEA and GESI Strategy approach underway. M&E framework under development.	A - As above.The M&E Framework is under development

Key Points
A key objective of STAR Ghana’s PEA is to ensure that the programme draws on the critical contextual knowledge to inform decision making processes on an on-going basis. This is to ensure that its activities are informed by systematic political economy knowledge which is embedded within the PMT, planning and implementation processes and that it is dynamic, feeding into an iterative learning process throughout the lifecycle of the programme. The GTAG has been constituted to provide the space for feedback and other interactions with Programme’s stakeholders. The GTAG is a multi-stakeholder community of gender, vulnerability and civil society experts appointed by the SC as a critical friend and sounding board in the development and implementation of the programme’s GESI Strategy. The absence of PEA and attention to GESI was identified as a weakness in Phase 1. It is therefore important that this valuable technical resource is utilised effectively by SC Members. Both PEA and GESI outputs must therefore be practical and implementable.

The M&E Manager is currently a temporary post holder to March 2016. It will be important to continue to view M&E as a high priority and ensure the proposed Framework is substantive enough to track progress and impact across the diverse range of STAR Ghana beneficiaries. This should also include appropriate tracking tools (including direct beneficiary monitoring) to ensure support to women and persons with disabilities is having the anticipated impact. The Programme also proposes to develop a Community of Practice and Learning: A Strategic Framework for Continuous Learning, which will need to be closely aligned with its M&E functions.

Summary of responses to issues raised in previous annual reviews. N/A. This is the first annual review.

Recommendations

1. Outputs from the PEA and the GESI Strategy should be practical and implementable to ensure SC Members make effective use of these valuable technical inputs;
2. The proposed Strategic Framework for Continuous Learning should dovetail with M&E functions and have well established feedback loops to ensure learning is actually utilised as part of programme implementation.

Output Title	STAR2 grant component effectively managed, helping grant partners to link citizens and local issues to policy level
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		First Review	Impact weighting % revised since last AR?	First Review

Indicator(s)	Milestones	Progress
% grant bids with appropriate, realistic theory of change (focus on empowerment)	Grant Management Framework developed; first call Launched; Framework for PEA to determine entry points for calls discussed and agreed.	A - Grant manual from Phase 1 has been revised to support the urgent Elections Call. The Grants Management Framework is under development. First call for proposals was launched in December 2015. Framework for the PEA approved by the SC in January.
Measure on grant project effectiveness. To be decided during inception.	Grant Management framework developed; first call Launched; Framework for PEA to determine entry points for calls discussed and agreed	A - As above.

Key Points
The PMT prioritised a limited revision of the Grants Manual to support the urgent call for Election proposals which was launched in December 2015 - this yielded 219 proposals. The SC will approve grants by 21 February and awards will be made by 1 March 2016. The PMT developed a Concept Note for the Election call which proposed a scoping study to identify key issues around which a call should be launched. However, in view of the limited timeframe available the PMT demonstrated adaptability by shifting to a Elections Roundtable event on 11 December where a wide range of stakeholders were invited to share their views on priority needs to ensure peaceful and credible elections. The PEA is expected to inform day to day programming decisions and the development of the underlying theory of change, to understand how change happens in practice and incorporate strong evidence gathering to inform subsequent actions.

Greater clarity is needed on what the Grants Management Framework will entail and how this will incorporate various other on-going processes, such as M&E, PEA, GESI, VFM, Risk Management Outreach Plan etc. The PMT has coped admirably in responding to major pressures around the Elections call and should be commended, particularly for their outreach work to ensure partners understand the application process; eligibility criteria and budget ceiling. The Elections call will provide an opportunity for the PMT to test the quality of proposals received and look for areas of improvement in subsequent calls for proposals.

Whilst the SC has expressed a strong commitment in connecting to grant partners and beneficiaries in order to directly assess effectiveness and impact, a system is not yet in place to ensure this actually occurs. Although STAR Ghana is still at an early stage of inception, it is important that this commitment does not fall by the way side.

Summary of responses to issues raised in previous annual reviews. N/A. This is the first annual review.

Recommendations:
1. The PMT should start to define the scope of the Grants Management Framework and how it will interlink with other Inception Phase deliverables.
2. The M&E Framework should incorporate the requirement for the SC to connect directly to beneficiaries through field visits to assess first hand the effectiveness and impact of their decision-making on grant proposals. This should be seen as a critical part of the feedback loop.

Output Title	Ghanaian owned, strategic and fundable organisation established.
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		First Review	Impact weighting % revised since last AR?	First Review

Indicator(s)	Milestones	Progress
Readiness for body corporate (quality of options, ownership)	Options for body corporate under preparation	A - Social Development Direct (SDD) have presented a discussion paper to start framing the conversation about the national entity.
Quality of STAR2 strategic, applicable analysis, M&E and lesson learning (incl. quick feedback loops), internal and external comms.	GESI Technical Advisory Group constituted. First visit from Oversea Development Institute (ODI) to consult with the SC on the PEA. M&E framework under development.	A - Met expectation. All milestone targets achieved. A draft communication strategy has been shared with the SC for review. Website has also been updated and activitated.
Quality of the PMT strategic and operational financial management (incl. grant management).	Inception Phase deliverables revised and agreed by SC. Finance Team operating Operations manual developed. Evidence of sound procurement practices . Grants manual under revision; First visit from Mango to scope financial management requirements for grant partners. Lesson learning for STAR 1 shared with Service Provider.	A - All milestone targets achieved. There was a strong focus on lessons learning from the weakness in financial management under Phase 1 which will inform the grants manual/framework and communications with grant partners.

Key Points
Consortium members are gearing up to provide a range of critical technical inputs to inform planning during the Inception Phase. The phasing, alignment, coordination and appropriateness of these inputs will be critical to ensure value added. The PMT and SC should agree the most appropriate way of managing knowledge and information to ensure that technical advice actually informs decision making. The next Annual Reveiw should seek clear evidence of the extent to which decision-making is being informed by technical inputs to ensure vfm.

SDD has presented the SC with various options for a national entity. An urgent task for STAR Ghana is to reflect in more detail on a range of options and choices to determine the institutional format that will best facilitate a sustainable realisation of its goal and mandate. The SC has already taken steps towards registration of STAR Ghana as independent legal entity. A letter has been submitted to the Registrar of Companies requesting a name reservation to secure STAR-Ghana’s name and brand for the registration process and into the future. STAR has been informed by the Registrar General’s office that it can only register STAR-Ghana as a “private company limited by guarantee to operate as a non-governmental organisation” and has been advised to proceed with the company registration process. The SC should not underestimate the time it will take to review, decide and test the feasibility of the various options presented, therefore this task should be prioritised within an already hectic schedule.

Summary of responses to issues raised in previous annual reviews. N/A. This is the first annual review.

Recommendations
1. The next Annual Review should review the extent to which SC decision-making is informed by technical expertise provided by consortium partners.
2. The SC to set clear timelines to consider, decide and test options for the national entity.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The programme uses a hybrid payment method - fees, grants and expenses are based on actuals. A portion of the fees are based on milestone payments to the suppliers.

The key cost drivers are:

1. Consultancy fees for technical experts
2. Indirect overhead cost of administering the project through a management team. These include the costs of being in business, including corporate operations, managed costs, recruitment, back office administration, UK and local office costs.

The key cost drivers have not changed. The service provider have been incentivised to maintain a focus on cost drivers. In the period under review, the key cost drivers were office set-up costs and cost of technical experts.

VfM performance compared to the original VfM proposition in the business case

The VFM measures expected to be measured over the lifetime of the project set out in the Business Case have not changed.

Assessment of whether the programme continues to represent value for money

It is too early to assess meaningfully performance on VFM measures. A key milestone (month 6) during the inception phase is for the service provider to develop a framework/strategy for mainstreaming VFM into programme activities. VFM measures will be assessed against this framework during the implementation phase. However, it is worth noting that the programme has achieves economy and operational efficieny by maintaining the original STAR-Ghana Office premises for the second phase of the programme. This has saved time and resources. By maintaining the original office and all the structural additions and reburbishement done during STAR-Ghana phase one including the equipment, furniture and fittings has not only saved cost to STAR-Ghana II but has also daved time by enabling the core team to hit the ground running and focus immediately on programme delivery.

Quality of financial management

It is too early to fully assess the quality of financial management . Monthly reports for the first two months of the inception phase have been received and have generally been of high quality with minimal revisions and inputs from DFID. The first quarter report which will include financial analyisis for the first three months is not expected until the end of February 2016. The monthly forecast for the inception phase has just been submitted and currently being reviewed with the service provider. A fuller asessment of the quality of forecasting will be done in the coming months. The service provider is currently setting processes and procedures for the grants. The quality of financial management at the grant partners’ level will be fully assessed when the first grants for the election calls are disbursed.

As part of DFID’s reqular monitoring to ensure financial compliance, 6-monthly expenditure verification
exercise has been agreed with the service provider. The first one will be done in May 2016 to cover inception phase activities. Going forward, this exercise will also be extend to the Grant partners.

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

Key risks at this stage of programming include the operating environment (particularly around macroeconomic stability, and the fact that 2016 is an election year in Ghana); poor transition management between Phase 1 and 2; STAR Ghana maintaining credibility; the Steering Committee and PMT not taking full responsibility and poor donor commitment, with a low to medium probability. This assessment remains current at the time of this review. Additional risks will emerge as the environment becomes more intense and unpredictable in the lead up to elections in November. The disbursement of grants will also generate programme management and financial risks which the programme must assess and agree mitigation as part of the grant management framework.

The PMT has ensured all individuals linked to the programme sign a conflict of interest statement. Funders will need to review risks associated with the programme and consider their risk appetite.

Outstanding actions from risk assessment

The risk assessment and mitigation strategy should be completed by end February 2016 to support the programme in navigating the high risk operating environment around elections. This should be presented to the FC to consider their risk appetite as donors, to avoid any knee-jerk reactions. A process for dealing with concerns, including managing political and reputational risks to funders, should be agreed as part of this strategy.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Inception Phase deliverables were revised, in agreement with the SC and DFID, in view of the burden of managing the Elections call. However, this needs to be formalised in line with contractual requirements. A revised Inception Phase Work Plan should be presented with a clear timeframe and a supporting budget. This matter has already been discussed between DFID and Christian Aid. However, it is clear that good progress is being made, with consortium members rapidly mobilising to deliver their various technical contributions.

Performance of partnership (s)

All partners have demonstrated high commitment and energy in getting the programme up and running, but relationships are still “forming” and “norming”. The challenge will be to maintain pace and momentum, but not neglect attention to relationship management. The programme management structure is complex and the performance of partnerships will largely depend on establishing greater clarity around roles and responsibilities. There is also a need to build trust and confidence and focus on developing common principles to strengthen mutual accountability . This requires a significant and continuous investment by all parties concerned. Two events are planned in April:

SC Retreat – where it will be important to explore strategic leadership issues emerging in the Inception Phase; reflect on the Election Call; capacity constraints etc.
An Away Day with DFID Ghana and the PMT – where parties should reflect on the performance of the contract, including reviewing inception phase deliverables;

Relations; communications and risk management should also feature highly at both events.

Asset monitoring and control

The office premises for the STAR-Ghana 1 programme was retained and the supplier mobilised the team to occupy the same office. All assets under the STAR-Ghana 1 programme have been transferred to STAR-Ghana	II. The supplier is in the process of replacing some of the STAR-Ghana 1 assets which are damaged and also purchase additional items required for the programme. The supplier has been informed to record all assets purchased for the programme in the required format and also to update the asset inventory list and submit to DFID by 15 February. The supplier has committed to ensuring that assets acquired are clearly labelled and identified with the UKaid logo; are well maintained and used solely for the purpose of the programme.

The programme team will carry out a physical verification of these assets in March 2016 as part of the office wide yearly physical assets verification exercise.

As part of our monitoring and control, the supplier will be submitting an updated asset inventory as part of the quarterly report. This will also include assets with grant partner.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Although the Partnership Principles (PPs) are not directly relevant to STAR Ghana, since none of the funds are channelled through Government, STAR Ghana does have the potential to bolster Government commitment to the PPs, through its role in supporting civil society and citizenry to hold Government to account.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Currently, there is no evidence to suggest the programme design and Theory and Change is no longer appropriate.

A Monitoring and Evaluation System and Manual will be developed during the Inception Phase. This will be informed by a range of strategic documents currently under development – PEA, GESI etc. However, it will be important to establish clear baseline information with which to measure impact. The M&E System should be subject to an independent review at the end of the Inception Phase to ensure gender and PWDs considerations are properly taken into account.

Monitoring progress throughout the review period

Implementation of programme monitoring has not yet commenced. However, a strong monitoring arrangement is already in place. Progress on Inception Phase deliverables is being monitored through monthly Progress Meetings between DFID and the PMT. The PMT also report to the SC on progress made on a monthly basis.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process