Annual Review

Title: African Agriculture Technology Foundation Phase III (2015-2020)
Programme Value £ (full life): £10M		Review Date: 14TH December 2019
Programme Code: 204988	Start Date: 5th October 2015	End Date: 30th September 2020

Summary of Programme Performance
Year	2016	2017	2018	2019	2020
Programme Score	A+	A	A	B
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Documents:	https://devtracker.dfid.gov.uk/projects/GB-1-204988/documents

A. Summary and Overview (1-2 pages)
Description of programme
To achieve the Sustainable Development Goals, a step-change is needed in smallholder agricultural productivity, incomes, and resilience in Africa. Key to achieving this – and in line with the ambition of DFID’s work on Strategic Directions regarding technology - is to ensure that African smallholder farmers have access to appropriate and effective agricultural technologies including mechanised equipment and high-quality seeds. However, smallholder farmers often lack the purchasing power to access new technologies, which reduces incentives for private sector companies to develop agricultural technologies that meet their needs.
To overcome barriers to technology adoption by smallholder farmers, DFID supports the African Agricultural Technology Foundation (AATF). AATF is internationally recognised as a leader in the identification and development of appropriate agricultural technologies and their delivery to smallholder farmers. Its central value is in bridging the crucial gap between agricultural technology researchers and smallholder farmers. AATF therefore directly contributes to DFID’s strategic direction on Harnessing Technology for Development by taking technologies to scale and promoting DFID’s role as a global leader
This programme builds on the UK’s previous support to AATF from 2010-2015, during which AATF consistently met or exceeded expectations: AATF delivered drought tolerant maize varieties to over 57,000 households and developed a pipeline of new products including Water Efficient Maize for Africa (WEMA). Ongoing support enables AATF to continue to deliver essential agricultural technologies to smallholder farmers, while also preparing the ground for a transition from DFID support. Funding will support AATF through institutional change to adapt and embrace a more inclusive and sustainable business model.
The programme supports AATF activities in two areas: support to organisational systems and support to specific projects. The expected impact of support to the proposed intervention is increased productivity of smallholder farmers in SSA. This impact will be achieved through two outcomes:
1. Increased access/availability of appropriate agricultural technologies for smallholder farmers in target countries in SSA.
2. A financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers in ensuring that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed.
Summary supporting narrative for the overall score in this review (1/2 page)
The overall score given for this Annual Review is B: Outcomes moderately did not meet expectations. Full details for this assessment are provided in this report and summarised here.
AATF is at a critical juncture, as they enter the last year of DFID funding. While AATF has performed satisfactorily with respect to delivery of technical outputs (Outcome 1) progress on institutional change (Outcome 2) has stalled, after significant progress in 2018. At present there is limited evidence that three key assumptions underpinning the theory of change for DFID support to AATF are holding in practice. These are set out in detail in Section C of this report. In summary due to failure to improve their impact assessment work, AATF have not demonstrated that they are delivering technology at scale; the performance related funding component has had mixed success in driving change; and AATF has struggled to identify a sustainable business model and transition to it. Progress on institutional change in 2018, reflected delays in achieving key milestones in 2017, which were then achieved rapidly in 2018. 2019 has seen a return to slow progress.
In the past year, AATF estimates that a total of 631,600 farmers were reached directly through AATF products/technologies, an increase from 529,363 in 2017/2018. Cumulatively, after two years of the new strategy this is a total of 1,160,963 farmers. This is 30% of the total they aim to achieve at the end of the 5-year strategy.
AATF’s new strategy helpfully groups their products into five new pillars and, along with the successful rebranding, has enabled AATF to communicate more clearly with a wider audience through various channels. There has also been some degree of success in attracting new donors, although total funding targets for the year were not met.
However, AATF is “stuck in 2nd gear”, having started a strategic shift, but being unable to bring together the various excellent components of their work, including communications and advocacy, into a coherent, forward-looking organisation that is at the centre of discussions around agricultural technology and innovation in Africa. The Business Case set out four potential scenarios at the end of the five-year period with respect Outcome 2. Scenario 3 was considered the optimum outcome, but Scenario 2 the most likely.
1. AATF has not made significant changes to its business model, has struggled to achieve impact at scale and has not been able to diversify its investor base.
2. AATF has made considerable changes to its business model, has achieved reasonable impact at scale and has made substantial progress in diversifying its investor base and has the potential to become financially sustainable, possibly as a social enterprise, within two to three years.
3. AATF has become financially sustainable having changed its business model, achieved impact at scale and attracted significant investment from diverse sources.
4. The market failures that AATF was set up to address are no longer present due to intervention by other actors, such as seed companies or national governments.
AATF is unlikely to achieve Outcome 2 and is somewhere between Scenarios 1 and 2. The significant progress that was highlighted in the 2018 Annual Review has stalled and AATF is only making slow advances on key issues. While there is still a need for an organisation like AATF to identify the needs of small holder farmers and develop appropriate innovations and take them to scale, slow progress in the past year suggests that AATF is not able to fulfil this role effectively. AATF does have unique experience in Africa on managing crop development programmes with a transgenic component but is not making the most of this. Poor progress with respect to impact evaluation poses particular challenges in assessing the organisation’s effectiveness in delivering technology to farmers at scale to transform African agriculture.

Recommendations for the year ahead (1/2 page)
1. If AATF is not able to position itself effectively in the market as a key player in taking innovation to scale, allowing it to set a clear innovation agenda, they need to consider other options for the future of the organisation. This could be simply as a trusted implementer of projects for donors or in providing services to the private sector. (by June 2020)
2. AATF to consider the opportunities for more projects like CAMAP, given the success of the project. This has the potential to deliver impact more quickly and diversify the portfolio (by March 2020).
3. Given current slow progress on organisational change, despite consistent engagement from donors, DFID will consider options for support to and engagement with AATF over the remaining year of the programme, taking into account resource constraints and challenges. (by February 2020)
## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Diversify agricultural technologies accessed for use in SSA
Output number per LF		1	Output Score	B
Impact weighting (%):		30	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestone(s)	Progress
Number of new agricultural technologies accessed targeting agricultural productivity, nutrition and post-harvest loss.	No Target.	AATF is working to have at least three new technologies targeting nutrition, post harvest and productivity between 2020 and 2022.
Number of products/ varieties accessed	109	62 – Partially Met / Seeds2B Project: Ghana 34 (17 tomatoes, 9 Chilli, 8 Onion); Malawi 17 (8 cowpea, 6 pigeon pea, 3 soybean and I groundnut); Uganda 11 (5 soybean, 2 tomatoes, 2 groundnuts and beans 2)
Number of Products/ varieties developed	10	20 – Exceeded. / TELA (9), hybrids transformed with traits and available for use. Hybrid Rice (11) hybrids in National Performance Trials in Kenya .
Number of Products/ varieties released	10	13 – Exceeded / 7 TEGO varieties released in Dec 2018 and 6 TEGO released in 2019 respectively.
Number of farmers participating in AATFs agricultural education sensitization and outreach activities (demos, field days, trainings, workshops etc.)	62.000	42,101 – Partially Met. / The 32% variance in achievement was because the OFAB project was a no cost extension period and they were not able to implement most of the activities initially planned.
Number of other stakeholders (excluding farmers) engaging with AATF through AATF training workshops, seminars, outreaches, advocacy meetings	700	6,456 – Exceeded / The over achievement was as a result of communications outreach program held in 2019
Number of nutrition-based technologies being deployed by AATF	0	0
Number of farmers aware of mechanization services by AATF (engaged through training workshops, seminars, outreaches, field days etc.)	650,000	656,783 – Exceeded / In the reporting period, the project reached about 206,783 new farmers with mechanization information. Cumulatively a total of 656,783 farmers were reached
Increased number of digital platforms used by farmers	1	1 – Met.
Number of farmers linked to AATF technologies using digital solution platforms	15,000	8,000 - Not Met / AATF was able to link more than half of the targeted farmers through CAMAP

Provide supporting narrative for the score
In the past year AATF carried out a major restructure of their institutional logframe to bring it in to line with their shifts in focus and the new strategy and workplan. This was a recommendation of the 2018 DFID Annual Review. This Output includes a number of indicators carried over from the previous logframe, but also new indicators to reflect AATF’s shift in strategy and new projects and partners for which they have received funding. A list of AATF’s current projects is provided in Table 1. A number of new projects have been added to the project list in the past year as a result of successful engagement with new partners and investors (Output 4).
Table 1: Current AATF projects
Project	Summary
AGRA Seed Policy	an Alliance for a Green Revolution in Africa (AGRA) supported project to conduct incisive diagnosis of challenges hindering policy implementation in the seed sector. The project aimed to improve the enabling business environment for agriculture to catalyse and sustain inclusive agricultural transformation.
AgriDrive	is a social enterprise wholly owned by AATF to engage in various commercial ventures in the agricultural sector as a business platform that complements AATF’s initiatives in agricultural development in Africa. It provides mechanization services, inputs and agribusiness support to farmers in Nigeria. The mechanization services are being offered on a commercial basis across various crop value chains.
Bacterial Wilt resistant potato	is exploring two transgenes – pflp and EFR as proof of concept for efficacy in the control of bacterial wilt disease (BWD) caused by Ralstonia solanacearum in potato. The project aims to develop and deploy disease resistant transgenic potato varieties against BWD. The expected outcome is commercial disease resistant popular potato varieties in Ethiopia.
Cassava Mechanization and Agroprocessing (CAMAP) Project	negotiates access and transfer of cassava mechanisation and agro-processing technologies for the benefit of smallholder farmers by increasing production efficiency and reducing drudgery. It aims to increase cassava yield per unit area through adoption of mechanization and best agronomic practices across the entire cassava value chain.
Hybrid Rice	explores the breeding by Design approach to develop hybrids based on the use of 2-line hybrid rice technology to increase the productivity of rice in Africa. The expected outcome is commercialisation of 2-line hybrid rice varieties that are well adapted to African conditions and efficiently satisfy market needs/demands.
Maize Lethal Necrosis Diagnostics and Management	aims at mitigating grain yield losses incurred by maize farmers in Africa as well as preventing the spread of MLN from endemic countries to non-endemic areas on the continent. The expected outcome is to establish and operate a functional MLN Phytosanitary Community of Practice in Africa.
NEWEST Rice	is a multiple-partner collaboration project aimed at developing and disseminating genetically improved African rice varieties with enhanced agronomic traits, specifically Nitrogen-Use Efficiency (NUE), Water-Use Efficiency (WUE) and Salt Tolerance (ST) for the benefit of smallholder farmers in Africa.
Open Forum for Agricultural Biotechnology (OFAB)	focuses on strengthening the policy and regulatory environment required to accelerate agricultural biotechnology development and promote the uptake of its products in Africa. The project aims to enhance capacity of stakeholders to understand, accept and safely use ag-biotech products for agricultural transformation in Africa.
Pod Borer Resistant Cowpea	addresses the high infestation of Maruca that accounts for high yield losses of cowpea in SSA. The PBR cowpea project is focused on developing and disseminating Maruca resistant transgenic cowpea varieties Burkina Faso, Ghana, Nigeria and Nigeria. The project is also strengthening seed company capacities for the production of transgenic PBR cowpea seeds to drive commercialisation of PBR cowpea varieties.
QualiBasic Seed Company (QBS)	is a special initiative set up as a business entity to mitigate the paucity in supply of early generation seed and more specifically foundation seed. It aims at ensuring the production of quality foundation seeds for demand driven commercial hybrid maize towards strengthening the maize value chain in Africa.
Seeds2B	applies a market-led methodology to transfer seed technologies from research programs/technology developers from different parts of the tropical world to seed enterprises in Africa. The initiative strengthens farmers access to quality seeds for a wide range of new improved varieties of strategic crops.
TAAT Maize Compact	aims to harness high-impact proven agricultural technologies of maize to raise agricultural productivity in Africa by promoting the dissemination and massive scale-up of proven water efficient maize varieties in combination with other complimentary technologies (including fertilizers, seed treatment with pesticide for Fall Army worm etc). The project aims to increase maize productivity by up to 30%, through increased uptake and use of high yielding climate smart maize hybrids as well as increased profit margins for actors in the maize value chain.
TAAT Policy	is facilitating the creation of a conducive policy and regulatory environment for accelerated deployment of agricultural technologies and efficient marketing/trade of outputs from other TAAT compacts. Anticipated outcomes include drafting/review, adoption and implementation of regulations, laws, guidelines and standard operating procedures (SOPs) in Africa south of Sahara.
TELA	is developing drought tolerant and insect resistant transgenic hybrid maize varieties. This phase aims is to secure regulatory approvals and initiate commercialization of transgenic drought-tolerant (DroughtGard® trait) and insect-protected (Bt trait) maize hybrids (TELA® maize hybrids) in at least four African countries to enable deployment of these maize varieties to smallholder farmers in sub-Saharan Africa.
[note] Technologies for African Agricultural Transformation (TAAT) programme funded by the African Development Bank (AfDB)

Not all indicators have been achieved in the past year, although some have been exceeded, as demonstrated in the indicator list above. The detailed technical reports, provided by AATF as part of their report to DFID, demonstrate that research and development activity is continuing under individual projects.

Lessons identified this year, and recommendations for the year ahead linked to this output
1. AATF continues to implement an extensive programme of research and development, working through a number of partners. These continue to be primarily funded by the Bill and Melinda Gates Foundation (BMGF) and the United States Agency for International Development, although other new donors are coming on board. The new AATF strategy aims to structure work under five pillars
    1. Productivity and Stress Management,
    2. Mechanisation and Digital Agriculture,
    3. Nutrition, Food Quality and Post-harvest Management,
    4. Market Systems for Commercialisation
    5. Policy Environment and Public Participation.
However, AATF’s current approach to fund raising, engaging with potential donors to support specific projects, is not facilitating the shift to the new structure as new donors have their own priorities and AATF is not communicating their “value-add” effectively.
This challenge is not unique to AATF but does highlight the challenge they face in driving forward a clear strategy and calls into question their ability to shape the market for agricultural innovation, as opposed to being a project implementer or service provider to the private sector.
If AATF is not able to position itself effectively in the market as a key player in taking innovation to scale, allowing it to set a clear innovation agenda, they need to consider other options for the future of the organisation. This could be simply as a trusted implementer of projects for donors or in providing services to the private sector. (by June 2020)

Output Title	Accelerate commercialization of agricultural technologies for improved farmer livelihoods
Output number per LF		2	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestone(s)	Progress
Number of business models for licencing, production ,distribution to ensure quicker and faster technology adoption	0	1 - Exceeded
Number of extension agents trained as TOTs	85	124 – Exceeded / AATF continuous to work with extension agents through the CAMAP, TELA, OFAB, Cowpea and TAAT Maize program and Seeds2B
Number of value chain actors that AATF works with to create market systems supportive of agricultural development.	5000	920 – Not Met / AATF worked with a total of about 920 value chain actors who included seed companies, agrodealers, seed producers, grain traders, processors, etc during the reporting period. The huge variance is as a result of an assumption that the TAAT policy project would work with a number of actors which wasn't the case. It’s a recommendation that the targets for this indicator be revised during the next reporting period.
Number of farmers linked to off-takers (CAMAP 55,000; TAAT Maize 1,400)	26,000	61,033 - Exceeded / TAAT Maize was able to link a number of farmers through the Nigeria ABP and the Kenya food chain millers. There is need to revise the target in the next reporting period.
No. of technology policies, laws, regulations and standard operating procedures harmonized across countries and regions	2	Partially met – 1 (Harmonized EAC Pesticide Reg. Guidelines

Briefly describe the output and provide supporting narrative for the score
As noted above, in the past year AATF carried out a major restructure of their institutional logframe to bring it in to line with their shifts in focus and the new strategy and workplan. This was a recommendation of the 2018 DFID Annual Review. This Output comprises a number of new indicators focussing more substantively on commercialisation of agricultural technologies to reflect AATF’s shift in strategy and new projects and partners. AATF has a portfolio of products, but needs to focus more on taking them to market through a broader range of channels. Through two programmes, CAMAP/AgriDrive and TAAT Maize, AATF is also working to link farmers more closely to markets for their increased production.
Two areas to note are the work through the Technologies for African Agricultural Transformation (TAAT) programme funded by the African Development Bank (AfDB) and on-going development of two new, commercial operations as part of AATF’s portfolio.
TAAT: aims to radically transform African agriculture into a competitive sector by deploying productivity enhancing technologies and focusing on 9 Priority Areas. AATF has successfully positioned themselves as a key partner in implementing three “compacts”: cassava, maize and policy. This provides an opportunity to raise AATF’s profile in a number of new African countries. However, changes to project budgets and bureaucratic process in AfDB posed a number of challenges to project implementation, resulting in failure to meet some targets, notably indicator 3.3.1.
AgriDrive: offers cassava mechanisation services on a commercial basis in Nigeria. Original testing and piloting under the CAMAP project, funded by DFID, demonstrated that there was a viable market for cassava mechanisation and AgriDrive as a commercial enterprise was established to continue expansion on a commercial basis. Farmers pay for the service which is on track to be delivered on over 9,000ha of land in Nigeria. The revenue target for 2019 is $425k and AgriDrive is on track to meet this target.
QualiBasic Seed Company: aims to address market failures in the production of hybrid seed in East Africa and is supported by BMGF. QBS contracts out the production of Foundation Seed (FS) and then sells the seed to private seed companies for the production of hybrids from inbred lines. Seed companies then sell the hybrids to farmers. QBS is in its second year of operation and has successfully raised the profile of the hybrid varieties they have to offer, resulting in increased demand for seed from a number of companies. However, poor rainfall in the region has impacted seed production and also demand for seed from farmers. This has impacted QBS’s bottom line and the company is looking at other options to increase revenue.

Lessons identified this year, and recommendations for the year ahead linked to this output
AATF’s shift to more diverse approaches to taking technology to market has been facilitated by the TAAT approach in their 9 priority areas. TAAT aims to take a more coordinated approach to deploying technology by bringing together key actors in the supply chain. AATF was particularly well positioned with the success of the CAMAP project, which is now being expanded through the TAAT Cassava compact. CAMAP was AATF’s first product not related to crop breeding and has progressed from pilot to commercialisation and expansion much more rapidly than other technologies. This was anticipated, but confirms the advantage to AATF of having a diversified portfolio of technologies, tackling different gaps in the market of innovation, outside improved crop varieties.
AATF to consider the opportunities for more projects like CAMAP, given the success of the project. This has the potential to deliver impact more quickly and diversify the portfolio (by March 2020).

Output Title	Create an enabling environment for increased uptake and use of agricultural technologies
Output number per LF		3	Output Score	A
Impact weighting (%):		15	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestone(s)	Progress
Number of countries with functional biosafety systems	1	2 – Exceeded
Number of polices/legislations passed/amended to aid testing and commercialization of improved technologies in target countries	3	2 – Partially Met / 2 (Biosafety Regulation in Ghana and; Biosafety Directives in Ethiopia)
Number of governments engaged on policy deliberations on commercialization of agricultural biotechnology/technologies	6	9 – Exceeded / (Biotech – KE, UG, TZ) Other – EAC BR & RW, Agra- ET, GH, MW& MOZ
Number of governments indicating formal commitments to implement policy, regulatory reforms for technology deployment	3	3 – Met / DRC and Kenya , and OFAB 1- Ghana - with AG's office and parliament finally passing the LI - and now NBA is fully fledged and ready to operate
Number of polices/legislations passed/amended to aid testing and commercialization of improved technologies in target countries	3	1 – Not Met / OFAB 1 - Ghana Biosafety Implementing Regulations came into force 28 June, 2019
Number of beneficiaries reached through advocacy, outreach and regulatory interventions that will bolster enhanced capacity for private sector and seed systems in general.	2,000,000	1,681,905 – Partially Met

Provide supporting narrative for the score
For the reasons outlined previously, this Output includes modified/updated indicators when compared to the previous logframe.
Ensuring a favourable regulatory environment for AATF technologies is a key part of project activities as unfavourable regulation poses a major risk to AATF (see risk section). AATF’s work in this area is funded by BMGF under the OFAB project and under the TAAT Policy Compact. AATF works to support governments and policy makers to develop the appropriate regulatory framework for biotechnology in African countries.
Over the past year at a continental level the regulatory environment has remained stable, with challenges in some countries balanced by successes in others. For example, the Ghana Biosafety Implementing Regulations came into force on 28 June 2019 and Mozambique now has a functional biosafety system.

Output Title	Cross cutting focus areas for the organization
Output number per LF		4	Output Score	A
Impact weighting (%):		14	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestone(s)	Progress
Number of requests for partnerships; specialist technical expertise/ experience and knowledge sharing on agricultural technology transfer among key targets.	25	47 – Exceeded
Number of new partnerships/ collaborations/strategic alliances actualized to enhance the quality of AATF interventions	7	3 – Not Met
Increase (quality and quantity) in number of mentions in both traditional and social media and drive stakeholder engagement (retweets, likes, clicks, views and responses) to support organization goals	25,000	31,575 – Exceeded / Social Media Platforms - 31,163 (Facebook - 11,000 followers; Twitter 4,000 followers; PBR Twitter 163 followers; Total engagement 16,000;) Traditional Media Mentions AATF Jan - Sept - 412; Social Media analytics attached.
Knowledge products developed and disseminated (Impact stories, books and booklets, journal articles, policy briefs, conference proceedings published, book chapters	12	15- Exceeded
Number of trademarks/patents/PVP filed in project countries	2	2 – Met / HYRISE (Hybrid Rice project), PBR (PBR Cowpea Project)
Number of sub-licenses negotiated and signed with partners	20	10 – Partially Met
Percentage of review/audit/evaluation recommendations implemented.	90%	100% – Met
Staff turnover rate (below 10%)	5%	2% – Met

Provide supporting narrative for the score
Again, as a result of logframe restructuring, this output groups together a number of updated cross-cutting or administrative indicators.
AATF’s partnership approach forms a key part of their delivery of projects. As a consequence, they are able to implement a significant number of projects with relatively few staff. The bulk of project work is conducted by project partners. Their target for new partnerships was not met in the past year, but the level of engagement from other organisations was higher than the target. This includes requests for partnership, for specialist technical expertise/experience, for knowledge sharing and for specific technologies. AATF maintains a record of requests.
The launch of a new corporate strategy, and accompanying social media strategy, and the completed rebranding exercise has supported increased AATF engagement on social media with clearer targeted messages, linking to an updated website. This has substantially increased engagement with AATF on social media.
AATF continues to have a strong track-record implementing audit recommendations and after significant staff changes in 2018, linked to the new strategy, 2019 has seen greater staff stability.

Output Title	Performance Related Funding Assessment
Output number per LF		5	Output Score	B
Impact weighting (%):		21	Impact weighting % revised since last AR?	Y

A key component of DFID funding to AATF in Phase III is the Performance Related Funding Component. This new component of funding is structured to incentivise more rapid progress by AATF as a whole in key areas of interest to DFID, including: achieving and assessing impact at scale, financial sustainability, and strengthening of the commercial product pipeline. Of the total funding of £2million/year, £500,000 is Performance Related Funding and is awarded following assessment of AATF’s performance against an agreed set of performance indicators. Performance Related Funding can be awarded in its entirety, partially, or not at all depending on performance. However, no specific sum is attached to each indicator as they are assessed as a whole. This objective has been clearly communicated to AATF management. Progress against each indicator is reported in the table.
Organisational Behaviours	Progress
Commercial/Private Sector Focus / Number of seed companies engaged on seed production and overall business management through licensing and contract. / The number of seed companies with capacity enhanced and audited for compliance – through seed production and stewardship training and retooling, etc. / Operationalization of AgriDrive, tracking the following indicators (2019 to act as baseline) / Number of mechanisation operations done under AgriDrive / Percentage increase in sales revenue under AgriDrive / Percentage increase in profit under AgriDrive	PARTIALLY ACHIEVED / Although AATF has continued to work through a increasing number of private seed companies, they have not provided evidence of increased capacity of the companies as a result of AATF support. AgriDrive has had a stronger year in 2019 and is close to hitting targets for mechanisation operations and increases in sales revenue. It is on track to reach break-even in 2020, the third year of trading.
Gender and Inclusion / Partner training on gender mainstreaming modules / Mainstreaming gender at AATF	NOT ACHIEVED / Although AATF’s Board Members received gender training at the October 2019 meeting, partners have not received training.
Business Plan and strategy / Implementation of the AATF Business Plan and Strategy, focussing on achievement of the institutional framework and key deliverables in the business plan.	ACHIEVED / AATF has an average achievement rate of 102% for all Business Plan indicators in 2019. ie some targets have been exceeded.
Monitoring ,Evaluation and Learning / Conduct at least two impact evaluations/assessments and at least 1 in depth assessment. / Sharing relevant evaluative information through an appropriate use friendly mechanism for the collection and dissemination of lessons learned to generate informed programmatic decisions (At least 2 learning workshops)	PARTIALLY ACHIEVED / While two evaluations have been commissioned, they are not yet completed.
Fund raising / Develop and submit at least 12 concept notes/ proposals for consideration / Number of proposals funded (at least 3) / Number of new donors (at least 2) / Amount raised from new donors (At least USD 2.5M)	PARTIALLY ACHIEVED / 15 proposals and concept notes where submitted / 5 proposals were funded / AATF received funding from a total of 3 new donors / USD 0.97M was received from new donors.
Reach or scale -AATF Products / TAAT Maize 3000 Tons, WEMA -250 Tons, Striga 100 Tons: Distributed through 95% Seed Companies and Agrodealers and 5% AATF supported demonstrations, 10% NGOs, Goverments. / CAMAP - 11,150 Mechanization operations (9750 Nigeria (includes Agridrive) ,700 Zambia , 700 Uganda) Taat Cassava : 300 Operations. Delivery channel is through private service providers and AATF through full cost recovery	ACHIEVED / In total, 6,316 tons of certified seed were supplied through private companies and government input programmes. This was 600 tons above the target and is sufficient to reach about 631,600 households. / The new TAAT Maize programme was a significant factor in reaching this target. / A total of 10,426 operations carried out Nigeria, Uganda, Zambia and Tanzania, through CAMAP, TAAT Cassava and CAMAP

Based on the analysis above, and discussions during the AATF Board meeting in October 2019, DFID intends to award a Performance Related Payment of £150,000. Progress on key issues has been slow over the past year, as has AATF’s progress in implementing Board decisions.
## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)
Summarise the programme’s theory of change and any major changes in the past year (1/2 page)
The Theory of Change for AATF is that investment by DFID in both the project pipeline and institutional development will deliver the parallel outcomes of increased availability of technology and a financially sustainable organisation. The figure below, taken from the original Business Case for funding to AATF, provides details on the Theory of Change.

As the programme enters its final year, it is appropriate to assess whether underlying assumptions are holding. Assumptions were grouped into three categories. A brief assessment of each assumption is provided below and each assumption is colour coded using a RAG rating.
Assumptions about CAUSALITY
  1. New investors exist and are attracted by the impact of AATF technology on smallholders and AATF’s pipeline of new technology.
AATF has had moderate success in attracting new investors, principally for delivery of technology at scale, as opposed to the product pipeline. However, they are operating in a challenging environment.
  1. AATF continues to deliver appropriate technology for small-holder farmers during and after this phase of funding.
AATF are delivering technology, but evidence on uptake remains limited due to the slow pace in implementing improved M&E.
  1. There is strong evidence that the adoption of new technology contributes significantly to improved agricultural productivity.
This is external to AATF, but continues to be true.
  1. A performance related funding component that is mutually agreed between DFID and AATF supports more rapid development of new technology and the transition to a financially sustainable organisation.
There is mixed evidence that this assumption continues to hold. The performance related funding component has incentivised some changes, but progress has been slower in other areas, as outlined above.
  1. Other donors support the implementation of the performance related funding component.
There has been strong donor support from BMGF and USAID for this approach.
  1. A sustainable business model for AATF can be identified and institutional development of AATF enables the transition to the new model.
Although institutional changes at AATF have enabled a number of shifts in their business model (AgriDrive, QBS and the potential for profit consultancy services), AATF continues to be heavily dependent on public investment from current investors.
  1. AATF technologies are able to compete with others in their target market.
AATF technologies are being adopted, but whether this is being constrained by competition in the market is difficult to assess.
Assumptions about PROGRAMME IMPLEMENTATION
  1. Private sector holders of new and promising technology/IP remain committed to a process of sharing proprietary technologies.
AATF continues to have good relationships with holders of technology and has not encountered any issues in access technology/IP.
  1. AATF does not receive negative publicity linked to their involvement in research on genetically modified crops.
This risk is proactively managed by AATF, through other programmes not funded by DFID, so no major negative publicity has been received.
  1. AATF is able to maintain good relationships with stakeholders and partners to support project activities.
AATF have been able to do this.
  1. The AATF Board remains proactively engaged with AATF’s agenda and supports the Leadership Team.
The AATF Board is very active and engaged, challenging AATF Management to deliver more.
  1. The regional integration agenda in East Africa with respect to seed certification moves forward, reducing the burden of see registrations in multiple countries.
This assumption has not held and the complexities of seed certification in East Africa continue.
Assumptions about EXTERNAL FACTORS that could influence the programme
  1. The policy and regulatory environment with respect to varietal development and release and biosafety remains favourable.
While there have been a number of changes in the policy environment across AATF target countries, on balance the environment has remained stable.
  1. There is no political instability or conflict in AATF target countries that impacts the ability of AATF or partners to operate freely.
This assumption has held, and AATF has not been constrained in their activities.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)
This programme targets two, related outcomes from DFID funding to AATF, as set out in the Business Case.
1. Increased access/availability of appropriate agricultural technologies for smallholder farmers in target countries in SSA
2. A financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers in ensuring that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed
In the past year, AATF estimates that a total of 631,600 farmers were reached directly through AATF products/technologies, an increase from 529,363 in 2017/2018. Cumulatively, this is a total of 1,160,963 farmers or about 30% of their 5-year strategy targets. AATF are on track for the first outcome, particularly through their engagement with the TAAT programme.
With respect to the second outcome, the Business Case set out four potential scenarios at the end of the five-year period with respect to AATF as an organisation. Scenario 3 was considered the optimum outcome, but Scenario 2 the most likely.
1. AATF has not made significant changes to its business model, has struggled to achieve impact at scale and has not been able to diversify its investor base.
2. AATF has made considerable changes to its business model, has achieved reasonable impact at scale and has made substantial progress in diversifying its investor base and has the potential to become financially sustainable, possibly as a social enterprise, within two to three years.
3. AATF has become financially sustainable having changed its business model, achieved impact at scale and attracted significant investment from diverse sources.
4. The market failures that AATF was set up to address are no longer present due to intervention by other actors, such as seed companies or national governments.
At this juncture, the end of the fourth year of funding, AATF is unlikely to achieve Outcome 2 set-out in the Business Case, and is somewhere between scenarios 1 and 2. The significant progress that was highlighted in the 2018 Annual Review has stalled and AATF is only making slow progress on key issues. After slow progress in developing the new Strategy and Business plan in earlier years, it has been finalised and is being rolled out, the balance of skills on the Board has shifted to reflect the new strategy and significant cost saving measures have been introduced to reduce dependence on DFID funds. Only three AATF staff are charged 100% to core costs, with 28 100% funded by projects, and the remaining 15 partially funded by projects and partially by core costs. Additionally, there has been reasonable success in attracting new donors and new more commercially focused programmes have been established.
However, progress has been much slower in other areas, notably gender and impact assessment, and the quality of reporting and responsiveness from AATF has declined in the past year. There is an impression that AATF is “stuck in 2nd gear”, having started a strategic stiff, but being unable to bring together the various excellent components of their work into a coherent, forward looking organisation that is at the centre of discussions around agricultural technology in Africa. Given their wide range of partnerships there is great scope to do this. This impression was confirmed at the AATF Board Meeting in October 2019, attended by DFID staff.

Explain major changes to the logframe in the past year (1/2 page)
Following last year’s Annual Review, and as recommended by DFID, AATF carried out a major restructure of their logframe to bring it in to line with their shifts in focus and the new strategy and workplan. No changes had been made in the previous three years, so this update was needed. Impacts and Outcomes remained the same, but the Output Areas were updated and restructured to reflect new priorities and changes in AATF’s business model. The changes were agreed by DFID in April 2019.

Describe any planned changes to the logframe as a result of this review (1/2 page)
There are no planned changes to the logframe, apart from an update in targets for 2020.

Given current slow progress on organisation change, despite consistent engagement from donors, DFID will consider options for support to and engagement with AATF over the remaining year of the programme, taking into account resource constraints and challenges

## D: VALUE FOR MONEY (1-2 pages)
Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
The key cost drivers for AATF are Personnel and Administration costs (including financial and audit), monitoring and evaluation, and accessing technical expertise.
AATF have maintained a consistent cost structure with a major proportion of the budgets being designated for project and programmatic work, with a lean budget for core functions (resource mobilisation, monitoring and evaluation, governance, administration). AATF also have robust systems in place to deliver VfM, both within the organisation and with their sub-grantees.
VfM performance compared to the original VfM proposition in the business case
Since the AATF Business Case was approved in 2015, Research and Evidence Division (RED) has articulated a ‘quality and value at each step’ approach to value for money which provides a more useful framework for ensuring VfM than the original metrics proposed. This framework recognises that assessing VfM for agriculture research investments is challenging, as the outcomes and impacts cannot be easily determined. While the evidence of positive rates of return from investment in agriculture research is clear, this is not sufficient for ensuring VfM at programme level. This is a common issue for all research programmes. VfM is delivered by:
- Picking the right problems – AATF have a robust process to identify constraints to smallholder agricultural productivity before identifying potential technological solutions to addressing the constraint.
- Working through strong partnerships – DFID has a strong partnership and working relationship with AATF, and they have good track record in meeting DFID management expectations. AATF has robust systems in place to manage their delivery chain to ensure VfM and reduce risk (see Risk section below)
- Always requiring good quality – AATF ensures that their product development is of high quality and conducts robust field trials of new technologies.
- Programme Management – AATF’s programme and financial management are strong and they have managed DFID resources effectively.
During the period of the report AATF reported many cases of how they have delivered VfM in the past year. The following are set out against the four E’s of the Value for Money Framework.
Economy:	AATF continue to promote WebEx meetings reducing the number of costly face-to-face meetings. / All AATF salary reviews are made using local comparators as benchmark and implemented only when approved by the Board. The last review took effect in 2016 and AATF have frozen salary increase until 2021. / IT and cleaning services were outsourced and AATF have engaged Corporate Uber Services as an additional cost saving measures. / All AATF Projects steering committee members are on pro bono basis. AATF pays only the meeting costs (travel, visa, accommodation and per diem). The AATF office in Nigeria is provided free by Nigerian authorities. / Negotiated Accommodation rates /Use of Partner Rates where more cost effective
Efficiency	AATF use project management software and systems to reduce the complexity of project management and ensure the highest levels of project efficiency and effectiveness. These help to manage the flow of work through the entire project lifecycle. / Contracts are now paid in instalments to ensure payment is based on delivery of quality work. If the work is not satisfactory, the instalment is not paid. / AATF has continued to publish a number of articles in high impact journals and media outlets. AATF Staff have also had chapters in books published. / AATF selects best implementation partners based on their value proposition / contribution to the projects. Timelines and quality are central to the selection of partners and monitoring of the partner’s activities is done to ensure quality results.
Effectiveness:	AATF is partnering with policy actors like AU, FARA, FANRPAN, and ABNE to assist in creating a conducive regulatory environment for agricultural development in SSA. / AATF mode of operation is through Public Private Partnership (PPP) and involves a lot of consultations and advocacy with governments to position agriculture to be transformative. AATF works with the NARS and their representatives are members of project committees to assist in advising on how best to implement projects to get better outcomes. In new areas like Senegal and Rwanda strong government relations are cultivated at Agricultural ministry level to identify priority areas of collaboration. / Results from market assessments, baseline and adoption studies, and impact assessments have been used to realign the project. Lessons from these assessments have also led to creating technology awareness creation campaigns to ensure that smallholder farmers are aware the new technologies that are available from AATF and partners. / To ensure that AATF maximises the benefits of monitoring; evaluation; and learning activities that are undertaken, staff with the guidance of the MEL unit develop M&E plans for their projects/programs including Impact Evaluation plans. These plans need to be negotiated and agreed with all delivery partners and other key stakeholders / AATF conducted a WEMA adoption study in Kenya to learn lessons during the first three years of selling WEMA seeds. Lessons from this study will be used to develop strategies for implementing WEMA in the other four countries. / From 2018, an independent evaluation will be carried out for AATF Projects. The impact evaluation ONGOING for OFAB will generate lessons and trends with regards to biotechnology adoption.
Equity:	AATF has prioritised to assess the needs of its implementing partners on gender mainstreaming and fill gaps where necessary. An annual review of the gender implementation plan has been scheduled to assess the progress in the past year. This will address the issue of intersectionality (segregation of men and women based on age, race, culture religion, literacy among others) within the projects. This knowledge is intended to enhance social inclusion within projects through gender analysis or assessments to be conducted at project onset and reviewed throughout the implementation phase.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)
Tackling hunger and malnutrition (Sustainable Development Goal 2) is a key priority for the UK Government through helping to saves lives, preventing various illnesses, helping people escape from poverty and be more productive, and contributing to economic growth. The DFID Research Review highlights agriculture as a priority theme for spending and impact. DFID’s investment in AATF contributes to the continuation of large-scale research investment into sustainable agriculture, to improve nutrition and food security and increase resilience to climate change in developing countries. Agricultural research remains crucial to the DFID objective of accelerating economic growth, particularly in Africa, as reflected in the new Strategic Directions on sub-Saharan Africa and Harnessing Technology for Development. This is also reflected in DFID’s Economic Development Strategy and DFID strategy for private sector engagement on food systems and nutrition.
Overall, AATF is a well-managed organisation with a focus on results and delivery. It continues to deliver new agricultural innovations for smallholder farmers in SSA and has made significant cost savings in the past two years, as DFID funding will end in October 2020.

E: RISK (½ to 1 page)
Overall risk rating: Moderate
Overview of programme risk
DFID have reviewed the risks associated with his programme and the overall risk rate remains moderate, as set out in the table below. One new risk has been added and relates to two key staff changes in the next 18 months.
AATF have a robust approach to Risk Management and their Risk Management Committee reports to AATF Management and the Board. AATF have a detailed Strategic Risk Register which clearly sets out Risks and Mitigation steps being implemented by Management across a range of categories, including procurement, finance and project management. Of specific interest to DFID as a core investor in AATF is the strategic risks identified by AATF Management. A number of others relate to the regulatory environment and management of intellectual property. These risks are included in the DFID risk table below, as they are considered of particular relevance to the programme.
AATF have a zero-tolerance approach to any fraud or corruption and have internal control systems in place to adequately identify and prevent misuse of funds in Finance and Procurement. In the past year, AATF’s systems identified three potential fraud cases, which were investigated, following AATF procedures. The concerned individuals no longer work for AATF and funds were recovered from them.

Risk category	Description of gross risk	Mitigation strategy	Residual risk rating / (minor/moderate/major/severe)	Risk Trajectory over next year
Context	Failure to adopt appropriate biosafety regulations in AATF target countries / A significant proportion of AATF’s technology portfolio includes traits introduced through genetic modification. If biosafety regulations and their implementation in AATF target countries prevent or ban the trialling and introduction of GM crop varieties AATF will not achieve its objectives. / As reported under Output 3, the positive changes in the regulatory environment have continued in the past year.	AATF is fully aware of this risk and continues to engage partners and countries in dialogue on biosafety through BMGF funding to the OFAB project.	Moderate	Stable
Context	Lack of/withdrawal of investor funding / The funding environment for AATF remains challenging. / The short-term risk to AATF is low, although increasing.	AATF Management and Board are implementing a number of cost saving measures and new investors have committed funds	Major	Stable
Delivery	There has been no change to risks in this category.		Minor	Stable
Safeguarding	There has been no change to risks in this category.		Minor	Stable
Operational	Staff transition / In the next two years, the current Executive Director and Finance Director of AATF are due to retire having worked for AATF for 10 years. This poses a risk to AATF given their knowledge of the organisation and processes and challenge of identifying high quality successors	The AATF Board is fully aware of the situation and discussed recruitment at length during the October 2019 Board meeting. Recruitment will be launched in early 2020.	Moderate	Increasing
Fiduciary	Poor financial management by downstream partners / This risk has not changed. However, as AATF works with 38 partners across 13 countries, issues with any of these partners could impact DFID’s reputation even if DFID funds are not directly involved. / Misappropriation of Funds by AATF Staff and Partners	AATF carries out regular audits of sub-grantees internal control systems at country level ensuring accountability of donor funding. / AATF have robust policies in place to identify any potential misuse of funds and these have been successfully acted upon.	Moderate	Stable
Reputational risk	Reputational Risk is linked to the Risks defined in other categories above		Moderate	Stable

A refresh of DFID’s Due Diligence Assessment, including Enhanced Safeguarding in 2018 recommended that AATF develop a mechanism for reporting Safeguarding concerns AATF have incorporated this process into the HR Manual which , when read with the Whistleblowing policy, sets out in detail the process to follow.
A particular challenge is that AATF works with a diverse range of Downstream Partners, including large multi-nationals, local companies and government agencies. In order to give a clearer picture of the risks and challenges AATF categorised the partners and contacted the UK Charity Commission for advice on this issue and have strengthened clauses in documentation issued to downstream partners to ensure full accountability for finance and management processes.

Compliance with DFID commitments:
1. The programme complies with 2014 Gender Equality Act commitments.
2. The main supplier complies with the Equality Act 2010 according to its annual report.
3. The supplier complies with DFID branding. Branding guidance had been shared with the supplier and spot-checks confirmed that produced materials do use the DFID branding correctly.
4. Programme’s documents which fall into the 11 document types listed in the Transparency Smart guide are displayed on the Development Tracker.
5. Programme information is not published on the International Aid Transparency Initiative (IATI) website.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)
Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)
Funding remains at the same level as in the previous phase of funding (£1.5 million/year) under an Accountable Grant. In addition, a performance related component of up to £500,000/year is structured to incentivise more rapid progress in key areas: achieving and assessing impact at scale, financial sustainability, and strengthening of the product pipeline.

Quality of financial management
Invoices and Financial Reports are submitted quarterly to DFID outlining the expenditure incurred against the agreed budget from the previous quarter and the forecast for the next quarter. Full explanations are recorded for any significant differences between forecast and actual spend. Payments are now made quarterly in arrears.
AATF have submitted invoices against agreed forecasts during this period to maintain spend at agreed figures for each programme year. £1.5m was paid in Core Funding during Year 4, together with the performance related payment of £400,000 for 2018. AATF’s Organisational budget is planned in US Dollars. The Pound Sterling/Dollar exchange rate remained stable during the year and therefore had minimal impact on Budgets.

Forecast	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Core Funding	1,500,000	1,500,000	1,500,000	1,500,000	1,500,000	7,500,000
Performance Payment	500,000	500,000	500,000	500,000	500,000	2,500,000
Disbursement
Core Funding	1,500,000	1,500,000	1,500,000	1,500,000
Performance Payment	250,000	250,000	400,000	150,000
Total	1,750,000	1,750,000	1,900,000

The total expenditures on DFID funds amounts to £1,479,702 during the period Oct 2018 – Sep 2019, out of which 20% were spent on project activities.
A full audit of AATF is carried out on a yearly basis by external auditors and the report provided to DFID.
AATF also carries out audits of sub-grantees’ control systems to ensure management and financial accountability and a summary report is provided to DFID. Generally, the controls in place are good; however, there were instances where financial controls could have been more robust. AATF follows up issues with the sub-grantees, and if necessary, will withhold funds until satisfactorily resolved. Additional Audits were conducted in October/November 2019 and AATF continues to engage with Project Managers and Partners to remind them of their financial management responsibilities.

Date of last narrative financial report(s)	October 2019
Date of last audited annual statement (s)	December 2019

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)
Monitoring (1/2 page)
Notwithstanding the issues outlined in this review, DFID continues to have a good working relationship with AATF. In general, they respond promptly to requests for information and provide reports on time, although they have not been as punctual in 2019, and reports have not been as concise or well written.
Reports were received in October 2019 and the Annual Review was carried out by the SRO. The SRO attended the AATF Board Meeting in October 2019 as part of the review process. Amongst other supporting documents, AATF provided a Technical Progress Report, Social Media Strategy, Resource Mobilisation Update, and details of key achievements.
DFID works closely with the other core investors (USAID and BMGF) to ensure agreed objectives. Investors are represented at each Board Meeting (attending on a rotational basis) and provide feedback and regularly engage with each other over key issues.
Evidence (1/2 page)
The evidence of the need for support for the development and delivery of agriculture technologies appropriate for smallholder farmers in SSA has not changed from that set out in the Business Case for this programme. Detailed analysis of the assumptions under-pinning the logframe and evidence that they are holding true in practice is provided under Section C of this report.
Learning (1/2 page)
The past year has confirmed learning from 2018 that while AATF has demonstrated that it is capable of kick-starting institutional transformation in a challenging environment, for example though the establishment of the new social enterprise and the new Strategies, it is much more difficult to deliver organisational change.
Progress on recommendations from previous reviews (1/2 page)
#	Recommendation	Progress
1	AATF to assess and update the logframe to bring it more into line with shifts in focus and the new strategy and workplan. For example, the closure of WEMA project and creation of Agridrive need to be reflected. Logframe changes to be agreed between AATF and DFID by the end of March 2019.	Completed
2	AATF to implement plans and monitor the impact of increased social media interaction outside of key events, reporting specifically on this in the next report to DFID (October 2019).	Completed
3	As with some of the indicators under Output 1, Indicator 4.3 has been substantially exceeded. AATF is recommended to review whether these indicators and targets continue to align with AATF’s workplans, for example with the newly approved projects. Logframe changes to be agreed between AATF and DFID by the end of March 2019.	Completed
4	AATF to continue to report on the performance of Agridrive, integrating reporting into the logframe	Completed
5	AATF to share the TOR for the OFAB impact evaluation and the final report, along with the new evaluation framework.	Completed
6	DFID and AATF to agree performance indicators for Year 4 by the end of March 2019.	Completed in May 2019
7	AATF to provide a clear plan of action with measurable indicators of progress on improving recruitment of women to improve the organisation’s gender balance (carried over from 2017 Annual Review).	Not completed / Although they are tracking indicators in recruitment, they have not developed a clear plan of action.
8	AATF should have a clear plan in place for implementing the new approach to project overheads (by February 2019).	Completed and shared with DFID.
9	AATF to report to DFID on the categorising of downstream partners in terms of safeguarding, fraud, and anti-corruption procedures and how they will adapt their approach to limit risks (by June 2019).	Completed in November 2019
10	AATF to take forward recommendations from the due diligence review (by May 2019).	Completed.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided