ADDENDUM TO BUSINESS CASE FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	NRC Information, Counselling and Legal Assistance (Residency)
Country or region targeted	Occupied Palestinian Territories
Type of cost extension	Scale-up
Original project budget	GBP 3,000,000 (2013-2015)
Original project start and end dates	1 April 2012- 31 March 2015
Cost extension value	GBP 500,000
New project end date	31 March 2015
Business Case Quest Document No.	3879571

INFORMATION
What is the project’s purpose?
The project aims to facilitate the provision of free legal aid services, including information, counselling and legal assistance, to Palestinians in the West Bank and Gaza Strip in the area of residency rights, travel permits between Gaza and the West Bank and the right to adequate civil documentation to facilitate freedom of movement internally and externally and access to services. / Palestinians currently face difficulties in accessing these rights on account of policies and practices which restrict employment, social, cultural, educational, medical and other opportunities. These factors can cause displacement, particularly where residency rights are revoked. / Between 2009 and 2013 the Norwegian Refugee Council’s Information, Counselling and Legal Assistance (ICLA) project concentrated on providing legal assistance to Palestinians in the area of Housing, Land and Property (HLP) rights. The April 2014 Annual Review of the ongoing DFID-funded element of this project entitled ‘Legal Assistance to prevent displacement and demolitions in the Occupied Palestinian Territories (OPTs)’ scored an A, meaning that it is delivering well and in line with expectations. / Now that this programme has met many of the basic legal needs in this area, the programme would like to expand into residency rights as another area of legal need by the Palestinian community within the West Bank and the Gaza Strip. As the issue of residency and civil documentation rights affects Palestinians throughout the West Bank and Gaza and has a further regional dimension, the programme would be well-placed to use its offices and resources in the West Bank and Gaza, as well as its regional networks, to further the aims of the project. / The purpose of the residency project within the wider ICLA programme would thus be to assist Palestinians to exercise these rights and avoid displacement.
What is the objective of the cost extension?
The objective is to more holistically address the issue of displacement of Palestinians in the West Bank and Gaza. This will be done through the provision of free legal aid services, including information, counselling and legal assistance, to Palestinians in the West Bank and Gaza Strip in the area of residency rights, travel permits between Gaza and the West Bank and the right to adequate civil documentation to facilitate freedom of movement internally and externally and access to services. / The purpose of the original project is to provide facilitate the provision of free legal aid services, including information, counselling and legal assistance, to Palestinians in the West Bank and Gaza Strip in order to prevent displacement. This proposal fits within the original purpose as it is addressing another potential cause of displacement. / The outcome of the project would be reworded to read - ‘Palestinians at risk of displacement within the OPTs are better able to uphold their housing, land, property and residency rights through provision of legal aid services and increased access to justice’.
What is the additional and total support the UK will provide?
The proposal is budgeted at GBP 500,000.
What are the expected results?
The expected results are as follows: / Palestinian residency and civil documentation rights are protected. / Beneficiaries are empowered and have improved understanding of administrative procedures related to residency. / More specifically:70% of surveyed beneficiaries report the ability to act on their residency and civil documentation rights 40% of beneficiaries experiencing residency or access restrictions receive a remedy (grant of permit, registration or civil documentation provided) due to legal assistance provided (this indicator will involve a comparison of the numbers of instances in which a remedy was granted as compared with those refused in the project period). / 60% of beneficiaries participating in information sessions who report the information presented will assist them in their daily lives
What is the approach to implementation?
The project would make use of the existing networks, providers and activities utilised for the ICLA programme. This would be a cost-effective use of existing resources and would allow NRC to take the same coordinated approach to residency issues, as it has done with HLP rights. The project would be implemented utilising the following stakeholders and activities: / Legal aid providers specialising in residency and civil documentation rights (NGOs and private lawyers) to provide information, counselling and legal representation; / NRC staff in the West Bank and Gaza to provide counselling, information and referrals and to follow up on cases and issues with providers and national and international stakeholders; / Linking residency and civil documentation issues affecting Palestinians in the West Bank and Gaza, through the NRC offices and networks in both regions; / Usage of coordination mechanisms including; Protection Cluster, Legal Taskforce, AIDA networks and other forums; / Close coordination with the Palestinian Authority on activities and key issues; / Research into topical areas of interest for legal practitioners and national and international stakeholders;
Describe any key changes to the original business case?
The current DFID funded project ‘Legal Assistance to prevent displacement and demolitions in the Occupied Palestinian Territories (OPTs)’ is meeting expectations and scored an A in the Annual Review conducted in April 2014. The present proposal involves an expansion of this original project to new activities in the field of residency and civil documentation rights.