Intervention Summary
## UK Anti-Corruption Action (UK ACT)
## (The renamed ‘Enhancing International Action against Corruption)

What support will the UK provide?

The UK will provide £21,000,000 of new funding for 2015-2020 to the existing UK law enforcement programme ‘Enhancing International Action against Corruption’ which tackles the UK end of corruption relating to developing countries. This next phase of the programme will be renamed UK Anti-Corruption Action (UK ACT). The funding will go to two police units dealing with corruption in the Metropolitan Police and City of London Police, to the Asset Recovery Unit in the Crown Prosecution Unit (CPS) and to the International Corruption Intelligence Cell in the National Crime Agency (NCA). £500,000 will fund an evaluation of the programme from inception in 2006 until the end of this phase of funding in 2020; and £230,000 for contingencies.

DFID is currently providing £18,725,000 for the period 2009-2016. The new support will scale up the final year of the existing programme (2015/16) and provide new funding for 2016-2020. Other programmes provide funding for UK asset recovery action focused on specific countries: £950,000 for 2013-2015 has been provided under the Arab Partnership Enablement Fund for the Prime Minister’s Egypt Asset Recovery Task Force; and an additional £500,000 for 2014-16 has been allocated under the Ukraine Crisis Programme to support asset recovery work on Ukraine.

The support will be in the form of a cost extension to the existing programme.

Why is UK support required?

Corruption is a major problem for many of the countries where DFID works. It threatens economic growth, wastes resources, deters investment and also hurts the poor the most. Corruption takes many forms including ‘grand’ corruption where large sums of money are stolen from national resources limiting funds available for development; and bribery by foreign companies and nationals to obtain contracts and benefits in the developing countries.

Tackling corruption affecting developing countries requires action on several fronts: support to partner countries to build better governance to deal with corruption issues within their borders; international action on standard setting and oversight mechanisms; and action in the UK to recover and return money stolen from developing countries and to ensure UK companies and nationals who bribe in developing countries are held to account.

This intervention is focused on action in the UK and will provide additional support to law enforcement action in the UK to increase the work already being done to address corruption affecting developing countries. Strong competing pressures across HMG have in the past prevented cases from developing countries securing adequate attention. Without DFID support, the corruption cases relating to developing countries, particularly the poorest and most fragile and difficult, are unlikely to be pursued.
What will we do to tackle the problem?

We will extend and increase support to four specialised units in UK law enforcement:
- the ‘Proceeds of Corruption Unit’ (POCU) in the Metropolitan Police to investigate and trace funds stolen from developing countries that are found in the UK and to bring the perpetrators to justice;
- the ‘Overseas Anti-Corruption Unit’ (OACU) in the City of London Police to investigate and take action against UK nationals and UK companies which bribe in developing countries;
- the International Corruption Intelligence Cell (ICIC) in the National Crime Agency to ensure the police units have the best intelligence tailored to developing country cases; and
- the ‘Proceeds of Crime Unit’ in the Crown Prosecution Service (CPS) to ensure assets stolen from developing countries are recovered and returned.

What are the expected results?

The programme’s intended impact is that incentives are reduced for corrupt individuals in developing countries to use the UK to launder money: or for UK business and UK nationals or their agents to bribe in developing countries.

The outcome is that developing countries benefit from action in the UK:
1. to recover and return assets stolen from them by corrupt individuals and
2. to pursue UK companies and nationals who use bribery and corruption in developing countries.

The programme will deliver 5 outputs:

Output 1 – Sustained and increased level of prevention, disruption and investigation of money laundering cases in the UK.
Output 2 – Sustained and increased level of stolen assets recovered and returned to developing countries.
Output 3 – Sustained and increased level of prevention, disruption and investigation in the UK of overseas bribery and corruption cases relating to developing countries.
Output 4 – Enhanced and strategic intelligence relating to UK-linked corruption affecting developing countries.
Output 5 - Increased and co-ordinated action by HMG and developing country partners to prevent corruption and build capacity supported by a new combined team at the National Crime Agency.

1. Strategic case

Context and need for DFID intervention

  1. DFID recognises that combating corruption is a vital part of the development process. It threatens economic growth, wastes resources, deters investment and also hurts the poor the most. There are many forms of corruption affecting developing countries: the forms relevant to this programme include ‘grand corruption’ where large sums are stolen from the public funds of the developing country and then laundered, often through other countries with more secure financial systems; and bribery by foreign companies and nationals to secure benefits in the developing country.

  1. With grand corruption, the theft of public funds usually takes place at senior levels where policies and executive decisions are made. This is one of the most challenging dimensions to address as the stakes are typically high, and those involved are normally members of the political and business elite – politically exposed persons (PEPs), who may be difficult to hold to account especially in countries with weak justice systems. Grand corruption often takes place through convoluted mechanisms that are well concealed from the public eye and require specialist expertise to investigate and sanction. Poor quality financial management, procurement and tax systems, and weak oversight and law enforcement capacity, make it easier to commit grand corruption. The proceeds of corruption may then be used domestically, for example to fund political parties or elections; or sent to foreign bank accounts, trusts and other financial ‘vehicles’, often well-disguised as being for apparently legitimate reasons.
    [note] A recent report by StAR - the World Bank/UN Office on Drugs and Crime (UNODC) Stolen Asset Recovery Initiative - reviews 150 of the largest grand corruption cases and highlights the numerous ways in which the proceeds of corruption have been transferred and concealed. http://www1.worldbank.org/finance/star_site/publications/Puppet-Masters.html - 2011. The StAR database of corruption cases can be found at http://star.worldbank.org/corruption-cases/assetrecovery/?f[0]=bundle%3Apuppet_masters

  1. There are no reliable estimates on the scale of grand corruption, either globally or at country level, but there can be little doubt that it has a severe detrimental effect on many developing countries. The recent fuel subsidy corruption case in Nigeria is estimated to have lost the country US$4bn from 2009 - 2011. Some estimates suggest Suharto stole US$15-35bn, Mobutu US$5bn and Abacha US$2-5bn during their time in power. Such amounts massively exceeded the donor assistance that flowed into the countries. Little of this money has ever been recovered. Recovering and returning even a fraction of these or other sums stolen would provide a significant increase in the resources available for development and send a strong message deterring money laundering.

  1. Foreign businesses and foreign nationals working in developing countries can also have a significant impact when they engage in bribery and other corrupt practices. They may bribe to get contracts, they may facilitate grand corruption by political elites and they may be involved in fraudulent and dangerous trade. Some UK businesses and nationals are part of the problem and recent cases, investigated by the DFID funded City of London Police Team, involving UK companies have included Macmillans Publishers, caught bribing for book contracts in Southern Sudan; and UK companies and individuals caught selling fake bomb detectors around the world. Tackling these forms of corruption by UK nationals and businesses is critical both to counter the culture of impunity and to enforce the international anti-corruption standards and UK law.
    [note] Macmillan Publishing Ltd was investigated for paying bribes to obtain sole tendering rights to supply educational material to the Government of Southern Sudan. Macmillan subsequently self-referred to the Serious Fraud Office (SFO) resulting in a £11.4 million fine.
    [note] In 2013, UK national, Gary Bolton was convicted of the manufacture and worldwide sale by his company ‘Global Technical’ of fake explosive and drugs detection equipment, which secured over £5,000,000 of contracts. He was sentenced to 7 years imprisonment.

  1. The cost to developing countries of corruption is not just financial: failure to take action against grand corruption sends out a message that the political and business elite are unaccountable; grand corruption can become a way of life for those in power, resulting in generalised corrosion of state institutions, systems and laws; it may facilitate a ‘race to the bottom’ in which elites compete with each other to grab the greater share of state resources while in office. Such costs become all the more noticeable in countries with low rates of economic growth, where grand corruption can represent a substantial share of a small resource ‘pie’. Similarly, failure to act against bribery and corruption by international companies can send the message that corruption is a way of life for international business in which they can engage with impunity.

Tackling corruption is difficult enough for developed countries, particularly where cross-border co-operation is required. For developing countries, it is an even more difficult task: they rarely have the law enforcement capacity to tackle the corruption within their own borders, let alone the capacity to take action on cross-border money laundering or bribery by foreign companies or foreign nationals. International support and action is essential to challenge the assumption that corruption is an inevitable way of life.

  1. Ensuring corrupt individuals are brought to justice and that assets are recovered and returned is a fundamental reason to take action. Another fundamental reason is that failure to act has other costs for UK development goals. There is a cost to the UK in reputation and credibility as a development partner where money laundering through the UK and overseas bribery by UK businesses continues unchecked.

  1. Tackling corruption affecting developing countries requires action on several fronts. Actions at country level need to include long term interventions to reduce scope for corruption, for example through strengthened institutions and public financial management, improved voice and accountability. DFID country offices are actively supporting these areas of work. At the same time, tackling corruption requires international action to address cross-border money laundering and bribery by foreign nationals and companies. DFID supports such international action though standard setting (such as UNCAC or OECD) and has recently increased this support to regional financial organisations in Africa under the 2013 Anti-Money Laundering Programme.

  1. The other important area for intervention is in the UK and it is action in the UK which is the focus of this programme. For the UK to play its part in supporting developing countries to fight corruption, it has a responsibility to deal robustly with cases where the UK is a facilitator or ‘supplier’ of corruption. Cases relating to developing countries that are within the UK’s jurisdiction must therefore be tackled as effectively as possible.

  1. Corruption in developing countries often has connections to developed countries with significant trade or financial services such as the UK. There is much that can and must be done to make sure that work to tackle corruption in developing countries and at the international level is not undermined by lack of action in the UK. Support is therefore required to continue and extend the work of dedicated UK law enforcement teams to tackle the corruption issues affecting developing countries and to make sure they get the priority and attention required. This means taking action in the UK on two main fronts: firstly to recover and return money stolen from developing countries and laundered through the UK and to bring the perpetrators to justice; and secondly, to ensure that UK nationals and companies which engage in bribery or other corrupt practices in developing countries are held to account. Tackling both these aspects for which the UK has a direct responsibility …

Tackling Money Laundering in the UK

  1. ‘Money laundering’ refers to concealing the source of illegally obtained money and assets. In the UK, any handling or involvement with the proceeds of crime constitutes money laundering. Money may be laundered through the UK in many ways: by buying property and luxury assets; by transferring funds into UK banks; by using UK financial systems to transfer money to overseas banks, off-shore trusts and overseas companies where identities may be more easily concealed.

  1. Many low and lower middle income countries face major problems in even having the basic institutional structures in place to tackle corruption, let alone ensuring that they are functioning effectively. The lack of effective systems means that poor countries are ill-equipped to tackle money laundering and corruption, either within their own borders or to take action when the stolen funds have left the country.

  1. Many corrupt PEPs are attracted to the UK to buy into the lifestyle, property, financial security available here. James Ibori, the former Governor of Delta State, Nigeria was one such person and laundered the assets he stole from Nigeria, through bank accounts and property in the UK. The successful prosecution against him, following an investigation by the DFID-funded Met Police Unit, is a landmark cases in using the UK justice system to successfully tackle cross-border grand corruption. James Ibori and his associates are now serving long prison sentences and the assets they stole are being recovered. Approximately £80 million of assets stolen by Ibori are currently in the process of confiscation in the UK by the DFID-funded CPS Asset Recovery Unit.

Tackling Overseas Bribery and Corruption by UK Companies and Nationals

  1. Most UK businesses and nationals operating in developing countries aim to do business cleanly. However some UK businesses and nationals have been convicted of paying bribes to secure lucrative contracts and to facilitate corrupt procurement processes following investigations by the DFID-funded City of London Police Unit. In other cases, connected UK companies have sold fake bomb detection equipment to developing country governments, causing great risk to many lives.
    [note] UK cases have included: The CEO of CBRN Company who authorised payment of £50,000 to a Ugandan presidential adviser to secure a government contract. The CEO and Adviser were sentenced to 5 and 12 month terms of imprisonment respectively. In another case, a BP contracts manager received bribes to favour bidders for maintenance contracts. Two defendants sentenced to 3 years and 12 months respectively.
    [note] A recent case concerned a bribe of US$200,000 paid to the Russian director of the European Bank of Reconstruction and Development by the CEO of Vostok Energy Ltd (Capelson) to secure a $100,000,000 loan. In 2013, CEO Capelson was convicted of corruption and imprisoned for 12 months. In another case, Dutch nationals, assisted by UK solicitor, were alleged to have accepted bribes to influence the award of aid contracts in the Democratic Republic of Congo and as a result won a contract valued at over US$1.1 million. One suspect pleaded guilty in 2012. Two await retrial in 2014.

  1. Investigations of overseas bribery and corruption cases such as these are a critical part of tackling corruption: they maintain the pressure on UK companies to do business cleanly; they send a message that the UK has a zero tolerance for overseas bribery and corruption by its own companies and nationals; and it provides support to developing countries which often lack the specialist expertise required to investigate these crimes within their borders.

  1. Under the Bribery Act, the UK has strengthened powers to investigate cases of overseas bribery. New powers to prosecute senior officials in companies under a ‘corporate responsibility’ offence are encouraging companies to ensure they have adequate procedures in place to guard against corrupt practices by their staff and agents.

Enhancing Intelligence Support

  1. Targeted intelligence for developing country cases is critical to start and develop ongoing investigations into money laundering and overseas bribery. UK intelligence has limited experience of identifying and developing this type of intelligence in relation to corruption relating to developing countries and so building a dedicated resource is essential. In the last two years of this programme, the National Crime Agency has developed its experience of work on money laundering linked to developing countries but there is a continuing need for a dedicated intelligence resource on overseas bribery. In addition, strategic level intelligence on developing country corruption and high risk individuals is an important dimension. This is needed to ensure HMG and UK law enforcement are well-informed and prepared for crises and opportunities that arise in developing countries, to identify high risk countries where money laundering has a strong connection to the UK; or highly corrupt countries where British business operates.

Asset Recovery and Return
  1. Developing countries face two principle challenges in this area. First, they often lack the specialist expertise required to investigate complex economic crimes and obtain the necessary evidence domestically or from other countries. Second, their law enforcement systems are often weak and corruptible (ie those under investigation can pay, or place pressure on the authorities, to ensure a favourable outcome).

  1. Based on experience of the strong competing pressures within UK law enforcement, it is our judgement that DFID needs to provide the funding for this work. This is for a number of reasons. UK law enforcement, given the free choice about where to use its restricted capacity, has preferred cases coming from familiar and trusted quarters – EU, US, Canada, Australia, South Africa – over those coming from unfamiliar and untested jurisdictions such as those in developing countries. UK law enforcement does not often have the links or experience in dealing with those legal systems and has low confidence in the chances of effective co-operation.  Cases from familiar and trusted jurisdictions can often seem to offer better prospects of success given the greater trust in processes and greater reliability of evidence. Other government departments and agencies also have different priorities from DFID which can often involve addressing issues and cases from countries that pose the greatest risk to the UK. Although there is overlap, DFID’s objectives are focused on addressing poverty reduction, not risk to the UK. DFID funding can ensure the extra time and effort is put into identifying, investigating and pursuing cases from developing countries. This has been shown to bring big dividends not only in the financial value for developing countries but in the symbolic value of tackling impunity. Without DFID funding and intervention, it is unlikely that cases from poorer, developing countries would secure adequate attention. In the first phase of the programme there has been some shift in this position and over the next phase of the programme, DFID will work across HMG to develop a firm basis for our exit strategy, using the means of a cost recovery process for money laundering cases and clear terms of reference to ensure that developing countries cases are given proper attention. We believe this approach will enable the handover of the work from 2020.

DFID support needed
  1. Experience to date and recent developments have demonstrated that there is a need for extended and increased support: there is increased demand for asset recovery work; new opportunities for preventive work on bribery; a need to increase the intelligence support for bribery and strategic work; and a critical role for the funded units in the evolving UK international anti-corruption agenda.

  1. In the last two years, new and urgent asset recovery work has been required on Arab Spring countries, mainly Egypt, and now similar demand for work has emerged from Ukraine. The expertise to tackle this work is concentrated in the DFID funded Met police team although the NCA are building their capacity by

leading on the Ukraine asset recovery work. A proposal for an international ‘Rapid Response Team’ is currently being developed to combine UK and international expertise in tackling urgent demands such as those from Egypt and Ukraine.

  1. Now that the work is established with a track record of cases, there is the opportunity to improve the balance between investigative and preventive work by increasing the latter. On overseas bribery and corruption, the City Police Unit will increase preventive work with UK business and work more closely with the World Bank and regional banks on procurement and other corruption risks with a focus on the poorest countries.

  1. Intelligence capacity across HMG remains insufficiently focused on developing countries at both routine and strategic levels and this needs increased attention to ensure the police units have the best possible intelligence to develop their cases.

  1. With increased HMG attention on international corruption and the 2014 Independent Commission on Aid Impact report on corruption, the continued and extended work of this programme is essential to ensure efforts to tackle developing country corruption are a core part of the UK effort.

  1. By the end of the next phase of the programme, DFID aims to have an exit strategy in place to hand over the work to the Home Office and NCA with sustainable funding and without losing the focus on developing countries. The Law Enforcement Review, led by the Home Office has recommended that DFID and the Home Office explore how best to pursue full cost recovery. In the last two years since the Arab Spring and the demand from Egypt to recover stolen assets in the UK, there has been a higher priority across HMG given to tackling corruption. The aim will be to move towards full cost recovery of the costs of taking corruption cases while setting clear terms of reference to ensure that developing country cases are given proper attention.

  1. The issues, existing support and future needs are set out in the table below.

Issue	Existing support	Future needs
Increasing pressure of asset recovery work from developing countries and countries in crisis and transition (Egypt and Ukraine).	DFID funding to 2016 to the Metropolitan Police to investigate grand corruption cases and to the Crown Prosecution Service to pursue asset recovery following conviction. Some short term support to Egypt.	Increased assistance needed to investigate backlog of cases from developing countries and to sustain assistance to Egypt. Extended support proposed to 2020
Better balance needed between investigation and prevention work to address bribery and corruption by UK companies and nationals in developing countries.	DFID funding to 2016 to the City of London Police to investigate bribery and corruption by UK companies and nationals,	Assistance needed to increase the pipeline of cases and to develop the prevention work with UK companies operating in developing countries.
Intelligence insufficiently focused on corruption in developing countries either at routine or strategic level.	DFID support a small intelligence unit in the NCA with a predominant focus on grand corruption and asset recovery. Currently only limited support on overseas bribery and corruption and strategic assessments.	Assistance to increase intelligence support to overseas bribery and corruption to a comparable level to asset recovery and to give greater priority to strategic intelligence
The corruption agenda is being shaped across HMG departments and law enforcement agencies around a Task Force Model; Prevention and capacity building is increasingly needed as a component of the work. / Transfer of the Met Police and City Police Units to the NCA needs careful handling and continuity of funding to enable an orderly handover of the work with no loss of impact.	DFID funded units are a key part of Whitehall representation and co-ordination. / Funding until 2016 of all the units involved in the transfer to a new combined team at the NCA.	Increased assistance to enable participation in shaping the HMG agenda on corruption and development issues; and for prevention and capacity building work with developing countries. / Stability of funding until 2020 to enable a process of full cost recovery to be developed and terms of reference for the new team to be embedded to ensure a continuing focus on developing countries.
[note] The task force model brings together government policy departments and operational agencies in a more structured way to co-ordinate efforts on countries and cases. It developed as part of the Egypt asset recovery work and proved very successful in ensuring a co-ordinated and effective HMG response under Cabinet Office leadership. This differs from the past when there was no clear lead or co-ordination.

B. Impact and Outcome

  1. The aim of this programme is set out in the diagram below. On the right are indicative success measures.

Programme Impact, Outcome and Outputs

OUTCOME: Developing countries benefit from action in the UK to recover and return assets stolen from them by corrupt individuals and by action to pursue UK companies and nationals who use bribery and corruption in developing countries.

IMPACT: Incentives are reduced for corrupt individuals in developing countries to use the UK to launder money: or for UK business and UK nationals or their agents to bribe in developing countries.
OUTPUT 1: Increased and sustained level of disruption, investigation and prosecution of money laundering cases in the UK.

OUTPUT 2: Increased and sustained level of stolen assets recovered and returned to developing countries.

OUTPUT 3: Increased and sustained level of disruption, investigation and prosecution in the UK of overseas bribery and corruption relating to developing countries.

OUTPUT 4: Increased and enhanced intelligence relating to UK-linked corruption affecting developing countries.

OUTPUT 5: Increased and co-ordinated action by all units/new combined team mobilises HMG and developing country partners to prevent corruption and
build anti-corruption capacity.

Increase in successful cases and assets returned.

Increased and sustained action in the UK against corruption linked to developing countries.

Output 1 Indicators
Cases under investigation by POCU.
Developing country jurisdictions on which POCU has cases in progress.
Assets restrained by POCU.

Output 2 Indicators
Cases appraised by the CPS for criminal confiscation or civil recovery.
Value of assets returned by CPS to developing countries.

Output 3 Indicators
Intelligence packages developed by OACU intelligence desk.
Foreign bribery cases under investigation by OACU.
Foreign bribery cases referred to CPS by OACU.
Disruption results on bribery and corruption.

Output 4 Indicators
Increased intelligence support on asset recovery for POCU.
Increased intelligence support on asset recovery for OACU.
Strategic intelligence on DFID priority countries useful to DFID, POCU and OACU.

Output 5 Indicators
Disruption actions and cases on which POCU, OACU and ICIC collaborate.
Formation of a joint International Anti- Corruption Team at the NCA is well-managed to ensure minimum impact on work of all teams.
Collaboration on cases and other disruptions with overseas partners including foreign law enforcement, DFID country offices and posts.
2. Appraisal Case

This section will now identify and appraise the available options to deliver the desired new programme outcome – that developing countries benefit from action in the UK to recover and return assets stolen from them by corrupt individuals; and by action to pursue UK companies and nationals who use bribery and corruption in developing countries; and the new programme impact that incentives are reduced for corrupt individuals in developing countries to use the UK to launder money: or for UK business and UK nationals or their agents to bribe in developing countries.

General Overview

The existing programme has been running since 2006 when two police teams were first established with DFID funding to tackle corruption from developing countries with a UK connection. This is a ground-breaking initiative and over the eight years of the programme, the police teams have built a portfolio of cases and world class expertise and reputation for tackling corruption linked to developing countries. This phase of the programme has been running since 2009 and has had one in-depth review in 2011 in addition to routine annual reviews. It is a highly innovative programme, uniquely supporting the delivery of work in the UK to deliver benefit to developing countries. Although the funding is spent in the UK, the benefit to developing countries from tackling corruption affecting those countries and returning stolen assets means that the funding satisfies ODA requirements. The programme has been a significant catalyst boosting wider and more co-ordinated HMG activity on tackling corruption linked to developing countries.

Context

For most of the life of the programme, the two DFID-funded police units have worked in a context of limited action across HMG to tackle international corruption. However, since the end of 2012, there have been several important developments in this context:
- The Prime Minister has put tackling corruption at the top of the development agenda.
- The Arab Spring and the assets stolen from Egypt under the Mubarak regime, led to the formation of Prime Minister’s Egypt Asset Recovery Task Force (EARTF). The Task Force dynamics have led to a new way of working on asset recovery across HMG. A ‘task force’ model is now seen as the ‘gold standard’ approach in the way it co-ordinates and mobilises government departments and law enforcement agencies. This task force model is currently being put to good use on Ukraine.
- A re-energised HMG anti-corruption effort has led to a new governance architecture being created for international anti-corruption. Inter-ministerial and director level groups have been established to lead and co-ordinate across HMG and the Cabinet Office is setting up a central secretariat.
- After several years of planning, the National Crime Agency (NCA) was been created in October 2013 to replace the Serious Organised Crime Agency (SOCA) with a specific remit on economic crime. As part of its new approach on economic crime, the NCA is establishing a dedicated Anti-Corruption Team as part of its Economic Crime Command.
- The Inter Ministerial Group on Anti-Corruption agreed in October 2014 that the two DFID-funded police units should move to the NCA and form a combined anti-corruption team.
- HMG has committed to an Anti-Corruption Action Plan under the Open Government Partnership (led by the Home Office) and is currently developing this for publication in November.
- The FCO is refreshing its approach to anti-corruption and has a new Anti-Corruption Team.
- The Home Office is reviewing the gaps in UK law enforcement on international corruption, partly as a result of the work of this programme.

1. These developments provide important opportunities for DFID to influence HMG coordination and effectiveness on tackling corruption in developing countries with a UK aspect. DFID has been an important player and influencer in this process, based on the substantial experience of this programme. For example, the 2011 review of EIAAC recommended the establishment of a ‘UK International Counter-Corruption Task Force’ combining the police units and the International Corruption Intelligence Cell (ICIC) in the NCA. Since that review, police units have seconded staff to work in ICIC and the Inter Ministerial Group has agreed that both police teams should combine operationally with the ICIC in a new ‘International Corruption Team’ at the NCA. NCA, the Metropolitan Police and the City of London Police are currently planning this move and the new team could form the basis for a more wide-ranging team in the NCA which also covers corruption from countries beyond DFID’s remit.
2. DFID’s priority remains to contribute to UK efforts tackling corruption affecting developing countries at policy and operational levels. At the policy level, DFID must remain a core part of the cross-HMG policy efforts on international anti-corruption to ensure that developing countries are given proper attention.
3. On the operational level, DFID funding is required to support the work of law enforcement. This involves tracing proceeds of corruption from developing countries which are being channelled to or through the UK and bringing the cases to court, recovering assets and repatriating funds so they can be used for development purposes. The work also includes taking action against UK companies and nationals engaged in corrupt activities in developing countries. Although there is no firm evidence, successful cases are likely to be a deterrent to others using the UK to launder illegal money or who are engaging in corrupt activities in developing countries. They back up the HMG commitment to take a zero tolerance approach to corruption and to send a strong message that the UK will tackle international corruption when it can do so within its own jurisdiction
4. Successful cases are often the result of close bi-lateral collaboration between law enforcement in the UK and the counterparts in the countries with which they are engaging. As many of the countries in which DFID works have authorities which are themselves corrupt and/or limited in capacity, DFID works with a number of police and justice programmes to support the development of the justice sector. Over time, it is anticipated that collaboration on corruption cases, will lead to better mutual understanding of the necessary legal requirements for effective cross-border law enforcement and better results. The World Bank Stolen Asset Recovery Centre and the International Centre for Asset Recovery are important partners in country-level capacity building work.
5. This Programme supports UK law enforcement to operate in one of the most complex and challenging areas: corruption investigations involve working with law enforcement actors in countries which often have limited capacity and expertise; the cases require long and complex investigations through multiple financial layers; and the defendants regularly mount legal challenges including numerous judicial reviews. The UK system also imposes constraints to effective co-operation with developing and transition countries, such as short time limits for responding to suspicious activity reports and specific requirements for mutual legal assistance requests. Addressing these constraints is now on the agenda as a result of the experience of this programme and the Egypt Asset Recovery Task Force.
  [note] This is under review by Andrew Beloff QC and an amendment to the Proceeds of Crime Act will go to Parliament

Current Work of the Programme

The current programme supports two police teams in the Metropolitan Police and the City of London Police and has stayed at broadly the same size between 2006 and 2012 with approximately 12 officers per unit. Both units have developed a full portfolio of cases. The addition of funding to an asset recovery team in the Crown Prosecution Service (CPS) in 2011 and an International Corruption Intelligence Cell (ICIC) in the National Crime Agency (NCA) in 2012 were aimed at filling capacity gaps in dealing with the legal work to recover assets and the intelligence feed for police investigations.

The asset recovery cases, which are investigated by the Met Police Unit, usually take several years to develop. In the first few years of operation, the Met Police Unit had a string of Nigerian cases which led to the successful Ibori trial in 2012. Since then, they have diversified to a wider number of countries and cases. Now they are overloaded with work and have a backlog of cases; they have taken on the Egypt work with few extra staff; and have also been involved in the Ukraine work. They are currently running 17 investigations including one with a potential value in excess of £500 million in recovered assets.

The City of London Police investigates bribery and corruption cases in developing countries. Their caseload, currently averaging 30 cases a year, comes from a wide range of developing countries. Since inception, they have investigated 155 cases. They also have a proactive and preventive approach to working with business and through the EU Anti-Bribery Network. However, the intelligence feed has been a challenge: the NCA International Corruption Intelligence Cell (ICIC) is configured to work on intelligence that supports asset recovery work and they are still developing their support to bribery. An improved intelligence feed will lead to a larger portfolio of cases and better targeted prevention work.

The Crown Prosecution Service (CPS) Proceeds of Crime Team takes action to recover stolen assets following successful prosecutions. This dedicated asset recovery capacity within the CPS has been funded since 2011 when it became clear that additional capacity was needed to follow on from the investigative work of the Metropolitan Police Team. International asset recovery cases are more labour intensive and litigated than UK domestic asset recovery cases. There is also a lower incentive to take international cases as any assets successfully recovered are repatriated rather than reinvested in future UK asset recovery work. These factors made it difficult for CPS to undertake international work and to build on the investigative work of the POCU, to implement its civil recovery powers and to respond to PEPs-related mutual legal assistance requests received from developing countries. Dedicated funding under this project to the CPS Asset Recovery Unit addresses these issues. DFID support to CPS increased with the Egypt Asset Recovery Task Force in 2013 to enable a lawyer to be located in Cairo to provide support to legal assistance requests. A CPS lawyer is also shortly due to start work in Ukraine under the Ukraine Crisis Programme.

The National Crime Agency International Corruption Intelligence Cell (ICIC) was set up in 2012 to provide focused intelligence on corruption relating to developing countries. The ambition when funding began was that ICIC would provide intelligence for the Met Police Unit on asset recovery work, for the City of London Police Unit on overseas bribery and would also develop strategic intelligence on DFID partner countries. ICIC have provided extensive intelligence support to the Met Police with 142 intelligence packages and 23 developed subjects; and lower levels of intelligence support to the City of London with 50 reports and 2 developed subjects. The lower level of the intelligence feed to the City of London Police remains a critical issue to address in order to maintain and increase their portfolio of cases.

In December 2012, the Secretary of State agreed to a small extension of the funding to all four units until March 2016 and asked for the Programme to be scaled up. Progress on this scale up was delayed until 2014 because of internal police issues and recruitment freezes in both the police forces which prevented additional staff being available to scale up the police teams. However, although these issues have now been resolved, they are partly superceded by the decision in October 2014 by the Inter-Ministerial Group that both police units should move to the NCA.

Over the last year, the NCA and Met Police have been working on relocating POCU to the NCA. Building on this, there will now be a process to agree the timescale and arrangements for the transition of both police teams including addressing the sensitive issue of the differing terms and conditions in the police teams and at the NCA. We have made it clear that it is vital to have a long transition of 2-3 years to ensure the work is not undermined by a loss of skills and expertise. As the police units and the NCA work to ensure this smooth transition over the next three years, DFID’s continued support will be critical.

What are the feasible options that address the need in the Strategic Case?

The main programme options to appraise are:
1. To mainstream the programme with other government departments and agencies to enable them take over the funding and work of this programme when current funding ends in 2016;
2. To scale up the programme by 25% and work to achieve transition to partial or total self-funding over 5 years; or
3. To scale up the programme by 50% and work to achieve transition to partial or total self-funding over 5 years.

Option 1: Mainstream the current programme with other Government Departments and Agencies

The current programme has committed DFID funding until 2016. The first option is to ‘mainstream’ the programme across government and to discontinue the programme from 2016 when current funding ends. To pursue this option, DFID would work to persuade parts of government such as the FCO, Home Office, NCA and SFO to take over the funding and management of the programme in 2016.

Our assessment is that it is unlikely that this option will be successful. If left to UK law enforcement, the combination of higher risk from the unfamiliar developing country jurisdictions and the often smaller values of cases, consistently disadvantage developing countries when decisions are made on competing for scarce UK law enforcement expertise.  Hence, the original decision when the programme began in 2006 to fund bespoke police units to service the countries that are of priority concern to DFID. This has ensured developing countries are not squeezed out in the regular prioritisation process in UK law enforcement. The experience of the Units since 2006, in particular the lengthy investment that has proved necessary to build up trusted relationships with opposite numbers in developing countries, has borne out the original presumptions on the need for ring-fenced funding. This judgement continues to hold. There has been, over recent years, increasing demand for UK attention to marginal (to DFID) countries such as Egypt and Ukraine. This suggests a free competition now would be even more disadvantageous to DFID priority countries than previously.

If there is no additional funding to extend the programme beyond 2016, it is likely that the units will stop taking cases and wind down from early 2015. Without DFID support, there may be some continued work by the National Crime Agency and possibly some small support from the FCO. However, this more limited support is unlikely to give attention to cases from developing countries and there would be a tangible drop in cases relating to developing countries. This would have a knock on effect on UK reputation and credibility as a country committed to tackling international corruption.

With the proposed transfer of both police units to the NCA which is expected to take two to three years, it is critical that DFID continues its involvement and support to the work. This will allow the new combined team to establish itself and DFID’s exit strategy to be developed.

There is currently a strong momentum on tackling international corruption across HMG. The opportunity of using this momentum for developing country work will be lost if the extension and expansion of funding is not approved.

Option 2: 25% scale up the programme over 5 years (the preferred option)

The process of developing this business case has involved consideration of a larger scale up of up to 50% as set out in Option 3 below. However, the budget cuts and staffing constraints across government have had an impact on law enforcement capacity so a 50% scale up is not viable at this stage. The Home Office is currently leading a review to address these and other constraints on tackling international corruption.

In the meantime, the police units continue to operate within the constraints of the wider dynamics of their police forces and this has been a particular issue for the Metropolitan Police which has had staff cuts and a continuing freeze on recruitment. These constraints mean that there can be only a small scale up of Metropolitan Police Proceeds of Corruption Unit (POCU) capacity with four additional posts starting this year. This will enable POCU to start to deal with the backlog of developing country cases which has built up, partly as a result of the focus on Egypt. As the police units and the NCA work on the transfer of POCU to the NCA over the next three years, this continued support will enable the work to continue during the planning process and a smooth and orderly transition of staff and cases.

The City of London Police Overseas Anti-Corruption Unit (OACU) has also been constrained by a staff recruitment freeze and staff vacancies. However this freeze has now been lifted and vacancies can now be filled. During the next phase of the programme, there will be a tapered increase of officers, including investigators and intelligence analysts. The proposed scale up will enable the City Police to develop a tailored intelligence feed which in turn will increase the numbers of cases and also help to build their prevention work. A properly developed intelligence resource within OACU and linked to the NCA International Corruption Intelligence Cell will improve performance by increasing the intelligence feed into OACU and the development of cases as they progress with investigations. This will complement the ‘single reporting hotline’ proposed by the Home Office in the National Anti-Corruption Action Plan. The cornerstone of the scale up is the inclusion of dedicated intelligence officers to identify instances of corrupt activity through available intelligence systems. This is a vital aspect of the scale-up as it will enable OACU to identify and adopt new investigations. These intelligence officers will also map foreign bribery and produce strategic assessments to inform both operational and policy decisions. This is something that is not currently within the capacity of the existing intelligence provision in ICIC and it is vital that this is established in OACU and ICIC during the transition period to ensure it is fully embedded in the new combined team.

Increased funding will enable OACU to develop a leading role on prevention work. This will include better targeting and engagement with companies in high risk countries and sectors; training and briefings for FCO and DFID posts in developing countries; and more effective communications on bribery and corruption issues.

DFID has funded the small International Corruption Intelligence Cell (ICIC) in the National Crime Agency since 2012. The full ambition for the cell is to provide an enhanced intelligence feed to the Metropolitan Police POCU team, to the City of London OACU Team and to develop strategic intelligence on corruption relating to priority DFID countries. This ambition has so far not been met and the cell has mainly dealt with intelligence connected with the money laundering and asset recovery work investigated by POCU. This is partly because of the demands of the money laundering work and partly because the NCA background is in intelligence on the ‘politically exposed persons’ most commonly connected with money laundering. NCA has had little previous experience in intelligence related to overseas bribery and corruption. With the existing capacity of four staff, which includes one POCU officer, the cell has not had the skillset or capacity to effectively address the different and challenging intelligence needs of OACU or the strategic level of work. However, building intelligence capacity for the programme is critical as it forms the main source of intelligence leads for the police teams. There is a risk that ICIC will be slow to deliver appropriate intelligence for the OACU work on overseas bribery. This risk will be managed by ensuring additional capacity in ICIC will be ring-fenced to focus exclusively on overseas bribery and corruption work and will be managed by OACU officers based in NCA.

The intention for the cell to develop a more strategic intelligence function has not been realised. Now that the basic cell is established, this aspect of the work must be developed. At present, there is little strategic intelligence being done on corruption between the UK and developing countries. UK cases tend to remain reactive to when intelligence leads emerge or crises develop. The aim of the strategic work is to be on the front foot; to be better balanced between reactive and proactive work; and to better anticipate cases and corruption related crises. A new dedicated ICIC officer will focus on strategic assessments of developing countries’ corruption issues and high risk individuals.

The precise details of the funding for the three existing units (POCU, OACU and ICIC) will change over this phase of the programme as the police units move and then merge into the NCA combined Anti-Corruption team. These changes will be managed and the budget adjusted as the transition to a combined team is planned and executed. However, it is anticipated that a 5 year extension and a 25% scale up will both allow a smooth transition and enough resources to continue with existing cases, deal with the backlog and increase the number of new cases.

The Crown Prosecution Service Proceeds of Crime Unit will not be scaled up at this stage but funding will be extended to 2020. CPS can manage the current workload with the current level of funding. It is uncertain if and when the demand on them will increase to deal with work form the Met Police so the need for increased resources will be kept under review. The CPS will remain separate from the new combined team as it has to retain operational independence from the investigation side of law enforcement.

Option 3: 50% scale up the programme over 5 years

  1. The initial ambition was for a larger scale up of 50% of the police units. There is a significant backlog of asset recovery cases and a potential to develop a much bigger portfolio of cases on overseas bribery. However, the constraints on both the Metropolitan Police and City of London Police mean that a bigger scale up is not currently possible. Apart from the recruitment constraints outlined above, there is an insufficient pool of trained financial investigators available to scale up of the DFID-funded work. This will also affect the NCA in its recruitment for the new combined team. These issues are being considered by the Home Office review of the prioritisation, resourcing and co-ordination of anti-corruption work. However, until these issues are resolved, a larger scale up is not possible.

Evidence, Assumptions and Theory of Change
  1. The evidence on the effectiveness of anti-corruption interventions remains scarce and the available evidence is mixed. ‘Put simply, there is a large number of studies on corruption but few on anti-corruption, and even fewer that answer questions around effectiveness and impact’. At present, there are very few studies that look at the empirical evidence of the wider impact of reforms aimed at addressing corruption in developing countries; or on the wider impact of specific interventions such as the ones addressed by this programme - tackling illicit financial flows from developing countries and bribery and corruption by foreign companies and nationals in developing countries. DFID has funded initiatives in recent years to better understand the effectiveness of donor-funded anti-corruption interventions, including a systematic assessment of the strength of evidence found in the international literature. However, the evidence of impact from the many types of anti-corruption intervention remains scarce. DFID’s Research and Evidence Division is developing a new research programme, the Anti-Corruption Evidence Programme with a budget of £13.6 million that aims to address some of these gaps.
    [note] Jesper Johnson, Nils Taxell and Dominik Zaum: Mapping Evidence Gaps in Anti-Corruption: Assessing the state of the operationally relevant evidence on donors’ actions and approaches to reducing corruption. Chr Michelson Institute. U4 Issue 2012/7

  1. At present, we have no firm evidence that action in the UK against corruption linked to developing countries has a wider impact on corruption levels in developing countries or on development impacts, beyond the use of returned stolen assets for development purposes. Although the direct impact of this programme can be measured (for example: companies and individuals prosecuted; assets recovered and returned; returned funds used for development), measuring the wider impact of anti-corruption interventions on levels of corruption or improved development outcomes is difficult, largely because measuring corruption itself is difficult.

  1. In the next phase of the programme, we plan to address this issue by carrying out a full external evaluation of the impact and outcomes of the programme on reducing corruption relating to developing countries and improving development impacts. However, because of the general difficulties of measuring impact on corruption and the specific challenges of measuring development impacts of this programme, we will start by carrying out an Evaluability Assessment. This will test the programme’s theory of change, the data availability and the value of an evaluation to stakeholders; it will provide recommendations for a full evaluation. The evaluability assessment will be done in early 2015 so that account can be taken of the annual programme review, due to be completed in January 2015.

  1. Following the evaluability assessment, we will work up evaluation questions, methods and approaches to determine the evidence base for success, how evidence will be collected and how the evaluation process will impact on the programme. The evaluation will be designed to be carried out over the 5 years of the programme phase on an ongoing basis, probably in two to three parts. This will allow evidence gathered early in the evaluation, to be used to inform the later years of the Programme. £500,000 will be allocated to the evaluation over 5 years, although this may be adjusted downwards, depending on the findings of the evaluability assessment and the evaluation design.

  1. Although the evidence on the indirect and wider impact is not yet available, the evidence of the direct impact of the first phase of this programme is impressive. There have been over 150 cases taken against UK nationals and companies for bribery and corruption in developing countries and over £120 million of stolen assets have been restrained, recovered or returned to developing countries. In addition to holding to account the individuals and companies engaged in corruption, the prosecutions send a strong message to developing countries, to UK business and internationally, that impunity on corruption in developing countries can and will be addressed by the UK; and that assets can be recovered and returned.

  1. Building on the analysis in the strategic case, this programme therefore assumes that:
1. Prosecutions and other interventions in the UK to tackle overseas corruption in developing countries will contribute to the accountability of UK nationals and business and increase their incentives to do business cleanly;
2. Targeted action in the UK to reduce money laundering from developing countries will reduce UK-linked corruption in developing countries;
3. Prosecution in the UK of politically exposed persons will contribute to the accountability of political elites in developing countries;
4. Returning stolen assets will increase the country's development resources;
5. Prosecution, prevention and disruption in the UK of corruption linked to developing countries will provide innovative examples and incentives for increased international action;
6. A dedicated ring-fenced UK law enforcement capacity focused on developing countries is essential until developing country work gets equal priority.

A diagrammatic representation of the theory of change is set out in Annex 1.
Climate Change and Environment

  1. The Climate and Environment Sensitivity Analysis was done for each feasible option to identify the expected impacts. The analysis takes into account the effect of climate change and environment on the proposed intervention and conversely, the effect of the intervention on climate change and the environment.
A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation.
Option	Climate change and environment risks and impacts, Category (A, B, C, D)	Climate change and environment opportunities, Category (A, B, C, D)
1	C	C
2	C	C
3	C	C

  1. It is not anticipated that the intervention will make any systematic contribution to climate change and environmental degradation. Direct negative impacts would be limited to resource use from incremental office-based activities and GHG emissions from incremental travel in the course of programme activities.
  2. Money laundering is a major vehicle for transmitting the proceeds of corruption out of a country. Funds may be corruptly obtained through a range of routes, many of which may pose a risk to the environment. For example, illegal logging, and trade in banned chemicals and endangered species. Bribery and other forms of corruption can result in bypassing regulations which can then result in inadequate safeguards to the environment. By tackling money laundering and bribery, this programme should help reduce the opportunity for this type of corruption. However, as these beneficial effects cannot be quantified in advance nor linked through specific chains of causality to climate chains and environmental protection, the programme is assessed as having no direct benefits for climate change and the environment. Indirect benefits, however, could be significant and would be enhanced further if awareness on environmental crime were to be raised within the institutions funded by the Programme.

Social impact appraisal

  1. Corruption distorts development processes and directs public funds away from the public good, resulting in fewer and lower quality services for the poor. Corruption can also concentrate wealth in the hands of the few, increasing inequality. This can result in privileging specific social or ethnic groups and marginalising others, in turn, fostering more crime and social exclusion. Thus, in theory, preventing money laundering should help to reduce these negative impacts, although there is no systematic evidence to prove specific connectivities. This is particularly the case in low income countries with weak financial systems, judicial processes and poor data/monitoring.

Impact on Gender Inequality
  1. As with appraisal of the wider social impact, corruption is also likely to distort and reduce the development benefits for women and girls. The concentration of wealth in the hands of the few tends to increase inequality and marginalisation of less powerful groups such as women and girls. Taking action against corruption should, in theory, help to reduce these negative impacts although there is no systematic evidence to prove these connectivities. As the programme increasingly returns the stolen assets, regard will be had in the agreement with each developing country, as to how the additional funds will contribute to reducing gender inequality.
Fragile and conflict-affected countries

  1. In the Strategic Case, this business case already set out the political context in which grand corruption occurs, and some of the potential constraints to tackling it. In states that have a fragile political settlement, there may be limited prospects for domestic action against political elites committing grand corruption. In many such states, capacity is extremely weak, and the sophisticated institutions required for anti-money laundering may have low capacity or be low priority. On the other hand, uncontrolled grand corruption may further destabilise, by weakening political pacts, driving competitive corruption and delegitimising government in the eyes of the public. It may also accelerate abuse of natural resources or the takeover of the state by organised crime elements. Therefore, the merits of addressing money laundering, where to target action, and the methods by which it is most appropriate to do this, need to be judged on a case by case basis.

C.	Costs and benefits

Expected resource costs of the intervention:

  1. The UK will provide new funding of up to £20,263,000 over five years, in the form of grants to four UK law enforcement teams. These funds will be provided quarterly according to progress against agreed milestones. The four law enforcement agencies will provide office accommodation, facilities and other overhead costs.

Expected benefits of the intervention

  1. The benefits of this intervention may be calculated in both financial and
    governance terms. These are difficult to quantify, but may include:
- Recovered assets. Asset recovery work has restrained, recovered and returned £120 million between 2006 and 2014 on an outlay of £9 million to the Met Police Unit. Now that the Met Police Unit has built up a pipeline of cases, this amount is likely to be equalled and exceeded over the next 5 years. A case currently under investigation could recover £500 million in recovered assets;
- Higher risk of detection/confiscation of stolen assets = reduced incentive to commit financial crime in the UK;
- Increased prevention and strategic intelligence is likely to make the UK a more hostile environment for corruption;
- The higher risk of detection is likely to deter UK Business from bribery and corruption in developing countries;
- Reinforcement of the UK message of zero tolerance for corruption.

What measures can be used to assess Value for Money for the intervention?

  1. This programme will use the following Value for Money measures to assess
    the economy, efficiency and effectiveness of the programme:
  - Value of assets restrained with potential for recovery and return;
  - Value of confiscation orders and fines in overseas bribery and corruption cases.

3. Commercial Case

3.1.	This section sets out the arrangements for implementing this programme and achieving value for money.

3.2.	The programme will be delivered through four organisations, all of which are HMG law enforcement institutions: the Metropolitan Police (MPS); the City of London Police (COLP), the Crown Prosecution Service (CPS) and the National Crime Agency (NCA). The Memorandum of Understanding (MoU) with each organisation will be amended following approval of this cost extension. Each MoU will set out what each organisation will deliver to realise the programme outcome and how they will deliver it within the agreed budget for each year.

3.3.	Due diligence is not required for HMG.

Core competences of organisations to deliver

3.4.	All the organisations have a track record of delivering in their areas of law enforcement which are anti-money laundering (MPS), bribery (COLP), intelligence and economic crime (NCA) and asset recovery (CPS). DFID has successfully partnered with the police teams since 2006, with the CPS since 2011 and with NCA since 2012. The programme has performed well every year scoring at least A+ (moderately exceeding expectations).

Delivery of outputs

3.5.	For each organisation, the same management principles will apply, namely: invoices will be paid quarterly in arrears on the basis of progress against the agreed results logical framework with clear indicators and milestones; and on the basis of an agreed budget that represents value for money. The costs are linked to specific teams and posts in each organisation. The teams were all established to deliver the specific work of this programme and are monitored to ensure the funding is not used for other work in the organisation. Progress is checked through monthly meetings, quarterly reporting, annual reviews and other evidence of progress against the agreed milestones. This is specified in the MOU with each partner.

Opportunity to reduce costs

3.6.	This opportunity is limited as the principal costs of the programme are for staff in government agencies on agreed terms and conditions. DFID will continue to carefully review the detailed annual and quarterly budgets proposed by the organisations and push for improved economies where these are possible, for example, the percentage spent on overseas travel and ensuring travel complies with HMG policy. We pay no management fees.

Value for Money

3.7. All four organisations contribute significant overhead costs to support the work
        of this programme which cover office accommodation, surveillance vehicles and
        equipment, legal and administrative costs. DFID does not pay for any of these
        costs.

3.8. In the first phase of the programme and on an investment of £10 million between
       2006-2013, there has been over 150 cases taken against corrupt individuals and
       companies and over £120 million of stolen assets restrained, recovered or
       returned, Current cases being investigated by the Met Police Team are expected
       to recover in excess of £500 million. This represents a significant return on
       DFID’s investment.

3.9. In this next phase of the Programme, DFID will be working with the Home Office
       and law enforcement partners towards sustainable funding of the work of the
       Programme by 2020. This option is possible as the UN Convention against
       Corruption permits countries to recover their reasonable costs from the stolen
       assets recovered. The UK Attorney General has agreed in principle to this
       approach as long as the UK costs are small in proportion to the amount to be
       returned to the developing country. Although there are various hurdles to jump to
       achieve full cost recovery (such as sustaining the pipeline of cases, agreeing a
       realistic process of returning large amounts of stolen assets to individual
       developing countries and navigating the interests of other Whitehall partners),
       this is an achievable objective for this phase of the Programme.

4.	Financial Case

Overview of costs

This section sets out the nature and value of expected costs.

Nature and value of expected costs
Flow of funds	The recipients of the proposed payments will be: / The Proceeds of Corruption Unit (POCU) in the Metropolitan Police Service; / The Overseas Anti-Corruption Unit (OACU) in the City of London Police; / The Proceeds of Crime Unit in the Crown Prosecution Service; / The International Corruption Intelligence Cell (ICIC) in the National Crime Agency.
Costs to be incurred directly by DFID	£500,000 for an external evaluation.
Costs to be incurred by / third party organisations	DFID intends to provide additional grants to HMG agencies as follows: / £7,400,000million to MPS over five years / £8,360,000million to COLP over five years / £2,665,000 to NCA over five years / £1,845,000 to CPS over 5 years. / The breakdown of these costs is provided for each organisation in Annex 3. / Each organisation will provide its own overhead costs. / The funding arrangements are expected to change as the two police units merge with the NCA team in the next 2-3 years. / A further £230,000 is being allocated for contingencies over the 5 years of this phase of the programme.
Affordability	The required funding is available and has been budgeted within GOSAC’s budget to the end of the CSR period). Thereafter, the commitment would constitute a first call on the future GOSAC budget allocation.

There are no anticipated tax liabilities that should arise as a result of DFID’s support to the above organisations. We have confirmed that VAT is not payable.

Delegated authority

This programme extension will be submitted for approval by the Secretary of State.

Cost profiling and forecasting

1. The profile of the estimated costs is a gradual increase over the 5 years of the programme. We will work to ensure accurate forecasting by meeting with all partners on quarterly basis and asking for a projected forecast before the invoices are due. A breakdown of overheads and salaries is asked for on each occasion. A further meeting will be arranged at the end of each financial year and beginning of next to ensure forecast figures for the year are correct and to make any adjustments if necessary. We anticipate that the figures will need to be adjusted as three teams merge at the NCA in the next 2-3 years. However, although we do not yet know the details, this will be closely planned and monitored.
2. In addition to the main costs of implementation, and additional £500,000 will be allocated for an external evaluation of the programme.

Estimated schedule of disbursements to partners

Year	2015/16	2016/17	2017/18	2018/19	2019/20	Total for each Agency
	New Upscale plus existing approved amounts

Met POCU	£1,483,000					£1,483,000
Existing budget
Met POCU	£252,000	£1,745,000	£1,760,000	£1,776,000	£1,864,600	£7,397,600
New budget
Total	£1,735,000	£1,745,000	£1,760,000	£1,776,000	£1,864,600	£8,880,600
City OACU	£1,350,000					£1,350,000
Existing budget
City OACU	£248,647	£1,971,000	£2,006,000	£2,042,000	£2,090,000	£8,357,647
New budget
Total	£1,598,647	£1,971,000	£2,006,000	£2,042,000	£2,090,000	£9,707,647
ICIC NCA	£319,000					£319,000
Existing budget
ICIC NCA	£220,901	£566,796	£595,241	£625,003	£656,253	£2,664,194
New budget
Total	£539,901	£566,796	£595,241	£625,003	£656,253	£2,983,194
POCU CPS	£407,000					£407,000
Existing budget
POCU CPS		£428,000	£449,000	£471,524	£495,000	£1,843,524
New budget
Total	£407,000	£428,000	£449,000	£471,524	£495,000	£2,250,524
Annual	£4,280,548	£4,710,796	£4,810,241	£4,914,527	£5,105,853	£23,821,965
Overall Totals
GRAND TOTAL						£23,821,965
All Columns

Financial and Fraud risk assessment
The financial risk in this programme is assessed as very low. The programme only disburses funds to UK law enforcement agencies and the principle fraud risks relate to DFID’s finances being misused by the law enforcement partners.

Monitoring, reporting and accounting for funds
The principal monitoring and reporting mechanisms for this programme will be as follows:

- Regular meetings with each agency on a monthly basis;
- Self-reporting against progress by partners on a quarterly basis;
- Annual reviews by DFID
- An external evaluation process that will run throughout the life of the programme from 2015-2020.

See below for more details:

Reporting requirements	The partners will be required to submit quarterly financial statements. / The partners are also being required to submit quarterly monthly narrative progress reports, including progress against agreed outputs and indicators in the logframe at Annex 2. These are backed up by objective evidence where available.
Transparency and accessibility of information	DFID requires full transparent access to financial information within the partner agency in relation to funds provided by DFID. This is specified in the MOU with each partner.
Asset management	The partners are responsible for the ownership, custody, maintenance and control of any assets to be purchased with DFID funds. They keep an assets register to monitor the assets during the project life cycle and will be asked to agree with DFID what will happen to the assets are replaced and when the project is complete.
Fraud risk	In addition to DFID oversight, each partner agency has their own robust mechanisms to manage the risk of fraud.
Return of funds	The MoUs governing DFID funds specify the right of recovery should funds not be spent for the purposes of the project. Should there be unexpended funds at the end of the project, arrangements will be made to have funds returned to DFID (pro rata with DFID’s level of contribution to the pool of funds)

Financial accounting considerations
There are no special accounting issues arising from these grants. There are no contingent or actual liabilities for DFID arising from this project.

5. Management Case

 Management Arrangements for implementing the intervention

Programme oversight will be provided by the Senior Responsible Owner (SRO) in the Financial Accountability and Anti-Corruption Team (FACT) in the Governance, Open Societies and Anti-Corruption Department (GOSAC). Day to day management will be the responsibility of the Financial Accountability and Anti-Corruption Team. The four law enforcement agencies will deliver the interventions.

In this phase of the programme, it is expected that three of the teams (POCU, OACU and ICIC) will combine into a new Anti-Corruption Team at the National Crime Agency. The exact timescale, arrangements and structure of this new combined team are not yet clear. However, the management arrangements will be kept constantly under review to ensure they are appropriate to the new structure. We will consider whether locating a DFID member of staff at the NCA would facilitate the transition into a combined team and the greatest impact for a developing country focus.

A Delivery Plan for the next phase of the Programme will be developed by February 2015. This timing will allow the annual review to be taken into account (carried out in January) and for the plans for the combined Anti-Corruption Team at the National Crime Agency to be further developed.

What are the risks and how these will be managed?

Programme risks and mitigation measures
Risk	Probability	Impact	Mitigation	Residual Risk
1. Met and City Units move to the NCA leads to loss of staff and police skills with a negative impact on cases.	M	H	Close engagement with the Met, City and NCA to ensure the move is well-managed and staff on board with the transition.	M
2. Cases reduce for the Met or City Police Units	L	H	Monitoring of the pipeline of cases on a quarterly basis and remedial action taken if pipeline decreases.	L
3. Increased intel resources do not lead to increased pipeline of cases to the City Police Unit	M	H	NCA and CoLP expand and diversify sources of intel	L
4. Low availability across agencies of additional law enforcement officers for new anti-corruption work.	H	H	Issue raised and monitored at the Inter-Ministerial/Director level Groups to ensure prioritisation of new anti-corruption work and ensure appropriate staffing levels	M
5. Ukraine or other low priority countries divert resources from work on DFID priority countries	M	H	Issue raised and monitored at the Inter-Ministerial/Director level Groups to ensure the additional funding is used for additional staff	L
6. Recovered assets not returned in a timely way.	M	M	Increase pressure to develop modalities for return of assets.	L
7. Strategic approach remains undeveloped.	M	M	Ensure dedicated resource allocated to developing the new approach in intel and law enforcement units.	L

Based on previous performance by the police units over the two phases of the programme, there is a high probability that this programme will meet expectations. The risks to the work of the police units as they move to the NCA, are less predictable but manageable with a well-planned move and transition process. The transition to the combined team at the NCA will require careful monitoring to ensure the programme remains on track. DFID will stay closely involved in the transition planning and implementation to ensure the risks associated with this transition are managed and reduced.

This phase of the programme increases the support to do more of the successful asset recovery and anti-bribery work. However, the purpose of the new support is also to build a more strategic approach to enable more effective prevention and disruption of corruption. This will require more collaboration between agencies, and increased work across Whitehall as a new approach is developed.

As a general way of working, should it emerge that certain components of the programme are not progressing, despite attempts to keep them on track, DFID will consider reducing or stopping contributions to those components and increasing support to the more effective areas. Trigger points would include: a poorly managed transition to a combined team at the NCA with a high loss of staff and cases; the partners no longer reporting effectively (financially or in narrative terms) on progress; consistently negative feedback from partners; and/or failure to meet more than half the milestones over two consecutive years.

How will progress and results be monitored, measured and evaluated?

The performance of the intervention will be measured against the DFID logical framework, specifically the indicators and milestones. Progress will be monitored quarterly and annually, through quarterly narrative and financial reporting. Annual reviews will be conducted by DFID and will involve the programme partners and other stakeholders across HMG. Monthly financial and performance meetings are held with each partner.

An external independent evaluation will be carried out to evaluate value for money, and the outcome and development impacts of the programme since it began in 2006 and to inform the programme going forward to 2020. An evaluability assessment will be done in February 2015 to help with the planning and design of the evaluation. The evaluation plan will be developed by March 2015 in order to be in place for when the new phase of the programme begins. Key areas that will be considered for evaluation will include the impact on corruption and development at country level, the impact of the use of returned assets for development and the impact on women and girls. More detail of the ideas and process for the evaluation are set out in paras 2.30 - 2.34.

Climate and Environment Risks

The main impacts from the programme of increased resource use and increased GHG emissions are limited and easily managed with appropriate management measures. Implementation of environmental management measures by partner institutions to minimise operational impact on the environment will mitigate the risk of additional resource use. We will consider options to off-set increased GHG emissions from incremental use of transportation by partner institutions.