Business Case

Summary Sheet

Title: Montserrat Financial Aid 2016 to 2019
Project Purpose: To support the provision of public services to meet the reasonable assistance needs of the people of Montserrat, including health, education and securing air and sea access, given self-sufficiency is currently not a viable option for this UK Overseas Territory. This is in line with the 2012 Overseas Territories White Paper and consistent with relevant elements of UK’s Aid Strategy and DFID’s 2015-2020 Single Departmental Plan.
Programme Value: £20.6 million		Country/ Region: Montserrat: UK Overseas Territory
Project Code: 204038	Start Date:1st April 2016	End Date:31st March 2019
Overall programme risk rating:	Major
Quest Number:	5352795

Intervention Summary

What support will the UK provide?
The UK Government’s fundamental responsibility and objective is to ensure the security and good governance of its Overseas Territories and their peoples. This responsibility flows from international law including the Charter of the United Nations. It also flows from our shared history and political commitment to the wellbeing of all British nationals. This requires us, among other things, to promote the political, economic, social and educational advancement of the people of the Territories, to ensure their just treatment and their protection against abuses, and to develop self-government and free political institutions in the Territories. The reasonable assistance needs of the Territories, where financial self-sufficiency is not possible, are a first call on the UK’s international development budget[1].
[1] The Overseas Territories: Security, Success, Sustainability, 2012: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/12249/ot-wp-0612.pdf

In Montserrat DFID has provided over £400 million of assistance since the volcanic crisis of 1995-7 which destroyed the island’s capital and shattered the economy. This assistance includes separate investments in capital infrastructure, economic growth and public sector reform, as well as direct financial aid support to the Government of Montserrat (GoM) for the provision of public services to meet the reasonable assistance needs of the people of Montserrat, including health, education and securing air and sea access. This business case focusses on and makes the case for DFID to continue to provide financial aid to the GoM over the 3 year period 2016/17-2018/19 given self-sufficiency is currently not possible for this UK Overseas Territory.

Although this business case sets out the rationale for continued DFID investment over the next three years, it sets out only DFID’s contribution for 2016/17 and provides indicative figures for the outer two years. The GoM has put forward three year budgets estimates covering the period 2016/17-2018/19; however DFID will continue to negotiate its financial aid contribution to GoM on an annual basis, with key deliverables linked to payments. When GoM further improves the robustness of its budget planning processes ensuring a focus on reasonable needs, value for money, delivery and clear results, the intention is to recommend a three year settlement. A MoU for 2016/17 will set out the agreed settlement amount and key deliverables linked to financial aid payments.

For 2016/17, the financial aid provision to GoM will be a sum not exceeding the lower amount of £20.6 million or EC$79.2[2] million. This is roughly the same proportion (62-63%) of GoM’s budget as for the past two financial years. Although the 2016/17 settlement is about 1% lower than the settlement approved last year (EC$79.7 million), which given deflation of -1% equates to more or less a real terms freeze. Nevertheless, it is an increase of 4% on what GoM actually received/spent in 2015/16 (EC$75.93 million). DFID analysis of the budget suggests that approximately 64% of the budget is allocated to ‘front-line services’[3], with 24% on administration, 11% on pensions and gratuities and 1% on audit functions. We believe this is reasonable given the diseconomies of small scale in Montserrat. The budget for ‘front-line services’ focuses on health and social services, infrastructure, law and order, disaster management, education and access, and includes a 90% increase in provision for child-safeguarding, and support for adult safeguarding, consistent with need and in line with UK Ministerial priorities around disability.
[2] £1=EC$3.85, which is the lowest average monthly rate over the past 12 months. However claims will be based on the exchange rate provided by Bank of Montserrat at the time of making the payment.
[3] This calculation excludes budgets allocated for ‘strategic administration and management’ as well as other lines of expenditure which can be classed of fulfilling a more or less administration function e.g. ‘fiscal policy and economic management’ etc.

The settlement includes two ring-fenced amounts totalling £3.1 million (EC$12 million) for specific deliverables, or 10% of the proposed total settlement for 2016/17:
- £1.40 million (EC$5.40[4] million) to subsidise air and sea access to the island; and
  [4] This includes EC$200,000 contingency to cover potential increases in fuel prices over 2016/17.
- £1.72 million (EC$6.62[5] million) for Technical assistance and capacity building.
  [5] This includes EC$2.6m for short-term technical cooperation usually lasting up to 6 months; EC$1.88m for the Annual Country Training Scheme (ACTS), which funds scholarships to attend university; EC$1.05m for long-term technical cooperation usually lasting more than 2 years; and EC$1.1m for child safeguarding TC.

GoM is entirely responsible for delivering services through financial aid.

What are the main programme activities?

The financial aid to GoM is focussed on four main areas:
- Funding the shortfall between GoM’s domestic revenue and the minimum spend GoM needs to undertake the main functions of government to a reasonable standard including the delivery of basic services such as health, education, and social services which meet the needs of the most vulnerable in society.
- Montserrat is a Small Island Developing State (SID) and so access is critical, the settlement therefore includes a subsidy to sea and air service providers to ensure that access needs are met.
- Given the small population, GoM struggles to meet its human resource needs and so the settlement includes funding for technical cooperation and capacity building to enable GoM to function effectively and to build and access the skills it needs, regionally and internationally.
- Montserrat remains prone to natural disasters and so the settlement funds recurrent expenditure linked to disaster management and response including hurricane preparedness, monitoring and responding to ongoing volcanic activity.

Why is UK support required?

Montserrat was largely a self-sufficient economy until hurricane Hugo struck in 1989 and volcanic eruptions in the mid-1990s devastated Montserrat’s infrastructure, rendering two-thirds of the island uninhabitable including the former capital, airport, port and the best agricultural land.[6] This resulted in significant reductions in the population, particularly of the young and skilled, with the overall population falling from around 12,000 to 4,922[7] between 1995 and 2011. This has led to shrinking private sector activity with around half of the labour force now working in the public sector. Diseconomies of scale due to the island’s population and the higher needs also inflate the unit costs of providing a range of basic public services.
[6] IMF 2011 Article IV Report sets out further detail
[7] Montserrat Census 2011

Montserrat has struggled to get its economy going again following these two catastrophic events; the government’s inability to raise sufficient revenue locally has prevented any move back to self-sufficiency. The 2012 White Paper commits the UK to meeting the reasonable assistance needs of its Overseas Territories where financial self-sufficiency is not possible. Without direct UK support, and given that the GoM is not allowed to borrow, it would face a chronic budget deficit. This would result in GoM unable to provide many essential services for the people of Montserrat including health, education, and air and sea access. DFID has a separate, complimentary programme of development assistance aimed at boosting Montserrat’s economy and reducing its aid dependency in the medium term.

What are the expected results?

The 2016/17-2018/19 programme of financial aid to GoM is focussed on results aligned with the 2012 Overseas Territories White Paper1, the UK’s 2015 Aid Strategy[8] and DFID’s 2015-2020 Single Departmental Plan (SDP)[9]. Table 1, captured in the Strategic Case, on page 10 sets out the main expected outputs from the programme. The logframe for this business case captures these outputs and includes indicators for each that will be tracked over the three year period (April 2016 to March 2019).
[8] UK aid: tackling global challenges in the national interest, 2015: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/478834/ODA_strategy_final_web_0905.pdf
[9] https://www.gov.uk/government/publications/dfid-single-departmental-plan-2015-to-2020/single-departmental-plan-2015-to-2020

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

Financial aid to GoM is a core part of delivering DFID’s overall programme of support to Montserrat, as reflected in OTD’s strategic objectives and Operational Plan for 2016-2019. As well as maintaining reasonable assistance needs, financial aid strengthens both technical capacity and systems that deliver wider benefits to DFID’s other projects in Montserrat. These projects are a key component of GoM’s economic development strategy. The OTD’s Operational Plan includes a number of specific targets for financial aid, including on good governance, provision of basic services and protection of the most vulnerable in society.

What are the key risks to the success of the programme?

In OTD’s terms the risk of this programme is major, but in terms of DFID’s Strategic Objectives the risk is minor.  The key risks are set out in detail in the Management Case, and will form part of the wider OTD risk register. These include: 1) weaker than expected standards of public financial management and procurement that undermine value for money and/or result in remedial measures which slow project implementation; 2) lower revenue growth than assumed in the budget; and 3) planned improvements in technical capacity do not materialise due to: resistance from GoM to the provision of regional or international expertise or an inability to attract Montserrat expertise of that quality; higher emigration of skilled Montserratians; and an HR department struggling to deliver. The main external risks come from: a) natural disasters, principally hurricanes and volcanic activity; b) weaker external demand, particularly in tourism, as economic activity slows globally; and c) large sterling depreciation relative to the US (and so EC)$ reduces the resources available to GoM.
Strategic Case

Context

The UK’s obligation to the OTs derives from the United Nations’ Charter: “to promote to the utmost, within the system of international peace and security established by the present Charter, the well-being of the inhabitants of these territories”. The 2012 White Paper1 sets out the UK’s vision for its Overseas Territories (OTs) to be vibrant and flourishing, proudly retaining aspects of their British identity and generating wider opportunities for their people. The paper has three main strands: to strengthen the engagement and interaction between the UK and the OTs; to work with OTs to strengthen good governance arrangements, public financial management and economic planning; and to improve the quality and range of support available. In the Paper the UK also commits to meeting the reasonable assistance needs of its OTs where financial self-sufficiency is not possible. The Paper goes on to specify that the reasonable assistance needs of the Territories are a first call on the UK’s international development budget. There are currently three OTs (Montserrat, St. Helena, Pitcairn) receiving financial aid from DFID, referred to as aided OTs.

The UK’s relationship with its OTs is very different to that with independent developing countries. The International Development Act 2002 specifically exempts aid to the OTs from the poverty reduction criteria that apply to the rest of the DFID budget. With the exception of the European Union (EU)[10] and the Caribbean Development Bank (CDB)[11], in the case of Montserrat, UKG is the only source of significant grant funding to the aided OTs and the only source of direct grant funding for recurrent expenditure.
[10] The EU provides grant funding to the aided OTs through the European Development Fund (EDF). The allocations in the last (EDF10) and upcoming windows (EDF11), covering a 3-4 year period, are as follows: - Montserrat €18.27m and €18.4m - St Helena (inc allocations for Tristan & Ascension) €19.4m and €21.5m - Pitcairn €2.4m and same again under EDF11.
[11] CDB provides about EC$7m a year from its Basic Needs Trust Fund (BNTF) which GoM has to provide about 5% counterpart funding – DFID is one of the largest contributors to the BNTF.

The need for intervention in Montserrat

1. In addition to the challenges noted above, Montserrat’s barriers to growth include:
  1. Difficult access: The main entry point to Montserrat is a ferry from Antigua to an unprotected jetty (where landing is not possible 30% of the time). There is the alternative, but more expensive option, of a short flight between Antigua on an 8-seater plane. This impedes tourism and increases cargo costs.
  2. Poor infrastructure: Montserrat has a poor infrastructure stock marked by poor roads; poor internet connectivity (although DFID is looking at funding a new fibre optic cable for Montserrat through a separate project); poor health facilities (the hospital was moved, during volcanic eruption, to a former school and remains there where the buildings are increasingly unfit to meet the health needs of the island); and poor tourism (e.g. limited hotel and other facilities).
  3. Limited land and natural resources: Montserrat is severely land constrained, which largely precludes agriculture as a driver of growth, and does not benefit from commodity exports (other than a small amount of volcanic sand). It imports 95% of its consumption.
  4. The on-going threat of natural disaster: principally hurricane and tropical storm, and associated with this, extreme wind and rainfall. There is still ongoing subterranean actively from the volcano which has the potential to damage or destroy existing infrastructure and also acts as a deterrent to long-term investment.
  5. Weak technical capacity: This constrains public sector policy-making and delivery and private sector development; as does poor data collection and management.
  6. Fiduciary risks and risks concerning public sector management: Weak financial and programme management, weak procurement (although a new DFID funded Head of Procurement post should improve performance in the medium term), and corruption, undermine programme delivery channels and value for money. Weak management throughout the public sector, including HR, poses a significant risk of delays to policy formulation and implementation.

These challenges go some way to explain why Montserrat has struggled to get its economy to a level which would make it self-sufficient again. There has been limited economic recovery as illustrated in Figure 1 below; with the economy currently about half of what it was pre-volcanic eruptions and only slowly recovering to what it was in the mid-1970s. According to GoM annual real GDP growth over the period 1999-2014 has been stagnant, averaging 1.7%.[12]
[12] GoM, 2016/17-2019/20 Medium Term Economic and Fiscal Outlook Statement

Figure 1: Montserrat's Real GDP 1997-2013

Figure 2 below sets out the sectoral composition of Montserrat’s GDP in 2014, reemphasising the point that Montserrat’s GDP is dominated by the public sector. “Public Administration, Defence & Social Security” alone represents 32% of total GDP. Overall, the public sector has been estimated to account for some 75% of GDP[13] and for close to 50% of overall employment. Tourism is the sector in which Montserrat has the most comparative advantage and which represents the best opportunity for growth. There is no GDP breakdown for tourism - the nearest proxy (albeit a relatively weak one) is “Hotels and Restaurants” which only accounts for 3% of GDP. Other tourism related activities will be captured elsewhere, for example under the “Real Estate, Renting and Business Activities”).[14]
[13] 2014 Standard and Poor’s ratings update on Montserrat.
[14] According to ECCB GDP data tourism accounted for 9.7% of GDP in 1985 (the highest point in a GDP series from 1977).

Figure 2: Sectoral composition of Montserrat's GDP 2014 (%)

The economy of Montserrat is currently weak with forecast low growth, deflation and a weakened exchange rate. The Eastern Caribbean Central Bank (ECCB) in its September 2015 Economic and Financial Review expressed uncertainty about the outlook for economic growth in Montserrat in the last quarter of 2015/16.[15] GoM estimates that growth in 2015/16 will be weak, falling from the annual average of 1.7% to 0.5%.12 One of the main drivers of the slowdown in 2015/16 has been a decline in physical capital expenditure, (see construction in Figure 3), although ripple effects will be felt more widely throughout the economy. Another driver is negative growth in public administration, defence and compulsory social security driven by a reduction in personal emoluments and pensions, given that last year there was a one-off pay increase and a number of retirements in the senior civil service leading to large gratuity payments.12
[15] http://www.eccb-centralbank.org/PDF/efr_sept2015(1).PDF

Figure 3: Contributions to the forecast headline 2015/16 rate of real annual GDP growth of 0.5% on Montserrat, by sector, percentage points

Over the course of the past year GoM has undertaken a programme of work to better understand how prices are changing for those products consumed by the average Montserratian household. GoM have used a 2009 Household Budget Survey to update the basket of goods used in the Consumer Price Index (CPI. This provides an important update to the CPI, which was previously based on a 1982 survey, making the CPI far more relevant for use in analysis today. This updated CPI suggests that Montserrat may have been experiencing deflation for the past two years, with data for 2015 suggesting that this was in the region of -1.1%, higher than the regional average rate of deflation, which is about -0.7%. Deflation is being driven by the fall in oil prices but also because of the general underperformance across the economy, leading to reduced business and consumer spending confidence. While in the short run deflation can feel like a welcome boost to households, prolonged periods will likely result in: a spiral of underinvestment; reduced business and consumer spending and confidence; increased unemployment; and weaker growth.

Recent depreciation of the pound against the US dollar (to which the EC dollar is pegged) is also significant. Since November 2015, when the last payment was made to GoM, the EC dollar value of sterling has fallen 5.6%. There are continuing downward risks to the value of sterling going forward (e.g. related to the UK’s EU referendum in June 2016). For this business case we have adopted a conservative rate of £1 to EC$3.85 for 2016/17 (compared to £1 to EC$4.15 in last year’s business case), which is the lowest average monthly rate over the past 12 months.

UK financial aid to Montserrat

DFID support to Montserrat includes a capital infrastructure and economic growth investment portfolio[16] which is directly managed by DFID, as well as financial aid direct to GoM. This business case focusses on the latter. Over the past three years DFID has on average provided about EC$75.1m (approximately £17.4 million) annually to Montserrat as financial aid, which has equated to approximately 62% of GoM’s annual recurrent budget. This support has been delivered through a range of financial aid instruments. Based on the definitions in DFID’s New Framework for Financial Aid to Governments (see figure 4), the funding mechanism is non-budget support financial aid.  It is a mixture of Category B - Core Systems Support and D - Aligned Financial Aid. [17]  UK Government’s financial aid supports GoM’s objectives to maintain and strengthen basic state systems.  Without salary support (including local salaries and technical cooperation) GoM would find it difficult to deliver basic services.  Apart from specific ring-fenced lines for technical cooperation and air and sea access subsidy, GoM’s budget is earmarked at Ministry level.  At the annual DFID missions the Ministries’ 3 year plans, which includes expenditure, are discussed.  This expenditure is then tracked at monthly monitoring meetings and performance is evaluated using the logframe targets Output Indicator 1.1 and 1.2 “Aggregate expenditure out-turn compared to original approved budget” and “Composition of expenditure out-turn compared to approved budget”, which are assessed against Public Expenditure and Financial Accountability (PEFA) criteria.  There is significant alignment between UK Government and GoM objectives.  For example, in recent years there has been a real push to improve the provision of Health and Safeguarding Services on island – this aligned policy objective is reflected in the increase in spending.
[16] This portfolio has averaged approximately EC$17.4 million (£4.1m) annually over the last three years, making up approximately 40% of GoM’s capital budget. The remainder of the capital budget is made up of grant contributions from the EU through the EDF and the CDB through the BNTF.
[17] Financial aid for capital spending (approximately 20% of all support to GoM from DFID) is directly managed by DFID. This reflects continued weaknesses in GoM’s procurement, project management and delivery systems.

DFID’s financial aid to Montserrat has historically been on the basis of annual settlements supported by a single year business case. Moving this year from a one year to a three year time horizon has a number of advantages. It will help support GoM’s medium-term budget planning and monitoring, whilst also ensuring greater continuity and lesson learning, and reducing the transaction costs to DFID and GoM of opening and closing one-year projects. This brings it in line with good practice across other DFID programmes. The move to a three year business case is also consistent with advice received from both ICAI and DFID’s Internal Audit Department. However, given uncertainties in the global economy, and the implications of that for investment and tourism in Montserrat, the value of the financial aid settlements will still need to be agreed on an annual basis. As a result, this business case sets the value for DFID financial aid for 2016/17 only. There will be a follow-up ministerial submission in March 2017 (but not a separate business case) for the approval of the value of the 2017/18 DFID settlement alongside more detailed advice on the outlook for the 2018/19 budget.

Figure 4: DFID’s New Framework for Financial Aid to Governments

DFID, FCO and GoM have committed this year to setting out a shared vision for Montserrat covering a 10 to 20 year time period that will realise the hopes and ambitions of Montserratians and in doing so maximise the impact and value for money of all investments, including financial aid to GoM as well as the portfolio of capital investments. The aim is that the shared vision and GoM/UKG partnership will shape and guide future UK support to Montserrat. The vision will be underpinned by a Memorandum of Understanding (MOU) that captures a set of specific actions (agreed annually) aimed at strengthening the capability and capacity of GoM to enable it to be more self-sufficient. For 2016-17, the actions in the MOU will focus heavily on addressing the known governance weaknesses in GoM e.g. budget and financial planning and management, project management, procurement and audit. The MOU will include some of GoM’s own key performance indicators for all the UKG support it receives (capital and recurrent) and incentivise the delivery of these by linking performance against them to future investments.

UK Objectives for financial aid to the Government of Montserrat

1. Consistent with the 2012 Overseas Territories White Paper1, DFID’s provision of financial aid to some Territories, including Montserrat, funds essential public services that cannot be funded from local resources and provides technical assistance to support improvements in the quality of public services, good governance and opportunities to pursue economic growth and financial independence. The 2015 UK Aid strategy sets out the four strategic objectives for UK aid spending as follows:
  1. Strengthening global peace, security and governance
  2. Strengthening resilience and response to crisis
  3. Promoting global prosperity
  4. Tackling extreme poverty and helping the world’s most vulnerable

The strategy also emphasises the UK’s continued commitment to ensuring that ODA remains good value for money. These objectives, including value for money, are the five objectives of DFID’s 2015-2020 Single Departmental Plan (SDP)9. The 2016/17-2018/19 programme of financial aid to GoM is focussed on results aligned with these key policy documents. More specifically DFID’s financial aid to Montserrat will:

Table 1: Alignment of financial aid objectives to relevant UK policy
DFID’s financial aid to the Government of Montserrat will:
Prioritise transparency and accountability of GoM to its people by supporting a budget developed through a transparent and consultative process with a clear focus on GoM’s published long-term strategic policy priorities.	2012 OTs White Paper: Making government work better / 2015 UK Aid Strategy and SDP 1: Strengthening global peace, security and governance
Make provision for GoM to have the capacity and skills to deliver on its priorities through supporting capacity building and use of technical assistance to fill key gaps, including strengthening its public financial management and data collection/analysis for strategic planning purposes as well as monitoring and evaluation.	2012 OTs White Paper: Making government work better / 2015 UK Aid Strategy and SDP 1: Strengthening global peace, security and governance
Make provision for recurrent expenditure linked to disaster management and response including hurricane preparedness, monitoring and responding to ongoing volcanic activity.	2012 OTs White Paper: Defence, Security and Safety of the Territories and their People / 2015 UK Aid Strategy and SDP 2: Strengthening resilience and response to crisis
Support the provision of safe, reliable and regular sea and air access, which is a key component of economic development but also a basic need for a small island developing state.	2012 OTs White Paper: developing successful and resilient economies / 2015 UK Aid Strategy and SDP 3: Promoting global prosperity
Make provision so that GoM has the funds to deliver key basic services with a focus on making sure these are inclusive, and available to all (including poorer migrants), with a focus on the most vulnerable, including women, children, the elderly and disabled, e.g.: / Promoting healthy lifestyles (such as lowering percentage of children and adults that are obese or overweight) to prevent non-communicable diseases (e.g. diabetes, hypertension, coronary heart disease); and / Increasing education completion rates and providing specialist interventions.	2012 OTs White Paper: supporting vibrant and flourishing communities / 2015 UK Aid Strategy and SDP 4: Tackling extreme poverty and helping the world’s most vulnerable
Increase provision of social services in response to the 2015 Montserrat Child Safeguarding Review and evidence of insufficient provision for child abuse and neglect, and for the most vulnerable adults (including the elderly and disabled).	2012 OTs White Paper: vibrant and flourishing communities / 2015 UK Aid Strategy and SDP 4: Tackling extreme poverty and helping the world’s most vulnerable
Be disbursed on time and on the basis of evidence of delivery but not in advance of need.	SDP 5: Value for money

GoM’s 2016/17 – 2018/19 budget estimates

The budget estimates for the outer two years of the period are not considered in detail for this business case, because although the Business Case makes the case for the continuation of budget aid over the next three years, the value of the settlement in each year will be agreed on an annual basis.

GoM has put forward a budget with total recurrent expenditure of EC$126.5 million for 2016/17. The estimate of total recurrent expenditure for 2016/17 is a decrease of approximately EC$450,000 (-1%) on the budget which was approved for 2015/16, which given deflation of -1% equates to more or less a real terms freeze. Nevertheless this is an increase of EC$3.3 million (4%) on what was actually spent/delivered in that year. This increase is mainly due to increased budgets for social services, education and technical cooperation and capacity building, linked to spending on child and adult safeguarding.

DFID analysis of the budget suggests that approximately 64% of the budget is allocated to ‘front-line services’[18] with 24% on administration, 11% on pensions and gratuities and 1% on audit functions. This seems reasonable given the diseconomies of scale in Montserrat. Figure 5 shows that the budget for ‘front-line services’ focuses on health and social services, infrastructure, law and order, disaster management, education and access.
[18] This calculation excludes budgets allocated for ‘strategic administration and management’ as well as other lines of expenditure which can be classed of fulfilling a more or less administration function e.g. ‘fiscal policy and economic management’ etc.

Figure 5: Breakdown of GoM's 2016/17 'front-line services' budget

Alignment of GoM’s 2016/17 budget with UK objectives for financial aid

Prioritise transparency and accountability of GoM to its people by supporting a budget developed through a transparent and consultative process with a clear focus on GoM’s published long-term strategic policy priorities. [SDP 1]

Improvements to GoM’s Policy, Planning and Budgeting Process

Montserrat’s 2008-2020 Sustainable Development Plan (SusDP) sets the long-term vision and strategy for Montserrat’s development.[19] In September 2015 Montserrat’s Cabinet of Ministers approved a new policy agenda for the period 2016/17-2018/19. The Policy Agenda sets out 23 priorities based on the five strategic goals of the 2008-2020 SusDP namely prudent economic management, enhanced human development, environmental management, good governance and population growth. (See Annex 1)
[19] SusDP 2008-2020 Vision: A healthy and wholesome Montserrat, founded upon a thriving modern economy with a friendly, vibrant community, in which all our people through enterprise and initiative, can fulfil their hopes in a truly democratic and God-fearing society.

Over the course of 2015/16 GoM has undertaken important work to strengthen its strategic planning and budgeting process, which has realised improved links between policy development and budget allocations and is a noteworthy step towards developing a three year rolling budget. GoM has produced (and will continue to do so annually), a Medium Term Economic and Fiscal Outlook, which is used to set the government’s budget envelope.

To ensure the priorities of the Policy Agenda are driving budget setting, Ministries have received significant support through the Ministry of Finance in the development of Key Strategies, costings and Key Performance Indicators (KPIs) – the majority of strategies were submitted against good governance, prudent economic management and enhanced human development in decreasing order. For the first time, every Ministry in GoM has a fully developed Strategic Plan, with clear budget asks and a full set of KPIs with baseline data and targets. Many of these elements are essential to robust, accountable and transparent public financial management, which will be assessed in the 2018 PEFA assessment.

GoM intends to continue to refine and improve the KPIs. Nonetheless GoM will now be better able to monitor and evaluate the performance of programmes, which in turn ought to help refine the government’s Policy Agenda and improve accountability. GoM plans to publish these documents. Further, a new process integrating the additional and separate capital budget into the overall budget cycle and plans to strengthen the appraisal process for capital investments, should ensure a more complete and integrated budget as well as a more strategic approach to the capital budget.

Unicef have also been supporting GoM to apply gender budgeting, primarily to identify the fiscal space available for strengthening programmes and services which help to ensure gender equality and better provide for the needs of vulnerable children.

Make provision for GoM to have the capacity and skills to deliver on its priorities through supporting capacity building and use of technical assistance to fill key gaps, including strengthening its public financial management and data collection/analysis for strategic planning purposes as well as monitoring and evaluation. [SDP1]

Technical cooperation and capacity building

Financial aid to GoM to fund the provision of technical cooperation and capacity building is ring-fenced in order to secure the funds for priority needs in core system strengthening. This funding is used for short (STTC) and long-term (LTTC) technical cooperation as well as to fund university scholarships through the Annual Country Training Scheme (ACTS). The 2015/16 financial aid settlement for technical cooperation and capacity building support was EC$ 5.18 million – an increase of 2% compared to 2014/15. The budget for 2016/17 has been increased by 28% due to technical cooperation and capacity building costs linked to child-safeguarding.

Table 2: Budget for technical cooperation and capacity building
Description	2016/17 EC$
Long Term Technical Cooperation (LTTC)	1,050,000
Short Term Technical Cooperation (STTC)	2,600,000
Child Safeguarding	1,090,600
Capacity building (ACTS)	1,880,000
Total	6,620,000

Historically GoM has struggled to optimise the benefits from resources available for technical cooperation only managing to fill approximately 50% of the identified posts. This is partly because of the length of time it takes to recruit regionally and internationally into these posts as well as offsetting salaries too low to attract suitable candidates, and poor advertising strategies. There is some continued resistance to accepting non-Montserratians into posts even where there is no local capacity. GoM is working on streamlining the recruitment process with a target of cutting the recruitment time from 140 days to 120 days in the short-term and to 90 days in the long-term.

For 2016/17 DFID is working with GoM to better utilise the technical cooperation funds by identifying a focussed set of priorities for technical cooperation and to allocate realistic salary packages for recruitment. The posts identified to date for 2016/17 are given in Annex 2, although these are still to be agreed with GoM.

Make provision for recurrent expenditure linked to disaster management and response including hurricane preparedness, monitoring and responding to ongoing volcanic activity. [SDP 2]

Disaster management and response

GoM’s budget includes funding to its Disaster Management Coordination Agency (DMCA). In 2015/16 this budget increased by 5% and it will increase by a further 2 percentage points in 2016/17. The allocation for DMCA is primarily made up of a subvention to the Montserrat Volcano Observatory (~82%) which is budgeted to increase from EC$6.15 million in 2015/16 to EC$6.25 million for 2016/17. The DMCA is currently working towards full compliance with the regionally accepted Emergency Management Accreditation Programme (EMAP).  Currently, DMCA has achieved accreditation for 13 of the EMAP 64 plans.  The intention is that by April 2019 the DMCA will have achieved 50 of the 64 plans.  Given the high risk to Montserrat from natural disasters, this is an important and priority set of investments.

Support the provision of safe, reliable and regular sea and air access, which is a key component of economic development but also a basic need for a Small Island Developing state. [SDP 3]

Air and sea access subsidy

GoM’s budget includes 100% ring-fenced DFID funding for the provision of air and sea access subsidies. In 2015/16 the approved budget for the subsidy totalled EC$6.03 million, with the majority (~90%) going to the ferry service. The ferry subsidy is intended to cover the ferry operating costs that are not covered by the revenue generated through ticket sales. In 2015/16 the subsidy covered approximately 70% of the operating costs of the ferry.

In order to reduce the access subsidy and increase value for money DFID is advising GoM in moving towards a commercially sound management of the ferry service that seeks to maximise revenue generation. This includes improving the data on ferry costs and revenue as well as simplifying the fare structure. GoM has been asked to remove several unclear ticket discount options and complimentary tickets (which if justifiable should be funded from elsewhere in GoM’s budget) from the ferry budget line. In doing so we estimate additional revenue of around EC$450,000 (roughly 7.5% of the total subsidy).  Taking this into account as along with the increasing passenger numbers and associated revenue, DFID has agreed to a subsidy for 2016/17 of EC$5.4 million (this includes an EC$200,000 contingency to account for potential increases in fuel prices) – this is a ~10.4% reduction on last year’s subsidy.

Despite GoM’s recent efforts, we consider the overall management of the ferry service could be improved in order to deliver better value for money. Some feedback including by the local private sector points to sub-optimal communication of timetables and timetable changes. Addressing all of this will be a priority in 2016/17, which will likely require additional support for GoM to achieve this. DFID is currently preparing a separate Business Case analysing Montserrat’s access options, including ways to improve access coordination, the potential vfm of purchasing of a new ferry and the approach to subsidising air access.

Tourism

Tourism is currently the most promising sector for economic growth in Montserrat. In 2015/16 GoM received a total tourism budget of EC$1.473 million (EC$1.173 million from DFID including EC$331,800 from financial aid, and EC$300K from the EU). However GoM continues to lack the capacity and expertise required to effectively develop and promote an attractive tourism offer for Montserrat. To address this and reignite some growth in the sector, in 2015/16 DFID funded a tourism consultancy project. The funds supported GoM to: staff the small tourism office; employ consultant experts to draft a new tourism strategy for Montserrat, provide capacity support to the small tourism team in GoM and to carry out promotional activities; and to invest in tourism development activities. This expertise and additional capacity has created a positive momentum for tourism on Montserrat with tourist arrivals and coverage in international media increasing over recent months.

DFID is currently developing a business case on private sector development in Montserrat that will include a tourism development component looking to continue to build capacity in GoM to be able to lead on developing and promoting Montserrat’s tourist offer. In the meantime the financial aid allocation to tourism for 2016/17 will provide enough funds to enable the tourism team to continue its work, including beginning to implement the new tourism strategy. GoM will have to carefully prioritise the work of the tourism office and allocation of the budget.

While GoM was able to guarantee some EU funds for product development in 2016/17, these are below previous year’s contribution and make it necessary for DFID to provide funds that allow GoM to maintain its current tourism product development and promotion at activities over the next 6 months. Based on last year’s budget a reasonable contribution from DFID for a half year would be 45% of EC$1.47m (5% picked up by EU funds), resulting in EC$663,000.

Make provision so that GoM has the funds to deliver key basic services with a focus on the most vulnerable, including women, children, the elderly and disabled, e.g.: addressing the high prevalence of non-communicable diseases (diabetes and obesity); increasing education completion rates and addressing more equitable and inclusive access to basic services [SDP 4]

Health

GoM’s health sector needs have previously been funded through a mix of standalone projects and financial aid direct to GoM. In 2015/16, all health investments were brought together in the financial aid allocation of EC$15.8 million (excluding social services). The 2016/17 budget is set at EC$15.6 million.

The Ministry of Health and Social Services (MoHSS) continues to face challenges in delivering health services due to lack of capacity and facilities. Progress on procuring medical equipment has been very slow. The budget for equipment in 2016/17 has therefore been adjusted to reflect this and to recognise the continuing need for replacement hospital equipment. Following a 2015 (DFID funded) biomedical engineer review of the current medical equipment and likely future needs, GoM now has a clear understanding of what is required. The procurement plans are based on this report, although equipment identified for replacement will need to be procured over several years. GoM will have to develop an adequate policy for strategic procurement, management and maintenance of medical equipment. In 2016/17, DFID payments for non-emergency equipment will be based on having these policies in place.

The biggest long-term challenge in the health sector is to increase prevention and health promotion in order to make a substantial difference to the incidence of non-communicable diseases (NCDs). Health promotion and prevention is currently very limited on Montserrat. While vaccination rates are reportedly very high, and there are excellent approaches towards improving nutrition of adolescents, more needs to be done to address the growing incidence of NCDs. GoM will need to focus on filling key vacant positions (e.g. Chief Medical Officer) as soon as possible to address the NCD needs and to develop a workplan for strengthening prevention. A planned functional review of the health care sector will help this process by better defining the balance between prevention, primary and secondary care. Other health challenges include: incidence of mental health, including the use of the prison for detaining patients; the policy for admissions; and coordination of referrals across the three elderly care facilities which has been drafted but requires agreement and adoption.

In addition the Ministry of Health and Social Services faces capacity constraints, including the aforementioned Chief Medical Officer position and other key health related absences in the Ministry. GoM has been asked to develop a plan and specific measures on how capacity, coordination and effectiveness can be improved.

We are in discussion with GoM in response to a request for a new hospital but we have been very clear that various pre-conditions need to be met before such a significant investment can be approved: this includes the completion and adoption of two sectoral reviews, funds for which were partially included in the 2015/16 and fully covered in the 2016/17 budget.

Education

The 2016/17 budget for Ministry of Education, Youth Affairs and Sports (MEYAS) is EC$10.9m. This is approximately a 10% increase on funding received in 2015/16 and is mainly attributed to an increased subvention to Montserrat Community College (EC$420,000) as well as to addressing key recommendations of the Montserrat Child Safeguarding Review targeted at the education sector, the additional posts for this are set out in Table 3. The recommendations focus on issues around current exclusion of non-native English speakers from effectively accessing education, as well as the rise of gang culture and violence on the school premises.

Non-native English speakers (largely from Guyana and the Dominican Republic) tend to integrate well into the primary school, and to pick up English quickly. At secondary level, children find language a greater barrier to participation both in the classroom and in the playground. It is also widely believed that young Hispanic boys are dropping out of school early, though education statistics are not available to confirm or refute these claims.

Meeting the needs of the disabled

Historically GoM has catered for disabilities on a case by case basis. This has been largely due to the relatively small number of disabled citizens, and also to a lack of reference to any disability standards within the building code.  In mid-2015 GoM produced a revised building code that caters for disabilities.  This is a welcome progression that is in line with the DFID Disability Framework (Leaving No One Behind, December 2015).  The revised building code has been adopted and GoM must now begin to implement the necessary changes to meet the needs of the disabled (including the elderly and the infirm). This should initially focus on government owned buildings and then be rolled out to public areas and facilities.  In order to be successful, it must form part of GoM’s routine maintenance plan. GoM must therefore commission an assessment of the scale of the requirement and potential costs; and work this up into a prioritised 3 year plan.   It will be important that GoM provides for adequate year on year funding to meet this requirement. DFID will work with GoM to ensure that this is covered in the maintenance strategy being developed in 2016/17.

Increase provision of social services in response to the 2015 Montserrat Child Safeguarding Review and evidence of insufficient provision for the elderly and disabled. [SDP 4]

Adult and Child safeguarding

The 2016/17 budget includes EC$1.9 million for child safeguarding (including the funding to Ministry of Education, Youth Affairs and Sports; Health and Social Services, the Police and funding for technical cooperation and capacity building), which is an increase of 90% on last year’s budget. Montserrat completed its Child Safeguarding Review (CSR) in March 2015. This produced a list of recommendations which were accepted by GoM. Funding of EC$1 million was included in the 2015/16 financial aid settlement to take forward some of these recommendations. Progress on this has been fair, with the main constraint being recruitment for key posts, and, as in many other sectors, the bottleneck caused by HR procedures and delays. Good progress has been observed in areas where the key Departments have more direct control over implementation – including training for the police on interviewing children, procuring equipment for child friendly courts, and establishing a family centre as a safe place for extremely vulnerable mothers and children. GoM deserves credit for delivering on it commandments to prioritise child and adult safeguarding by allocating the necessary increase in budget resources to properly staff, train and equip those post required across GoM to deliver on this priority agenda.

A high profile child abuse trial is also currently underway on Montserrat, and child safeguarding staff are seeing a steady increase in reporting abuse as a result of the increased publicity around the issue. A similar trend started in St Helena in 2013, with a significant uplift in safeguarding staff across all key disciplines in order to process not just current but a steadily increasing backlog of historic cases of abuse.

The Governor of Montserrat has a lead responsibility for and is very supportive of the need for more concerted action on the prevention and protection of children against abuse, and has supported significant consultation across Government. Papers put before Cabinet in advance of the FAM mission have resulted in more strict prioritisation of additional spending needs, of which the need to protect children and vulnerable adults feature prominently. The success of safeguarding depends on such high level commitment. The Governor has coordinated discussions and planning across GoM’s ministries in order to set up an Inter-Agency Board to ensure inter-agency working. Initial meetings have agreed the necessary systems and sought clarity from Ministries of what should be included in the 2016/17 budget to enable them to deliver on their respective safeguarding roles.

An urgent priority for 2016/17 is to ensure that there are sufficient numbers of trained and experienced social workers in the Ministry of Health and Social Services to respond to cases of abuse and neglect of both adults and children, and to provide appropriate oversight to institutions and facilities for vulnerable adults. Some of these institutions have been chronically understaffed and having to deal with clients with very high levels of disability and dependency needs. During a visit last year, it was apparent that elderly clients had to stay where they’d fallen overnight, or were wandering round the roads confused in the mornings. A relatively new facility had been established for mental health and learning disabilities, but staffing and socialisation were poor. These are the kind of issues identified by Wass in St Helena, and could be addressed by better staffing, supervision and case work through the Ministry of Health and Department of Social Services. A split of responsibility has been proposed, with a new unit being established in the Ministry to deal with the investigation of cases of current and historic abuse and following those cases through the courts; with broader issues of child safeguarding, including institutional development and policy, and adult safeguarding remaining in the Social Services Department.

A second priority identified in the 2015 CSR is to ensure adequate staff and resources for child safeguarding are available in Montserrat’s schools. As detailed in Table 5, this includes guidance counsellors and additional security to help address issues of exclusion of ethnic minority students, and the related disruption in the school grounds. The recent Situation Analysis of the status of children in Montserrat (Unicef, 2016) also highlights this as a significant concern.

Montserrat is fortunate to have at least three local, though not professionally qualified social workers, in the Department of Social Services. Though a significant amount of technical cooperation will be needed in the short to medium term, future provision for effective succession planning could enable all three to achieve the necessary qualifications over the next 9 years. We will work with GoM to expedite the recruitment of the additional staff required, which may include outsourcing a dedicated recruitment process, and the possible use of a specialised agency. Initial investigations suggest there would be significant interest amongst agencies specialised in this field, that the costs would be less than for a generic head hunting firm, and that the timeframe and numbers of staff required would probably enable a discount to be negotiated. As work on safeguarding scales up, it is very likely that further gaps will be identified in other core agencies, including the police and legal system. We will review this mid-year.

Recurrent revenue budget estimates

GoM needs EC$126.5 million of revenue to finance expenditure in 2016/17. This revenue will be generated from local sources as well as financial aid from DFID.

Local Revenue

GoM estimates that it will raise EC$47.3 million of local revenue in 2016/17. This would be an increase of 3.3% compared to revenue of EC$45.8 million actually collected in 2015/16, which was a decrease of 0.6% on revenues collected in 2014/15. As shown in Figure 6, Montserrat’s local revenue is dominated by taxes on international trade and on income which between them account for over 70% of the revenue collected.

Figure 6: Composition of local revenue

Montserrat’s key revenue aggregates are directly linked to the health of the economy, which itself (see figure 6 above) is largely driven by government expenditure. During the 2015/16 fiscal year GoM struggled to deliver infrastructure projects and underspent on its recurrent budget, which negatively impacted economic activity island wide. In the private sector growth was only experienced in the mining and quarrying sector, which is currently a relatively small part of the economy. The poor performance in the economy explains the lower than expected revenue in 2015/16. While economic activity is expected to pick up over the next budget period, growth is still unlikely to be significant. There is little reason to anticipate significant growth in local revenues. As such, on the whole, revenue figures are forecast to grow in line with inflation.

The Montserrat Customs and Revenue Services (MCRS) have taken measures to improve enforcement of collections and this drive will continue. To date these have offered some buffer to the slowdown in revenue collection. Relying on these measures indefinitely, however, is not sustainable with much of the ‘low hanging fruit’ already picked. Montserrat’s tax system is in dire need of modernisation, given it is largely paper based. Computerisation of the system might deliver more efficiency gains and DFID is exploring this as a potential area of funding for the 2017/18 financial aid settlement.

At present there are no definitive new policy measures that would impact Montserrat’s revenue collection over the budget period, although we are aware that some policy ideas may be in the pipeline. Should GoM fail to achieve its revenue target or take any measure which reduces revenue, it will either have to make equivalent expenditure reductions or implement measures to recoup that revenue from elsewhere. Increasing local revenue from its current baseline is difficult given the barriers to growth outlined earlier however there are some taxes e.g. stamp duty and property tax, which might be candidates for reform in terms of generating more revenue going forward.

DFID’s proposed financial aid contribution to GoM’s budget for 2016/17

Given GoM’s recurrent expenditure and local revenue estimates for 2016/17, DFID will provide a sum not exceeding the lower of either the amount of EC$79.2 million or £20.62 million as financial aid to GoM in 2016/17 to meet the shortfall in local revenue needed to finance public recurrent expenditure to meet the reasonable assistance needs of the people of Montserrat. DFID’s proposed financial aid is equivalent to 63% of the total budget, at a level which is in line with the previous two years (62-63%), when all recurrent budget lines are taken into account.[20] Although the proposed 2016/17 settlement is lower than the settlement approved last year (EC$79.7 million) by 1% (which given deflation of -1% equates to a real terms freeze) it is an increase of 4% on what GoM actually received/spent in 2015/16 (EC$75.9 million).
[20] In previous financial aid business cases financial aid for the health project, access, TC and contingency fund - to ensure the Operational Plan target is tracked on a “like-for-like” basis. Changing the previous methodology to include the Contingency Fund would put DFID’s share of the budget at 58%.

Ring-fenced budget lines

The settlement includes two amounts totalling £3.1 million (EC$12 million), that are ring-fenced for specific deliverables:
- £1.40 million (EC$5.40[21] million) to subsidise air and sea access to the island; and
  [21] This includes EC$200,000 contingency to cover potential increases in fuel prices over 2016/17.
- £1.72 million (EC$6.62[22] million) for Technical assistance and capacity building.
  [22] This includes EC$2.6m for short-term technical cooperation usually lasting up to 6 months; EC$1.68m for the Annual Country Training Scheme (ACTS), which funds scholarships to attend university; EC$1.05m for long-term technical cooperation usually lasting more than 2 years; and EC$1.1m for child safeguarding TC.

For 2016/17 approximately 10% of the budget (EC$12 million) will be ring-fenced compared to 14% (EC$17 million) of the revised budget estimates in 2015/16, reflecting the agreement with GoM to delegate responsibility and accountability where appropriate.

Gender Equality

Direct financial aid will enable GoM to fulfil its essential public administration function, providing access to public services to the benefit of all people, in line with its Strategic Development Plan.  Traditional measures of gender equality in Montserrat are good. Montserrat did not have any maternal mortality in recent years compared to 57 per 100,000 on average in other upper middle-income countries[23] and 190 per 100,000 in the Caribbean region[24]. Montserrat has very high and equitable literacy and completion rates for both girls and boys, though with a potentially higher dropout rate and poorer performance for non-native English speaking immigrant boys. Sex disaggregated education outcomes are tracked through the financial aid log-frame, though generally, statistical and socio-economic data across the board is poor, precluding a more in-depth gender analysis in this and other sectors. Priorities for technical cooperation included filling the Director of Statistics post which should facilitate a review of GoM’s statistical capacity, including of equality and diversity data. GoM failed to recruit into this post last year but it is now a priority for this year, with a more realistic salary attached to the post to increase the likelihood of it being filled. The census data from 2010 has not yet been released, due to this lack of capacity, and the last review of poverty and employment data was in 2009.
[23] According to the OECD Montserrat is an upper middle income country http://www.oecd.org/dac/stats/documentupload/DAC%20List%20of%20ODA%20Recipients%202014%20final.pdf. The UN classifies it as a Small Island Developing State.
[24] Maternal Mortality Ratios are, however, not easily comparable for small island states, as they are calculated with a denominator of 100,000 live births per year, which will not be reached in most if not all OTs (as well as other small island states). The absence of any maternal deaths should therefore be interpreted cautiously.

A recent UNICEF review of the situation of children in Montserrat, suggests the most disadvantaged children are from households where there is no wage, or a very low wage; from single/female headed households; or from migrant households. The poorest households include all three of these elements. The child safeguarding review also highlighted a lack of access to child care for the poorest families, meaning children were left at home alone whilst single mothers worked multiple low-income jobs.

Social welfare provision has been a priority policy area of the Premier of Montserrat since his election in September 2014. GoM aims to improve policy and programming on child safeguarding, social welfare and domestic violence. Financial aid is used to support a new family centre for women and children who need to be removed from abusive households, and new care workers will be trained to continue this facility over the coming year. Additional funding is also included for the highest gender priority on Island i.e. the prevention and response to child abuse (85% of reported cases target girls).

Interventions will also be targeted at the prevention of neglect of the elderly, the majority of whom amongst the very old (over 70) are women. This will involve more carers at the independent living facilities to manage those with high dependency needs (including mental health needs); and adoption and implementation of referral strategies to ensure residents are placed in facilities appropriate to their needs. The residential home will also need to be reviewed and upgraded, as currently prospective clients are unwilling to contribute to the cost of care in its current state. The strengthening of the social services Department and case work should ensure that these initiatives are taken forward.

## Appraisal Case

Overview

Given the UK’s obligations to meet the reasonable assistance needs of OTs where self-sufficiency is not yet possible, options for delivering this type of support through different channels are limited. For example, DFID managing the provision of public services to meet the reasonable assistance needs of the people of Montserrat, including health, education and securing air and sea access would be administratively burdensome for DFID and potentially compromise the delivery of services to the people of Montserrat. Further there isn’t a direct constitutional relationship between DFID and the people of Montserrat; the relationship is currently with the elected Government, which could cause issues around governance and accountability. Financial aid to GoM is currently the best option for the UK to fulfil its obligations as set out in 2012 OTD White Paper (see paragraph 23 above). However, there are a number of ways in which financial aid can be delivered that are in line with DFID’s revised approach to providing financial aid (as set out in Figure 4 above) including the length and size of settlement, results-based elements and the degree of earmarking.

Review of the options

According to the 2012 OTs White Paper, the UK is obligated to meet the reasonable assistance needs of OTs where self-sufficiency is not yet possible and has chosen to do so through the provision of financial aid to territory governments (see paragraph 23 above). The other options available to the UK and rejected are do nothing and project approach:

Option 1: Do nothing - DFID has funded more than half of GoM’s recurrent budget for a number of years. Montserrat is restricted by the UK government in terms of how much it can borrow and currently has no scope to increase tax revenue. Removing UK financial support would result in a substantial fall in public expenditure and a deep cut in services. This option is not considered feasible since it would leave GoM unable to fully meet the reasonable needs of the population and so would not deliver on the UK Government’s responsibility to Montserrat.

Option 2: Project approach - The project approach option involves establishing projects to deliver specific services, funded and managed by the UK Government. The main benefit of this approach is greater DFID control over specific areas of budget spending and delivery. Montserrat project implementation capacity is limited, and progress in a number of policy areas has also been slower than expected for example putting in place strategies for maintenance of existing infrastructure that enable GoM to spend the allocated budget to properly maintain its assets. However, this approach would reduce GoM’s autonomy, skew accountability away from Montserrat’s domestic constituents, and likely damage the UK’s relationship with GoM. It would also be a shift away from working through GoM’s systems and would need a parallel system of planning, budgeting and service delivery, significantly more costly than the system used for financial aid. There is also a risk that OTD would be stretched too thinly by such an approach, and so be less able to perform appropriate strategic policy planning, due diligence and robust programme management.[25]
[25] DFID does provide some assistance to Montserrat on a project basis, mainly its capital portfolio where fiduciary risks are greatest.

The financial aid option continues the existing arrangement, with DFID providing financial aid through GoM’s consolidated fund which is then allocated through GoM’s planning, budgeting and disbursement processes. Payments are released by DFID once GoM has provided evidence of need and satisfied any further conditions of the MoU budget agreement. This approach allows money to be ring-fenced for specific activities if required, and allows for the use of additional resources for targeted projects if necessary. This approach has lower transaction costs than a project-based approach (option 2). It gives GoM greater ownership and accountability by providing resources to GoM to deliver its policies. It also provides a channel for policy discussion between UKG and GoM, leading to better resource use and more scrutiny of public financial management.

Financial aid achieves multiple objectives, including:
- Greater macroeconomic stability: government supported with the resources to meet reasonable assistance needs of the public without the need to borrow.
- Reasonable assistance: financing a level of public services that meet the needs of the island - education, health care, security, etc.
- Better service delivery: providing an opportunity for policy dialogue between the government and DFID that improves efficiency and quality of resource use;
- Support public financial management: providing scrutiny that improves budget and economic management processes.

Figure 7: Theory of Change for financial aid to Montserrat

IMPACT:
“A healthy and wholesome Montserrat, founded upon a thriving modern economy with a friendly, vibrant community, in which all our people through enterprise and initiative, can fulfil their hopes in a truly democratic and God-fearing society” Montserrat 2008-2020 Sustainable Development Plan

OUTCOME:
Efficient and effective public services maintain coverage of social, economic and environmental reasonable assistance needs
INPUTS:
Finance- £20.4million in 2016/17; policy dialogue; results monitoring
HR- DFID advisory and programme management. GoM technical and administrative support.

OUTPUTS:
- Greater transparency and accountability of GoM to its people
- Improved GoM capacity and skills to deliver on its priorities
- Adequate disaster management and response including hurricane preparedness, monitoring and responding to ongoing volcanic activity
- Provision of safe, reliable and regular sea and air access
- Delivery of key basic services with a focus on the most vulnerable, including women, children, the elderly and disabled
- Increased provision of social services for child and adult safeguarding
- disbursed on time and on the basis of evidence of delivery but not in advance of need
ASSUMPTIONS

- Stable exchange rate
- No serious natural disasters
- Constructive relationship between GoM and DFID
- Technical Cooperation and capacity building effective
- GoM operates a balanced recurrent budget
- GoM delivers according to financial aid MoU

Financial aid delivery options

1. There are a number of decisions associated with delivering financial aid, each of which is articulated below:
  1. Level of settlement
  2. Length of settlement
  3. Level of earmarking

Level of settlement

Financial aid to Montserrat over the past three years is shown below. It has been on average 62% of the government’s total regular expenditure.

Table 3: Historical financial aid to Montserrat
	2013-14	2014-15	2015-16
Montserrat Financial aid (£)	17,520,377	16,979,999	17,578,697
Financial aid as share of regular GoM recurrent expenditure	61%	63%	62% (estimate)

The amount and composition of financial aid proposed in 2016/17 has been arrived at following close engagement with GoM including during the financial aid mission (FAM) and subsequent discussions. It is aligned with GoM’s Medium-term Economic and Fiscal Outlook (MTEFO) and GoM’s Policy Agenda.

A significantly lower settlement could encourage GoM to prioritise their objectives to a greater degree, improve productivity and identify efficiency savings. But it could also negatively impact on GoM’s ability to meet reasonable assistance needs, and could divert funds away from areas that DFID considers a priority. The proposed settlement already reflects a reprioritisation of funding to priority areas such as child safeguarding, the funding for which has increased by 90%.

The initial draft budget from GoM at the end of January would have required a DFID contribution of £21.4 million. We have negotiated this down to £20.6 million by focussing GoM on the non-discretionary elements of its budget. A notable saving negotiated with GoM is on the access subsidy which has previously funded a number of free or reduced costs ferry tickets. DFID has requested that GoM must maximise revenue from the ferry to reduce the need for subsidy. This will require GoM to fund any justifiable and affordable complimentary ferry tickets from elsewhere in its budget. To this end the subsidy has been reduced in line with the extra revenue which DFID has estimated could potentially be generated. DFID has also encouraged GoM to demonstrate spending restraint by rejecting a number of discretionary new spending requests and keeping a number of budget lines flat in nominal terms.

A significantly higher settlement could potentially lead to wastage and increase fiduciary risk. Last year GoM spent 95% of the financial aid which was approved. GoM faces capacity constraints and its systems are not yet strong enough to deliver large projects. DFID directly manages a separate portfolio of capital projects in Montserrat.

Length of settlement

This business case makes the case for continuation of financial aid to Montserrat for the next three years but sets the settlement amount for 2016/17 only. While a multi-year settlement would give GoM more predictability about the funding it will receive and support multi-year programming, GoM currently lacks the necessary financial forecasting and financial management capacity. Settlements will therefore continue to be agreed annually, while GoM forecasting and financial management is strengthened.

Level of earmarking

GoM and DFID have agreed that the 2016/17 financial aid settlement will include two ring-fenced budget lines (10% of financial aid). This compares to the 7 budget lines (14% of financial aid) which were earmarked in 2015/16. DFID has decided to reduce the earmarking in recognition of the notable improvements GoM has made in its budget planning processes. Although ring-fencing a greater level of funds ensures that resources are spent on DFID priorities, it can be administratively difficult to manage and reduces the ability of GoM to make adjustments mid-year. However, the MoU for each annual settlement will be used to specify exactly what the funds should be spent on. Expenditure will be tracked at monthly monitoring meetings and performance evaluated using the logframe targets Ouput Indicator 1.1 and 1.2 “Aggregate expenditure out-turn compared to original approved budget” and “Composition of expenditure out-turn compared to approved budget”, which are assessed against Public Expenditure and Financial Accountability (PEFA) criteria.

Value for money

1. Our approach to VfM is based on the 3Es - Economy, Efficiency and Effectiveness:
  1. Economy measures if we are buying the right things at the right price - We are monitoring key cost drivers particularly salaries, working closely with GoM to ensure that increases are justified and based on robust performance appraisal.
  2. Efficiency measures how well we convert inputs into outputs – The logframe for this programme includes VFM indicators based on the work done in previous Montserrat financial aid programmes to develop unit costs for specific outputs including cost per child (per year) in primary and secondary school; and road maintenance cost per square metre.
  3. Effectiveness measures how well we convert outputs into outcomes –We will track improvements to indicators in the key basic services sector, including health and education.

GoM’s own KPIs will also be used as a way of assessing the value for money of this programme. These targets are aligned with directorate strategic plans and the government’s vision, and have strong ownership by GoM. Delivery against the programme’s logical framework is also a measure of the returns to the UK’s investment, which will be assessed each year. Other measures that will be used as part of ongoing monitoring include assessments of public financial management, such as Public Expenditure and Financial Accountability assessments.

Risks to VfM

The greatest risks to value for money are related to the government of Montserrat’s financial management systems. A recent fiduciary risk assessment raised concerns about lack of oversight of statutory bodies, revenue forecasting and tax. OTD is working with the Ministry of Finance and Economic Planning and the Caribbean Regional Technical Assistance Centre (CARTAC) to develop and implement a new PFM Action Plan that addresses these concerns. DFID financial aid also supports the Internal Audit Unit, the Office of the Auditor General (External Audit) and the Head of Procurement (through TC) to mitigate these risks.

Commercial Case

General

The proposed mechanism is aligned financial aid, with a small element for core systems strengthening. In line with DFID’s Smart Rules, a Memorandum of Understanding between DFID and the GoM’s Ministry of Finance and Economic Management will set out the terms underpinning financial aid to Montserrat. The financial aid settlement is the result of detailed negotiations between DFID and GoM. We do not expect any scope for further negotiation or cost savings beyond those already achieved in agreeing the settlement although all spend will need to be supported by detailed reporting from GoM. Any in-year savings will be re-allocated based on needs, priorities and VfM.

Procurement

The OTs are not bound by UK Government or European Union procurement directives although we fully expect OTs to follow best practice. Ordinarily, GoM has accountability for procurement of major goods, services and capital projects required for the island. However, a DFID audit on overall GoM procurement processes in 2014 recommended a number of actions to deal with concerns over the commercial practices in Montserrat. OTD, working with DFID’s Procurement and Commercial Department (PCD) and the OTD Commercial Adviser, has put in place an Action Plan that provides assurance over procurement under financial aid and the rest of DFID’s Montserrat portfolio. DFID continues to work with GoM on the Action Plan as follows:

  1. Following an international recruitment GoM has appointed a Head of Procurement and Commercial Development (with top up funding provided by LTTC support from DFID’s financial aid). This new line ministry post will have oversight and lead on efforts to strengthen GoM’s procurement procedures and processes and for staff to effectively and routinely implement both. In the meantime the DFID resident representative and/or Infrastructure Adviser on island continue to sit as observers of the Public Procurement Board and DFID’s Commercial team undertakes regular quality assurance of GoM’s procurements.
  2. The Head of Procurement should focus on the strategic aspects of the GoM commercial function. DFID’s Commercial Advisor is working with the Head of Procurement to identify priority areas to address such as Terms and Conditions (Ts and Cs) and Standard Operating Procedures (SOP) rather than operational or even tactical challenges. Once these have been agreed a joint Delivery Plan will be put in place to ensure that appropriate resource and training is identified to allow sufficient focus on embedding the new procedures into the GoM commercial function. Successful implementation will allow DFID to gradually step back from the necessary management of a number of key and strategic procurements, reduce the oversight function and finally hand back full accountability for all procurements to GoM.
  3. One potential barrier to overcome is the lack of reliable systems for managing the commercial function on Montserrat, with the current default method of sourcing largely paper-based. This leads to an often resource-intensive, protracted tender and evaluation process and is counter-intuitive to delivering VfM. As part of the SOP work it will be necessary to explore the potential solutions and the extent to which e-based tender procedures can be implemented, given the lack of available e-solutions available both to the government and the potential supply base.
  4. As indicated the current capacity of commercial staff in GoM is insufficient to manage existing workload, even with DFID taking accountability for up to four significant procurements. Added to this, the new GoM Head of Procurement and Commercial Development is being forced, through this lack of resource, to deal with operational issues, to the detriment of the overall purpose of his role at a strategic level. This in turn will lead to prolonged resource requirement by DFID, a delay to the implementation of new Ts and Cs and SOP and overall a delay in returning accountability for procurement to GoM. In order to mitigate these risks and ensure the correct focus and timely delivery of these commercial imperatives the DFID Commercial Advisor will work closely with the GoM Commercial Lead to identify areas of focus and priority and where necessary identify resource gaps. Thereafter a plan will be proposed based on existing resource and potential additional resource in order to better understand the overall commercial risks to delivery of VfM, both within FY 16/17 and beyond.

Assets procured using DFID funds are owned by GoM. The development and implementation of a preventive maintenance programme for buildings and equipment is an integral part of ensuring adequate care and optimal life span of fixed assets. GoM lacks: a maintenance strategy, an all-inclusive asset database, coordinated and prioritised planning, and a means of effectively delivering and meeting requirements. DFID and GoM will work closely together to ensure that this issue is appropriately resolved in advance of the next financial aid mission.
## Financial Case

Breakdown of Financial Aid for 2016/17

For 2016/17, the financial aid provision to GoM will be a sum not exceeding the lower amount of either £20.6 million or EC$79.2 million (at an exchange rate of £1 to EC$3.85). This allocation will come from OTD’s programme resource allocation. The breakdown of DFID’s proposed financial aid for 2016/17 is shown in the Table below:

Table 4: Breakdown of financial aid
	2016/17
Recurrent budget	£15.5 million / (EC$59.6 million)
Access Subsidy	£1.4 million / (EC$5.4 million)
Technical Cooperation and capacity building (TC)	£1.7 million / (EC$6.6 million)
Disaster management	£2 million / (EC$7.6 million)
Total	£20.6 million / (EC$79.2 million)

The totals in the table above are the upper limit proposed for each area. Any in-year re-profiling of the budget will be undertaken by GoM only after agreement from the DFID Senior Responsible Owner. Should additional funds be required in-year as a result of unforeseen events, such as significant falls in the exchange rate, approval will be sought from the Minister.

Financial Arrangements and Process

GoM (Ministry of Finance and Economic Management) is the only direct recipient of financial aid payments under the Memorandum of Understanding (MoU) that sets out the conditions and process for delivering financial aid support. Payments are made to the consolidated account of GoM.

There are no third party organisations that contribute funds to the recurrent budget of GoM. The only other source of finance is from GoM’s own revenue streams. DFID has a portfolio of capital investments that seek to stimulate economic growth and increase GoM’s revenue. Funds in support of capital investments are made to GoM’s development account. DFID’s systems will record spend and forecast details of DFID’s contribution.

Where agreed with GoM, we havering-fenced two components of financial aid: the Access Subsidy and TC to ensure funds are utilised for those specific purposes, a process valued by both GoM and DFID.

1. Monitoring & Evaluation activities will be guided by an M&E framework put in place in February 2015 to monitor expenditure and delivery of financial aid. We will focus on the aggregate budget and headline sectoral level budgets, interrogating Departmental strategies and spending plans. To monitor the delivery of financial aid the Montserrat Programme Team and relevant advisers will:
  1. Conduct monthly meetings with Ministry of Finance counterparts to discuss and monitor budget performance.
  2. Conduct monthly TC meetings with GoM’s Human Resources Management Unit to discuss on-going TC requirements including the recruitment of key positions to fill critical gaps and build GoM’s capacity and capability.
  3. Review performance and progress of the GoM ministries in terms of delivery (including revenue collection) as part of the payment process for financial aid claims. The schedule for disbursement of financial aid will consist of three tranches released in April, July and November. The terms of these tranches will be fully documented in the MoU which will accompany the financial aid settlement.
  4. Undertake a Mid-Year pre-FAM Review and stocktake of logframe and budget to set the broad agenda for the FAM in late 2016.
  5. There will be two on island Financial aid Missions by the OTD budget team during the lifetime of this project, in addition to the FAM mission in January 2016, there will be missions in early 2017 and 2018 which will formally assess budget performance during 2016-17 and 17-18 and will form the basis of the submission to the Minister on the 17-18 and 18-19 budget settlements. DFID lead advisers will undertake regular thematic meetings with GoM counterparts to discuss and review performance against the logframe and budget commitments.

Assessment of Financial Risk and Fraud

1. The most recent PEFA undertaken in December 2014 highlighted some concerns about weak internal GoM controls. These included the strength of the internal audit process and a lack of follow up on external audit findings. The subsequent Fiduciary Risk Assessment (FRA) of GoM’s financial systems raised concerns regarding the lack of oversight of statutory bodies, procurement, revenue forecasting and tax. A number of measures and initiatives are in place or are planned to respond to these issues:
  1. GoM is working to strengthen the strategic planning process across the Ministries, with each now having a fully developed Strategic Plan, with clear budget asks and a full set of Key Performance Indicators (KPIs) with baseline data and targets. This work will bolster GoM’s preparation for the 2018 PEFA assessment and is essential to robust, accountable and transparent financial management.
  2. DFID funded Technical Cooperation has helped fund critical posts such as Chief Economist, Tax Adviser and Head of Procurement and have made provision to provide further TC support including such posts as Audit Adviser to strengthen GoM’s financial skills and capability.
  3. GoM’s Ministry of Finance and Economic Planning continues to work closely with CARTAC to strengthen its systems and approach to Public Financial Management and respond to the findings of the PEFA and FRA reports.
  4. The concluding Public Sector Reform 2 programme and its successor due to commence in 2016/17 both aim for greater administrative efficiency with the public sector and support the PFM action plan. OTD will work with GoM in monitoring progress against this action plan including through formal Annual Statements of Progress against the FRA.

Management Case

Governance and management arrangements

1. The programme will be governed by a bilateral Memorandum of Understanding (MoU) with the Government of Montserrat. This will follow the format required for financial aid programmes. The MoU will set out the following:
  1. The core objectives of the financial aid;
  2. A breakdown of how the contribution is broken down, including ring-fenced areas;
  3. Reference to the technical assistance and capacity building elements of the programme;
  4. Financial management, reporting and auditing arrangements; and
  5. Fraud and whistleblowing arrangements.
Protocols exist for: exchange rates; technical cooperation; and use of surplus funds

GoM’s Financial Secretary is accountable and responsible for the implementation of GoM's strategic priorities and for the management of DFID’s financial contributions in support of the recurrent budget, the provision of air and sea subsidies to facilitate and maintain access to the island and where appropriate, the filing of key and critical posts through the provision of TC funds.

Once the 2016/17 UKG financial aid settlement is approved, GoM’s Cabinet (which includes the Premier and the Governor) lead on the legislative and implementation processes within GoM. The budget passes to the Legislative Assembly (which has elected representatives from the non-ruling party) and is then made public to citizens of Montserrat through a budget speech. This includes a forward look of planned activities and expenditure and a statement on how funds from the previous year were spent. To improve budget transparency GoM has committed to publishing greater budget information, and quarterly budget reports are published for the Legislative Assembly.

Montserrat’s Auditor General produces annual audit reports (AAR) covering GoM’s recurrent expenditures and revenues. GoM has succeeded this year in bringing its AARs up to date. DFID will continue to monitor and support performance in this area.

Ability to Deliver

GoM has been in receipt of financial aid for many years and DFID has built up a good understanding of GoM’s capability and capacity to deliver public services over time. There is close ongoing engagement with GoM, particularly on capacity building and public sector reform, including through a DFID Public Sector Reform project and Technical Cooperation (TC) for filling critical posts. This TC forms part of this financial aid.

Given its historical financial independence, GoM’s preferred approach is to provide jobs for Montserratians and to consider TC support from others only where necessary. In order to address the evident slow budget spend and at times sluggish delivery, we are working with GoM to prioritise the key posts that have been vacant for some time and where the gaps are having a negative impact on GoM’s delivery e.g. Chief Statistician and Chief Medical Officer. It is hoped that by adopting a more focussed approach in 2016/17 there will be fewer, better resourced and more quickly recruited TC posts. All TC job descriptions will require post holders to develop the capacity of a local counterpart.

DFID and GoM financial aid team roles and responsibilities

The table below sets out details of the core Montserrat Financial Aid team. The main points of contact within GoM for Financial Aid are the Ministry of Finance & Economic Management (MOFEM) via the Financial Secretary and Budget Director.

Table 5: Financial aid team roles and responsibilities
Role	Responsibility
DFID
Senior Responsible Owner	Overseeing the overall design and implementation of the project, drawing on advice from lead advisers and Head of Department.
Deputy Programme Manager	Lead on programme management compliance for the design and implementation of financial aid and ensuring timely financial disbursements to GoM.
Economist/s	Lead on forecasting, monitoring and overall macroeconomic policy advice relating to budget design and performance. Hold regular discussion with GoM counterpart.
Private Sector Development Adviser	Lead on access subsidy budget line. Hold regular discussion with GoM counterpart.
Governance Adviser	Lead on Technical Cooperation budget line, general public financial management and public sector reform. Hold regular discussion with GoM counterpart.
Senior Social Development Adviser	Lead on social development components of the budget, including DFID’s support to child safeguarding. Lead on logical framework development and monitoring. Hold regular discussion with GoM counterpart.
Health Adviser	Lead on health sector components of the budget and preparation for hospital planning. Hold regular discussion with GoM counterpart.
Infrastucture Adviser	Lead on the infrastructure and maintenance components of the budget. Hold regular discussions with key stakeholders across GoM.
Government of Montserrat
MOFEM Financial Secretary	Oversees the overall implementation of the project.
MOFEM Budget Director	Leads on the provision of supporting budget analysis and financial reporting.
MOFEM Chief Economist	Leads on providing analysis of GoM’s financial reporting, projections and forecasts for both spend and revenue. Lead on monitoring and assessing the performance of the local economy and market conditions.
Chief of Human Resources Office	Leads on the provision of Technical Cooperation recruitment and advice.
Director of Policy and Planning, and the Monitoring and Evaluation Officer	Leads on monitoring and evaluation, including logframe indicators.
Auditor General	Produces an annual audit report covering GoM’s recurrent expenditures and revenues.

A Delivery Plan has been produced alongside development of the Business Case. The Delivery Plan, Risk Register and Logframe will be updated as necessary throughout the year to reflect any significant changes to the project. DFID’s Internal Audit Department will review the Montserrat financial aid investment (including BC and logframe) in April 2016 as part of its wider Assurance Review of Overseas Territories Department’s work. An evaluation is not planned for this project although we will seek to learn lessons during key review stages, from evaluations elsewhere in the Montserrat portfolio and from a planned evaluation of St Helena Financial Aid, where the circumstances have a number of similarities.

GOM processes

Beneficiary engagement

1. There will be two main vehicles for beneficiary engagement on the financial aid project:
  1. Primarily through GoM’s normal democratic process, including as outlined above the consultative and legislative process of approving a budget and reporting progress against it.
  2. During the lifetime of the project we will seek to prioritise and scale up GoM and DFID’s engagement with key stakeholders across Montserrat e.g. community and faith groups. DFID will keep in contact with Montserrat’s UK representative who engages with the UK diaspora and with the EU in Brussels.

Risk management

This project will be guided by (i) the OTD risk strategy and framework put in place in February 2015 to systematise OTD’s risk management procedures; and (ii) the full risk register for Montserrat, which has recently been finalised. Key financial specific risks are outlined below, and OTD will regularly monitor risk and engage closely with GoM on additional mitigation required should risks escalate or new issues arise.

Table 6: Key financial aid risks
Risk	Category	Impact	Probability	Risk Category	Tolerance/Mitigating
Natural disaster, particularly hurricanes and/or increasing volcanic activity leading to increased costs for response, recovery and re-building.	External context	Severe (impact delivery and need for public services, and damages economic growth, and private sector confidence).	Possible (in terms of volcanic activity this rating relates to serious volcanic ashing rather than an eruption of the scale in 1995).	Severe	Montserrat benefits from regional Disaster Risk Reduction programmes which include early warning and disaster risk management. Monitoring by the MVO will continue where there is proactive management of hazard levels and access restrictions. Disaster response plans will be kept up to date and fully operational. New development and design should take into account hurricane risk and be located on the relatively safer northern half of the island.
Decreases in the £ against EC$ means value of UK financial aid in local currency falls below amount in GoM budget estimates.	External / context	Minor (conservative exchange rate used upfront to set the £ value of the settlement and hence minimise the risk of running out of £; currency gains and losses likely to incur within the same FY)	Almost Certain	Major	There is no currency hedging in place and DFID has no separate contingency amount set aside to increase the £ value of the 2015/16 Montserrat budget. GoM and OTD will therefore closely monitor the exchange rate and discuss throughout the year where (a) additional savings within the agreed settlement could be made in the event of a significant fall in the £ against EC$; and (b) where additional resources would be spent if there is rise in the £ against EC$.
Regional financial instability impacts Montserrat’s banking sector and wider economy.	External / context	Minor (the banking sector has much smaller international exposures than many other banks in the region)	Possible	Moderate	As part of the Financial aid Process, DFID reviews the performance and policy of the key financial institutions (including remaining liabilities following the wind-down of the Government Savings Bank). / The Governor has principal responsibility for financial services. / The Governor and Financial Services Commissioner monitor risks and report to Cabinet, and escalate to DFID any risks to the budget.
Higher inflation negatively impacts consumer and GoM finances.	External / context	Minor	Unlikely	Minor	Diversify Montserrat's energy production by getting renewable energy sources on line as soon as possible. / Inflation monitored during year and reported on at budget meetings. / GoM to pursue Social Welfare Review to improve targeting of support and ensuring reasonable needs are met.
GoM fails to implement public financial management reforms required to address substantial fiduciary risk (e.g. as identified in PEFA and FRA reports).	Fiduciary	Severe	Likely	Severe	As set out in detail earlier in the Business Case, planned actions include implementation of a new PFM Action Plan as a co-ordinated GoM/donor response to risks identified in PEFA/FRA. / Further DFID assistance to strengthen GoM MoF and particularly the Treasury through advancing the public service reform programme and other technical assistance programmes.
Tax revenue growth is lower than expected due to lower than expected economic growth and/or weaker reform and implementation of tax policy.	External context	Moderate	Possible	Major	OTD monitors tax performance as a core part of the financial aid process. / Working group set up with GoM and DFID representatives to review issues including tax policy. / Governor to discourage and potentially overrule conferment of any tax exemptions where economic justification absent.
Human resource capacity cannot be improved sufficiently to support planned public service delivery - compromising the quality and impact of services and overall value for money.	Delivery	Major	Likely	Severe	As set out in more detail earlier in the Business Case, DFID is providing finance via financial aid to allow GoM to source experts for critical areas, as well as wider recruitment support to GoM’s Human Resource Department . / Additional technical assistance support via Public Sector Reform programme and Short Term TC.
Risk that OTD is compelled to continue active management of procurement services and the GoM’s mechanisms do not improve sufficiently. / Risk that progress is slower than required with strengthening GoM’s procurement services.	Delivery	Major	Likely	Severe	GoM’s SOPs approved by DFID are operational. / Expected improved GoM procurement practice given that there is a Head of Procurement TC in post. / DFID’s representative sits in the GoM’s public procurement Board / Montserrat Team and Commercial adviser meets regularly with Head of Procurement. / In medium term, aim to transfer back full responsibility for procurement activities to GoM.
Change in GoM policy commitment to key assumptions underpinning delivery and risk management of financial aid programme. / Risk that Public Service Reform is not implemented to the extent necessary.	Delivery	Major	Unlikely	Major	New GoM has shown willingness to strengthen governance (PFM, procurement, project management, child safeguarding) which is being managed through the Public Service Reform 2 project. Alongside the changes, GoM is seeking an increase in HMG/DFID investments. DFID will continue to promote and work alongside GoM in these key areas: through the Financial aid project and wider programme engagement.

This project will not be delivered under a Partnership arrangement. There are however ongoing discussions across HMG and with GoM to agree a ‘New Deal’ for the wider governance and management of UK support for Montserrat. Linked to this, DFID is working with GoM to agree a strategic package of investments to stimulate the economy.

Annex 1: Government of Montserrat’s 2016/17-2018/19 Policy Agenda

Annex 2 – TC Posts
*These posts have already been filled and will therefore have an incumbent in place for the start of FY 16/17.
No.	Ministry/Department	Post
Short-Term TC
1	Legal	Consultant - Senior Legal Adviser
2	MOHSS	HRA/ Director of Health Services
3	MALHE	Environment Officer
4	MOHSS	Child Safeguarding Specialist
5	IRD, MCRS	Tax Advisor
6	Cabinet Secretariat	Monitoring and Evaluation Advisor
7	MoHSS	Biomedical Technician
8	Internal Audit Unit, MoFeM	Audit Advisor
9	Office of Auditor General	Audit Advisor
10	MOHSS	Senior Social Worker
11	MOHSS	Clinical Psychologist
12	Office of the Deputy Governor	Building Maintenance Appraiser
13	Legal	Consultant Parliamentary Counsel
14	MoHSS	Occupational Health Therapist
15	Office of Director of Public Prosecutions	Senior Crown Counsel
16	MOHSS	Crown Counsel, CPU
Child Safeguarding STTC posts
17	MOHSS	Child Protection Unit Manager
18	MOHSS	Senior Probation Officer
19	MOHSS	Adult Policy and Planner
20	MOHSS - Child Protection Unit	Social Worker
21	MOHSS - Child Protection Unit	Social Worker
Long Term TC
1	Ministry of Finance & Economic Development	Head of Procurement
2	Magistrate's Court	Chief Magistrate
3	Ministry of Finance & Economic Development	Chief Economist
4	Legal	Parliamentary Counsel
5	MCWL	Director of PWD
6	Office of the Premier/Cabinet Secretariat	Senior Policy Analyst
7	Ministry of Health	Community Mental Health Officer
8	Ministry of Finance & Economic Development	Chief Statistician
9	Ministry of Health	Chief Medical Officer
10	MCWL	Geothermal Project Manager
11	Office of the Auditor General	Audit Manager No. 1
12	Office of the Auditor General	Audit Manager No. 2
13	Office of the Premier/Cabinet Secretariat	Social Policy Planner
14	MATLHE	Housing Officer I - Policy & Planning
15	Ministry of Education	Mathematics Teacher No.1
16	MATLHE	Director of Lands & Survey/Chief Surveyor
Child Safeguarding LTTC posts
17	MOHSS	Counsellor, Child Protection Unit
18	MOHSS	Senior Social Worker
19	MOHSS	Senior Social Worker
20	MOHSS	Social Worker
21	MOHSS	Social Worker
22	MOHSS	Senior Probation Officer

Smart Guide
The Business Case

- Sets out the case for a programme, adapted to suit the context
- Explains very clearly what the programme will do within what timeframe and is explicit about the risks and uncertainties and how they will be managed
- Records an understanding for DFID, our partners and intended beneficiaries about what we are planning to do and the results we expect to achieve
- Allows DFID to report to the UK public on what we are doing with taxpayers’ funds

The Business Case is structured around the Treasury 5-case model. Within this broad framework the design should be adapted to suit different contexts and investment types. The content is indicative, not prescriptive and teams are encouraged to use judgement in making a logical argument to make the case in a way that suits the individual investment. There is also a set of questions in the Smart Rules that design teams should consider during the process. This is not a checklist and only the questions relevant to the context should be answered.

Teams should refer to the considerations below as a guide to writing the business case

Intervention Summary (2 Pages)
A succinct and unambiguous description of what the project will do. The summary sets out the problem the programme will address, what it will do and what the money will be spent on. It sets out the expected results in the context of the Operational Plan and DFID’s wider priorities and a summary of risks. The accompanying submission should set out any sensitive information that supports the case (e.g. risk tolerances and escalation measures)
Strategic Case
This section makes the case for DFID intervention by setting out the overarching context and the problem to be addressed. It should be clear what the programme will do and how with evidence. It should link to – but not repeat – the Operational Plan with a clear illustration of how the programme contributes to DFID global and portfolio priorities of poverty reduction.
Appraisal Case
The Appraisal Case explores how we will address the need in the Strategic Case in a way that optimises value for money. It appraises genuinely feasible options for achieving the objectives, including high level commercial choices , with a summary of the quality of evidence. The appraisal considers delivery mechanisms including capability and capacity, costs and benefits, risks and likelihood of success. It concludes with a preferred option.
Commercial Case
This section provides more detail on implementation and how value for money will be achieved. It sets out the procurement approach and requirements, proposed funding instrument and how the choice of instrument will be used to ensure vfm. It considers the market place response to this intervention with an explanation of how supplier performance would be managed. It sets out the procurement policies, capabilities and systems of the third party entity to ensure we get vfm.
Financial Case
This section sets out issues of affordability and the sources of funding. It includes a high level budget which does not impair VfM in procurement exercises for individual contracts. It sets out how funds will be disbursed and how expenditure will be monitored, reported and accounted. It highlights the evidence underpinning a judgement that funds will be used for the intended purposes.
Management Case
This section focuses on governance and management arrangements and the ability to deliver. It sets out the management implications for the business unit/ level of effort with realistic timings for mobilisation and start up. It outlines out the expected roles and responsibilities, including DFID’s own resourcing strategies (SRO, project team etc). / It sets out how it will respond to changes in context and the key elements of the Delivery Plan, key milestones and decision points where we can course correct. It includes a clear illustration of the risks, tolerances and approach to escalating problems and issues as well as exit and possible closure scenarios.