Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	08-22 February 2016

Title: Low Carbon Support Programme to the Ministry of Finance of Indonesia
Programme Code: 203123	Start Date / 30 January 2013	End Date: / 18 December 2015

Summary of Programme Performance

Year	2013	2014	2015
Programme Score	A+	A	A
Risk Rating	Moderate	Moderate	Moderate

Financial Position

Original Programme Value	£ 4,500,000 (Business Case)[1]
Original contract / Extensions/ amendments / Total Programme Value	£3,758,517 (OPML contract) / £110,046 (OPML contract) / £ 3,868,563 (total contracted to OPML)
Log-frame revisions (with dates)	Minor changes to wording of log frame targets (December 2013) / New log frame for extension phase (March 2015)
Total programme spend	Total final programme spend £ 3,825,694.72 (as per Aries Financial Report , 23 February 2016) [2]
[1] The original value of the approved within the business case was £ 4,500,000. This sum was divided into the sum for the contract to the project provider with the remaining allocated for a monitoring and evaluation component
[2] Not yet included additional invoice £202.58 which will be send to DFID A/P. The spend figures at Devtracker is £3,693,449 which not yet updated (not included the December invoice and additional invoice of OPML totalling £202.58)

Follow up actions required following closure
UKCCU support on energy sector ended in 2015 allowing the UKCCU to focus exclusively on emissions from forestry and land-use. However, the team will engage the Prosperity team in the British Embassy to monitor the progress of low carbon policies resulting from the project in the near future.
Introduction and Context (1 page)
DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203123/documents/ / Quest no 3719312
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203123/documents/ / Quest no 4175355

Outline of programme and what it has achieved

Indonesia is centrally important to the world's efforts to mitigating the impact of climate change. Emission reductions will only be politically and economically sustained if Indonesia is able to move onto a low carbon growth path, that generates employment, growth and poverty reduction. To do this, the Government of Indonesia will need to undertake a range of policy reforms which will be complex, politically sensitive and difficult to implement; and support and encourage its increasingly important domestic investment agency to embrace and adopt a low carbon approach into its investment portfolio.

To achieve the twin objectives of economic growth and low-carbon development Indonesia has to restructure its economy while simultaneously building its democracy and eradicating poverty. This is a transition that goes far beyond the scope of conventional structural adjustment programmes.

There is a strong body of evidence from around the world to show that fiscal policies can be both, the most effective driver (eg, via feed-in-tariffs) or the single biggest obstacle (eg, via fossil fuel subsidies) to low-carbon development. Unless Indonesia is able to design and implement a comprehensive and consistent approach to fiscal policy which directly prioritises low carbon development, the prospects for Indonesia being able to break-out of its future “business as usual” emission trajectory is very low.

As well as policies, experience from the UK, Germany, China and other countries has shown that investment funds that can channel public funds to promote public/private co-investment are vital to catalyse and lead investment in low-carbon and clean technology.

The Low Carbon Support (LCS) programme provided low carbon policy research development support to the Centre for Climate Change Financing and Multilateral Policy (PKPPIM) in the Fiscal Policy Agency of the Ministry of Finance (MOF) and to the Indonesian Investment Agency (Pusat Investasi Pemerintah - PIP) in Indonesia. The policy research development support improved MOF capacity to develop appropriate fiscal policies and financing arrangements to address the issues of climate change and the implementation of effective low carbon policies by the Government of Indonesia.

The LCS programme was two year and nine month project of support to the Ministry of Finance, This support has developed relationships and built trust between the UK and Indonesia. Past results and the strong relationship with the Fiscal Policy Agency and Indonesia Investment Agency under Ministry of Finance have been the catalyst for the request for broader and deeper assistance on low carbon development.

The need for the support was recognised by the DFID’s Secretary of State in February 2012 during a meeting with Indonesia’s Vice Minister for Finance and it was agreed that the UKCCU would develop a business case for UK support to continue up to March 2015.

The LCS programme was delivered by a consortium led by Oxford Policy Management Limited (OPML) which commenced activities in the Ministry of Finance Indonesia on 4th March 2013. The LCS was due to concluded on the 31th March 2015. However, a brief extension phase was approved to cover the period from 1st April 2015 to 18th December 2015. A new log frame was and agreed for the extension phase with an increased emphasis on policy impact and a reduced emphasis on capacity building.

Results

In PKPPIM and PIP, the programme substantially increased the institutional capacity each unit to formulate and disseminate fiscal policies to reduce carbon emissions, for example through:

PKPPIM	PIP
Substantial capacity building activities including training courses and study tours/field visits on renewable energy initiative and financing;
An improved evidence base for policy making, through 14 high quality policy studies (including recommendations on fiscal policies for the energy sector and supporting policy papers for the energy sub-sector i.e fiscal policy studies in rail transport and motor vehicle emissions);	Extensive work to unblock the legal and institutional hurdles to investing in low carbon projects, including a strategic management and legal studies that recommended the need for a significant restructure of PIP (broadly along the lines of the eventual merger with PT SMI);
Better relationships with other stakeholders involved in the development and acceptance of policy through 45 policy workshops and focus group discussions; [3]	Development of Standard Operating Procedures (SOPs) and investment processing approaches for renewable energy and geothermal projects.
Delivery and launching of several guiding policy frameworks, most notably the Green Planning and Budgeting Strategy which were accepted (approved by the head of the Fiscal policy agency) and disseminated (shared more widely in the ministry of finance, related technical line ministries and other non-government stakeholders such as universities and the private sector). This is part of the medium term strategies and policy framework	Facilitation and assessment of a pipeline of potentially viable renewable energy and geothermal projects.
Pursuit of a number of specific policy initiatives from design through to MoF acceptance and implementation by the government, e.g. the draft regulation(s) for energy conservation/efficiency financing scheme and bio-mass waste to energy credit scheme.
Development of skills and institutional capacities including the building of an economic model for internal use and in conjunction with key land based Ministries;
[3] Focus group discussion participated by the MoF, technical line ministries related and stakeholders (industry, NGOs, university).

In March 2015, the Minister of Finance announced that PIP and PT SMI/ Sarana Multi Infrastruktur (a similar though differently structured body to PIP, under the management of the Ministry of Finance) would merge under the leadership of PT SMI. Based on Ministerial regulation on mergers and take overs, PIP’s assets together with the pipeline of possible investments and the newly augmented institutional capacity (in the form of SOPs etc.), will transfer to PT SMI by December 2015. PT SMI will take forward the progress made by LCS with PIP on the renewable energy and geothermal project investment.

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

Outcome indicators and milestones for December 2015 are presented below, with an assessment of progress

Outcome	Target	Results as at December 2015	Scoring
Original programme
Supportive environment for low carbon investment established in Indonesia.	Strategic Policy papers are substantially accepted and implemented (e.g. through new government regulations, new MoF Regulations or new budget allocations)	14 policy papers completed with 11 accepted and disseminated; / tangible results include simplified processing for renewable energy incentives through a design of energy conservation/efficiency financing schemes and energy resilience fund schemes; and the establishment of PKPPIM as the National Designated Authority (NDA) for the Green Climate Fund;	A+
	Low carbon funds total: $300m	Low carbon funds for renewable energy and Geothermal funds total: $310m to date	A
Extension
Improved awareness of low carbon fiscal policies by a wide range of gov’t and other stakeholders	Assessment of awareness of GBP Strategy, Consolidated Energy Paper and Land Use Fiscal Policy Framework	Widespread knowledge of at least one of BKF's strategic policy papers	A
Progress towards implementation of policy recommendations for low carbon development	Number of policy initiatives to promote low carbon development that are approved by the Minister and in process of being made into regulation/implementable policy	One initiative is approved by the Minister and in the process of being made into regulation or policy implementation	A
PKPPIM coordinates with stakeholders in the forestry and land-based sectors and identifies fiscal policies for reducing emissions	Number of recommendations for fiscal policy on forestry/land-based sectors with agreement outside of PKPPIM	Broad agreement by key sector stakeholders on areas of interest but not specific policy recommendations	B

Original Programme Outcomes

Outcome indicator 1 – Supportive environment for low carbon investment established in Indonesia. By December 2015, strategic policy papers on Green Planning and Budgeting, Sustainable Development of Land Based Sectors, Fiscal Policy Options for the Energy Sector in Support of Indonesia’s Sustainable Development and A Coherent Fiscal Policy Framework for Promoting Renewable Energies and Energy Efficiency had been accepted by the MoF. The Green Budgeting paper in particular was commended by government officials as having broad and high-level support. Implementation will occur over 4 years. Initially, the Low Emissions Budget Tagging and Scoring System will be piloted by seven ministries beginning in 2015. Many policies proposed in other papers are also being implemented. These include the continued moratorium on new forestry licences, minimum biofuel blends, the implementation of the geothermal fund facility, fossil fuel subsidy reform, and the implementation of FiTs. Only three recommended policies were decided impractical or politically out of favour on completion of the papers following consultations within MoF as well within the technical line ministries. [4]
[4] The LCS project studies can be found at  http://mirrel.web.id/website/pkppim2/site/index/studies

Outcome indicator 2– Low carbon funds total: The outcome target of having at least US$300 million in funds available to PIP for low carbon investment was also met. PIP noted that the work of the LCS programme contributed to securing these funds. The support that came from the LCS programme gave PIP the confidence in their pipeline to demand the allocations for low-carbon investment and on that basis attract further allocations of money.

Extension phase outcomes

1. Outcome indicator 1 - Awareness: Widespread knowledge of the Green Planning and Budgeting document was generated through the high profile launch event. More generally, the LCS programme’s research outputs gave constant visibility to these issues and enabled the PKPPIM and PIP to better engage and influence seniors in the MoF and the programme allowed the MoF to engage key stakeholders in the land based sector (15 events).
2. Outcome indicator 2 – Implementation: Progress was made on a number of fronts. Work towards each of the policy initiatives is ongoing, making assessment difficult. However, given that a ministerial regulation on tax incentives was produced that applies to renewable energy; we judge that both of these targets were met.
3. Outcome indicator 3 – Policy recommendations: Progress towards this target was made. An event was hosted to socialise the Land Use Fiscal Policy framework paper with 35 participants from a wide range of institutions. Broad agreement on policy recommendations was not achieved. Despite the work of the original LCS programme, there seemed to be a lack of understanding within government, both within the MoF and in other ministries, about why fiscal policies are needed in the land-use related sectors. There was agreement on the areas of interest across ministries but no clear recommendations on policies to date.
Programme Impacts, as set out in the original and extension phase log frames, have been achieved.

Low carbon development is shown to be viable and able to deliver results:
Feed-in-Tariffs (FITs) have been put in place and implemented for 3 renewable energies (biomass, solar, geothermal), the LCS project had provide the technical line ministries with a capable Ministry of Finance staff who understand about the FITs and impact to the budget and finance policy from the result of the fiscal policy studies. The capacity building work with the MoF helped improve the knowledge of staff on FITs issues. The strategic policy papers and financing modality schemes as a result of LCS research study has also bring the impact to the approval of FITs on biomass, solar and geothermal;

Fuel and energy subsidies have been significantly reduced (mostly abolished) from the expected 20% subsidy reduce in the business case, which partly also because of the new government strong intention on reducing the subsidy;

Low carbon fiscal incentives and regulations have been introduced:
Numerous government low-carbon policy initiatives were implemented between 2013 and 2015. These include initiatives on prescribed biofuel blends in retail fuels, vehicle emissions standards, FiTs, energy targets in National Energy Policy, fossil fuel subsidy reform, moratorium on issue of new forest licences, Ministry of Development and Planning (BAPPENAS) green growth roadmap, and the MoF Emissions Budget Tagging and Scoring System, amongst others.

Output Score and Description

Output targets during the initial phase were all met and are therefore given a score of A.
Achievements under Output 1 (high quality TA to MOF) included:
  - finalization and dissemination of medium term fiscal policy frameworks for green planning and budgeting and launching to public and local government; launching of consolidated paper on energy fiscal policies; launching of land-use fiscal policy framework;
  - supporting policy papers in 8 energy sub-sectors and also for commuter rail transport and reductions in motor vehicle emissions;
  - support in developing 5 MOF regulations; and
  - support to development of PKPPIM skills and institutional capacities including building an economic model; on the job training; convening 15 training courses; and support for 15 external conferences, study tours, field visits.
- Achievements under Output 2 (wider stakeholder input to MOF low carbon policy making) included 45 policy outreach FGD’s between PKPPIM and key stakeholders.
- Achievements under Output 3 (low carbon investment objectives incorporated into PIP operations) included:
1. strategic management and legal studies mapping significant restructure of PIP (in line with the merger with PT SMI);
2. significant training and capacity building including SOPs for mini hydro, biomass and geothermal sectors and investment processing approaches; and
3. operational support in developing and processing the pipeline of investment applications.
Output targets during the extension phase were met and scored as an A.
- Under Output 1 (launching and dissemination of 2 policy papers), the LCS project manage to launch and disseminate 3 papers which are green planning and budgeting (GPB), consolidated paper on energy fiscal policies; launching of land-use fiscal policy framework and a further 8 studies were finalized and disseminated.
- Under Output 2 (achievement of at least one policy initiative from earlier policy recommendations) tangible initiatives were achieved through a design of energy conservation/efficiency financing schemes and energy resilience fund schemes
- Under Output 3 (convene 2 outreach events in the land based sector) some 15 events were convened.
Lessons and how these have been shared

A number of lessons have been learned from the programme through the regular quarterly reports and the final external review. In brief the main lessons for the future are:

1. Project Theory of Changes needs to be re-visited especially if significant changes occur (i.e new government elected and/or new policies enacted i.e removal of transportation subsidy)
2. Matching the programme duration to budgeting, planning and election cycles in Indonesia. The timeframe was too short to achieve significant policy reform. It needed at least 5 years to have a substantial policy and regulation impact
3. If policy objectives and policy intervention are the goal, the programme should be situated in a higher level branch of the Ministry of Finance and cross cutting with several units within MoF
4. Aligning the objectives of the programme with those of the counterpart governments to ensure Indonesian leadership, which is of fundamental importance to successful capacity building and policy reform;
5. Being aware of counterpart absorptive capacities when designing and delivering programme;
6. Ensuring programme governance structures and long term consultant management arrangements adapt to changing counterparts structures and personnel. To note during project duration there were three changes of Minister, two changes of vice minister, three changes of Chairman of the Fiscal Policy agency, 2 changes of Directors and five different deputy heads of PKPPIM. These changes meant significant project time was taken up educating new officials about the programme in these lead organisations. There have also been 3 lead advisers from UKCCU during the project which impacted programme implementation and result

By addressing the constraints above, together with other challenges, the chances of policy analysis being converted into major tangible reform implementation will be maximised.

Aside from the lessons learned, the LCS benefitted from an approach according to the MoF which was innovative for three reasons:
1. the LCS team was housed within the Ministry of Finance’s Fiscal Policy Agency which eased communication
2. the project governance structure firmly placed responsibility for the LCS’s project direction with the MOF; and
3. the use of national consultants rather than international consultants was greatly appreciated by MoF as they felt that this generated strong level of national ownership and confidence in sharing financial data.

A detailed matrix of performance against log frame is available in Annex 1.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	High Quality Technical Assistance to the Ministry of Finance
Output number per LF		1 (main phase)	Output Score	A
Risk:		Moderate	Impact weighting (%):	22%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress (Final at 31/3/2015)
Preparation of policy papers (PKPPIM)	At least 8 policy papers by March 2015	14 policy papers completed in English and Indonesian languages. / 11 policy papers were disseminated and 3 policy papers are kept by MoF
Holding of low carbon training events (PKPPIM)	At least 6 events for PKPPIM (and other parts of MoF) by March 2015	On job training, 15 training courses,15 conferences / study tours / field visits supported

Key Points

Output 1 targets (policy papers and training events in PKPPIM, MoF all met expectations. Important achievements in relation to targets under Output 1 include:

- Finalization, acceptance and dissemination (English and Indonesian) of medium term fiscal policy frameworks for: (i) green planning and budgeting; (ii) renewable energy and energy conservation; (iii) energy sector policies; and (iv) for the land based / forestry sectors;
- The Green Planning and Budgeting Strategy, in particular, which was commended by government officials as having broad and high-level support from internal MoF, technical line ministries and provincial governments. This support was generated both during development of the document and by a high profile launch event with participation from across the Government. Implementation will occur over 4 years. To begin with the Low Emissions Budget Tagging and Scoring System will be piloted by ministries in 2016.
- 8 energy related policy papers in English and Indonesian (on natural gas; biofuels; waste to energy financing; energy efficiency financing; oil and gas wastes; producing biomethanol from forest wastes; carbon capture and storage; and fuel subsidies in Jakarta Bogor Depok Tangerang and Bekasi);
- Fiscal policy studies (English and Indonesian) on rail transport and motor vehicle emissions;
- Support to develop regulations and budget reforms including in the areas of: reduced fuel and energy subsidies; FIT reforms; budget tracking system for green expenditures; biomass waste to energy credit schemes; the fiscal and market regime for bio-fuels; 2 energy efficiency financing schemes; and the simplification of procedures for receiving fiscal incentives for renewable energy investments; and
- Support for the development of PKPPIM skills and institutional capacities including: (i) the building of an economic model to be run internally and in conjunction with key land based Ministries; (ii) substantial on the job training and support; (iii) the delivery of 15 training courses; and (iv) support for 15 external conferences, study tours; and field visits.
It was also strongly noted by PKPPIM that high technical assistance to MoF helped the MoF in preparing presentations for international and domestic fora and meetings. The programme provided ad-hoc technical assistance on renewable energy issues following a request from interested technical line ministries.
Summary of responses to issues raised in previous annual reviews
The main recommendations from the two previous annual reviews were:
1. to pursue conversion of policy studies to reform implementation;
2. not to introduce more studies beyond those in the approved work plan;
3. ensure all policy studies are completed and disseminated on time;
4. ensure that capacity building is linked to priority work tasks of PKPPIM.

These 4 recommendations were all addressed as management priorities in the final 18 months of the programme. Success was achieved in converting policy analysis to reform though further time and work is needed for major progress. No significant new studies were introduced after early 2014. All policy studies have now been completed and disseminated to the relevant units within Ministry of Finance and to relevant other line ministries. Capacity building was targeted to the needs of PKPPIM as agreed with all parties in line with a Steering Committee approved capacity building plan.

Recommendations for future programmes
Output 1 recommendations are in line with broader issues and lessons summarized in Part B above.

Output Title	Wider Stakeholder Input to MOF Low Carbon Policy Making
Output number per LF		2 (main phase)	Output Score	A++
Risk:		Moderate	Impact weighting (%):	9%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress (Final at 31/3/2015)
Holding of outreach events	At least 4 outreach events	46 outreach events completed
Preparing outreach publications	At least 4 low carbon development publications	28 publications (14 each for PKPPIM and PIP). 11 widely disseminated (all PKPPIM)

Key Points
Output 2 targets for wider stakeholder input to MoF low carbon policy making were all significantly exceeded. Important achievements in relation to targets under Output 2 include:
46 policy workshops / focus group discussions (FGDs) involving a broad cross section of stakeholders (1,719 participants from Government, civil society, private sector - average numbers of 38 per event). Events included:
7 workshops (and one study tour to South Korea) for an Inter-ministerial Working Group (10 Ministries / Agencies) on Green Planning and Budgeting which become a good platform for sharing experiences and knowledge between the Indonesia and South Korea governments ;
- Support to the MOF Annual Climate Change Conference in 2013;
- Policy discussions focusing on all 14 core policy topics in conjunction with PKPPIM with an average of around two FGDs / workshops per topic;
- Support for pipeline development and business promotion in PIP; and
- Support for development partner coordination across the low carbon and green development fields.
- Post FGD evaluations were overwhelmingly positive on the quality of all events held. The FGDs helped to build relationships and policy consensus between MOF and its key stakeholders;
- PKPPIM was supported to prepare 14 substantive policy reports (all in English and Indonesian languages) 11 of which were accepted and widely disseminated (see Output 1 for details). LCS helped PIP to prepare 14 technical reports (most in English and Indonesian) but for commercial confidentiality reasons these were not disseminated.
Summary of responses to issues raised in previous annual reviews

The main recommendations from the two previous annual reviews were to:
1. continue to integrate communications into each work activity;
2. enhance PKPPIM / PIP skills in communications;
3. provide and utilize communications skills in LCS to support PIP and PKPPIM; and
4. spread results of studies widely.

These issues were all addressed as management priorities in the final 20 months of the programme through the active role of the LCS communications consultant and as evidenced by
the large number of very successful FGDs mainly linked to policy studies and wide dissemination of 11 study reports.
Attempts to develop communications skills in PKPPIM only partially succeeded due to the absence of any dedicated communications personnel in the unit. A major communications programme for PIP was designed but was only partially implemented prior to cancellation following the 2015 merger with PT SMI.

Recommendations for future programmes
Output 2 recommendations are in line with broader issues and lessons summarized in Part B above.

Output Title	Low carbon investment objectives fully incorporated into the operations of PIP
Output number per LF		3 (main phase)	Output Score	A
Risk:		Moderate	Impact weighting (%):	31%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress (Final at 31/3/2015)
SOPs established for low carbon development	SOPs for mini hydro and 1 further low carbon sector in place	SOPs completed on mini hydro, geothermal, and biomass technologies and applied as part of PIP investment guidelines
Implementation of PIP’s institutional capacity strengthening plan	- Legal and institutional review complete and recommendations accepted by PIP / - PIP Capacity is strengthened by 6 training events	- Reviews completed and broadly accepted by MOF / PIP with eventual restructure with PT SMI / - 10 formal training events on the technical of renewable energy, legal review and financing assessment for renewable energy and geothermal proposal, plus on the job training and 3 study tours

Key Points

Output 3 targets were all exceeded with the following important achievements:

- Completion of strategic management / legal studies providing a roadmap for organizational and legal reforms emphasizing the need for significant restructure away from the risk averse Public Agency (BLU) approach (and in line with the eventual merger with PT SMI);
- Significant focus on training and human capacity development, including:
- On the job training (which was the focus of around 30% of the time of the long term LCS consultant in PIP) supplemented by PIP collaboration with the work of short term consultants;
- Support to 10 formal training events involving 252 participants, averaging 25 persons per 2 to 3 day course. Key themes covered were communications; negotiations, legal skills, business development for various clean energy technologies and risk assessment and management; and
- 3 international study tours focusing on clean energy and geothermal financing topics (Australia, United Kingdom, New Zealand (geothermal));

- Broader capacity building through review of investment processing approaches and development of SOPs. LCS directly supported development of SOPs / manuals for hydro and geothermal technologies while supporting other development partners on biomass and energy efficiency SOPs; and
- Operational support to develop the investment pipeline, including: (i) a strategy for expanding new business; (ii) processing 2 hydro and 2 geothermal applications; and (iii) pipeline development of energy efficiency and biomass proposals including regional visits.
Note: the independent reviewer of LCS project from ODI noted that the mini hydro and biomass SOPs were of a particularly good quality, providing information on each technology and the market in Indonesia, as well as guidance on risk assessment and loan appraisal procedures.
Summary of responses to issues raised in previous annual reviews

Key recommendations from 2 previous annual reviews were:
1. continue to support PIP to operationalize low carbon financing;
2. continue to support development of an energy efficiency financing facility; and
3. pursue revisions to PMK 03/2012 regarding the geothermal financing facility.

These issues were all addressed as management priorities in the final 24 months of the programme as evidenced by:
1. support for the processing of 4 applications on mini-hydro and geothermal sectors and significant development of the pipeline of new applications;
2. the development of 2 energy efficiency financing schemes which are expected to be implemented by PT SMI or a similar body, while incorporation into the existing Kredit Usaha Rakyat/KUR (credit for people business) scheme will be managed by MOF; and
3. the development of revisions to recommendations for PMK/ Peraturan Menteri Keuangan / Ministrial regulation although these remain to be implemented by PT SMI.

Recommendations for future programmes

Output 3 recommendations are in line with broader issues and lessons summarized in Part B above.

Output Title	Approval and dissemination of strategic policy papers by PKPPIM
Output number per LF		1 (extension phase)	Output Score	A
Risk:		Moderate	Impact weighting (%):	12%
Risk revised since last AR?		Not Applicable	Impact weighting % revised since last AR?	Yes (previously undefined)

Indicator(s)	Milestones	Progress (at 18/12/2015)
Finalize and disseminate key policy papers	Approval and dissemination of at least 2 BKF strategic policy papers	14 BKF policy papers finalized and with 11 approved and widely disseminated.

Key Points
The extension phase Output 1 target was directly linked to requirements under the main phase outputs 1 and 2. The extension target for Output 1 was met through delivering the following:

- 14 main policy papers were completed (in English and Indonesian languages) and accepted by end October 2015 with 11 of these approved by Head of Fiscal Policy Agency and widely disseminated to around 400 stakeholders and posted on the BKF /PKPPIM website (see Output 1 under the main phase for the topic details);
- The extension phase work plan particularly targeted 3 key policy reports for completion and wide dissemination. All 3 of these were completed and disseminated before the end of October 2015.
- The GPB Strategy (including a 2015 update) was formally launched in October 2015 with senior MOF and UK Embassy leadership along with 160 key stakeholders. MOF presented the strategy internationally at the UNFCCC COP meeting in Peru in late 2014 and at a September 2015 UN-led Asian regional climate finance conference. The strategy was presented and disseminated at the international COP meetings in Lima and Paris;
- The white paper on Fiscal Policies for the Energy Sector Energy was initially socialized in two internal MOF FGDs in June / July 2015 followed by broader FGD socialization in August 2015 with key stakeholders, including key Government Ministries (including Energy) and the private sector, with presentation and discussion of the priority policy reforms recommended in the Report; and
- The Land Use Fiscal Policy Framework Paper initially underwent 2 internal FGDs in the MOF following which a broad based FGD was held in June 2015 to socialize the paper with key sector stakeholders. This FGD reached consensus on key fiscal priorities for the sector. The meeting also confirmed short term priorities for follow up under the extension phase (see Output 3 for details).
During the Government of Indonesia’s climate festival that was held in February 2016, the MoF used their communications booth to share and distribute hardcopies of the policy report studies as well a presentation which was well used by technical ministries.
Summary of responses to issues raised in previous annual reviews

Not directly applicable although comments under the main phase Outputs 1 and 2 with regard to finalization and dissemination of key study publications also apply here.

Recommendations for future programmes
Extension Output 1 recommendations are in line with broader issues and lessons summarized in Part B.

Output Title	Achievement of policy initiatives on low carbon development by PIP and PKPPIM
Output number per LF		2 (extension phase)	Output Score	A
Risk:		Moderate	Impact weighting (%):	12%
Risk revised since last AR?		Not Applicable	Impact weighting % revised since last AR?	Yes (previously undefined)

Indicator(s)	Milestones	Progress (at 18/12/2015)
Implement low carbon policy initiatives	Achievement of at least 1 low carbon policy initiative from a number of policies being pursued.	3 initiatives finalized / very advanced (see points 2,3 and 6 below) & 3 others progressing well

Key Points

Work under extension phase Output 2 occurred on six fronts with excellent progress made the majority despite a challenging environment as the Ministries of Energy and Mineral Resources and Environment and Forestry finalized their institutional restructuring and approaches to structural issues through all of 2015. Progress against the 6 activities include:

- Completion of appraisals on 2 geothermal and 2 hydro investment applications in PIP which were passed on to PT SMI after the merger with PIP. PIP will consider these in due course. Due to PIP being absorbed into PT SMI, none of the four ongoing loan appraisals have been approved to date. LCS support provided to this initiative and appraisals which have now have been handed over to PT SMI, along with the SOPs for investments. It was recognised by PIP that a loan for a geothermal and/or mini hydro project would have occurred had it not been for the merger, and that PT SMI might approve at least one in due course.
- Work on an Energy Conservation / Efficiency revolving fund facility which made good progress on two fronts: (a) a draft regulation and paper on the Energy Resilience Fund to be managed by Ministry of Energy and Mineral Resources; and (b) the Ministry of Finance, DG Treasury and Directorate Energy Conservation have agreed with the KUR Committee under Coordination Ministry for Economic Affair (CMEA) to incorporate energy efficiency financing into the existing interest subsidy mechanism, Credit for People’s Business (KUR). It is anticipated that this will enable businesses to secure low-interest credit for energy efficiency investments and renewable measures from banks. The KUR scheme will be expanded from IDR 40 trillion to IDR 100 trillion in 2016. The MoF have confirmed that the size of the KUR scheme has been increased from IDR 40 trillion to IDR 100 trillion. Access has also broadened from small enterprises to allow access to medium and larger enterprises. The KUR allows access to both loans and interest subsidies through participating banks.

Completion in line with recommendations a MOF Regulation, of a suite of tax incentive reforms for renewables and energy efficiency which have been identified under various energy related policy papers . These recommendations, which clarify and simplify procedures for accessing existing fiscal incentives for low carbon investments, have now been formally passed from MoF to Ministry of Energy and Mineral Resources;
- A draft regulation has been prepared on the implementation of the waste to energy credit support scheme but this still awaits decision from the main implementing agency, the Ministry of Environment and Forestry which has been inactive on this regulation pending finalization of its recently agreed restructure;. A list of potential users was drawn up by an LCS consultant and the Ministry of Environment but will need to wait until the new management of the ministry reaffirms its support. However, it was unrealistic that such a regulation would be passed during the course of a 2.5 years project and therefore LCS support on the waste to energy credit scheme focused on raising awareness through FGDs, meeting and studies and bringing it to the attention of relevant technical ministries for future development.
- Preliminary work has continued on the design of a policy approach to issuing Green Bonds in Indonesia. The programme delivered a number of FGDs to discuss key issues; and
- MOF / PKPPIM has now been confirmed as Indonesia’s National Designated Authority for the Green Climate Fund (GCF).
Summary of responses to issues raised in previous annual reviews
N/A

Recommendations for future programmes

Extension Output 2 recommendations are in line with broader issues and lessons summarized in Part B above.

Output Title	Improve Dialogue between PKPPIM and Key Stakeholders in the Forestry and Land Based Sector
Output number per LF		3 (extension phase)	Output Score	A++
Risk:		Moderate	Impact weighting (%):	13%
Risk revised since last AR?		Not Applicable	Impact weighting % revised since last AR?	Yes (previously undefined)

Indicator(s)	Milestones (at 18/12/2015)	Progress
Improve Dialogue between PKPPIM and Key Stakeholders in the Land Based Sector	Convene at least 2 outreach events	15 outreach events convened

Key Points

Work under extension phase Output 3 delivered 15 high quality events (as evidenced by participant evaluations) having been held, thus very significantly exceeding the target of 2 events. Details of the events are:

- 1 sector stakeholder FGD held to promote dialogue on the Land Based Fiscal Framework Report including the socialization of concept of fiscal policy for the forestry/land-based sectors ;
- 1 FGD and 1 field visit (both interministerial across the land based sector) held to strengthen dialogue regarding forest management units and the forestry revenue system;
- 1 FGD and 1 field visit (both interministerial across the land based sector) undertaken to strengthen dialogue and policy in relation to promotion of investment on degraded land;
- Outreach to 35 stakeholders (including in the land based sector) through participation in the PKPPIM perceptions study which has been finalized;
- 3 FGDs / workshops supporting development across Ministries of a systems dynamics model for the land based sector with a fourth and final workshop in November 2015. The model is was used to model basic implications of Indonesia’s INDC which was submitted to the UN in the lead up to the UNCCC COP meeting in Paris in December 2015;
- 6 training / mentoring / outreach events held across Ministries in relation to strengthening international negotiations for climate change, with some emphasis on the land based sector with all land based Ministries as well as various parts of MOF, Bappenas and the Ministry of Foreign Affairs. The work supported the development of Indonesia’s positions in the INDC and to the UNFCCC COP 21 meeting; and
- A website was developed for PKPPIM with LCS support to assist in improving policy and technical dialogue with key stakeholders, including in the land based sector.
Summary of responses to issues raised in previous annual reviews
N/A

Recommendations for future programmes
Extension Output 3 recommendations are in line with broader issues and lessons summarized in Part B above.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Expenditure on consultant fees represents 73% of total programme expenditure and therefore the key cost driver of this programme is the average daily fee rate. Both DFID and OPML worked hard to keep fee rates low, with the fee rate of each consultant selected to work on the project being subject to approval by DFID. Furthermore, OPML instituted a bidding process for all consulting activities over £25k.

The average fee rate was £409 per day. This is a reduction of 6% on the average fee rate of £435 per day in the contract with the service provider. This implies a saving of £177,593 over the 6,831 consultant days used on the project.

Another significant cost driver was the costs of workshops, which were kept low by a strict bidding process as set out in a LCS project financial manual.

VfM performance compared to the original VfM proposition in the business case
The key indicator for measuring value for money compared with the VFM proposition in the business case is the additional finance that the programme secures for deployment into low carbon development - principally the level of public finance that has been allocated as a result of the LCS Programme. This indicator also contributes to the International Climate Fund KPI 11 target (the volume of public finance mobilised for climate change purposes as a result of ICF funding), target of $ 300 million which was achieved and allocated for renewable energy and geothermal funds under the PIP.

Assessment of whether the programme represented value for money

As well as delivering VFM with respect to economy, the programme also delivered value in terms of efficiency and effectiveness by directing funds into areas that showed the greatest prospect of return. For example, after initiating a number of policy studies, PKPPIM took a judgement on which had traction with the government and allocated additional funds put into further developing those policy areas.

The majority of the value created by the programme is very difficult to measure (e.g. improved capacity of staff, improved evidence base for policy, improved institutional processes, and development of strategic frameworks for future policy). However, a number of quantifiable successes can be identified. For example, through including energy efficiency in the KUR (discussed above), the Government of Indonesia will make approximately £600m available for interest subsidy which the government hopes to generate investment of up to £6bn from the private sector.

Even if only these quantifiable successes are considered, this programme represents a significant return on investment for a programme of £3.8m. The programme therefore delivered excellent value for money.

Quality of financial management during programme

The programme produced a narrative financial report on a quarterly basis, highlighting expenditure by line item and by log frame output. A commentary on value for money was also included. Whilst forecasting of expenditure could have been better during the programme, the final programme expenditure was within 1% of the total budget.

The programme has also been subject to three external audits (at the end of each financial year and the completion of the programme). All three audits have found the programme accounts and financial management system are accurate. The Management Letter in each audit found only very minor areas for improvement. The quality of the financial management can therefore be considered to be high.

In respect to the Government of Indonesia compliance, the regular BAST (Berita Acara Serah Terima/ Transfer report) was co-signed by the Director of PKPPIM and the Head of UKCCU on a quarterly basis.

Date of last narrative financial report	1st December 2015
Date of last audited annual statement	18th December 2015[5]
[5] Audit report for April-December 2015 is still on drafted and will be send to UKCCU once it is finalized

E: RISK (½ page)

Quality of risk management over the life of the programme

The overall risk level assigned to the Business Case was moderate. This has not changed

The Business Case for the programme identified three major areas of risk for the programme.

The mitigation measures identified in the matrix were applied throughout the programme to address these risks. Risk management can be considered to have been of good quality. The risk management strategy was not used as a tool for the Steering Committee. However, it was regularly considered by the LCS programme management team.

Risk	Impact	Mitigation measures
Risk of no influence, all the capacity building and advice provided is neither used nor has any impact on policy.	UK taxpayers money will have been wasted	The Ministry of Finance has requested this support from the UK as a fellow G20 country. / The governance arrangements specifically allow for the MoF to determine the detailed work programmes of the technical assistance and to respond directly to the requirements of Ministers and senior leaders in the Ministry of Finance. / The UKCCU is a member of the Technical Committee and Steering Committee and will be in regular contact with the Fiscal Policy Office.
Risk of corruption	UK finance will be wasted, stolen or misappropriated	The UKCCU implement the latest DFID guidance on avoiding corruption in the management of the programme. This guidance shared with all project partners and an appropriate training on anti-corruption and bribery has been conducted twice during the project life time / A financial spot check and audit were conducted regularly as part of mitigation risk of corruption
Risk of underspend	Results will not be delivered on time.	A regular and close review on the project spending and forecasting played a key role. Programme had variance of only 1 percent at the time of project close.

The assessment of risk at the outcome level was rated moderate. The risks at this level were that MoF was unable to gain cross government support for new regulations and Parliament do not agree to any new laws or regulations proposed by the Ministry of Finance.

As mentioned above, it was very ambitious to have expected any regulation or policy to have been approved over the life of this 2.5 years programme. The LCS programme played their agreed role and addressed these risks by helping to transform the approach to consultation and presented fiscal policy through a series of FGDs that enabled the PKPPIM to build strong links with stakeholders such as MoF DG Budget and DG Treasury and private sector institutions. These links are essential to build support for the fiscal policies that will drive low carbon development in Indonesia.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The original programme duration was approximately two years. In April 2015, the programme was extended by nine months to mid-December. The extension largely reflected the desire to continue existing lines of work (and open a small number of new ones) needing additional time for finishing incomplete work. However, the finalisation of a few activities did continue from the main phase into the first couple months of the extension phase.

The external review found that even with the time extension the timeframe was unanimously considered too short. The programme duration did not allow sufficient time to develop and gain acceptance of significant policy changes, especially when combined with the impact of several changes in leadership at PKPPIM.

Performance of partnership(s)

One of the highlights of the programme has been the relationship built between the programme implementers and the government counterpart institutions. In both institutions, but especially in PIP, the project outputs were co-created between programme consultants and government staff. The partnership between the programme and the government has therefore been very strong.

Partnerships were also strengthened between PKPPIM, PIP and UKCCU by the convening of a monthly Working Committee to discuss progress and agree future activities. This led to co-ownership of the work plan and provided a forum to discuss differences when these occurred.

The programme also had a significant outreach component which aimed to strengthen partnerships between PKPPIM, PIP and their key counterparts (for policy formulation/acceptance and for investment, respectively). The significant number of events held has certainly improved relationships between MoF and key counterparts (technical line ministries) and has increased the profile of both institutions.

Asset disposal and value obtained by DFID

The programme only procured modest assets during its existence – the most significant items being 2 laptops, 2 desktops and limited office furniture. These assets were transferred into their ownership at the end of the programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

An external review of the programme was commissioned in November 2015 and conducted by the Overseas Development Institute (ODI). The review has verified progress against the log frame targets indicated in this report and also looked at wider programme performance. In brief, the review found:

- Successes at PIP included: the objective of disbursing money would have been achieved if not for the delay caused by the merger with PT SMI; substantial increases in staff and institutional capacity; funding allocations were surpassed, and a strong legacy exists through PT SMI, energy efficiency scheme and renewables pipeline.
- Successes at PKPPIM included: successful high profile work, small attribution of LCS towards fuel subsidies being removed; improved evidence base for policies; good feedback on the quality of outputs and a general increase in PKPPIM’s capacity.
- The programme could have benefitted from improved clarity on its objectives and theory of change. If the programme is primarily about policy impact, then it might be better located higher in the Ministry.
- The timeframe for the programme was considered unanimously by stakeholders as being too short.
- There was differential success in capacity building at PIP and PKPPIM due to different absorptive capacity.
- The programme was most successful when LCS was totally aligned with PKPPIM and PIP’s objectives.

The programme has contributed to ICF targets on:
- ICF KPI 11 Volume of public finance mobilised for climate change purposes as a result of ICF funding, target been achieved which is $ 300 million allocation for renewable energy and geothermal funds under the Ministry of Finance – Indonesia Investment Agency
- ICF KPI 13 Level of integration of climate change in national planning as a result of ICF support

Monitoring progress throughout the programme

The programme was subject to regular monitoring. On a monthly basis, UKCCU was represented at the Working Committee to review progress and participating in decision making on programme activities. On a quarterly basis, the programme produced an extensive progress report which was presented at quarterly meetings of the Steering Committee for discussion. The programme also produced a separate financial report on a quarterly basis for discussion with UKCCU. The programme was also subject to two annual reviews led by UKCCU.

Financial spot checks by UKCCU were conducted regularly over the project lifetime. In addition, anti-fraud and corruption training was delivered to LCS project team and MoF team by of the UKCCU’s programme management team.

The PCR process

The PCR draws from independent review assessment by ODI, OPML self-assessment, and interviews with Ministry of Finance team members, Kindy Reynaldi (PKPPIM), (Ibu Dian Lestari (PIP) and Puji Harjiman (PIP).

The following key documents related to the LCS programme were also used to prepare this PCR:
- Business case : Quest id 3509050
- Letter of Agreement between Ministry of Finance and UKCCU : Quest id 4399882
- Log frame extension : Quest id 5004087
- Annual review 2014 : Quest id 4339091
- Annual review 2015 : Quest id 4831996
- LCS independent review by ODI : Quest id 5325965
- Asset handover : Quest id 5343816

Annex 1.
Performance against logframe

LOGICAL FRAMEWORK

PROJECT TITLE	LOW CARBON SUPPORT PROGRAMME TO THE MINISTRY OF FINANCE Duration: 25 months (1 March 2013 to 31 March 2015)
Impact	Indicator		Baseline / Jan 2012		Milestone 1 / December 2014			Target / March 2015				Evaluation
Low carbon development is shown to be viable and able to deliver results.	Energy pricing and feed-in tariffs supportive of low carbon investment		Energy/fuel subsidies running at $27 bn per year (2011). / Only feed in tariffs (FiTs) for mini and micro hydro effective.		Subsidies as a percentage of government expenditure reduced by 6%[6] / FiTs for biomass and solar considered effective by investment community			Subsidies as a percentage of government expenditure reduced by 8% / FiTs and or tariff caps for geothermal considered effective by investment community				Fuel subsidies have been reduced to 7% and FiTs available for biomass, solar and geothermal are in place. It is unclear whether the FiTs are considered effective by the investment community. / Many factors were at play in securing these policies. However, a government official stated that the LCS programme did play a role in securing subsidy reductions.
			Source
			Ministry of Energy, Ministry of Finance
	Indicator		Baseline / Jan 2012		Milestone 1 / June 2014			Target / March 2015
	Low carbon fiscal incentives and regulations introduced		Limited		Low carbon fiscal policies announced in government programmes and/or the 2014 Budget[7]			Enhanced measures in place in government programmes and/or the 2015 Budget				Target met. Numerous government low-carbon policy initiatives were implemented between 2013 and 2015: prescribed biofuel blends in retail fuels, vehicle emissions standards, FiTs, energy targets in National Energy Policy, fossil fuel subsidy reform, moratorium on issue of new forest licences, Bappenas green growth roadmap, and the MoF Emissions Budget Tagging and Scoring System, amongst others. / LCS programmes’ influence in securing these low-carbon policies varied.
			Source: Presidential Address on Budget, MoF Budget,

Outcome	Indicator		Baseline / Jan 2012		Milestone 1 / August 2014			Target / March 2015			Assumptions
Supportive environment for low carbon investment established in Indonesia.	New low carbon incentives & regulations introduced and implemented.		Various low level government initiatives		A strategic policy paper on Low Carbon Development[8] / A strategic policy paper on Green Economy/ Green Budgeting			Strategic policy papers are substantially accepted and implemented[9]			MoF able to gain cross government support for new regulations. / Parliament agrees to new regulations	Target exceeded: Strategic policy papers on Green Planning and Budgeting, Sustainable Development of Land Based Sectors, Fiscal Policy Options for the Energy Sector in Support of Indonesia’s Sustainable Development and A Coherent Fiscal Policy Framework for Promoting Renewable Energies and Energy Efficiency were accepted. / The Green Budgeting paper in particular was commended by government officials as having broad and high-level support. Implementation will occur over years. To begin with the Low Emissions Budget Tagging and Scoring System will be piloted by seven ministries beginning in 2015. / Many of the policies outlined in the other papers were also being implemented including the continued moratorium on new forestry licences, minimum biofuel blends, the implementation of the geothermal fund facility, fossil fuel subsidy reform, and the implementation of FiTs.
			Source
			Ministry of Finance, Project reports
	Indicator		Baseline / Jan 2012		Milestone 1 / June 2014			Target / March 2015			Assumptions
	Funds available in PIP for low carbon investment[10]				Low carbon funds total: US$100m			Low carbon funds total: US$200m			MOF does not redirect regular PIP investment away from low carbon sector	Target met: At least US$300 million were allocated to PIP by the MoF for investment in low-carbon development, largely for geothermal. / One interviewee suggested that the work of the LCS programme enabled the Director of PKPPIM to help influence the MoF to allocate the funds.
			Source					RISK RATING
			PIP Accounts, financial returns to MoF, Project progress reports					Medium
INPUTS (£)	DFID (£)		Govt (£)		Other (£)			Total (£)			DFID SHARE (%)
	xxxxx		0		0			xxxxx			100%
INPUTS (HR)	DFID (FTEs) / A2 Adviser – 20% / B1 Programme Manager – 10% / C1 Programme Assistant – 10%

OUTPUT 1	Indicator		Baseline / Jan 2012		Milestone 1 / March 2014			Target / March 2015			Assumptions
High quality technical assistance to the MoF	Evidence papers presented[11] and high level policy seminars		MoF releases very few policy papers		Policy papers: at least 4			Policy papers: at least 8			MoF engages fully with the support team and it quickly establishes its reputation with policy makers in MoF.	Target met: Interviewed officials agreed that the technical assistance provided by the LCS programme was largely of a high standard, though concerns were raised about the quality of a few of the papers. As the total number of papers exceeded the target, we argue that this target has been met.14 policy papers were completed, with 11 accepted by MoF for publication and dissemination.
			Source
			Project reports, Press reports, MoF website
IMPACT WEIGHTING	Indicator		Baseline / Jan 2012		Milestone 1 / June 2014			Target / March 2015
35%	Staff trained through UKCCU support.[12]		Zero		Low carbon training events for PKPPIM, including participants from other parts of MoF: At least 3			Low carbon training events for PKPPIM, including participants from other parts of MoF: / At least 6				Target exceeded: 15 formal domestic training events were held for PKPPIM supporting 381 participates, with average duration of 3 days.
			Source					RISK RATING
			Project reports, Press reports, MoF website, Minutes of Steering Committee.					Medium

OUTPUT 2[13]		Indicator		Baseline / Jan 2012			Milestone 1 / June 2014		Target / March 2015	Assumptions
Wider stakeholder input to MoF low carbon policy making.		Numbers of outreach events		None			Outreach events: At least 2		Outreach events: At least 4	Board is able to attract interest of credible non-government stakeholders.		Output met and targets significantly exceeded. Overall, LCS convened 25 training events supporting 633 participants. / Support was provided to staff in PIP, PKPPIM and other centres in the MoF to attend 10 conferences and forums, 4 international study tours and 4 domestic field visits.
				Source
				Minutes of the Steering Committee.
Impact Weighting				Baseline / Jan 2012			Milestone 1 March 2014		Target / March 2015
15%		Number of publications by PKPPIM and PIP[14]		-			Low carbon development publications: At least 2		Low carbon development publications: At least 4			Target exceeded: 14 policy papers were completed, with 11 accepted by MoF for publication and dissemination.
						RISK RATING
						Medium

OUTPUT 3		Indicator		Baseline / Jan 2012			Milestone 1 / June 2014		Target / March 2015	Assumptions
Low carbon investment objectives fully incorporated into the operations of the Indonesia Investment Authority.		Standard Operating Procedures (SOP) established for low carbon development		None			SOP for mini-hydro sector		SOP for one additional low carbon sector (e.g. energy efficiency, biomass)[15]	PIP staff capacity building programme implemented fully and staff remain in place		Target met: SOP for mini-hydro, geothermal and biomass sectors developed.
				Source
				Project reports
IMPACT WEIGHTING		Indicator		Baseline / Jan 2012		Milestone 1 / Dec 2013			Target / March 2015
50%		Implementation of PIP’s institutional reform and capacity strengthening		-		Legal and institutional review complete and recommendations approved by PIP			Capacity strengthened through 6 training events			Targets met: A legal and institutional review was completed and presented to top PIP management before PIP was absorbed into PT SMI. 10 formal domestic training events were held supporting 252 participants.
				Source					RISK RATING
				Project reports					Medium
[6] i.e. a reduction of 6 percent, not a reduction of 6 percentage points.
[7] Includes all MoF fiscal policies, both those in the Budget (and its revisions) and those outside the Budget.
[8] e.g. energy efficiency or clean energy.
[9] e.g. through new Government Regulations, new MOF Regulations or new budget allocations.
[10] This does not refer to any specific fund (e.g. Indonesia Green Investment Fund) and can include any fund related to low carbon issues.
[11] The choice of which institution/audience to present the papers to (e.g. Parliament) will depend on their content.
[12] The training will be targeted to ensure it is provided to the relevant staff. Recipients of the training may include PKPPIM, other parts of MOF or provincial governments.
[13] Activities under Output 2 should be closely integrated with those under Outputs 1 and 3 and be designed to achieve the objectives of those outputs.
[14] Examples may include, briefing notes, books, CDs, media appearances, pamphlets, brochures, promotional materials etc.
[15] Or a more generic SOP that is suitable for all or most forms of clean energy financing.

Logframe for Extension Phase - Low Carbon Support (LCS) Programme
April December 2015

IMPACT	Impact Indicator 1	Baseline (Apr 2015)	Target (Dec 2015)	Evaluation
Energy subsidies remain at recently reduced levels	Energy subsidies as a percentage of total expenditure	Current energy subsidy is 7% of total expenditure	Energy subsidies remain within (revised) budgeted levels of 7% of total expenditure	Achieved. Energy subsidies remain at 7% of budgeted levels of government expenditure.
Feed in Tariffs remain in place and effective for bio-mass, solar and geothermal energy production	Impact Indicator 2	Baseline (Apr 2015)	Target (Dec 2015)
	Number of FITs in place and effective	Currently three FITs are in place	Three FITs remain in place and effective	Target achieved. All three FiTs remain in place.
Appropriate fiscal policies and incentives introduced for reducing emssions from forestry and land-based sectors	Impact Indicator 3	Baseline (Apr 2015)	Target (Dec 2015)
	Assessment of fiscal policies and incentives in forestry and land-based sectors	Few effective fiscal policies and incentives in place for the forestry and land-based sectors	Progress towards effective fiscal policies and incentives for the forestry and land-based sectors	Target achieved. The MoF Strategy Document on Fiscal Policy Framework for the Sustainable Development of the Land Based Sectors in Indonesia was produced and was reviewed by officials in the Ministries of Finance, Agriculture, and Environment and Forestry. Progress towards the various components of the strategy is at different stages. / The Fiscal Policy Framework for Sustainable Development of Land Based Sectors is in progress.
OUTCOME	Outcome Indicator 1	Baseline (Apr 2015)	Target (Dec 2015)
Improved awareness of low carbon fiscal policies by a wide range of gov’t and other stakeholders	Assessment of awareness of GBP Strategy,Consolidated Energy Paper and Land Use Fiscal Policy Framework	Limited awareness of Green Planning and Budgeting Strategy	Widespread knowledge of at least one of BKF's strategic policy papers	Target reached: Widespread knowledge of the Green Planning and Budgeting document existed through the high profile launch event.
	Outcome Indicator 2	Baseline (Apr 2015)	Target (Dec 2015)
Progress towards implementation of policy recommendations for low carbon development	Number of policy initiatives to promote low carbon development that are approved by the Minister and in process of being made into regulation/implementable policy	Several initiatives have been explored but currently no initiatives are being implemented	One initiative is approved by the Minister and in the process of being made into regulation or policy implementation	Progress was made on a number of fronts. Work towards each of the policy initiatives is ongoing, making assessment difficult. However, given that a ministerial regulation on tax incentives was produced that applies to renewable energy, we judge that both of these targets were met. / See table 1 in the main report for a full breakdown of progress against different policy initiatives.
	Outcome Indicator 3	Baseline (Apr 2015)	Target (Dec 2015)
PKPPIM coordinates with stakeholders in the forestry and land-based sectors and identifies fiscal policies for reducing emissions	Number of recommendations for fiscal policy on forestry/land-based sectors with agreement outside of PKPPIM	Limited knowledge of appropriate fiscal policies in the sector	Broad agreement by key sector stakeholders with policy recommendations	Progress towards this target was made. An event was hosted to socialise the Land Use Fiscal Policy framework paper with 35 participants from a wide range of institutions. Broad agreement on policy recommendations was not achieved. / Despite the work of the LCS programme (discussed in output 3), there seemed to be a lack of understanding within government, both within the MoF and in other ministries, about why fiscal policies are needed in the land-use related sectors. This is the only part of the second log frame where there is little evidence to support that it is fully met.
OUTPUT 1	Output Indicator 1	Baseline (Apr 2015)	Target (Dec 2015)
Approval and dissemination of strategic policy papers by PKPPIM	Number of strategic policy papers on low carbon development approved and launched	One strategic policy paper has been approved, one is a final draft and one is being drafted	At least two strategic policy papers on low carbon development approved and launched	Output achieved: The Green Planning and Budgeting Strategy was approved and launched. / A Consolidated Energy Paper was endorsed and approved for publication and dissemination by PKPPIM.
OUTPUT 2	Output Indicator 2	Baseline (Apr 2015)	Target (Dec 2015)
Achievement of policy initiatives on low carbon development by PIP and PKPPIM	Number of policy initiatives on low carbon development achieved	No loan appraisal processes complete in PIP, limited agreement for implementation on a number of policies	At least one of the policy initiatives on low carbon development achieved (see footnote 2)	Output achieved. See table 1 in the main report for analysis.
OUTPUT 3	Output Indicator 3	Baseline (Apr 2015)	Target (Dec 2015)
Improved dialogue between PKPPIM and other stakeholders in the forestry and land-based sectors	Number of outreach events involving PKPPIM and at least one forestry and land-use sector stakeholder	Limited interaction with MoEF and MoA	At least two outreach events with forestry and land-use sector stakeholders	Target exceeded. At least 13 outreach events were held with forestry and land-use stakeholders. / A training workshop was held with 27 participants from the MoF, Bappenas, the Ministry of Environment and Forestry, and the Ministry of Energy and Mineral Resources on a systems dynamic modelling for policy development in land-based forestry. It was agreed that the model should have a fiscal module to it, allowing simulations of fiscal policy effects.

NOTES
1) This logframe only covers new work under the extension phase. It does not reflect the work required to finalise and disseminate the numerous existing workstreams from the current phase.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process