Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / Programme for the Promotion and Protection of Women and Children’s Rights in Zambia
Programme Value: £2.3m		Review Date: January/February 2015
Programme Code:	Start Date: / 12th March 2013	End Date: / 30th June 2017

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	A	A	A
Risk Rating	Medium	Low	Low

Summary of progress and lessons learnt since last review

The overall progress for 2015 is judged at A. Most targets were met with some exceeding expectations. The programme contributed to policy development thereby strengthening government systems to support and promote gender equality. The Ministry of Gender (MoG) demonstrated good progress in its leadership, coordination and monitoring of actions to improve gender equality, particularly in the implementation of the National Gender Policy. The enactment of the Gender Equity and Equality Bill in December 2015 is a particularly significant achievement which required rigorous consultation with a wide range of government and civil society stakeholders.

MoG has made good progress on its coordinated action to domesticate the Convention on Elimination of all forms of Discrimination Against Women (CEDAW) in a holistic manner. The Kabwe launch of the first ever Fast Track Court on Gender Based Violence (GBV) in Africa was another significant achievement for the MoG. The Rules of Court to assist the implementation of the Fast Track Courts were approved in December 2015.

Good progress has been made on the national strategy to increase women’s representation in decision-making positions. MoG launched the ‘Count-Her-In’ strategy aimed at increasing women’s political representation. However, more work needs to be done on engendering the public service to ensure there is greater female representation at senior levels of the public service.

DFID-funded training and capacity development has generally been well received with positive feedback and some level of improvements has been observed in MoG, notably in the Ministry’s ability to work as a team and improved level of understanding on their role as a ministry. The capacity building that has been funded through the programme has greatly contributed to the acquisition of gender analysis skills among more than 90% of Directors in the MoG and gender focal points in the line ministries. In addition, the Gender Institutional Strengthening Support Project (GISSP) implemented by Volunteers Services Oversees (VSO) has equally greatly contributed to the institutional and capacity development of the MoG in the area of Results Based Management Systems (RBMS), Management Information Systems (MIS), and planning.

MPSAs (Ministries, Provinces and Spending Agencies) are beginning to make budget allocations for gender interventions. However, there are still low levels of funding to these interventions. Furthermore, MoG continues to be underfunded by central government. In 2014 only 26% of the total budget allocation was disbursed to MoG. The 2015 budget saw an increase in the allocation to the MoG but only on one budget line: the Women’s Economic Empowerment Programme. The 2016 budget has also been cut by 25%. With the persistent underfunding, there is a risk that MoG will continue to perceive all the support in the implementation of it’s national policy as separate donor funded programmes. It is also the
view of the review team that the MoG could further improve on targeting the scarce resources towards activities with high impact on gender inequalities.

 With the Ministry being courted by an increasing number of donors to implement programmes e.g. USAID, UNDP, World Bank and UN Women, there is a serious risk that MoG will be overwhelmed, thereby increasing the risk to policy prioritisation and the ability to deliver its existing programmes, including the PPPWCR. The PPPWCR has seen a number of key activities lagging behind. It is recommended that donors take a more coordinated approach in their support to MoG. Support to the performance management system ought to be considered because it can help the ministry to deliver on their mandate better than the case is at the moment.

Summary of recommendations for the next year

1. DFID and UNDP should liaise with other donors supporting MoG to ensure there is a coordinated approach on their support (December 2016).
2. Recommend that indicator 2.1 be replaced by one that is in control of the MoG. DFID will work with MoG and UNDP to revise this (June 2016).
3. As a coordinating Ministry, MoG should conduct annual analysis of budgets and expenditure of line ministries to assess how much is allocated and spent on gender programmes. In addition to the annual analysis, MoG need to have a more robust system to record percentage of budgets allocated against percentage of budget actually expended. This needs to be made easily available (from 2016 Annual Review).
4. MoG should prioritise their engagement with the Ministry of Lands on the land allocation strategy and ensure increased awareness to the public (October 2016).
5. MoG needs to ensure that the design for evaluating the fast track courts is robust and assesses the effectiveness and costs of this approach (December 2016).
6. DFID and UNDP to consider re-aligning its support to increase the number of fast track courts and lobby with MoG for provision of safe houses (October 2016).
7. DFID to revise weightings for all the five output indicators (June 2016).
8. DFID to transform output indicator 2.1 into an outcome indicator (June 2016).
9. DFID and UNDP to include an outcome indicator relating to fast track courts (July 2016)
10. As this is the final year for the GEF where VSO results are reported, there is need to include an output indicator on VSO’s work. DFID and VSO to agree an output indicator for VSO (April 2016).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

DFID is providing £2,337,500 over four years (2013-2017) to strengthen the capacity of MoG through funding for the Ministry’s Programme for Promotion and Protection of Women and Children’s Rights (PPPWCR) and flexible technical assistance. This program builds on previous initiatives on gender and child development implemented by MoG in collaboration with civil society organizations and cooperating partners. DFID funding is managed by UNDP, who also provide technical and advisory support.

MoG is expected to deliver effective leadership, coordination and monitoring of action on gender equality; support to priority ministries to implement gender-responsive planning and budgeting; coordinated action to domesticate the Convention on Elimination of all forms of Discrimination Against Women (CEDAW) and implement the Anti-Gender Based Violence (GBV) Act; a national communication strategy to promote positive gender norms and increase awareness of laws and policies; and a national strategy to increase women’s representation in decision-making positions.
There are three programme components which are:

The direct support for the implementation of the PPPWCR.

Gender Equality Fund (GEF) - technical assistance for training and capacity building of MoG’s staff, Committee of Permanent Secretaries and gender focal points from the line ministries.
Under the GEF, there are three strands which are:
- gender analysis skills by JIMAT,
- Strategic leadership development & team building by Presencing Institute and
- mentoring and coaching system for the MoG leadership by FABULA and all contracts are managed by the MoG.

The Gender Institutional Strengthening Support Project (GISSP) is the second aspect of capacity building programmes and is implemented through the Volunteers Services Oversees (VSO) through an Accountable Grant. VSO has placed three volunteers at MOG who work alongside Ministry staff in order to build their capacity in the three areas mentioned below:
- Results Based Management Systems (RBMS);
- Management Information Systems (MIS); and
- Planning.

The objective of GISSP is to build systems and capacity that will support MoG to implement its core mandate that is to plan, coordinate, budget and monitor and evaluate the gender and child development policies and programmes. Through GISSP, the Ministry is expected to have a structure that ensures gender responsiveness, coherence and coordination within the ministry itself and across relevant sectors.

The main programme assumption is that if the laws which provide equal rights for women and men are implemented and enforced, and the social norms are changed, this will increase women’s voices and influence. In turn, it will reduce gender inequality by providing an enabling environment for the legal, political, economic and social empowerment of women in Zambia.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome: Enabling environment for legal, political, economic and social empowerment of women
Indicators	Milestone 2014 (March)	Milestone 2015 (March)	Milestone 2016 (March)	Progress
1.1 Number of laws revised to conform to CEDAW provisions	1	2	1	On track-Constitution articles 8,9 & 231 outlines the values and principles of gender equality was signed, Gender Equity and Equality Bill was passed by Parliament.
1.2. % newly allocated state land allocated to women	20%	28.3%	30%	On track- Based on data from Ministry of Lands, 29% of newly allocated state land was allocated to women in 2015.
1.3. % women in decision-making positions in the civil service	PS: 22%; Director: 25%; Deputy Director: 45%	PS / Directors / No milestone	PS 24%: Director 35% : Dep Director 45%	Off track- PS 28%: / Director 30% :Dep Director 28%

The theory of change assumes that action in a number of areas (social, legal, economic and political) will result in a more enabling environment for the empowerment of women and girls. For this to occur, building sustainable institutional capacity is critical since only government can bring about the policy and legislative change to address structural barriers to gender equality and ensure that sector ministries deliver gender responsive programmes.

Although there are a number of external and internal challenges to the achievement of the outcome, it is expected that the programme will strengthen the enabling environment for the empowerment of women and girls, thus achieving its outcome. The Strategic training and capacity building of the Ministry is a key underlying factor for this overall outcome achievement and it is encouraging that the Ministry has embraced the training under the Gender Equality Fund and the Gender Institutional Strengthening Support Project. The work of the Committee of Permanent Secretaries is also a good indicator that government is taking the necessary steps to improve the enabling environment for women and girls.

Moreover, the PPPWCR has contributed to strengthening the enabling environment for the legal, political, economic and social empowerment. This is evidenced by the improvement in the Gender Inequality Index (GII) which has fallen from 0.752 in 2012 when the programme commenced to 0.617 in 2014. This is an indication that the status of women has improved, in the three dimensions that are used to measure the GII, during the period of implementation of the PPPWCR. There was also an increase in the number of female MPs from 11.4 percent in 2011 to 13.3 percent in 2014 and 14.5% (23 female MPs) in 2015 (Electoral Commission of Zambia).

There are three outcome indicators, two of which are on track. One is slightly off track.

Outcome indicator 1.1 is on track: There has been remarkable progress with efforts to ensure that legal frameworks are in place that conform to CEDAW and Convention on the Rights of the Child (CRC) provisions.

The Gender Equity and Equality Bill, which encapsulates key issues from CEDAW and the SADC Protocol on Gender and Development, was passed by Parliament and is awaiting enactment by the President. MoG has also drafted the Child’s Rights Code Bill (CRC) which aims to domesticate the CRC provisions in their entirety. The CRC bill is currently being circulated in ministries for comments after which it will be tabled for consideration by Cabinet. Once approved, it will be taken through the process of enactment.

Outcome 1.2: This is on track, in 2014, the Ministry of Lands directed land agencies, particularly local councils, to give 30% of newly allocated land to women. In 2015, the Minister of Lands declared that this increases to 40%. Based on data from Ministry of Lands, 29% of newly allocated state land was allocated to women in 2015. Traditional leaders have also increasingly been allocating land to women. Examples of these leaders include: Zumwanda in Lundazi, Nyamphande in Petauke, Simwatachela in Zimba, Chama and Mushota in Kawambwa. However, there is still a case for stronger awareness raising of this policy, including monitoring its implementation.

Outcome indicator 1.3: Current data for this was unavailable at the time of the annual review.

Overall output score and description

Key lessons

- Non accountability of performance on certain programme components inevitably makes some staff members less committed to their responsibilities. Implementing a performance assessment system would help the MoG staff to be accountable. We were informed of recent changes in performance appraisals for the Permanent Secretaries which will also be pushed down to the Directors and staff. We will watch closely to see if these changes impact on MoG’s work.
- Prior engagement of Members of Parliament (MPs) before legislation goes to Parliament for debating is vital. The extensive sensitising of legislators before the presentation of the Gender Equity and Equality Bill was a catalyst for the smooth passing of the bill to domesticate the CEDAW.
- Implementation of the 2015 workplan was delayed and certain activities for 2015 started slowly. Delivery has since improved and has yielded some substantive results that will contribute to the goal of attaining gender equality in Zambia. The MoG coordinated the implementation of activities with other institutions and was able to deliver despite the slow start.

- Splitting of line ministries could have a negative effect on programme implementation if not done well. The shifting of the Child Department to the Ministry of Youth and Sport affect some programme activities. For example, the MoG no longer has a presence at provincial level. Provincial Child Officers who were implementers at the provincial level have moved with the Child Department to Ministry of Youth and Sports. MoG will need to think through how to increase its outreach to the provinces .
- President Lungu has shown a high level of political will to mainstreaming gender as evidenced by the inclusion of a gender mainstreaming objective in the new job description for all Permanent Secretaries. MoG should take full advantage of this development to ensure implementation of gender equality commitments.
- Progress on increasing women’s access to land is being made albeit slowly. There is a need to intensify efforts to review and strenghthen the administrative process at the Ministry of lands and the District Councils to facilitate easy issuance of title deeds to women.
- Increasing the number of women in the civil service in decision making positions will take longer and requires society and high level political buy-in.

Key actions

- MoG to prioritise the National Gender Perception Survey and ensure that it is conducted by March 2016.
- MoG should therefore produce the Gender Status Report by March 2016 as it provides information on Gender equality status. If the battle on gender equality is to be won, policy and research work at national level should be conducted and results disseminated on time to the key stakeholders.

Has the logframe been updated since the last review?

Yes – changes are as follows:
- The indicators were initially set up to March 2016 but, following consultation with MoG, Output indicators for 2017 have been included to align the programme with its end date.
- The 2014/15 Annual Review recommended that Outcome 1.4 be turned into impact indicator. This is now impact indicator 2. The rationale for the change is that achievement of the indicator is dependent on a large range of factors, which are mostly outside the control of MGCD.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	MGCD delivers effective leadership, coordination and monitoring of action to improve gender equality
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones / March 2016	Progress

1.1 Number of functional working groups for coordinating gender programmes and strategies that include all relevant stakeholders including civil society other line ministries, traditional leaders	All 7 committees are set up and met at least twice in past year	Exceeded: 11 groups all of which have met at least twice in the past year.[1]
1.2 National gender M&E plan and system established and implemented	15 (or 80%) MPSA-Ministries, provinces and spending agencies submit data on core indicators in the national M&E plan	Exceeded: 19- Education,Health,Community Development, Gender, Transport, Communications, Lands,Local Govt, Labour, Commerce, Agriculture, Livestock, Justice,Mines,Chiefs and Traditional Affairs,Home Affairs,CSO,Parliament and PSMD.
1.3 Annual publication and dissemination of National Gender Status Report	2014 report produced and disseminated to key stakeholders	Partially achieved: It was agreed at the 2014 Annual review that the 2012 - 2014 data be combined and the resulting status disseminated. The report has been finalised and is therefore yet to be disseminated by March 2016.
1.4 Gender Equality Fund used for training and capacity building of MoG and gender focal points	Gender Equality Fund used to develop capacity of gender focal points (i.e. Directors of Planning) in priority line ministries and 70% of gender analysts and directors in MoG trained	Achieved: The Gender Equality Fund has been used to train more than 90% of Directors, Assistant Directors and gender analysts for MoG and gender focal points for line ministries, District Commisioners, Provincial Development Officers and Permament Secretaries from the line ministries.
[1] Gender Status Forum 2).PITC meetings quarterly 3).Social Protection Group 4).Ministry of Lands Taskforce 5).Anti GBV Forum 6).Committee of PSs 7).Committee on Gender statistics coordinated by Central Statistical Office 8).Zambia Police Men’s Network on Gender and GBV 9).Coordination meetings with Ministry of Gender and Ministry of Finance on Planning and budgeting 10).Inter-ministerial committee on Women empowerment under the Advance Project involving 6 ministries meeting monthly. 11).Interministerial Committee on Girls Education, Women Empowerment and livelihoods (GEWEAL), comprising three ministries: Gender, Education and Community Development) meeting fortnightly.

The outputs moderately exceeded expectation.

Achievements
- The 11 functional groups for coordinating gender programmes and strategies have been established, up from seven (target) in 2014. All the groups met at least twice and in line with the set target.
- 19 MPSAs have submitted data on core indicators for the national M&E plan against a target of 15. This data is critical for the mainstreaming of gender in all the MPSAs to be monitored through a central Gender Information Management System (GMIS). The GMIS is expected to be functional during the course of 2016.
- Capacity development has been well received by both MoG and line ministries. The capacity building has greatly contributed to the acquisition of gender analysis skills among more than 90% of gender analysts and Directors in the MoG and other line ministries. It has further enhanced coordination among key stakeholders and created an environment conducive to the implementation of the programme.
- The VSO component faced delays at inception due to delays in recruiting experts and also lack of local staff to implement activities at MoG. To mitigate this, an adjustment was made to the work plan and VSO are now on course. According to VSO, MoG has changed into a positive place to implement this project in comparison to last year. This is due to a combination of factors including the fact that MoG has employed a few staff to help implement their objectives.
- The project has also greatly contributed on the capacity development for MoG in RBMS, MIS and Planning. The M&E (Monitoring and Evaluation) key indicators and planning framework for MoG were developed. On MIS, an assessment of the suitability of the hardware architecture to support the planned M&E system and planning functions was undertaken.

Challenges
- The Gender Status Report is an important document as it provides strategic information on the status of gender equality in Zambia at a glance and needs to be produced in a timely manner. The 2014 Annual Review recommended that three Gender Status Reports for 2012 to 2014 be combined, finalised and disseminated (indicator 1.3). The report has been finalised, validation meeting with stakeholders and is therefore yet to be disseminated by March 2016.
- For capacity building, two of the three strands whose sessions are hosted at external venues (gender analysis skills and strategic leadership development & team building) are on track and early impacts are becoming noticeable. However, the coaching strand for senior management has however dragged with only two people out of a possible six having requested for a coaching session once. The GEF ends in April 2016.

Recommendations
MoG should work at producing the Gender Status report on time as it provides important information on the status of gender equality in the country and ensure the 2012 to 2014 report is finalised by March 2016.
- MoG needs to continue to have close communication and coordination with MPSAs and key stakeholders.
- DFID and UNDP to revise the definition of indicator 1.1 to make it more pointed.
- As this is the final year for the GEF where VSO results are reported, there is need to include an output indicator on VSO’s work. DFID and VSO to agree an output indicator for VSO.

Summary of responses to issues raised in previous annual reviews (where relevant) / Gender Focal Points especially those in planning have been trained in gender responsive planning and budgeting. / Status: Training was conducted / Ministry of Gender yet to establish electronic database of Gender Focal Points before end of 2016. / Status: Work in progress and data collection has started / MoG to meet with GFPs at least once a year. / Status:This was done

Output Title	Priority line ministries implement gender - responsive policies, planning and budgeting
Output number per LF		2	Output Score	A+
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones / March 2016	Progress

2.1. Priority ministries demonstrating increased gender planning	Budget releases match allocations in priority ministries[2]	Partially Achieved: All priority ministries have received funds from the treasury on gender activities, although budget allocations and releases are sometimes not matched.
2.2. number of line ministries that have operationalised gender-responsive budgeting tools	(15) of Line Ministries have operationalised gender responsive budgeting tools	Exceeded: 17 line ministries[3] have gender-responsive budgets.
2.3. % (number of line ministries) reflecting expenditures on gender programmes	55% (12) line ministries	Exceeded: – 17(77%) line ministries and some spending agencies have reflected budgets on gender activities.
[2] Priority Ministries: Lands, Education, Health and Agriculture
[3] Ministries Agriculture ,Health, Community Development, Lands, Higher Education, General Education, Home Affairs, Commerce, Labour, Foreign Affairs, Chiefs, Justice, Mines, Finance, Fisheries & Livestock and Youth and Sports.

The outputs moderately exceeded expectation.

Achievements

- Under indicator 2.1, four priority ministries undertook gender responsive planning and budgeting.
- MoG developed guidelines on gender responsive planning and budgeting and convened meetings to orient line ministries and provincial Gender Focal Points (indicator 2.2). 17 out of the targeted 15 line ministries can now prepare gender responsive budgets. In addition, meetings have been held with the Committee of Permanent Secretaries led by the Secretary to Cabinet to orient them on gender-responsive budgeting.
- The new performance management system for Permanent Secretaries which has a gender mainstreaming objective provides a good opportunity to institutionalise the prioritisation of gender and equity issues. If implemented, it will ensure that gender is integrated in planning and budgeting process and Permanent Secretaries will be required to report against it.
- On indicator 2.3, 17 line ministries have expended budgets on gender activities according to discussions with MoG. This indicator was exceeded.

Challenge
Even though ministries may have prepared gender responsive budgets, there is a general mismatch between budget lines and the resources received from government. In 2016, ministries received even less allocations, at 40-50% of what they had budgeted (according to discussions with MoG). In addition, there is still a challenge of conceptualizing gender and its implications on resource allocation in the various MPSAs. This output is however outside the control of the MoG or indeed any of the service providers

Recommendations
- DFID to transform Output indicator 2.1 into an Outcome indicator by June 2016.
- As a coordinating Ministry, MoG should conduct annual analysis of budget and expenditure of line ministries to assess how much of the national budget is allocated and spent on gender programmes. In addition to the annual analysis, MoG need to have a more robust system to record percentage of budgets allocated against what is actually expended. This needs to be made easily available.

Summary of responses to issues raised in previous annual reviews (where relevant)

MoG and MoF need to work together to develop clear, practical guidelines for line ministries on how to do gender-responsive planning and budgeting, and to ensure that gender is addressed in MoF guidelines for output-based budgeting and the draft bill. / Status: Guidelines have been drafted and yet to be disseminated / MoG needs a clear plan for influencing and training line ministries in gender-responsive planning and budgeting. This should include a meeting or workshop to sensitise Permanent Secretaries, capacity development for line ministry Directors of Planning and Gender Focal Points, and capacity development for the MoG’s own staff in gender-responsive planning and budgeting. / Status: Trainings have taken place.

Output Title	Co-ordinated action to domensticate CEDAW and implement the Anti-GBV Act
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones / March 2016	Progress

3.1 Strategy to review and revise constitution and laws to confirm to CEDAW provisions developed	Legislation passed by National Assembly	Achieved: Constitution was signed , Labour Act came into force and the Gender Equity and Equality Bill has been enacted by Parliament and waiting consent by the President by end of first quarter of 2016.
3.2. % (number) of traditional leaders trained in CEDAW provisions and the Anti-GBV Act	30% (69) traditional leaders trained	Exceeded (69%)156 traditional leaders trained in CEDAW provisions and the Anti GBV Act. These trainings were conducted jointly with other similar trainings and sensitizations across the programmes in the MoG such as the HeForShe and the Joint Programme on Gender Based Violence.
3.3 (Number) of fast track courts for cases of GBV pilot implemented	2 Fast track court implemented	Achieved: The first ever fast track court in Africa was launched in Kabwe January 2016. The second one will launched in Lusaka in March 2016.
3.4 Strategy implemented to increase women’s land ownership	Awarness campaign launched to promote the new strategy	Not achieved: Awareness campaign on to to promote women’s land ownership will be implemented after the new National Land Policy is finalise by October 2016.

Overall, this output has met expectation.

Achievements
- The most notable achievement is the signing of the Constitution and the Labour Act . Articles 8, 9 & 231 of the new Constitution outlines the values and principles of gender equality. Another notable achievement was the passing of the Gender Equity and Equality Bill by parliament. MoG played an important role in coordinating the process, sensitising and lobbying parliamentarians before the Gender Equity and Equality Bill was tabled in parliament.
- MoG has improved collaboration on their work with traditional leaders on CEDAW provisions and the Anti-GBV Act. Coordination of donor support has proved to be a cost effective and efficient way of implementing the programme.
- The first ever fast track court dealing with Gender Based Violence cases in Africa was launched in Kabwe in January 2016 and was officiated by the Chief Justice. The second one is expected to be launched in Lusaka in March 2016. Fast Track Courts are aimed at speeding up hearing of GBV cases. This should not only reduce the possibility of victims being pressurised to drop cases or witnesses to withdraw, but will also reduce the time in detention of those accused of committing these crimes but whose cases have taken too long to come to court.

Challenges
- Fast track courts are currently lacking safe houses for survivors required during the legal process to house victims.
- MoG was unable to launch awareness campaigns aimed at promoting the new strategy of 40% land allocation to women and titling of such land. This was due to the National Land policy which has not yet been finalised by Ministry of Lands. Awareness raising is important given the existing challenge of low numbers of women accessing title deeds even after allocation of land has taken place.

Recommendations

MoG to prioritise its engagement with Ministry of lands on the land allocation strategy and ensure increased awareness to the public.
- MoG needs to ensure that the design for evaluating the fast track courts is robust and that it assesses the effectiveness and costs of this approach.
- DFID should consider re-aligning it’s support from the components which are underspending to increasing the number of Fast Track Courts for Gender Based Violence cases in other provinces in Zambia and also lobby for MoG to increase the fast track courts and provide safe houses to protect GBV survivors during the legal process.
- DFID and UNDP to include an outcome indicator relating to fast track courts
- DFID and UNDP to to revise 2016 milestone on the logframe to reflect increased support to the fast track courts
Summary of responses to issues raised in previous annual reviews (where relevant)

MoG needs to ensure that the design for evaluating the fast track courts is robust and assesses the effectiveness and costs of this approach (May 2015). / Status: Work in progress on the evaluation mechanism. / MOG should work with the MOCTA to clarify respective roles and responsibilities and ensure that training for traditional chiefs is well planned and coordinated (Sept 2015). / Status: Plans underway to discuss respective roles and responsibilities. This was discussed at the December 2015 quarterly meeting and a representative from MoCTA offered to help in facilitating this arrangement. / MOG should work with their Communications department to ensure increased public awareness on women’s land ownership issues (Dec 2015). / Status: Not done as MoG awaits finalisation of the new National Land Policy by Ministry of Lands / MOG to incorporate into their strategy some actions aimed at increasing women’s acquisition of land titles (Dec 2015). / Status: Not done because the communication strategy has not been evaluated yet.

Output Title	Communication Strategy promotes positive gender norms and increased awareness of laws
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones / March 2016	Progress

4.1 Number of radio programmes produced on community and commercial radio stations (cumulative)	300	Exceeded: 509 radio programmes on gender, GBV, women and child issues have been jointly aired so far, with the Joint Programme on GBV and HeForShe Campaign. DFID contribution is 50%.
4.2 Number of TV programmes on gender equality produced / and aired (cumulative)	100	Achieved: 101 Programmes have been aired on 4 TV stations(ZNBC,MUVI TV,Chipata TV & Northwest TV)
4.3. Number of journalists trained in gender/child responsive reporting (per annum)	20	On track: Training of 25 journalists will take place in early March 2016.
4.4 Film dealing with gender equality issues produced and aired
4.5 National Gender Perception Surveys conducted and disseminated and feed into gender strategy	2015 NGPS published	Not achieved: Preparations for the National Gender Perception Survey have commenced but will be completed by June 2016.

This output met expectation.

Achievements

- MoG has shown leadership by collaborating communication activities with other programmes like Joint GBV and HeForShe Campaign supported by other donors.
- Training of journalists is scheduled to take place in early March 2016 and all is in place for that, MoG has also been able to secure a journalist from a local daily newspaper (Daily Mail) to sit as a desk officer in the MoG to ensure sufficient media publicity on gender. There has been an increase in the publicity on gender issues as a result.

Challenges
- There have been significant delays in procuring the service provider to undertake an evaluation of the communication strategy. The evaluation would enhance activities under 4.1, 4.2. and 4.3 (although 4.2 was achieved due to collaboration with programmes supported by other donors). There was insufficient prioritisation of this activity within the Ministry.
- There were delays in carrying out the National Gender Perception Survey but preparations are now underway. MoG has signed a contract with the University of Zambia’s Institute of Economic and Social Research in collaboration with Central Statistical Office. The activity is expected to be completed by June 2016.

Recommendation
MoG should also prioritise the National Gender Perception Survey and ensure that it is conducted by June 2016.

Summary of responses to issues raised in previous annual reviews (where relevant) / MoG needs to take a more strategic approach to communication and use of media to promote positive gender norms and increase awareness of laws and policies. This should be reflected in a revised strategy (October 2015). / Status: Not done as the evaluation of the communication strategy is still at the procurement stage. / MoG needs a communication strategy that goes beyond use of media to include community approaches. Partnerships with district gender sub-committees and CSOs would enable the MoG to reinforce media activities. MoG should take forward plans for more road shows, but ensure that these are monitored and evaluated. / Status: Not done, this will be informed by the evaluation of the communication strategy / MoG communication strategy in 2015 should include evaluation of the audience, reach and impact of media activities and include a follow up National Gender Perception Survey. (Nov 2015) / Status: Both the Evaluation of Communication strategy and National Gender Perception Survey have not been conducted but will be done by April 2016. / The planned evaluation of the Communications Strategy should focus on how social norm change can be effectively achieved through media. / Status: Not done, to be conducted in 2016.

Output Title	Strategy to increase women’s representation in decision making positions implemented
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones / March 2016	Progress

5.1 Committee of Permanent Secretaries implementing the strategy	Action plan with priority issues to be mainstreamed developed	Achieved: Action plan with priority issues to be mainstreamed developed.
5.2 Number of parliamentarians sensitised on the 50/50 SADC Protocol (cumulative)	100 cumulative	Exceeded: 143 Parliamentarians (23 female and 120 male) have been sensitised on the 50/50 SADC Protocol.
5.3 Campaign to increase votes for women takes place	Launch the 2016 vote for women campaign & implementation of some key activities	Achieved: Count Her In Strategy was lauched in collaboration with various civil society organisations (Women in Law in Sothern Africa, Women’s lobby Group, Zambia Women in Media, FODEP) and political party representatives.

The output met expectation.

Achievements
- The action plan on gender mainstreaming was developed and the Committee of Permanent Secretaries agreed seven priorities to mainstream in their respective ministries. (Quest 5334345)
- On indicator 5.2, 143 parliamentarians have been sensitised on the 50/50 SADC Protocol against a target of 100. The sensitisation of MPs on the Gender Equity and Equality Bill played a big role in achieving this milestone.
- MoG - in collaboration with the various Civil Society Organisations and representatives from five political parties - launched the 2016 Count-Her-In Campaign Strategy. This Strategy is a multi-sectoral campaign by the women’s movement aimed at mobilising women and resources for the 2016 Tripartite Elections. If implemented, the August 2016 Tripartite Elections will see at least 50 percent female candidates successfully contesting and at least 30 percent women occupying elective positions post elections.
- One of the key activities under Output 5.3 was the National Conference which was held in January 2016 with a theme “putting women at the centre of 2016 tripartite elections”. The conference attracted national executive members (the highest organ in political parties) from ten political parties. An action plan on how political parties will ensure more women are adopted was agreed.

Challenge
Although the Count-Her-In Strategy is progressing well on the political front, MoG still needs to lobby on appointing more women in decision making position within the civil service.

Recommendation

- MoG should monitor the progress on the action plan to mainstream gender in the line ministries.
- DFID and UNDP to revise the 2016 milestone for indicator 5.2 and include a survey which will bring out the difference the sensitisation of MPs made to the passing of the Gender Equity and Equality Act by Parliament.

Summary of responses to issues raised in previous annual reviews (where relevant)
MOG needs to finalise the Count Her In campaign strategy, including identifying clear timeframes and roles and responsibilities for different partners in delivering the strategy, and ensure that there are regular meetings of all partners to coordinate activities and review progress (April 2015). / Status: Count-Her-In campaign strategy was finalised, printed and disseminated and implementation is in progress.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Support to MoG and Gender Equality fund Component (£256,268)
Key costs	% expenditure	Cost Drivers	Actions to manage them
Consultancy costs- capacity building	27%	Consultancy fees and international travel	Consultancy fees have been reduced by encouraging ministry staff to undertake gender related work which was done by consultants in the past. / The length of trainings and consultative meetings has also been reduced to lessen the cost.
Training Costs	24%	Local travel, accommodation meals and allowances	For allowances, UNDP only approves the use of government rates for local travel (which are lower than UN rates). / For international travel, UN rates (which is lower than Government rates) are used. / For a residential meeting/training, full board is provided and a payment of out of pocket allowance is made to the participant, which is 20% of the daily subsistence allowance rate.
Media costs	20.20%	Community Theatre, Printing Radio and TV programmes	MoG’s has shown leadership in combining communication activities from different programmes it implements which has proved to be cost effective.

VSO Component (£18,789)
Key costs	% expe- / nditure	Cost Drivers	Actions to manage them
Programme costs	53%	Selection, training (pre and post departure), travel, accommodation, planning and review visits.	Volunteer allowances are below the daily living rate and have been revised upwards. We therfore expect an increase on programme costs but the returns will also be high because of in-house expertise which is growing.
7Admin cost	38%	Procurement and office support costs	This cost is high due to a six months delay in the late implementation of the programme which consequently increased the percentage proportion of overhead costs.We expect this percentage to reduce in the second year of implementation..

VfM performance compared to the original VfM proposition in the Business Case
The Business Case noted that evidence was incomplete over which interventions addressing the gender-specific dimensions of poverty deliver the best VfM. However, in 2014, a VfM framework was developed which is used to assess the VfM measures proposed in the Business Case (Quest 5330010). This includes indicators on the Es Economy, Efficiency, Effectiveness. The programme is performing quite well on the economy indicators of the VfM framework although there is need to strengthen the efficiency and effectiveness indicators.
Economy – For consultancy on trainings, the rates are high but the trainings are high quality trainings. For the cost of training i.e. venue, accommodation and meals, steps have been taken by conducting these from Lusaka. The Unit costs per person trained in 2015 is at £714 compared to 2014 at £764. The costs of consultancy on trainings are however expected to reduce in 2016 as this is the last year for the GEF.
Admin costs for the programme as a whole stood at 11% which is a significant reduction compared to 2014 when it was at 17.8%. As noted in last year’s annual review admin costs have reduced because there were no substantial procurements undertaken in this year.
Training for capacity building comprises the majority of spend: combined consultancy and other training costs comprise 51% of the budget:

Consultancy fees: At 27% of the year’s expenditure, consultancy costs have risen by 11% over the 2014 level. The reason for the rise is due to the high number of capacity building trainings undertaken in the year under review. This was aimed at increasing gender related skills which are vital to the MoG and line ministries. We do not anticipate these to rise further as the trainings will be ending in March 2016 and general consultancy of the programme will reduce. However there has been a significant reduction in the number of consultants hired by the Ministry to undertake gender related work .

Training costs: these include costs for training venues, participants’ accommodation, allowances and transport. Beneficiaries are the MoG, line ministries and district staff and obtain gender related skills such as gender budgeting and policy influencing. The costs stood at 24% in 2015 compared to 16% in 2014 – of total expenditure. These costs are equally expected to be minimal going forward given the reasons mentioned above.

Media/communication costs: spending on media activities is aimed at raising gender awareness among the Zambian public. Activities include television and radio programmes. In 2015, media costs nearly doubled from 11% the previous year.

For the VSO component, the programme costs stand at 53% (£9,990) and Admin cost at 38% (£7,114). The admin cost is high because VSO component faced delays at inception due to delays in arrival of the experts and also lack of staff to implement activities at MoG. There was about six months delay in the placement of experts but the other admin costs were charged because recruitment and placement procedures were in process and so the programme was only spending on the admin side of it. We do not anticipate the admin cost to rise further because volunteers have been placed and implementation is on course.

Efficiency – Results are satisfactory relative to overall costs to DFID. Anecdotal evidence shows that these interventions appear to be effective. The programme was designed carefully so that activities within the same output area reinforced each other e.g. media activities. TA costs for training and capacity development are relatively high but the quality of output is also high and is beginning to demonstrate results. The disbursement against work plans in this year has not been good but most activities were completed due to the collaboration of activities with other programmes. This programme has attracted a number of donors to MoG who are supporting various programmes. We therefore recommend that DFID reduces support to the implementation of general activities and re-direct these resources to other areas in the MoG lacking support e.g. the roll out of fast track courts.

Effectiveness –. Overall, the programme has contributed to its intended outcome to “promote gender equality.” The programme contributed to the policy development thereby strengthening government systems to support and promote gender equality. For instance, the enactment of the Gender Equity and Equality Bill, domestication of CEDAW, implementing the Anti-GBV Act and establishment of fast track courts.

The programme has also been effective in building the capacity of government institutions through contribution of critical gender skills in gender mainstreaming, gender responsive planning and budgeting.
The level of awareness, knowledge and change in attitudes surrounding gender equity has improved and MPSAs are beginning to make budget allocations for gender interventions.
As a result of DFID’s supported capacity building and institutional strengthening, MoG’s capacity and that of relevant line ministries has improved greatly. The programmes continue to show value for money because the officers attending strategic capacity building activities are slowly starting to demonstrate improvements in their performance and knowledge of gender, though change of attitudes and adoption of new practices is still a challenge.

Equity- This programme is aimed at gender equity and equality and this measure is embedded in the programme.

Assessment of whether the programme continues to represent value for money
The expected results of the programme – reduced gender inequality in Zambia through empowerment of women and girls and improved legislation on gender equality and gender based violence - still justify the costs of the programme. The programme has continued to produce desired results even in the face of underspends on the DFID budget lines. We therefore recommend a realignment of the budget to the MoG in the 2016 budget and re-direct funds to fast track courts. This will improve impacts of the programme and VfM as gender related cases will be disposed off quickly. Because there will be evidence of negative sanctions on perpetrators of gender based violence, this has potential to act as a deterrent to potential perpetrators - the demonstration effect.

Summary of responses to issues raised in previous annual reviews
As the programme is in the 2nd year of implementation, MoG to reduce on conference services and focus more on programme implementation (ongoing) / Status: Conference and training services continued to be high in the past year due to the need for building the capacity of the MoG in particular. In the past a recommendation on the use of in-house conference rooms was given to MoG but this has meant that attendance is then usually very low. Support to training is reducing over the next year however. / MoG and UNDP to adhere to paying all DSAs from the GRZ funds. (March 2015). / Status: This was complied with on the programme activities. For the Gender Equality Fund, it was not complied with as it was an added cost to the Ministry which was not initially planned for. Again, this expenditure will now reduce as the training component is reduced. / VfM framework should be updated and establish the main unit costs and ensure they are reasonable and represent VfM.(June 2015). / Status: The VfM framework has been periodically updated, although not all unit costs are calculated. There is a need to include more efficiency and effectiveness indicators. / The training and capacity development programme DFID has embarked on with the MoG in both planning and gender analysis should address some of these internal risks, including weak performance, capacity and skills. MOG and UNDP need to monitor risks and develop a plan for risk management and mitigation (October 2015). / Status: The risk management plan was developed and shared agreed by MoG. Capacity building programme provided under the Gender Equality Fund is addressing the capacity and skills issues and progress is showing. / There is need to conduct a more rigorous assessment of the impact of trainings, including / training and capacity building activities implemented through the DFID-funded Gender Equality Fund. (October 2015). / Status: Not done due to the trainings which started late, however the capacity building will be evaluated together with the end of programme evaluation. / Communications activities in particular radio and TV shows needs further assessment, using listenership surveys and other tools to ascertain coverage and a better estimate of unit costs (Nov 2015) / Status: Not done - to be captured in the Perception Survey to be completed by June 2016. / UNDP and MOG need to identify how the expenditure approval process can be made more efficient. / Status: Done and in addition, UNDP has provided a capacity training on UNDP financial regulations and procurement procedures.

Recommendation
- DFID to reduce support to the implementation of general activities and re-align the support to other areas which still sit under the MoG but are lacking support e.g. fast track courts.
- DFID and UNDP to ensure that the end term review of the programme should include an assessment of the impact of capacity building activities implemented through the DFID-funded Gender Equality Fund.
- UNDP to propose additional indicators to Efficiency and Effectiveness in the VfM framework.
- Communications and media activities, in particular radio and TV shows needs further assessment to ascertain coverage and a better estimate of unit costs.

Quality of financial management:
Annual funding to UNDP is split in two tranches (March and September) to avoid payment in advance of need. For the year 2015/16, the programme has underspent. Forecast for the year was £534,909 but only (69%) £374,111 was disbursed. From the disbursed amount only 41% (£154,777) has been spent leaving a 59% under-spend.

The underspend has mainly been due to some key activities of communications which were not done but also because the MoG created synergies with the other programmes they implements and supported by other donors.

The risk of funds not being used as intended is considered low as the implementing partner (UNDP) has in place sound financial management systems.

For the VSO component, payments are made on a quarterly but reimbursable basis. Forecast for the year was £53,492 but only (35%) £18,789 has been spent. The under-spend on this component is due to implementation delay of six months which the programme experienced.

Date of last narrative financial report	UNDP-December 2015 / VSO-December 2015
Date of last audited annual statement	UNDP -not required, only annual certified report which is due in June 2015. Quest 5071718 / VSO- Annual Audited Statement is due on 30th Septemebr 2016

E: RISK (½ page)
Overall risk rating: Low/Medium/High
  The overall assessment of programme risk is low.

Overview of programme risk:
Risk	Description & Triggers	Mitigation Actions (i.e. treat or tolerate)	Residual Risk		Trend
			Probability	Impact	Dec-15
1 . MoG lacks gender analytical capacity and skills despite restructuring and expansion of staffing and inadequate M&E skills for monitoring progresss towards gender equality.	MoG staff lack capacity and gender expertise which might affect delivery of gender equity work and the lack of an operational M&E system may affect implementation, achievement of results and strategies.	DFID support for various quality TA to the MoG of which initial TA interventions appear to be effective. DFID hasl supported VSO to provide in-house capacity building staff. The MoG has also employed a number of staff including some decicated staff for M&E and planning in 2015.	Low	Low	Reducing
					Progress is slowly showing in MoG's gender capacity. The provision of volunteers by VSO to work alongside MoG staff is a real opprotunity for improved M&E skills.
2. Behavioral change, particularly of the traditional leadership will take too long.	The continued existence of dual legal systems comprising statutory and customary law may continue to posse a challenge on the hamonisation of legal proceedings for GBV cases and awareness activities aimed at changing attitudes.	DFID support for training and sensitization of traditional leaders on gender equality is expected to improve the knowledge and change attitudes of the Traditional Leaders and Customary Court adjudicators.	Medium	Low	Reducing
					The implementing of the constitution and enactment of the Gender Equity and Equality bill will hamonise the customary and statutory law
3. Priority ministries not demonstrating increased gender planning and budgeting	There is a challenge of conceptualizing gender and its implications on resource allocation in the various MPSAs by the treasury.	DFID support for training for MoG and line ministries on Gender Responsive Planning and Budgeting (GRPB). Guidelines on GRPB were developed and line ministries were oriented. The new performance management system for Permanent Secretaries has a gender mainstreaming objective which provides a good opportunity to institutionalise the prioritisation of gender and equity issues	High	High	Increasing
					Progress on this has been slow although its seen as increasing risk because of this year the budgets for most MPSAs were cut and being an election year. government might prioritise other funding other acitivites
4. Corruption and fraud.	Risk of funds not being used as intended.	Close monitoring of UNDP's internal systems. UNDP have sound financial management systems. In addition, DFID scrutinises project’s progress and financial reports, work plans and budgets.	Low	High High	Static
					This is static. A spot check will be carried out by March 2016 to provide an assurance on this.

Outstanding actions from risk assessment

A due diligence was conducted in December 2014 and the following are the outstanding actions for UNDP.
Finding	Recommendation
1. Despite fraud and whistleblowing policies and frameworks, previous agreements which UNDP signed with both Government and NGOs contain inadequate provisions on fraud reporting, investigation or recovery. There is potential scope to further strengthen fraud reporting provisions in the agreements UNDP signs with other partners.	UNDP to ensure all agreements with downstream partners contain robust anti-fraud provisions, including a clear statement of zero tolerance on fraud, a requirement upon the partner to immediately report any credible suspicions of fraud, and effective investigation and recovery provisions.(on going)
2. On procurement process, the OAI also observed few cases of procurement undertaken without evidence of competitive selection. Further, it noted unnecessary delays in the procurement lead-time.	It has been recommended that UNDP need to enhance its compliance with procurement policies and procedures and identify and address possible delays in processing time. (on going)

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The implementation of 2015 workplan was delayed by four months due to the late signing the work the 2016 workplan by MoG and UNDP. Activities for 2015 started on a slow pace but the delivery has improved and yielded some substantive results that contribute towards the achievement of gender equality in Zambia. To address this MoG partnered with other institutions to take lead on certain activities so that they are delivered quicker. For example, the drafting of 2012/2014 Gender Status Report was led by the Central Statistics Office and some activities of the Count Her in strategy had been spearheaded by Civil Society Organisations.

The GISSP component implemented by VSO faced delays at inception due to delays in arrival of the experts and also lack of staff to implement activities at MoG. To mitigate this, an adjustment was made to the work plan and VSO are now on course.

Performance of partnership (s)
The first component of the programme is implemented by MoG and managed by UNDP which also provides expertise to strengthen the capacity of MoG. DFID Zambia nurtured a good working relationship with UNDP, MoG and CSOs involved in the implementation of the programme, regularly meeting with them for updates on progress and quality improvement. However, the relationship between UNDP and MoG at times is less positive, due to the financial controls exercised by UNDP that MoG perceives UNDP to be bureaucratic and slow to approve expenditure requests. With the help of DFID, UNDP and MoG have managed to resolve these differences in many cases.
The MoG has generally good working relationships with its partners supporting the implementation of the PPPWCR.

The second component is implemented by VSO. There is a good working relationship between VSO, DFID and MoG.

Asset monitoring and control
UNDP maintains an asset register and so far only a few office equipment and one vehicle for the project was purchased using DFID’s funds. The vehicle is based at the MoG and log books are maintained and reviewed to monitor the use. Project assets are clearly labelled and an assets register is maintained .

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

A Midterm evaluation was conducted in 2014 by an external consultant. The evaluation conclude that overall, there has been good progress with leadership, coordination and monitoring of action to improve gender equality, particularly in the development of the Gender Equality Bill, revision of the National Gender Policy and production of the National Gender Status Report; however, coordination and monitoring and evaluation (M&E) need to be improved.

Monitoring progress throughout the review period

A Programme Implementation Technical Committee (PITC), chaired by the Permanent Secretary is responsible for oversight of the PPPWCR. The PITC comprises DFID, UNDP, PS MoG, Directors and
Deputy Directors from MoG, Central Statistics Office, Zambia Police Victim Support Unit, National Assembly, representatives from priority line ministries and also includes Civil Society Organisations and NGOs working in the Gender Sector.

The PITC meets on a quarterly basis to review progress, determine the strategic direction of the programme, and ensure a focus on results.

MoG submits quarterly progress reports to UNDP and DFID, reporting against the annual work plan, including progress towards milestones in the DFID logical framework. In addition, DFID meets with UNDP quarterly in advance of the PITC meeting to monitor progress towards expected results.

In addition, to the Annual Review a meeting was held on 18th January with MoG Director and Assistant Director responsible for the Programme. On 22nd January, a joint field visit was undertaken by DFID and UNDP to Kabwe to review the fast track court which was being launched.

Other monitoring activities included a number of regular monitoring visits by UNDP and meetings with individual Directors at MoG .The Annual Review was conducted by the SRO with assistance from the Social Development Adviser and the DFID Zambia Economist .