## 2015-2018
UK ISAR
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
To save lives, alleviate suffering and maintain dignity in the immediate aftermath of sudden onset natural disasters. | Rapid lifesaving emergency assistance provided to populations affected by sudden onset natural disasters. | Planned | Results from UKISAR reports and post disaster reports provided by OCHA (covering UNDAC and INSARAG) after each deployment. | Results dependent on frequency of disaster events to which international search and rescue teams are deployed. | Results dependent on frequency of disaster events to which international search and rescue teams are deployed. | Results dependent on frequency of disaster events to which international search and rescue teams are deployed.
Achieved
Source
Information from UKISAR reports and post disaster reports provided by OCHA (covering UNDAC and INSARAG) after each deployment. Lessons learnt from exercises and deployments, reports on the response by INSARAG, end of mission report to CFOA National Resilience, IER reclassification reports
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
UKISAR fully prepared to provide rapid, well coordinated and appropriately assessed international search and rescue responses saving as many lives as technically possible within the limited timeframes associated with rapid onset natural disasters. (UN GAR 57/150) | Rapid deployment of effective, immediately operational, well coordinated INSARAG classified "medium" or "Heavy" UK search and rescue teams to disaster affected areas. | Planned | 100% rapid operational response to appropriate requests within 6 hour deployment window and 100% maximum operational effectiveness. | Maintained 100% rapid operational response to appropriate requests within 6 hour deployment window and 100% maximum operational effectiveness. | Maintained 100% rapid operational response to appropriate requests within 6 hour deployment window and 100% maximum operational effectiveness. | Maintained 100% rapid operational response to appropriate requests within 6 hour deployment window and 100% maximum operational effectiveness. | That the significant and crucial commitment and in-kind commitments of staff time and other resources provided by the 15 fire and rescue services (FRSs) and DCLG/CFOA is maintained. Given the unpredictable nature of sudden onset emergencies it is not possible to predict how many times per year UKISAR will be called on to provide a response and therefore how often their preparedness for a response can be assessed. The INSARAG External Reclassification process, scheduled for may 2016 assesses this level of preparation.
Achieved
Source
Information from UKISAR reports and post disaster reports provided by OCHA (covering UNDAC and INSARAG) after each deployment. Lessons learnt from exercises and deployments, reports on the response by INSARAG, end of mission report to CFOA National Resilience, IER reclassification report
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 531000 |  |  |  | 531000 | 100%
INPUTS (HR) | DFID (FTEs)
5% - 1xA2, 5% -1xB1, 5% -1xOT
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
UK ISAR makes an effective contribution to the development of INSARAG governance and methodologies to improve international urban search and rescue assistance. | UKISAR make effective contributions to international, regional, national and technical meetings, that lead to improved guidance and processes | Planned | INSARAG guidance developed | Continued improvement of INSARAG guidance and governance processes | Continued improvement of INSARAG guidance and governance processes | Continued improvement of INSARAG guidance and governance processes | UK ISAR attends annual Team Leaders, and Medical/Training Working Groups. Regional and Steering Group meetings are attended at the request of DFID Political lead. There is a risk that an emergency requiring UKISAR happens and UKISAR cannot participate at INSARAG meetings.
Achieved
Source
Annual assurance report to DFID. Feedback from FCSS and regional INSARAG meetings. Feedback from UKISAR to DFID post meetings.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 39100 |  |  |  | 69100 | 100
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumption
Training - Current frameworks and processes are used to develop and deliver operational training to ensure the competence of all operational staff. This will include acquisition, developmental and maintenance of competence training, | Number of staff having undertaken technician acquisition and maintenance courses is maintained at 250 | Planned | 248 | Team capability maintained | Team capability maintained | Team capability maintained | With the next round of the comprehensive spending review, most FRS's will continue to reduce staffing levels, and make savings across all elements of service delivery. This will have an impact on staff attendance at UK ISAR training and development events. There is a risk that an emergency occurs just before or during an exercise or training course whereby staff are withdrawn and the training or exercise does not or only partially takes place.
Achieved
Source
Annual assurance report to DFID, annual competence assessment report to ISAR National Working Group (NWG)
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Number of staff completing specialist and technical support acquisition and maintenance courses. | Planned | 40 trained | 40 staff | 40 staff | Total of 160 staff members in 3 years (40 staff per year)
Achieved
Source
Annual assurance report to DFID, FRS training records, National Resilience database
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
30 | Number of national training exercises completed that include full deployment cycle (All UK ISAR personnel must participate in a national exercise on an annual basis to maintain international response currency). | Planned | Current delivery of 2 x national exercises | 2 x national exercises successfully completed. | 2 x national exercises successfully completed, and Reclassification pass at May 2016 IER exercise | 6 x national exercises completed including the 2016 IER by end of project
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Annual assurance reports to DFID, Exercise debrief and feedback reports |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 135500 |  |  |  | 135500 | 100
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Equipment - The UK ISAR heavy equipment cache is maintained at a constant state of mission readiness and complies with general requirements as determined by the INSARAG guidelines. This includes planned and agreed maintenance, R&D and asset refresh programmes. | The UK ISAR Medical Team (UMT) is equipped to deliver the required level of effective medical care in support of UK ISAR deployments. Includes charges applied for maintenance, logistics, drug turnover and staff costs. | Planned | Equipment provided through service arrangement with Event Medicine Company. | Equipment needs addressed and readiness maintained | Equipment needs addressed and readiness maintained | Equipment readiness maintained and refreshed as appropriate throughout term of project | The majority of logistical support equipment is owned by individual FRS's. Operational equipment storage is provided by West Sussex FRS, Communications by West Midlands and Welfare by Hampshire FRS. There is a risk that due to the ongoing comprehensive spending review support maybe withdrawn in terms of maintenance and asset refresh. Medical equipment continues to be effectively provided by EMC under the terms of an MOU.
Achieved
Source
Annual reports to DFID. National peer review assurance exercise.
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| The UK ISAR team has a mission ready complement of logistical support, coordination, administration, IT, communications, sanitation, accommodation, showering, food, and water, with appropriate maintenance and storage arrangements. | Planned | Provided and fully maintained by individual FRS's | Support arrangements and equipment readiness maintained | Support arrangements and equipment readiness maintained | Support arrangements and equipment readiness maintained and refreshed as appropriate throughout term of project
Achieved
Source
Annual reports to DFID. National peer review assurance exercise
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
40 | The UK ISAR team has a mission ready complement of operational equipment including, shoring, breaking, confined space, hot cutting, working at height, technical search, lifting and moving and hydraulic rescue components. | Planned | All equipment currently provided and fully maintained by a prime contract administered by CFOA National Resilience. | Equipment readiness maintained | Equipment readiness maintained | Equipment readiness maintained and refreshed as appropriate throughout term of project
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Annual reports to DFID. National Resilience annual report to DCLG |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 106500 |  |  |  | 106500 | 100
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
All UK ISAR personnel and canines on request are fully prepared to deploy overseas and operate in austere environments for up to 14 days. | Number of canines available for immediate response. | Planned | 12 | 10 canines available | 11 canines available | 12 canines available by end of project | 4 x UK ISAR canine handlers are due for retirement over the next three years. It will take time to recruit and train additional dogs/handlers
Achieved
Source
Annual reports to DFID, canine rota system
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Number of personnel who are fully vaccinated and prepared for immediate response. | Planned | 248 | Capability maintained | Capability maintained | Capability maintained
Achieved
Source
Annual reports to DFID, Team manifest and availability rotas
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20 |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 51000 |  |  |  | 51000 | 100
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
UK ISAR have effective management, financial, maintenance and administration functions in place to support the operational elements of the team. | Management, administration and reporting functions are effectively undertaken in the appropriate timeframe. | Planned | Invoice receipt timeframes on this budget and post deployment | All financial and reporting data submitted as per timeframes in the operational guidelines and DFID - CFOA MOU | All financial and reporting data submitted as per timeframes in the operational guidelines and DFID - CFOA MOU | All financial and reporting data submitted as per timeframes in the operational guidelines and DFID - CFOA MOU | If no emergencies take place where UKISAR deployed then the timeframe for receipt of reports and invoices post deployment cannot be assessed. Hovever, this can still be assessed for ongoing financial and reporting obligations under the MOU
Achieved
Source
Annual assurance report to DFID.
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
10 |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 30000 |  |  |  | 30000 | 100
INPUTS (HR) | DFID (FTEs)