## CGI Phase II logframe
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline (2014-15) | Milestone 1 (2015-16) | Milestone 2 (2016-2017) | Milestone 3 (2017-18) | Target (2019)
Sustainable investments and partnership between UK small NGOs, diaspora development actors and their counterparts in Africa are making an effective contribution to social and economic well-being in sub-Saharan Africa. | Number of poor, vulnerable and/or excluded people who benefit from CGI and Small and Diaspora UK NGO Fund and CGI elements | Planned | 0 | N/A | N/A | N/A | a) approx. 440,000 poor/vulnerable/excluded people benefit from the Small and Diaspora UK NGO Fund and the CGI elements
Achieved
OUTCOME 1 | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019) | Assumptions
Improvements in the lives of women and girls as a result of supported partnerships between the diaspora and civil society in Africa. | Percentage of partnerships reporting improved ability to strengthen W&G rights and examples of how they are doing this | Planned | 0 | 0= Selection of countries and issues may adjust this and consequent targets | 30% | 50% | 70% | Combined strategies engaging public opinion and African government actions are required for change; African civil society values diaspora contributions and partnerships; diaspora insider-outsider perspective and skills add value to African-led initiatives
Achieved
Source
Baseline data, quarterly reports, partnership monitoring tools, mid term reviews, annual reports, final evaluation.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Percentage of partnerships reporting progress in quality of services for women and girls | Planned | 0 | 0= Selection of countries and issues may adjust this and consequent targets | 30% | 50% | 70
Achieved
Source
Baseline data, quarterly reports, partnership monitoring tools, mid term reviews, annual reports, final evaluation.
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Evidence of shifts in government policies and practices towards women and girls rights in countries where partnerships operate | Planned | 0 | 0 | 0 | Evidence that key players are talking about issues in a more positive way | Evidence that key players are beginning to take action on women, girls and minority rights
Achieved
Source
Baseline data, quarterly reports, partnership monitoring tools, mid term reviews, annual reports, final evaluation.
Outcome 1 impact weighting - 30% | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
DFID (FTEs)
OUTCOME 2 | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019) | Assumptions
Diaspora investors increase and diversify their investment in SMEs in Africa. | Increased UK diaspora investment in African businesses which have a positive social impact |  | 0 | a) Identification of investment sectors with potential for maximum diaspora investment b) Identification of existing and new investment products for diaspora investment | 30% increase in diaspora investment via investment platforms / diaspora investment products | 40% | 50% | Increased diaspora investments in African SMEs will increase their sustainability and in turn benefit local communities and create opportunities for poor people; diaspora investments into Africa will be sustained if returns are good and risks are managed; financial sector institutions are interested to access diaspora investments and prepared to develop or adapt platforms targeting them; sufficient diaspora interest can be generated for new platforms and instruments to be tested; diaspora investment concerns regarding risks can be addressed in new financial instruments
Achieved
Source
Baseline data, investment platform data, research data, quarterly reports, mid term reviews, annual reports, final evaluation
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Number of Africa based SMEs in receipt of diaspora finance reporting social benefit in Africa | Planned | 0 | 0% | 20% | 35% | 50%
Achieved
Source
Baseline data, investment platform data, research data, quarterly reports,mid term reviews, annual reports, final evaluation
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 |  | Target (2019) | Assumptions
| Contributing to changes in regulations that support more competition among Money Transfer Organisations (MTOs). | Planned | 0 | Mapping of regulatory environment in 3 selected countries and UK. | UK and at least 3 African governments demonstrate increased awareness of solutions identified in CGI reports. | Champions in at least 3 African governments and UK promote reform of regulations drawing on CGI products. | Processes underway in UK and at least 3 African countries to change regulations. | Remittances remain at least at their current value or result in an increase in finance by recipients as a consequence of reduction in the costs of transactions
Achieved
Source
| Outcome Indicator 4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Contributing to greater transparency in the provision of information on costs including foreign exchange conversions. | Planned | 5-10% of MTOs currently share this information. | Mapping number and current practices of UK-based large and medium size MTOs operating in selected African countries. | From the mapped group (milestone 1) engagement begun between MTOs who are currently transparent and those who are less so. | 20 % of large and 10% medium MTOs committed to greater transparency. | 50% of large and 30% of medium MTOs committed to greater transparency.
Achieved
Source
| Outcome Indicator 5 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Contributing to increased understanding among remittance campaigners of how changes in charges affect regular remitters behaviour. | Planned | Anecdotal evidence suggests reduced costs increases remittance sent. | Updated baseline and research and work plan. | Systematic and robust evidence obtained about remittance trends of specific diaspora communities. | 50% of UK campaigners aware of new evidence about remittance behaviour in relation to costs. | 5 major international development actors understand impact of reduced charges on behaviour.
Achieved
Source
| Outcome Indicator 6 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Level of use by key stakeholders (campaigners, media, African governments, UK government, financial institutions) of new CGI generated evidence | Planned | 0 | Engagement of potential users in identifying key gaps and opportunities for evidence. | Use by stakeholders of CGI evidence from year 1 and 2. | Use by stakeholders of CGI evidence from year 1,2,3. | Evidence has played a key role in selected campaigns including SDG monitoring mechanisms at national and international levels.
Achieved
Source
Outcome 2 impact weighting -30% | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
DFID (FTEs)
OUTCOME 3 | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019) | Assumptions
Social and economic improvements to disadvantaged people in Africa. | Total number of people supported by Small and Diaspora UK NGO Fund 2014-19. | Planned | 0 | 80000; Final grants made may adjust this and consequent targets | 240600 | 360000 | 441382 | Grant-aided projects fulfil their stated objectives and are not undermined by economic recession, civil disturbance, exchange rate losses or other factors outside the control of the implementing organisations; existing green performers maintain their rating
Achieved
Source
Annual reports, start-up forms and evaluations from grantees
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Total number of people accessing basic services due, at least in part, to Small and Diaspora Fund grantees activity. | Planned |  | 40000; Final grants made may adjust this and consequent targets | 120300 | 180000 | 220000
Achieved
Source
Annual reports, start-up forms and evaluations from grantees
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Aggregated total of men and women supported into employment/generating their own income due, at least in part, to Small and Diaspora Fund grantees activity | Planned |  | 10000; Final grants made may adjust this and consequent targets | 23000 | 47000 | 59996
Achieved
Source
Annual reports, start-up forms and evaluations from grantees
Outcome 3 Impact Weighting - 40% | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target | Assumptions
Opportunities for engagement created between diaspora and civil society in Africa to share skills, address public attitudes and promote the rights of women and girls. | Number and type of partnerships established or supported and funded | Planned | 0 | 0 | 20 | 40 | 50 | Diaspora with the relevant skills, resources and expertise are willing to engage with African economic and social initiatives. Civil Society in Africa is interested in partnering and working with diaspora. Decision makers are open to engaging with diaspora.
Achieved
Source
Baseline data, quarterly reports, partnership monitoring tools, grant management data, mid term reviews, annual reports, final evaluation.
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Number of participants receiving capacity support for partnerships and description of capacity support provided to partnerships | Planned | 0 | 0 | 25 | 35 | 45
Achieved
Source
Baseline data, quarterly reports, partnership monitoring tools, mid term reviews, annual reports, final evaluation.
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Number of participants reporting change in partnerships (tracking tool to be developed aligning with other Aid Match partnerships - to be agreed Dec. 2015) | Planned | 0 | 0 | 5 | 20 | 30
Achieved
Source
Baseline data, quarterly reports, partnership monitoring tools, mid term reviews, annual reports, final evaluation.
| Output Indicator 1.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Number of participants reporting opportunities to influence decision makers around women and girls rights. | Planned | 0 | 5 | 10 | 15 | 20
Achieved
Source
Baseline data, quarterly reports, partnership monitoring tools, mid term reviews, annual reports, final evaluation.
| Output Indicator 1.5 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Number of media pieces produced which highlight the diaspora role in addressing issues of women and girls rights in Africa. | Planned | 0 | 0 | 6 | 12 | 20
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Baseline data, quarterly reports, media data, mid term reviews, annual reports, final evaluation. | [5 empty] | Medium
INPUTS (£) 2.8 million / (HR) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
Output 1 Impact Weighting - 25% | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019) | Assumptions
New models created, tried and tested to enable increased diaspora investment in SMEs in Africa. | Number of investment models created or adapted | Planned | 0 | Delivery partner in place; identification of different types of investment products. | One investment product developed or adapted and ready for testing. | Interim results from investment product 1. Development of investment product 2 begins. | 3 investment products tried and tested. | Sufficient diaspora interest can be generated for new platforms and models and sectors; diaspora investor concern regarding risks can be addressed in the new models/platforms
Achieved
Source
Baseline data, quarterly reports, mid term reviews, annual reports, final evaluation.
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Level of diaspora investment through investment products | Planned | 0 | 0 | £100,000 invested and/or XX investors attracted | £200,000 or XX investors | £250,000 or XX investors
Achieved
Source
Baseline data, quarterly reports, mid term reviews, annual reports, final evaluation.
| Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 |  | Target (2019)
| Number of evidence products with new information on the drivers and potential solutions to high costs of remittances | Planned | 0 | Identification of issues and opportunities; evidence gaps analysis. | 3 | 6 | 10
Achieved
Source
Baseline data, quarterly reports, mid term reviews, annual reports, final evaluation.
| Output Indicator 2.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Levels of awareness of new CGI-generated evidence among key stakeholders | Planned | 0 | Development of communications strategies that identifies key targets for advocacy and potential key advocacy allies. | UK-based campaign groups find CGI evidence useful as evidenced by satisfaction survey. Media coverage of new CGI generated evidence in at least 3 targeted African. countries. Governments in targeted countries aware of new CGI evidence of problems and solutions. | Governments in at least 3 targeted countries aware of new CGI evidence of problems and solutions. Continued media coverage and UK and international campaigns groups aware of new evidence. | Governments in at least 3 targeted countries aware of new CGI evidence of problems and solutions. Continued media coverage and UK and international campaigns groups aware of new evidence.
Achieved
Source
Baseline data, quarterly reports, mid term reviews, annual reports, final evaluation.
| Output Indicator 2.5 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019)
| Number of media pieces produced which highlight the diaspora role in investment in Africa. | Planned | 0 | 0 | 6 | 12 | 20
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Baseline data, quarterly reports, media data, mid term reviews, annual reports, final evaluation. | [5 empty] | High
INPUTS (£) 3.8 million / (HR) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
Ouput 2 Impact Weighting - 30% | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 |  |  | Target (2019) | Assumptions
Small and Diaspora UK NGO fund from which small and diaspora development organisations receive grants to meet the stated outcomes in Comic Relief's international grants strategy. | Number of grants (Implementing and Adapting grants and Generating Ideas grants) across Comic Relief's 7 goals made to small and diaspora organisations. | Planned | 0 | 55 |  |  | 55
Achieved
Source
Grant-making data from Comic Relief
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 |  | Target (2019)
| Number of grant holders reporting green performance rating for project delivery on Comic Relief grants performance criteria | Planned | 0% | 60% | 70% | 80% | 100
Achieved
Source
Grant-management data from Comic Relief
| Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 |  | Target (date)
| Increased understanding of how the 30 Generating Ideas grants helped recipient organisations. | Planned | 0 | 30 grants distributed | Follow up with 30 grantees to review experience. |  | Experience of 30 GI grantees reviewed.
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Final reports | [5 empty] | Low
INPUTS (£) 10.4 million / (HR) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
Output 3 Impact Weighting - 40% | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (2019) | Assumptions
Communications content on the role of diaspora in African development is generated | Number of media products produced which highlight diaspora role in issues addressed by CGI ie women and girls rights; diaspora investment and remittances into Africa. | Planned | 0 | Media Fund launched (integrated in part with delivery partners and some stand alone media activities). | 3 | 6 | 10 | Potential to increase public awareness of diaspora engagement in Africa, which in turn will build a conducive environment for UK diaspora and African cooperation
Achieved
Source
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 |  | Target (2019)
| Number of UK and Africa-facing platforms sharing new media content | Planned | 0 | 10 | 20 | 50 | 100
Achieved
Source
| Output Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 |  | Target (2019)
| Level of discussion generated by this new media content on UK and Africa facing platforms as monitored through online/other feedback | Planned | 0 | 100 participants in discussions | 300 | 400 | 500
Achieved
Source
INPUTS (£) 210,000 / (HR) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
Output 4 Impact Weighting - 5% | DFID (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.