Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Agricultural Model Intercomparison and Improvement Project (AgMIP) -The future of food and farming in Sub-Saharan Africa
Programme Value: 9.97 million		Review Date: 08-10/02/2016
Programme Code: 202108	Start Date: 1/03/2010	End Date: 31/03/2017

Summary of Programme Performance
Year	2011	2012	2013	2014	2015	2016
Programme Score	-	A	A	A+	A+	A
Risk Rating	-	Medium	Medium	Low	Low	Low

Summary of progress and lessons learnt since last review

Progress

Over the last reporting year the project has continued to perform robustly against all outputs, with performance in some areas slightly exceeding expectations. During this period the project has continued to consolidate technical improvements made to its crop and agricultural trade models and simulations of future climate impacts. Furthermore, it has developed a new set of research protocols, which describe AgMIP’s enhanced approach to identify and evaluate the interacting impacts of climate change, economic development, and adaptation in the agricultural sector. New elements of the new protocols include frameworks to separate current-period adaptation from (future) climate-oriented adaptation, and a clearer distinction between “sustainability-oriented” versus “economic development-oriented” pathways. This version of the protocols (v6.0) also contains new methods in each of the major disciplinary areas (climate, crops, livestock, economics, IT) as well as new sections on stakeholder engagement.

A new suite of climate scenarios, including revised and additional crops and livestock model configurations were generated, as well as new Representative Agricultural Pathways (RAPs) and adaptation packages for new geographical areas and farming systems across seven regions in Sub-Saharan Africa and South Asia. A total of 31 regional integrated assessments are planned, including a country-level assessment in Kenya and a state-wide assessment for the Free State, South Africa. An extensive climate-crop analysis is also underway for all of Tamil Nadu, India. New cropping systems have been configured for chickpea in Tamil Nadu and the Rice-Cotton system in Pakistan.

An important area of progress has been the development of the AgMIP-Impacts Explorer (IE), a user friendly web-based tool through which stakeholders can access AgMIP data and results as well as map based illustrations of future agricultural scenarios under different climate conditions. The AgMIP-IE features a clear interface that emphasizes key messages emerging from AgMIP research and hands-on exploration of AgMIP results. This aims to enable and stimulate the investigation and understanding of current and future challenges for agricultural risk management by policymakers and other users, who may not necessarily have a highly technical background in this field of research. The IE includes a guided explanation to assist new users and help navigating its many features.

An ongoing process to assess stakeholder needs in all phases of the decision-informing and decision-making process was undertaken as part of the enhanced scope of Phase II of the project. This includes the identification of stakeholders and their early engagement, communication of key messages, development of relevant RAPs and adaptation packages, and efforts to more clearly explain research approaches and risk factors. This has improved the engagement of developing country and other stakeholders across the range of project activities.

Lessons

Continuing to actively push the boundaries of stakeholder engagement and communication, especially in potential user communities remains vital, both for the remainder of the current DFID funded project and for the future role of AgMIP in helping shape the responses of international, national and sub-national institutions to climate change in the longer term.

The substantial progress made to date in relation to stakeholder engagement has largely been at the more technical / operational levels where the project has made substantial progress, including in strengthening national capacity and importantly, actively linking it to global expertise and centres of excellence. For the longer term, broadening the focus of stakeholder engagement to include more senior decision makers in both national government and other development institutions as well as international donors will be important. Engaging with key line ministries / departments outside of the usual partners (agriculture, rural development, environment etc.) will also be critical. Broadening out the stakeholder focus will also require more a nuanced engagement strategy combined with appropriate communications, depending on stakeholder roles and interest.

In relation to the above, having a simple, intuitive and easy to access internet based user interface that allows both scientists/researchers and non-expert users easy and free access to simple but powerful analytical and visualisation tools, as well as to the underpinning data and methodologies will be critical. As AgMIP develops and refines its impact explorer tool, it will be important for the project to continue to engage with stakeholders at all levels, including at more senior levels in sub-national and national government agencies, international development agencies and donors.

Stakeholders are eager for more information about the relevance and transferability of project findings to other potentially similar systems or scales.

The generation of relevant RAPs, adaptation packages, key messages and other products needs to be underpinned by an iterative process of co-development and co-analysis, supported by targeted capacity development. In this respect, the importance of building capacity should be noted. This is because the co-development of technical products and outputs, such as those produced by AgMIP, often requires a significant degree of training and capacity strengthening alongside it to enable it to work well.

The inclusion of climate and economic factors in the assessment of crop model responses allows improved calibration and configuration of the integrated modelling framework to provide more accurate results for the likely impacts of climate change on agriculture and farming systems in a number of regions.

Summary of recommendations for the next year

The AgMIP leadership should explore options to ensure the sustainability and legacy of the AgMIP-IE to facilitate the ongoing development of the tool and to promote its wider use among key stakeholders (Complete by Sept.2016).

The membership of the AgMIP-IE user panel should be kept under regular review to maintain useful perspective through all stages of development and to ensure relevance to a broad user base (panel to be reviewed monthly until end of project in March 2017).

The AgMIP Stakeholder Unit should produce a brief strategy that underpins stakeholder identification and tailored engagement activities. This should be produced in consultation and agreement with Regional Research Teams (RRTs) and the Project Leadership Team. (Complete by end of April 2016)

The Stakeholder Unit should continue to expand the range of stakeholders it engages, particularly toward more relevant and influential decision-makers and actors beyond the traditional remit of AgMIP engagement. This should include relevant knowledge brokers, intermediaries and similar figures, who can help uptake and use of evidence, data and results produced by AgMIP. (Regular updates to be given monthly from April 2016 to end of project)

RRT members’ capacity gains within the project should be measured through a combination of surveys and evaluation of outputs (By June 2016). Related to this, evaluations of developing country researchers’ capacity should be oriented toward ability to create and participate in future regional integrated assessments (By Sept. 2016).

Text for indicator 1 and 3 should also reflect the fact that AgMIP’s RAPs now include more than development policies alone (By end of March 2016).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3755603.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3640676.xlsx

Outline of the programme

Context
Agriculture is one of the most vulnerable sectors to the impacts of climate change. This is due to both direct impacts on crop yields and indirect impacts such as changes in water availability. As a result, climate change will tend to reduce global agricultural production and intensify the risk of hunger and malnutrition. The 4th and 5th Assessments of the Intergovernmental Panel on Climate Change (IPCC) confirmed that most of these impacts are likely to be felt in developing countries, where “even slight warming decreased yields in seasonally dry and low-latitude regions”.

This has significant implications for both food security and economic growth in many developing countries, where even with rapid urbanization; the majority of the poor are projected to continue to live in rural areas until 2040. Most depend on agriculture for their livelihoods, directly or indirectly. In large parts of Africa and South Asia, rural communities almost invariably tend to rely on rain-fed agriculture, so building their capacity to manage climate-related risks is a high priority. There is an expanding evidence base underpinning the need for strengthened climate risk management and climate resilience in the face of increasing impacts of climate variability on economic performance and livelihoods of the poor. Climate pressures will lead to shifts in patterns of household behaviour in response to shocks, including in relation to food security and exposure to infectious diseases.

Negative effects on agriculture in these areas are also likely to lead to impacts on growth and poverty reduction. Recent empirical evidence suggests that compared to growth from other sources, growth in agriculture generates welfare gains that are much stronger for the poorest parts of the population. Cross-country econometric work reported in the 2008 World Development Report shows that a 1% gain in GDP originating in agriculture generates a 6 % increase in overall expenditures for the poorest 10% of the population. GDP growth originating in non-agriculture sectors generates zero growth for the poorest 10% of the population.

DFID Support
DFID is providing £9.97 million over 6 years (FY2010/11-2016/17) to improve crop and agricultural economic models that help assess future climate impacts on the global agricultural sector and identify suitable adaptation strategies for developing countries in Sub-Saharan Africa and South Asia. Funding is channelled through the US Department of Agriculture (USDA), a funding partner and the International Crop Research Institute for the Semi-Arid Tropics (ICRISAT), an implementing partner.

Expected Outputs and Outcome
The project is expected to lead to a much improved understanding of the effects of climate change and economic development on agriculture and food security in Sub-Saharan Africa and South Asia over the coming decades. It will also generate improved evidence to evaluate priority adaptation strategies to enhance food security and agricultural productivity.

Planned outputs of the project include:
- Improved ‘toolkit’ for food security policy including crop, livestock and agricultural economics models, with specific outputs for Sub-Saharan Africa and South Asia;
- Reliable and accessible regional assessments of the impacts of climate change on crop production and associated economic implications;
- Identification and assessment of agricultural adaptation strategies;
- Development of an on-line platform for a global facility that will generate uniform, harmonised and openly accessible geo-spatial data on agriculture and the environment;
- Strengthened capacity of researchers in SSA and SA to access and use crop, livestock and economic models;
- Policy makers and planners in SSA and SA better able to access and use improved and relevant information on regional climate change impacts on agriculture.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome of the project is: “Development of tools, accurate estimates and detailed scenarios of how climate change will affect agricultural productivity and food security in SSA and SA, in a format that is relevant to the needs of stakeholders in partner countries”.

Overall, we found reasonable and substantial evidence to conclude that the project is on course to meet all of its objectives and to fulfil all indicators set as targets against the outcome for the end date of March, 2017.

More specifically, AgMIP has demonstrated the development and/or use of:

- an improved integrated assessment modelling framework;
- increased evaluation of sensitivity to key climate and economic factors;
- stakeholder engagement to co-develop and co-assess representative agricultural pathways (RAPs), adaptation packages, and key messages distilled from results;
- capacity of developing country researchers in technical areas relevant to the project, leading to an increase in institutional capacity, international exposure and leveraging of new skills;
- a web-based platform for discovery, communication and exploration of findings.

Overall output score and description

Overall AgMIP has continued to deliver solidly against all of its outputs and either met or exceeded all of its milestones for this year leading to an aggregate score of (A). A summary of the key points and accomplishments for all outputs is provided below.

The project has continued to deliver strongly against output 1. Carbon dioxide, Temperature, and Water (CTW) sensitivity tests were added to the model configuration process to better capture and explain extremes. Each research team is implementing at least two of these activities. Across all of the teams there is evidence of improvement in characterising each of the identified parameters and integrating these in the overall models configurations. Furthermore, two of the Regional Research Teams (RRTs), namely the East Africa and SAAMIP team are including larger-scale integrated assessments (state- and national-level, respectively).

The project has also continued to make good progress against output 2, all milestones for this reporting year have been met and significant progress towards the next set is expected to be made at the forthcoming regional technical workshop, which will be hosted in Dakar at the end of February. The project as a whole has developed a protocol for agricultural development pathways that span growth oriented and sustainability oriented future scenarios. The research teams are currently developing several adaptation packages that represent planned sets of interventions under different economic and climatic conditions; the co-assessment of policy and adaptation strategies is also well underway. Each research team is also developing two Representative Agricultural Pathways (RAPs) that chracterise development policies and future socio-economic and bio-physical conditions for each region’s integrated assessment. These will focus on two possible future scenarios: a high economic-growth, less sustainable one and a low economic growth, more sustainable one.

The project has delivered strongly against all milestones in output 3 resulting in significant advancements towards the creation and testing of the AgMIP Impact Explorer (IE) and AgMIP data interchange facility. These are key outputs for the second phase of the project, which underpin its renewed focus on impact and delivery of tools that are relevant to a wide range of users including regional, national and subnational policymakers and planners, international development agencies and NGOs. The development of the AgMIP-IE is proceeding well and has been shared widely within the AgMIP community and key stakeholders. A user panel comprising key stakeholders from the modelling community and partners from government agencies has been established and will meet in person for the first time at the forthcoming workshop in Dakar, to further test the user interface functionality and provide detailed feedback in a dynamic setting. The AgMIP Data Interchange is operational with an Application Programming Interface (API) that allows query and access to data to support the AgMIP Impacts Explorer text and images.

Overall progress against output 4 has been satisfactory with some elements having generated more impressive results than others. The Stakeholder Unit produced a stakeholder needs assessment, and findings have been integrated into the AgMIP protocols released in June 2015. This has resulted in a new orientation of AgMIP research toward assessing and meeting stakeholder needs. The stakeholder unit has also stimulated interdisciplinary dialogue and communication of methods and messages beyond the scientific community. The communications aspect of the project has undergone the most significant improvement and has generated some impressive outputs, which have resulted in the production of wide range of high quality products. These included policy briefings, factsheets, a completely revised and significantly improved website and a number of videos, blogposts and social media interactions.

Key lessons

Implementation of phase II of the project has led to the recognition of a number of important lessons which are summarised below:

- a continuing and dynamic process of stakeholder identification, engagement and needs assessment is essential to creating tailored products to inform decision-making across a diverse range of users;
- the generation of relevant RAPs, adaptation packages, key messages and other products needs to be underpinned by an iterative process of co-development and co-analysis, supported by targeted capacity development. In this respect, the importance of building capacity should be noted. This is because the co-development of technical products and outputs, such as those produced by AgMIP, often requires a significant degree of training and capacity strengthening alongside it to enable it to work well.
- the inclusion of climate and economic factors in the assessment of crop model responses allows improved calibration and configuration of the integrated modelling framework to provide more accurate results for the likely impacts of climate change on agriculture and farming systems in a number of regions;
- regular interaction between the leadership team and the Regional Research Teams (RRTs), including the use of virtual platforms, has accelerated capacity gains among the RRTs and has driven the advancement of the research outputs;
- stakeholders are eager for more information about the relevance and transferability of project findings to other potentially similar systems or scales.

Key actions

Develop clear messages for multiple stakeholder regarding the nature and impact of the most significant climate hazard for each farming system in the study regions.

The scope of additional elements to be carried out by each team should be finalised at the forthcoming AgMIP technical workshop in Dakar.

Following discussions with AgMIP partners and leadership team we have agreed that we should revise the text of indicators 1 and 3 for output 2. The changes should be aimed at portraying more accurately the processes underpinning the research activities in this area. This should be completed within 6 weeks from the end of this AR.

Improved communications around the range of products and results that can be produced by the modelling teams could expand the reach of the information that various categories of stakeholders need.

Has the logframe been updated since the last review?

Yes the logframe was almost entirely rewritten since the last AR to reflect the significantly changed scope and priorities for Phase II of the project.

We have now made recommendations for a few further amendments to be made against output 2 indicators 1 & 3 and output 3 indicator 1.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 1: Improved crop, livestock and agricultural economic models linked into calibrated framework capable of evaluating climate impacts and the potential benefits of adaptation and policy strategies.
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	30
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Improved representation of extreme events in decision-supporting modeling framework	Updated crop/livestock model components improve correlations and/or probability of detection for extreme events over last 30 years.	Milestone met and expected to be exceeded at Dakar Workshop to be held later in Feb 2016. / So far enhanced carbon dioxide, temperature, and water sensitivity tests were added to the model configuration process to better capture and explain extremes.
Enhanced scope of regional integrated assessments.	Each team documents increases in one of the following parameters: geographic extent; model types utilized; number of models in ensemble; extreme climate scenarios; elements of the farm system modeled; time frame examined	Milestone exceeded. Each team is implementing at least two of these activities. Across all of the teams there is evidence of improvement in each of the identified parameters.
Increased linkages to national and/or global scales	Preliminary protocol for coordinated regional and global assessment completed.	Milestone met. Two AgMIP RRTs (E Africa and SAAMIP) are including larger-scale integrated assessments (state- and national-level, respectively).

Key Points

By systematically characterising crop responses to key climate change factors, the crop teams in collaboration with the climate team are leading to a convergence of projected yields for each crop from different models. This will improve confidence in the simulation of impacts of variations in climatic conditions and recurrence of extreme climate events at the field level.

Phase II protocols include enhanced scope for assessment of multiple agricultural development pathways, as well as climate scenarios that incorporate changes in the sub-seasonal distribution of extreme events.

Conducted AgMIP Coordinated Global and Regional Assessment (CGRA) Workshop in Aspen (09/2015). Developed framework for multi-model, multi-scale, multi-disciplinary integrated assessment. Designed prioritized scenarios for assessment along the axes of adaptation, mitigation, food security, and food policy. AgMIP is also participating in a study focusing on national level impacts in India; this serves as a pilot activity for the CGRA.

The economics team is also developing a Regional Economics Model Intercomparison Project (REMIP), which is using the national level maize system analysis for Kenya. This will characterise the confidence of climate change impacts on maize farms overall income and other economic indicators.

Summary of responses to issues raised in previous annual reviews (where relevant)

In response to recommendations made at the last AR, in phase II AgMIP is:
- including more elements of the farm system in the models;
- improving confidence and capacity of researchers from the RRTs to interpret results from model simulations and characterize/define the impacts of extreme climate events on farm systems;
- linking global and regional assessments to achieve wider geographical coverage.

These measures are improving the reliability of crop models to project future yields and inform economic outcomes under different climatic conditions, creating more comprehensive impact metrics and more consistent messages to stakeholders.

Recommendations

Develop clear messages for multiple stakeholders regarding the nature and impact of the most significant climate hazard for each farming system in the study regions.

The scope of additional elements to be carried out by each team should be finalised at the forthcoming AgMIP technical workshop in Dakar.

Output Title	Output 2. Assessments of food security and economic implications of development policies and adaptation packages co-developed with regional stakeholders.
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	40
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Number of development policies configured for model-based assessment in each region co-developed by AgMIP and stakeholders	2	Milestone met and expected to be exceeded later this FY. AgMIP as a whole has developed a protocol for agricultural development pathways that span growth oriented and sustainability oriented future scenarios.
Number of adaptation packages configured for model-based assessment in each region co-developed by AgMIP and stakeholders	2	Milestone met and expected to be exceeded later this FY. The teams are currently developing several adaptation packages that represent planned sets of interventions under different economic and climatic conditions.
Number of assessments of policy and adaptation strategies to inform stakeholder decisions in each region	2	Milestone met. Co-assessment of policy and adaptation strategies is well underway. This will facilitate uptake into the decision making process upon completion of the integrated assessment process.

Key Points

With regard to indicator 1, each research team is developing two Representative Agricultural Pathways (RAPs) that characterize development policies and future socio-economic and bio-physical conditions for each region’s integrated assessment. The first is a high economic-growth (less sustainable) RAP and the second is a more sustainable (low economic growth) RAP. Each one of these is associated with one of the Representative Concentration Pathways (RCPs) and Shared Socio-ecosystem Pathways (SSPs) developed by the Intergovernmental Panel on Climate Change (IPCC) for the 5th Assessment Report (AR5), but includes national, state and local information in its model application scenario.

Teams are working with stakeholders to quantify RAP parameters for their specific regions, based in part on existing development policies and plans.

AgMIP now examines adaptation packages in the present condition, as well as under future climate and economic conditions, in order to distinguish climate oriented adaptations from climate neutral good practice.

Research Teams’ interactions with stakeholders are enabling the co-development and co-analysis of adaptation packages utilising feasibility analysis and existing adaptation plans and policies, which are expected to deliver more appropriate, realistic and user-relevant RAPS and adaptation packages.
AgMIP’s iterative process of RAP and adaptation development allows country stakeholders to participate in the general design and specific realisation of scenario configuration, vetting and analysis.

Summary of responses to issues raised in previous annual reviews (where relevant)

AgMIP’s stakeholder unit has substantially improved the Regional Research Teams’ organisation of stakeholder engagement and processes that enables the co-creation of RAPs, adaptation packages and related products that are relevant to stakeholder interests and concerns.

AgMIP has included more RAPs and adaptation packages in the integrated assessment framework to quantify the likely impacts of projected future climate on agricultural systems. This has enabled improved characterisation of plausible future outcomes, providing guiding information to facilitate risk management.

Recommendations

Following discussions with AgMIP partners and leadership team we have agreed that we should revise the text of indicators 1 and 3 for this output. The changes should be aimed at portraying more accurately the processes underpinning the research activities in this area. This should be completed within 6 weeks from the end of this AR.

Text for indicator 1 and 3 should also reflect the fact that AgMIP’s RAPs now include more than development policies alone.

Output Title	Output 3: Development and testing of interactive tool for illustration and access of AgMIP results "AgMIP Impacts Explorer" (IE).
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
AgMIP Impacts Explorer usage and diffusion	AgMIP IE prototype utilizing preliminary results shared with 200 visitors within the AgMIP community.	Milestone met. The prototype development is proceeding well and has been shared widely within the AgMIP community and key stakeholders.
AgMIP Impacts Explorer User Panel	AgMIP IE User panel has been established and provided feedback.	Milestone met. The user panel has been established and will meet in person for the first time at the forthcoming workshop in Dakar to further test the user interface functionality and provide detailed feedback in a dynamic setting.
AgMIP Data Interchange to store project data and results for access by AgMIP Impacts Explorer	Preliminary input data and outputs from Phase 2 regional integrated assessment included in Pilot AgMIP Data Interchange with prototype tools supporting AgMIP Impacts Explorer text and images.	Milestone met. The AgMIP Data Interchange is operational with an Application Programming Interface (API) that allows query and access to data to support the AgMIP Impacts Explorer text and images.

Key Points

The concept and initial working prototype of the AgMIP IE were presented in Victoria Falls and in stakeholder interactions in South India. The AgMIP IE revised prototype (http://agmip-ie.alterra.wur.nl) will also be presented at the Dakar Workshop.	Development of the final version will require a number of iterations and dynamic interactions with contributors and users from various disciplines and sectors including scientists, policymakers, extension workers and development agencies.
The AgMIP Impacts Explorer development team has solicited feedback from the stakeholder unit, regional research team members, and various stakeholders during a series of meetings in India. The IE team participated in the South Indian stakeholder exchange. Upon demonstrating the prototype at the Dakar Workshop the IE team will solicit feedback from a range of users.

The Impacts Explorer prototype is built upon Phase 1 results but is designed featuring slots for data and key messages from new results to fit into an overarching framework. This will allow Phase 2 results to be linked in seamlessly upon their completion around the Dakar Workshop, as well as their analysis and updates in the remainder of the project.

Summary of responses to issues raised in previous annual reviews (where relevant)

The main recommendation from the last AR in this area concerned the creation of a prototype for the IE, which is now the focus of this whole output.

Recommendations

The AgMIP leadership should explore options to ensure the sustainability and legacy of the IE to facilitate the ongoing development of the tool and to promote its wider use among key stakeholders.

The membership of the user panel should be kept under regular review to maintain useful perspective through all stages of development and to ensure relevance to a broad user base.

Output Title	Output 4: Project, stakeholder interaction, and communications support for AgMIP Phase 2.
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Stakeholder Needs Assessment	Stakeholder needs assessment completed and reflected in protocols for regional research team activities (by Mid-2015)	The Stakeholder Unit produced a stakeholder needs assessment and findings have been integrated into the AgMIP protocols released in June 2015. AgMIP has undertaken an ongoing stakeholder engagement process and RRTs have conducted 41 meetings reaching 424 stakeholders.
Capacity gains for project participants	RRT survey of capacity at mid-term regional workshop documents capability gains.	AgMIP conducted an RRT capacity survey at the kickoff workshop and will conduct the next capacity survey at the mid-term regional workshop in Dakar. AgMIP webinars have included co-analysis of initial results with research team leaders.
Communications	1 policy brief/fact sheet, updated webpage, and communications strategy informed by stakeholder needs assessment for each RRT	Teams have produced fact sheets and blog posts that are available on the AgMIP website. AgMIP has also updated webpages for each team, and created portal pages for sub-Saharan Africa and South Asia that link regional research team projects in each region (in beta).

Key Points

AgMIP protocols now reflect stakeholders’ interest in gauging how representative the modelled systems are of the broader region, co-developing RAPs and adaptation packages, and emphasizing communications and the distillation of key messages. This has resulted in a new orientation of AgMIP research toward assessing and meeting stakeholder needs. The stakeholder unit has also stimulated interdisciplinary dialogue and communication of methods and messages beyond the scientific community.

AgMIP has engaged a large and diverse set of stakeholders, facilitating co-development of RAPs and adaptation packages. Co-evaluation of Phase I results with RRTs and stakeholders provides useful perspective as to stakeholder relevance and will lead to more efficient co-analysis of Phase II results in the remainder of the project.

Overall, we have noted a very significant improvement in the range, quality, and quantity of communication outputs. This has resulted in a substantially improved external profile for the whole project and a noticeable increase in impact which resulted also in an increase in DFID-relevant communications activities and outputs.

AgMIP collected extensive video of stakeholders, AgMIP researchers, and AgMIP leaders at the Victoria Falls Workshop that we are now editing to produce online material.

Summary of responses to issues raised in previous annual reviews (where relevant)

The AgMIP Stakeholder Unit has created an ongoing stakeholder engagement and needs assessment approach that is producing new information and driving a more targeted project.

AgMIP’s Communications Coordinator has developed a large set of indicators which need to be further refined in order to reduce to a smaller, manageable number that is also more relevant and measurable.

AgMIP’s communications strategy is being finalized and will be presented at the upcoming Dakar Workshop.

Recommendations

The Stakeholder Unit should produce a brief strategy that underpins stakeholder identification and tailored engagement activities. This should be produced in consultation and agreement with RRT and Project leadership.

The Stakeholder Unit should continue to expand the range of stakeholders it engages, particularly toward more relevant and influential decision-makers and actors beyond the traditional remit of AgMIP engagement. This should include brokers, intermediaries and similar figures.

RRT members’ capacity gains within the project should be measured through a combination of surveys and evaluation of outputs. Related to this, evaluations of developing country researchers’ capacity should be oriented toward ability to create and participate in future regional integrated assessments.

Improved communications around the capability of the modelling teams could expand the reach of the information that various categories of stakeholders need.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
AgMIP activities were predominantly centred around three areas, namely: research, co design and development of outputs and tools for a wide range of users and capacity building. As the development of the Impact Explorer and associated products and outputs enters its crucial stages it is anticipated that they will involve a considerable portion of spending going forward. In addition to these standard elements there have been no unanticipated cost drivers since the last AR.

Over the past year there have been some fluctuations in exchange rates, which have generated some variations in income, but these are not deemed to be highly significant for the overall project.  In case of any exchange rate financial gains, any earnings are initially captured by USDA, who is in direct receipt of the DFID funding and subsequently either re-invested into financing further programme activities to be agreed with the DFID lead adviser or returned to DFID.

VfM performance compared to the original VfM proposition in the business case
VfM performance for the AgMIP project remains very high. The project has established a reputation second to none in its field and it is now compared to the highly prestigious and long established Coupled Model Intercomparison Project (CMIP).
Over the course of its life AgMIP has been really active in engaging with a number of global partnerships, which included some of the leading international consortia initiatives (e.g. CCAFS, MACSUR, ISIMIP, Global Futures, Harvest Choices, Yield-Gap Atlas) and it now has a wide reach among the climate and agricultural sciences academic communities. Over the past year this reach has also been extended to a number of academic institutions and policy actors across a number of countries.

AgMIP undertook a rigorous open competition for SA and SSA regional components at the beginning and now other partners are examining and contributing to the methodology for use in their regions.

USDA worked effectively throughout the life of the project to accommodate all DFID requirements concerning program management and to meet all corporate reporting requests.

AgMIP partnered with ICRISAT to ensure regional salaries and expenses were kept within appropriate levels and continued to monitor expenditures through the project reporting year.

Phase I of the project managed to achieve all of its objectives within budget and a total of approximately £300,000 in savings, which was accumulated because of exchange rates appreciation and cost efficiency/savings in programme management, was reinvested into Phase II.

Assessment of whether the programme continues to represent value for money
Yes the project continues to offer a high VfM proposition particularly because of its ability to source world class expertise in its academic domain and related fields of investigation.

The demonstrated project ability to leverage in-kind contributions from a very large pool of researchers and modellers worldwide adds considerable value to the project as a strong and highly yielding investment.

Quality of financial management
The overall quality of financial management for the project has increased substantially from last year. The project is now meeting all financial targets and producing accurate spending forecasts. The fiduciary risk is covered and monitored very effectively by our partner institutions (i.e. USDA and ICRISAT), who ensure that all due diligence procedures and related DFID requirements are adhered to.

Date of last narrative financial report	14/12/15 Quest Ref 5258866
Date of last audited annual statement	23/02/16 Quest Ref 5358025 & 5358002

E: RISK (½ page)

Overall risk rating: Low

The overall risk level has not changed over the past year and remains low.

The financial management risk element has now been lowered to low and is accompanied by a very low risk in the program delivery.

Overview of programme risk

The element of risk concerning the delivery of phase 2 objectives within the agreed deadline has also been abated and is now rated as low. This is mostly because of progress and an acceleration in the delivery of key output over the past six months, which made up for the delays in commissioning and signing of the MOU.

Outstanding actions from risk assessment

All outstanding actions from last years’ risk assessment have been resolved successfully and to our full satisfaction. We have now implemented a new system for the management of financial flows and resources within the project with USDA and ICRISAT managing and distributing all financial allocations.

This new arrangement has had the double-positive effect of delayering and simplifying the financial flows between partners, thus increasing the pace of delivery but also improving significantly the levels of financial accountability among partners.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Following last year’s no cost extension the project has continued to deliver well against all outputs and outcome and remains on course for a 100% completion rate.

Performance of partnership (s)

Our partnerships with ICRISAT and USDA remain very strong and continue to deliver excellent results and significant improvements in the financial and fiduciary risk management that have been described above.

Asset monitoring and control
N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

This is a centrally managed research programme, which we are funding in partnership with USDA and implementing through Colombia University and a number of other research institutions in the US, Europe SSA and SA.

We do not explicitly use the partnership principles in monitoring and managing the programme, but we rely on USDA to monitor the performance of all implementing institutions.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There have been no major changes in the evidence in this area of research since last year to determine any implications for the project or warrant any actions. Having successfully contributed to AR5, AgMIP is now gearing up to assemble evidence to contribute towards AR6.

Monitoring progress throughout the review period

Monitoring activities throughout review period consisted of a monthly iterative process by the leadership team to analyse datasets, model configurations and climate impacts results and interpretation. These were discussed regularly with the DFID advisers and any appropriate and relevant actions agreed to improve performance where needed.

Progress of regional research activities was monitored by participation of teams in regular calls, interaction with AgMIP team leaders and resource persons and participation at AgMIP events held on the margins of major international conferences. The results generated by the RRTs continue to be peer reviewed through publications in ISI listed journals (e.g. Nature and Science) and presentations at major events and academic conferences (e.g. America Society of Agronomy; American Geophysical Union).

The Annual Review process consisted of a field visit to Columbia University were the leadership and co-ordination teams of the project are based.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process