Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Africa Division funding to Africa Agricultural Development Company (AgDevCo)
Programme Value: £78.28m		Review Date: June 2015
Programme Code: 203232	Start Date: 1 July 2013	End Date: 31 December 2020

Summary of Programme Performance
Year	2013	2014
Programme Score	A+	A
Risk Rating	Medium/High	Medium/High

Summary of progress and lessons learnt since last review

AgDevCo has made good progress since the 2013 annual review, although there has been considerable variation in its performance against logframe targets. This is likely due to the logframe requiring better alignment with achievable outputs, barriers to building suitable teams in-country, delays in DFID funding, and the unpredictable nature of AgDevCo’s business. No major areas of concern were noted when reviewing AgDevCo’s procedures and investments.

The 2013 annual review took place early on in AgDevCo’s investment cycle, after only 6 months from DFID scale up funding. Since then, AgDevCo has (i) become more organised internally: it has created employee handbooks and templates to ensure staff across offices manage projects consistently; (ii) increased reporting quality and frequency: by monitoring projects and finances quarterly, to provide earlier insight into potential issues; (iii) become clearer on impact: before and during the investment process, they have conducted closer assessment on how each investment could and is expected to have development impact, shaping the portfolio towards this; (iv) put an environment, social and governance due diligence process in place: to ensure investments meet wider development goals and mitigate associated risks; (v) recruited more local staff and acknowledged the need to invest in more indigenously owned business and; (vi) improved its reporting of risk to DFID.

This is the first full year of AgDevCo operations being reviewed, and as a result many of the areas of improvement mentioned above are still work-in-progress; however AgDevCo is progressing well and working to implement lessons learnt.

Total funds committed by DFID to AgDevCo are £76.58 million (plus £1.7 million for an independent evaluation.

Summary of recommendations for the next year

A number of recommendations are made as part of this annual review. These have been grouped under the following headings:

Logframe/results reporting recommendations:

DFID should ensure the new logframe incorporates early lessons from the scale-up of likely impact from investments, including the longer time period needed to realise results from primary production and greenfield site development. (Recommendation 1)

AgDevCo to agree a clear methodology with DFID on how they count and report on farmers engaged in a business prior to AgDevCo funding being given. (Recommendation 2)

AgDevCo to reassess the methodology for calculation of full-time equivalent jobs (FTE) with the independent evaluators.. They should finalise a simple methodology to count and differentiate between seasonal/temporary workers. (Recommendation 3)

DFID/AgDevCo to alter logframe indicator 3.1 to (a) new jobs created (b) jobs maintained. (Recommendation 4)

AgDevCo to ensure a consistent methodology is applied for calculating ‘private capital leveraged’ that is accepted and clearly understood by all parties. (Recommendation 12)

Result reporting must be checked urgently to ensure that the same results are not being reported twice to DFID via different programmes – e.g. through AECF and AgDevCo. (Recommendation 13)

Risk mitigation recommendations

After the approval of an investment, AgDevCo should ensure that the company is not employing staff on temporary contracts to avoid payment of formal contributions/benefits to the detriment of employees, and aim for best practice in labour relations. (Recommendation 5)

DFID to be given the timetable for the ESG Specialist recruitment and to be thoroughly appraised of how this staff member will support and strengthen ESG due diligence across AgDevCo investees. (Recommendation 7)

DFID country offices to ensure risks are discussed systematically at quarterly steering committee meetings. Country offices must understand all highly likely and significant impact risks and be satisfied with the measures taken to manage/mitigate impact. (Recommendation 8)

All remaining DFID due diligence actions from the 2013 due diligence report to be completed by December 2015 (Recommendation 9)

VfM Recommendations

A clear timeframe to be agreed to confirm the methodology for reporting on VfM metrics from 2015 onwards. (Recommendation 6)

Operational recommendations

Further sustained work required by AgDevCo in some countries to ensure an increasing number of partnerships (directly or indirectly) with local/indigenous businesses (Recommendation 10)

AgDevCo to develop a gender strategy with support from DFID, to be implemented in 2016. DFID to monitor and provide support to its development, finalisation and roll-out. (Recommendation 11)

AgDevCo to focus on the development of the smallholder development model (including at Kilombero Plantations Ltd.) and to share and discuss with DFID. (Recommendation 14)

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3716864.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4489570.xlsx

Africa is recognized as the region with the most unexploited potential for agriculture production. Development of agribusiness and transformation of agriculture in Africa could create jobs, income and other opportunities for the African smallholder base, 60% of which are economically active women.
Yet there is relatively little investment in commercial agriculture, even in countries where the policy environment is more supportive. A major reason is because investors face very high costs and risks associated with early-stage development, poor access to, and high cost of finance, lack of experienced workforce and absence of a supporting network of service companies.
AgDevCo is a non-profit sharing investment company that makes debt and equity investments in early stage or growing agricultural businesses in Africa. It aims to address many of the constraints these businesses face in accessing the capital and support they need to grow.
The UK currently provides up to a total of £76.58 million to AgDevCo, plus additional funding for an independent evaluation of the programme (the total becomes £78.28mln). This is funded from a number of different departments in DFID, as follows:
- £50.0 million of re-deployable capital over 5 years channelled through 3 new Catalytic Funds in Malawi, Zambia and Ghana of £10 million each funded by DFID Country Offices and a new Regional Innovation Investment Fund of £20 million funded by Africa Regional Department;
- £15.58 million of additional re-deployable capital for specific investments in 3 projects in Tanzania, funded by DFID Tanzania;
- £11.0 million from Private Sector Department for mainly early-stage and greenfield large-scale agribusiness infrastructure, predominantly irrigation or irrigated large-scale production; and
- £1.7 million funding for an independent impact evaluation and research component in multiple countries to generate evidence and learning on stimulating private sector investment in agriculture.
The scale-up funding has thus far been disbursed through the Private Infrastructure Development Group (PIDG), although from April 2015 onwards disbursement will be through a direct agreement with AgDevCo as approved by the SofS in March 2015. (EDRM link 4864496).
Funding will result in an investment portfolio for 2013-18 that will directly benefit over 900,000 people (ideally 50% women) and is expected to positively impact many more through additional spill over investments and improvements in agriculture infrastructure. Expected Outputs by 2018 are:

- 57 agribusiness enterprises developed or expanded with an additional turnover of over £91 million;
- Over 900,000 individuals directly benefiting from the new investments, including: 190,000 smallholders’ households and 7,000 additional FTE jobs;
- Improved availability of agriculture supporting infrastructure – 34,000 additional hectares under irrigation (Ha) and 125,000 additional metric tonnes in processing throughput;
- Over $22million of additional regional trade directly generated by AgDevCo’s investments.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The outcome of the AgDevCo programme is to leverage private sector investment in agribusiness and agricultural infrastructure; increase agricultural cross border trade; and generate jobs and income in targeted countries. The investments made over the past 18 months have begun to make a contribution to achievement of the intended outcome; however, progress has been mixed, with some indicators substantially exceeding targets and others being missed.

Indicator(s)	Milestones 2014	Progress 2014
Volume of capital leveraged and invested in agribusinesses (cumulative) ($m): a) Private, b) DFI	0 / 0	$14,433,682 / $5,611,310
Direct increases in household income: a) outgrowers ($m); b) employed ($m).	$732,912 / $1,936,238 / TOTAL $2,669,150	$1,449,149 / $616,645 / TOTAL $2,065,794
Value (cumulative) of a) agricultural products exported; or b) imported by agribusinesses.	TOTAL Import and Export / $1,432,000	Exports 0 / Imports 350,000 / TOTAL Import and export $350,000
Percentage of private sector investment in DAC I, II countries	80%	80%

AgDevCo has leveraged over $20m of private sector capital into agribusiness investees building on good early progress for this indicator last year. Targets for increases in outgrower household income have been substantially exceeded, driven by over achievement of targets in Zambia, Tanzania, Malawi and Ghana. Increases in household income from employment and value of goods exported and imported substantially did not meet expectation.

Looking forward, AgDevCo is likely to continue to have strong figures on capital leveraged vs. plan as there are no milestone targets until 2017. As the pipeline matures, figures for direct increases in household income will increase; however it is too early to tell whether these will be in line with plan, as only 1/2 of funds have been fully committed by AgDevCo to businesses. The value of agricultural products exported/imported is also likely to increase, but again is likely to be less than logframe targets, although again with 1/2 of funds uncommitted, it is difficult to model in the longer term.

Overall output score and description

The overall output score is an A.

Output 1 moderately did not meet expectations (B); although AgDevCo exceeded the volume of investment committed to agribusiness, they fell short on the two other indicators of agribusiness turnover and the number of enterprises created or expanded. Future pipeline and the way results are reported means this is not a major cause for concern at this stage.

Output 2 moderately exceeded expectations (A+) with more farmers engaged than planned. However the robustness of this indicator needs further clarification.

Output 3 substantially did not meet expectations (C) as job creation figures were less than half that of the logframe. With a large proportion of investments made in primary production and greenfield site development, the trajectory of job creation figures was over-estimated in the logframe.

Output 4 met expectations (A). AgDevCo exceeded targets for processing throughput but fell short on targets for irrigated land. The current pipeline may mean that they continue to struggle to meet irrigation targets in future years.
Despite some indicators being missed this year there is no specific cause for concern. In the main, missed milestones can be attributed to an over-estimation of the likely trajectory of the targets set. The AgDevCo scale-up programme has been operational for only 18 months during which time significant progress has been made in strengthening operating policy and procedures, recruitment and deployment of staff, concluding investment decisions and pipeline development. AgDevCo now has 56 staff deployed across its head office and 5 country programmes and has committed over $40m to 24 investments. There is a healthy pipeline of investments across all countries.

Key lessons

A number of lessons are emerging from this programme:

For DFID, this is a new and innovative model to fund the growth of the commercial agricultural sector in Africa. The logframe was developed on a set of assumptions of what a country portfolio might look like and what the potential impact might be. Although this was based on AgDevCo’s operating experience at the time, inevitably a number of the early planned investments did not materialise and investments that were funded were materially different from those originally envisaged. Given that outputs for programmes such as this one are difficult to accurately predict early on, enough flexibility should be factored in to allow regular reviews of the logframe targets, to ensure the programme is not judged against milestones and trajectories that are no longer valid.

Experience is showing that slower trajectories are required to achieve development results, particularly for greenfield site development and primary production. This is where most of the AgDevCo portfolio is focused at present – although the extent of this varies by country AgDevCo will need to ensure that they generate a balanced portfolio to (i) reduce portfolio risk and (ii) ensure a balance of impact across different investments. This direction of travel was identified as part of the country-level investment portfolio strategies produced in September 2014

Comprehensive environmental, social and governance due diligence is absolutely key in ensuring that the risks of using public funds to finance private sector businesses are mitigated and that investments are ‘responsible’ in the widest possible sense. AgDevCo has formalised and is strengthening their work in this area, going forward this should remain a key priority for DFID.

As investments are made and businesses become more established, external factors in the business environment are playing an ever more apparent role in business success. Examples include both policy issues (for example import tariffs on rice, rules on VAT exemption, competition rules and a web of further regulations in Tanzania) and vital infrastructure to access markets. Going forward it will be important to ensure there is a process of capturing these wider issues to feed into work on the business enabling environment taking place in other parts of DFID. If not already taking place, more systematic discussion of policy concerns at country level between AgDevCo and DFID should also take place, with options to use existing programmes to help resolve sectorial constraints explored.

Key actions

The following additional actions on policy should be taken:

- Continued discussion of policy constraints to be discussed as a standing item at national level quarterly Steering Committee meetings between AgDevCo and DFID.
- DFID to lead on further sharing of policy issues/lessons during the DFID wide quarterly Steering Committee meeting
- DFID to lead an annual dedicated session of the DFID wide Steering Committee to take place on policy issues/lessons with an invitation offered to DFID business enabling environment policy leads.

Has the logframe been updated since the last review?

A new logframe has been put in place as part of the new business case approved in March 2015, which will be valid from 2015 onwards. Recommendations from the 2013 annual review have been incorporated into the new logframe as far as possible. All the logframe recommendations were considered by both the independent evaluators and DFID when re-designing the logframe in preparation for the new business case approved in March 2015. Following advice from the independent evaluators not all recommendations were adopted. A final logframe with full comparison with the 2013 annual review recommendations and recommendations included in the present review will be presented to next DFID wide SC for approval.

As AgDevCo reporting was completed before the new business case approval and the annual review process also started before approval, the old logframe is used for this annual review.
## C: DETAILED OUTPUT SCORING

Output Title	Develop or expand agribusiness enterprises that are financed, owned or operated on a commercial basis by AgDevCo
Output number per LF		1	Output Score	B
Risk:		Medium/High	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Number of enterprises created or expanded (cumulative): a) SME businesses, b) Medium size financial investments, c) Large project development investments	SME 14 / Medium 19 / Large 3 / TOTAL 36	SME 7 / Medium 13 / Large 4 / TOTAL 24
1.2 Volume of investment committed to agribusinesses or agricultural development projects (cumulative) ($m)	$35,000,000	$41,294,661
1.3 Agribusiness turnover (cumulative) ($M)	$6,803,333	$3,268,644

Key Points

Achievement of targets for 2014 was moderately below expectation for output indicator 1. Although the target for the volume of investment has been exceeded, the target for number of businesses and the resulting turnover of these businesses has been missed. There are a number of reasons for this slower than anticipated progress:

- Reporting is against logframe targets for a full 2 years, although AgDevCo only received the first tranche of scale-up funding in mid-2013, halfway through year 1 of the current logframe.
- Further disbursement delays were experienced following a requirement by DFID to undertake a more in-depth due diligence process in early 2014, further slowing down investment decisions.
- Results from primary production investments take time to emerge. When the log frame numbers were defined they assumed that ‘medium’ investments (then referred to as ‘financial’ investments) were in investments that were more advanced and therefore expected impact sooner. In practice a larger proportion of medium investments are greenfield / early stage. This explains in part the lower levels of turnover to date.

It should also be highlighted that the original logframe targets were based on an anticipated level of investment activity prior to funding being disbursed and any real development of the pipeline of investments taking place. Given the nature of the work that AgDevCo is undertaking, which is inherently iterative in nature with investments being explored, then developed or rejected once further due diligence work is undertaken, the logframe targets could only ever be an ‘estimation’ of what the portfolio would eventually look like. After 12-18 months of operation in countries where investments are taking place, AgDevCo should now be in a much better position to more accurately predict targets going forward.

Summary of responses to issues raised in previous annual review

Recommendations from 2013 Annual Review	Response
Indicator 1.2 should be amended to read as follows: Value of AgDevCo’s investment committed in agribusinesses or agricultural development projects ($m)	The amendment was not made to the current logframe, as 6 months into the year, AgDevCo had already begun to monitor progress for 2014. However, the change has been incorporated into the new AgDevCo logframe which will take effect from April 2015 onwards.
Indicator 1.3 should be amended to read as follows: Increase in agribusiness net profits ($m)	The proposed amendment to logframe indicator 1.3 has not been incorporated into the new logframe. Although this recommendation was considered, an alternative measure – EBITDA – was chosen given the early stage of investments.
Output 1 Risk raking should be raised to High	The risk rating alteration will be considered and discussed by the Steering Committee (SC) as part of the new logframe discussion and approval.
The following assumption should be added to Output 1: The failure rate of investments including both outright insolvency and failure to achieve development impact results will not exceed 25%	The assumption will be added to the new logframe to be discussed and approved by the SC.

Recommendations 2014

Recommendation 1: DFID should ensure the new logframe incorporates early lessons from the scale-up of likely impact from investments, including the longer time period needed to realise results from primary production and greenfield site development. A reassessment of the trajectory of results should be made: with circa half of funds either committed or allotted to pipeline for a large proportion of the logframe timeline, it should be possible to have a more accurate view of possible and likely results. Accurate targets can then be set. This applies across all logframe outputs.

Output Title	Increase integration of smallholders into commercial agribusinesses through access to irrigation, processing infrastructure, modern inputs, etc.
Output number per LF		2	Output Score	A+
Risk:		Medium-High	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Number of smallholder farmers engaged in agribusinesses (cumulative) : (a) male farmers; (b) female farmers; (c) total individuals benefitting (i.e. Total male and female farmers multiplied by household size)	Male farmers 1,571 / Female farmers 1,571 / Total individual 14,453	Male farmers 4,254 / Female farmers 3,872 / Total individual 37,381

Key Points

This target has been moderately exceeded. AgDevCo’s investments are currently engaging with 8,126 smallholders, 48% of which are women. Most countries had programmes that engaged smallholders with agribusiness, with the number of individuals ranging between 0 (Mozambique) to 3,710 (Tanzania). In Mozambique investments are at an early stage, with numbers set to increase in 2015 as the pipeline matures.

It is, however, worth noting that the additionality of AgDevCo funding is somewhat ambiguous in this output indicator. ‘Farmers engaged in agribusiness’ not only includes a wide spectrum of beneficiaries (anything from an as yet not realised potential increase in income to formal access to inputs and extension services), but also in some cases farmers who were engaged prior to the AgDevCo investment, where it is considered by AgDevCo that the company may have liquidated without further funds. Most of these categories have been agreed by DFID; however the issue of how farmers that were engaged prior to funding needs to be resolved. For example, 3,700 of the smallholders engaged in Tanzania via formal contracts were part of a pre-existing outgrower programme by the Rungwe Avocado Company (RAC); results are claimed in this case as it is likely RAC would not have been able to continue normal business operations in the medium/long term without AgDevCo funding.

For future years, further disaggregation of this indicator will help to avoid some of this ambiguity, and following last years’ annual review, changes have been made to the post 2014 logframe. However, in future narrative reporting should clearly highlight those investments where numbers relate to smallholder involvement pre-investment.

Summary of responses to issues raised in previous annual reviews

Recommendations from 2013 Annual Review	Response
Recommendation 4: Indicator 2.1 should be amended, as follows: delete cumulative.	Amended in the post-2014 logframe to: “Total number of smallholders engaged in agribusiness with and without formal contracts (annual): (a) male farmers; (b) female farmers; (c) total individuals benefitting (i.e. Total male and female farmers multiplied by household size)”
Recommendation 5: Additional Output 2 indicators should be added as follows / - Indicator 2.2 Increase in number of smallholder farmers using improved inputs / - Indicator 2.3 Increase in number of smallholder farmers selling to aggregating, storage or food processing services / - Indicator 2.4 Increase in number of smallholder farmers using agricultural extension services	Further disaggregation was needed. Output indicators added for the post-2014 logframe as follows: / - Indicator 2.2 Number of smallholder farmers engaged in agribusiness via self-employment/without formal contracts (annual): (a) male farmers; (b) female farmers / - Indicator 2.3 Number of smallholder farmers engaged in agribusiness via formal contracts (annual): (a) male farmers; (b) female farmers / - Indicator 2.4 Number of smallholder farmers selling to aggregating, storage, or processing services (annual): (a) male farmers; (b) female farmers / - Indicator 2.5 Number of smallholder farmers using agricultural extension services and improved management practices (annual): (a) male farmers; (b) female farmers

Recommendations

Recommendation 2: AgDevCo to agree a clear methodology with DFID on how they count and report on farmers engaged prior to AgDevCo funding being given.

Output Title	Increase employment through the development of agribusinesses.
Output number per LF		3	Output Score	C
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Number of jobs created (FTE)(cumulative): a) men; and b) women.	Men 684 / Women 684 / TOTAL 1368	Men 492 / Women 189 / TOTAL 681

Key Points

Job creation figures for this year were less than half that projected in the logframe, substantially not meeting expectation and as such a ‘C’ score has been awarded. There are a number of reasons for this target being missed:

- Job creation impact is only reported where investments have had 1 full year of operation, as such impacts from some investments made in 2014 will not be reported until 2015
- A late start and some disbursement delays resulted in less time for the pipeline to be developed (please refer to comments under output 1)
- Impacts on jobs created were likely overestimated when the logframe was pulled together (i.e. some investments are used for capital expenditure for mechanisation, which may not result in additional jobs).
- A larger proportion of investments in greenfield and/or primary production with longer start up times have resulted in a slower trajectory of impacts.

Jobs that were created came from investments across the portfolio including:

Tanzania- Sasamua Holding Ltd (banana and pineapple production)
Tanzania – Rungwe Avocado Company (RAC)
Mozambique - Westfalia (greenfield avocado)
Mozambique – AC Matama (soya)
Zambia – NWK Grainhandlers Ltd (soya and maize)
Zambia – Eastern Province Farmers’ Cooperative (groundnut)
Zambia – New Rotations (groundnut)
Malawi – Phata Outgrowers (sugarcane)
Ghana – ZOCOFFAMS (rice and maize)
Ghana – Samsford Enterprises (rice and maize)

There are a number of issues with the methodology for calculating this indicator that are worth noting. The methodology used for job creation is based upon the standard PIDG methodology where 2 seasonal jobs equate to 1 full time equivalent job (FTE). Although this is standard accepted practice in PIDG reporting, its limitations and/or accuracy should be taken into account when interpreting the indicator and this is rightly highlighted in the AgDevCo Annual Report. There was also some ambiguity between the reporting of temporary posts and seasonal posts, with AgDevCo reporting both 2 temporary or seasonal jobs as equating to 1 FTE, although there is a clear difference between the two. Work is now on-going between AgDevCo and Abt (the firm contracted for the independent evaluation) to assess the appropriateness of this methodology.

During some conversations with the AgDevCo country teams, it was apparent that teams were trying to compensate for these limitations by removing some casual workers from the jobs created calculation. For example, in Tanzania, casual workers with less than a certain number of days or hours worked were removed from the calculation for one investment. This approach will likely result in more accurate reporting of actual jobs created, however it will be important to ensure that this is undertaken systematically across the portfolio with clear guidance from AgDevCo HQ, rather than on an ad hoc basis driven by country teams.

In some instances the figures reported under this indicator are not just new jobs created, but also include jobs which existed before the investment took place. Existing jobs are counted where the AgDevCo investment is assessed as ‘rescuing’ an otherwise failing business where job losses could have occurred.

More importantly, it was reported that at least 2 firms, one in Tz and one in Moz did not give employees permanent contracts, but instead kept them on temporary contracts (for example, a 3 month contract, 2 week break, then another 3 month contract, repeated) to avoid having to pay social security and other government mandated contributions. If there is not a clear business case for doing this in the short term (i.e. the business will definitely fail), AgDevCo should ensure these types of issues are picked up during the ESG due diligence and work with investees to formalise employment, where it is of benefit to the employee.

Site visits gave an indication of the sometimes weak link between job creation and mechanisation of agriculture. RAC reported that the AgDevCo investment will likely reduce employment in the short term as further mechanisation occurs. This could also be the case across other investments in expanding commercial agriculture. The converse is also true: KPL was creating jobs in the short term, and there are often considerable spill-over effects that are not captured in reporting.

Summary of responses to issues raised in previous annual reviews

Recommendations from 2013 Annual Review	Response
Indicator 3.1 should not measure results cumulatively, such results are stocks (not flows).	The current logframe was not amended, but this change has been incorporated into the new AgDevCo logframe which will take effect from April 2015.

Recommendations

Recommendation 3: AgDevCo to reassess the methodology for calculation of full-time equivalent jobs (FTE) with the independent evaluators. They should finalise a simple methodology to count seasonal/temporary workers.

Recommendation 4: DFID/AgDevCo to alter logframe indicator 3.1 to (a) new jobs created (b) jobs maintained.

Recommendation 5: After the approval of an investment, AgDevCo should ensure that the company is not employing staff on temporary contracts to avoid payment of formal contributions/benefits to the detriment of employees, and aim for best practice in labour relations.

Output Title	Increase agriculture-supporting infrastructure in targeted countries.
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Hectares of irrigated land (cumulative) (Ha)	2,070 Ha	485 Ha
4.2 Processing throughput/capacity (cumulative) (Mt)	8,500 Mt	14,538 MT

Key Points

Output indicator 4.1 substantially did not meet expectations; however indicator 4.2 substantially exceeded expectations. An overall score of ‘A’ is awarded based on these two indicators. Although investments have been made in 2014 that are planned to lead to several thousand hectares of irrigated land from 2015 and beyond, only 3 countries – Mozambique (50Ha), Tanzania (110Ha) and Malawi (325Ha) – had an actual increase in irrigated land in 2014.

The surplus above the milestone for output indicator 4.2 was mainly driven by large increases in processing throughput in Zambia (8,199mt) and Ghana (5,550mt), via 2 investments. Malawi and Mozambique did not contribute any increases in throughput.

Summary of responses to issues raised in previous annual reviews

Recommendations from 2013 Annual Review	Response
Recommendation 6: Indicator 4.1 should not measure results cumulatively since results are stocks (not flows), therefore the same logframe correction as Recommendation 4 should be made to Indicator 4.1. / Indicator 4.2 cannot measure processing throughput (a flow) and capacity (a stock) in the same indicator. It is proposed that capacity be deleted as throughput is sufficient.	Output indicators have been amended/added for the post-2014 Log Frame as follows: / - Indicator 4.1 has been kept as is: “Hectares of irrigated land (cumulative) (Ha)” / - Indicator 4.2 has been amended as follows: “Processing capacity installed (cumulative) (MT/day)” / - Indicator 4.3 has been added: “Agribusiness (annual) processing capacity utilization rate (average daily throughput as % of installed capacity)”

Recommendations

No recommendations made

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

There are no major changes in key cost drivers; these remain as fund management costs and overheads. These compare favourably with fund management and overhead costs of similar institutions. AgDevCo’s fund management and overhead costs in 2014 amounted to $6.3m on $57.5m of committed funds (10.9%) decreasing from 18.9% last year as the investment portfolio grows (data for AgDevCo’s overall portfolio, although to be noted that not all this is currently invested).

VfM performance compared to the original VfM proposition in the business case

No specific value for money metrics were identified in the original business case. However AgDevCo are in the process of agreeing with DFID a complete set of VfM metrics that will be reported against from 2015 onwards. These form part of the newly approved AgDevCo business case and include:

1. Fund management cost ratio (the ratio of fund management costs to total investment funds).
2. Administrative cost ratio (the ratio of fund management and overheads to total investment funds).
3. Leverage ratio (The ratio of private and DFI finance committed to AgDevCo investment)
4. Smallholder engagement rate, disaggregated by sex (Ratio of total committed investment to number of smallholders engaged)
5. Job creation rate, disaggregated by sex (Ratio of total committed investment to number of jobs created)
6. Business failure rate (Number of investees ceased trading as a proportion of enterprises financed)

Assessment of whether the programme continues to represent value for money

Yes, at present the programme still remains value for money – no significant cost or benefit changes have occurred to change the original assumptions in the business case. Going forward, AgDevCo must report against the VfM metrics in the new business case to allow more accurate tracking of VfM over the duration of the programme.

Recommendation 6: A clear timeframe to be agreed to confirm the methodology for reporting on VfM metrics from 2015 onwards.

Quality of financial management

Financial management in AgDevCo is rated as good.  Annual audited financial statements are provided, which have been unqualified to date. In 2014 funding to AgDevCo was channelled through the PIDG; in line with this arrangement DFID disbursed funds based on a needs letter twice a year. The financial reports provided in the needs letter were clear, detailed and provided accurate information.

From FY 2015/16 DFID will have a direct funding relationship with AgDevCo. As part of the new arrangement AgDevCo will produce quarterly financial reports and disbursement requests. Moving to quarterly disbursements reduces the risk of investments not proceeding to Board approval and cash being held in the AgDevCo account for a long time before commitment.

Date of last narrative financial report	27 February 2015
Date of last audited annual statement	31 March 2015

E: RISK

Overall risk rating: Medium-High

The overall risk rating has not changed since the last annual review. AgDevCo’s business model, by nature, assumes high risk and as a result AgDevCo maintains a comprehensive risk register of 23 key risks. The following two risks are in the Highly Likely (highest rating) category on the global register: likely to occur every couple of months – i.e. there is an ongoing likelihood.

- Operational risk
- Regulatory compliance risk

The following seven risks are in the Significant Impact (highest rating) category on the global register: will require substantial resources (financial, management) to overcome damage.

- Reputational risk
- Funding risk
- Political/country risk
- Business system risk
- Regulatory compliance risk
- Development impact risk
- Social and environmental risk

‘Regulatory compliance risk’ receives the highest rating for both impact and likelihood. This risk occurs because the countries in which investees' or AgDevCo's own projects operate can have regulations that cause delays and increase costs associated with doing business in the region.

Overview of programme risk

AgDevCo Risk Management

Overall programme risks are formally reported to DFID at least quarterly, via submission of the risk matrix. Major changes in risk ratings are also raised at DFID wide steering committee meetings, submitted with disbursement requests, and voiced at monthly calls with DFID. Specific risks at the investee level are also monitored and are reported in the quarterly country level reports and portfolio review. This includes risks around impact, investment and environment, social and governance (ESG) criteria.

Significant progress has taken place since last year on formalising the ESG due diligence process for investees. Strong ESG assessments can help to identify and mitigate many of the risks associated with investing in businesses in Africa that are of key concern to DFID. For example, ESG due diligence would cover issues such as community conflict, land, child labour, sustainable water use, bribery, tax evasion and so on. For large investments (+$1m), AgDevCo requires investees to be compliant with IFC performance standards. For smaller investments a more pragmatic approach is taken with businesses put on an improvement plan, where required. AgDevCo is also developing manuals for smaller businesses to aid compliance.

The ESG process is led by the country team and quality assured by the AgDevCo Head Office M&E specialist. AgDevCo is still building its skills in this area and will boost capacity further by employing an ESG specialist. Given the importance of ensuring a comprehensive ESG process, this position will be key in providing assurance to DFID that non-financial risks are being identified systematically in all investments.

The following risks are highlighted at a country level by AgDevCo, as they are either highly likely to occur, or have significant impact if they do occur. Those highlighted in red receive the highest ranking in both likelihood/impact categories, thus should receive closer monitoring by country offices.

Country	Highly Likely Risks	Significant Impact Risks
Ghana	Reputational / Intellectual Property / Currency / Investment Performance	Reputational / Funding / Financial Crime
Malawi		Reputational / Currency
Mozambique	Reputational / Legal HR / Regulatory and Compliance / Investment Performance / Development Impact	Reputational / Legal HR / Regulatory and Compliance / Investment Performance / Employee Health & Safety / Political/Country / Financial Crime
Zambia	Investment Performance	Reputational / Financial Crime / Theft / Fraud / Social & Environment
Tanzania	Employee Health & Safety / Intellectual Property / Investment Performance	Employee Health & Safety / Reputational / Funding / Financial Crime / Theft / Fraud / Social & Environment / Political or Community

Investment risk, business risk, impact risk and ESG risks are clearly tracked for each investment and reported in quarterly and annual country level reports. The Tanzania portfolio currently has the highest level of reported risk. DFID country offices should ensure that they have a good understanding of what is driving the risk profile of investments within their portfolios.

DFID Risk Management

For the 2014 review period, a total of 6 major risks were highlighted. These risks are still relevant, and another 8 risks have been added to the 2015 business case that will need to be monitored going forward. Global risks from 2014 are:

	Risk	Probability	Impact	Mitigation Strategy
1.	Regional macro-economic stability is not sustained	M	H	Support to overall macroeconomic stability through DFID and other donor programmes
2.	Poor policy and regulatory environment deters investment in agriculture infrastructure and agribusiness	M	H	Criteria for selection of AgDevCo investments include countries where business climate is sufficiently well developed to attract private sector investment in agriculture.
3.	Fluctuating political support and strong vested interests hinders commercial investments	L	M	AgDevCo continues to establish and maintain good relations with local counterparts testing their support and locking it in where it exists. Ongoing policy influence by DFID country offices and other donors in-country.
4	Non-Tariff Barriers obstruct cross border trade flows, affecting levels and reliability of throughput for regional agro-processing investment	M	H	Criteria for selection of AgDevCo regional investment include an analysis of relevant costs of tariff and non-tariff barriers. Coordination with other DFID programs specifically targeting NTBs.
5.	Fees charged for use of improved infrastructure are unaffordable by the poor	L	H	AgDevCo projects are structured to be financially viable, which necessitates the price of services to be pitched at an affordable level to its customer base which are smallholder farmers.
6.	DFID money is used for projects which would be developed by private sector without any public sector involvement	L	L	AgDevCo’s investment framework requires additionality.

Currently DFID is the majority funder of AgDevCo (over 80%), with AgDevCo structured with a single shareholder. AgDevCo are currently in the process of transfering its shares to new a company limited by guarantee. AgDevCo and DFID have both seeking legal advice on this issue as DFID has been requested to agree to the proposed changes as per contract agreements. If AgDevCo became a company limited by guarantee then DFID could potentially become a member of the company, as is done in other programmes, with a role in AgDevCo’s governance commensurate to the level of funding provided.

Risks reported to DFID are kept live in the central ARD AgDevCo delivery plan, and monitored through formal meetings and before disbursements take place.

DFID Internal Audit report

IAD recently completed an audit of the PIDG which covered the AgDevCo portfolio in Tanzania. A number of recommendations have been made to strengthen risk management and will be actioned/responded to following finalisation of the DFID management response.

Outstanding actions from risk assessment

The actions log for the 2013 AgDevCo due diligence report has recently been updated (EDRM reference 4951999). The only remaining issue to be addressed is around the governance of AgDevCo including under what legal form AgDevCo will be registered and how disbursements will be made in future to avoid payment in advance of need. These issues are currently being discussed and agreements finalized.

The DFID risk register has recently been updated to include a total of 14 risks, it is held within the programme’s delivery plan, and includes ‘Recommendation 18: the high risk of failure to achieve development impact results should be added’ from the 2013 Annual Review.

Recommendations:

Recommendation 7: DFID to be given the timetable for the ESG Specialist recruitment and to be thoroughly appraised of how this staff member will support and strengthen ESG due diligence across AgDevCo investees.

Recommendation 8: DFID country offices to ensure risks are discussed systematically at quarterly steering committee meetings. Country offices must understand all highly likely and significant impact risks and be satisfied with the measures taken to manage/mitigate impact.

Recommendation 9: All remaining DFID due diligence actions to be completed by December 2015.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Overall AgDevCo delivered against their forecast for 2014. Requesting disbursements from DFID totalling £23,493,174 against a forecast of £23,580,522; this is within a 1% variance. On the individual budget lines there were higher variances. Africa Regional came out 8% under forecast mainly due to some large investments falling through at due diligence stage. The pipeline of regional investments however appears healthy enough to compensate for the underspent in 2014. It can take months for investments to move through the approval process, ensuring that they meet all the requirements, inevitably there will be times when investments don’t proceed and others come along.

Performance of partnership (s)

Overall the partnership between DFID and AgDevCo has been performing well. Highlights on AgDevCo’s performance include the strong, professional management teams in-country, good country knowledge, excellent feedback from beneficiaries on the support received, and clear reporting.

At a country level, interviews with DFID and AgDevCo staff highlighted several areas that could be improved:

1. Further work is needed to increase interactions with indigenous / locally owned business. Some countries have noted a bias to investing mainly in foreign owned/managed companies, with potential political and developmental repercussions. This issue was also highlighted in the 2013 annual review. Although AgDevCo is taking steps to increase marketing efforts, in some countries they are struggling to identify indigenous businesses that meet their due diligence and KYC requirements. Some countries are adopting alternative approaches, such as investing in smaller businesses with a partnership with a larger organisation (such as NWK Agropreneurs in Zambia. Further sustained work is needed in this area.
2. A greater focus on gender. Results are disaggregated by gender, however most countries argued a lot more could be done to target investments towards women (although it is noted that not all investments are suitable, and this cannot be the sole basis for an investment decision).
3. Lack of local staff. The difficulty in recruiting good, local staff at a competitive wage was raised by some AgDevCo offices. This is important in building a locally representative pipeline. Issues included possible lower than market wages and competitive job markets for employers.
4. Speed of investment. Several DFID country offices expressed concern at the lag in time between staffing up, and building an investment pipeline, as well as lags between having an active loan book and programmes actually beginning. These expectations that things may happen quicker than they actually do may create disparities between forecasting and reporting.

Feedback for DFID has overall been positive, although the speed at which the Blended Partnership financing and investment choices had to be made and announced was not conducive to the normal timeframe of making investment decisions. This raised the expectations and assumptions of investees, making it more difficult for AgDevCo to operate. A number of AgDevCo country offices expressed a desire for more joint contact with DFID Head Office and AgDevCo Head Office

Recommendation 10: Further sustained work required by AgDevCo to ensure an increasing number of partnerships (direct / indirect) with local/indigenous businesses in some countries

Asset monitoring and control

Through the provision of debt and equity AgDevCo will recoup a substantial proportion of the funds it invests. As a non-profit-sharing investment company, AgDevCo statutes confirm they will redeploy funds into future projects generating even greater employment, income and development outcomes. Assets are recorded on their financial statement and reviewed by the DFID Programme Manager.

G: CONDITIONALITY

Update on partnership principles (if relevant)

N/A.

H: MONITORING & EVALUATION

Evidence and evaluation

No new evidence has emerged which challenges the design of the programme.

As agreed in the original business case an independent evaluation will be undertaken for which ARD will contribute up to £1.7 million from its RDEL budget. Abt Associates has been contracted as the Evaluation Management Unit (EMU) to take this forward. The evaluation design report has now been drafted and is in the final stages of internal DFID sign off before being sent on for SEQAS clearance; thereby concluding the design phase.

The purpose of the evaluation is to independently assess the results achieved by AgDevCo and to learn where, when, for whom, how and why the investment approaches work within different contexts and attain development goals.

The independent evaluation uses a theory-based mixed methods approach that evaluates the impact of AgDevCo investment along its value chain. It has four objectives, with research questions designed to test the assumptions underlying the programme’s theory of change. In terms of products, the evaluation will deliver a qualitative assessment and financial analysis of AgDevCo’s entire investment portfolio, as well as five purposive deep dives of 1 investment in each of the 5 AgDevCo investee countries using the Structure, Conduct, Performance framework approach. By mid-2017, a Mid-term Evaluation Report will be produced, which presents preliminary findings and suggestions for the refinement of the End-line Evaluation design. This last will be produced in the summer of 2020.

The complexity of the evaluation approach poses a potential challenge in synthesizing and drawing out portfolio-wide lessons. The EMU’s framework for comparing and synthesizing findings, which builds on its system of coding data, seeks to effectively mitigate any issues.  Further, the six year duration of the Independent Evaluation limits the assessment of the impact of AgDevCo’s activities to those that are produced by the end of the programme. This means that longer-term and more tenuously-linked impacts will not be measured by this evaluation. In order produce a useful product within already constrained parameters it is essential that high quality, compatibly formatted data is produced by AgDevCo and the EMU. The EMU is working with AgDevCo to strengthen its data collection and database systems and quality assuring data produced.

2014 Monitoring Systems

Since last year AgDevCo have made significant improvements to their monitoring systems with clear evidence of more robust guidance from AgDevCo HQ on monitoring and reporting impact at each stage of the investment process, across country offices. Where feasible some investments had had baselines undertaken to allow more accurate reporting of before and after results, although funding constraints will limit the extent to which this can be done across the portfolio. If viable, independent verification of results reported by investees is undertaken through site visits and/or cross checking financial data produced. A number of observations were made during discussions of monitoring systems which it is worth noting for this review:

- Impact data is produced by the investee for AgDevCo, with some indicators being easier to report on than others. Household income uplift, job creation and numbers of smallholder beneficiaries present more challenges than other financial data, particularly given this is data not normally collated by businesses. AgDevCo has made real efforts to ensure data reported is as accurate as possible and to verify data presented, but inevitably some businesses have greater capacities than others. Where investees have less ability AgDevCo should sustain efforts to build capacity and verify data where feasible.
- Reporting of data for the outcome level indicator ‘household income increases’ presents particular challenges, given resources are not available for clear baselines to be set for all projects.
- Reporting of data for the outcome level indicator ’private capital leveraged’ raised a number of queries that will need clarification to ensure a methodology is applied to this indicator that all parties agree to and understand; (i) grants brought in alongside AgDevCo funds are included in the numbers reported for DFI capital leveraged; (ii) it was unclear how decisions were made about additional capital to be included, for example, whether this had to be capital uniquely brought in as a direct result of AgDevCo funds, or whether capital already committed or invested at later date could be included.
- Sex disaggregated data is presented in the logframe. To date targets have not been met for number of jobs created for women, although targets for female farmers are on track. All AgDevCo country offices felt they could do more in this area, but expressed the need for more support to do so. AgDevCo HQ is in the process of finalising a gender strategy and some linkages have been made with relevant teams in DFID.
- All of businesses visited in Tanzania had either received AECF financing (KPL, RAC and Suma Hydro) or were in the process of applying (EFTA). Given the presence of AECF and other DFID funded initiatives across the target countries (for example, Wakulima Tea Company also had funds from other DFID-backed programmes, and EFTA from FSD), it is of utmost importance to ensure that results were not being double reported. Programmes that receive AgDevCo funding on top of prior large DFID contributions through other sources should be scrutinised more closely for additionality and vfm.
- Counting smallholders. Several areas to review have been raised in the output indicator comments (what classifies as ‘engagement’; how are temporary workers counted). In addition, where AgDevCo states that their investment prevented a business folding, they count all smallholders as beneficiaries. In some investments the direct link to smallholders is ambiguous, with development indicators in negotiation (e.g. Suma Hydro, below). Clarification should be made on beneficiaries and more qualitative data can be used to illustrate AgDevCo’s overall impact.
- The logframe does not necessarily capture the many wider benefits of AgDevCo investments outside of income increases or employment, such as transparent pricing or prompt and reliable payments for crops. More qualitative case studies may help to tell this wider story.

Recommendations

Recommendation 11: AgDevCo to develop a gender strategy with support from DFID, to be implemented in 2016. DFID to monitor and provide support to its development, finalisation and roll-out.

Recommendation 12: AgDevCo to ensure consistent methodology applied for calculating ‘private capital leveraged’ that is accepted and clearly understood by all parties.

Recommendation 13: DFID (ARD) to urgently check result reporting to ensure that the same results are not being reported twice to/within DFID via different programmes– i.e. through AECF and AgDevCo.

Monitoring progress throughout the review period

Visit was undertaken to a number of investee businesses in Tanzania.

Kilombero Plantations Ltd (KPL).

This is AgDevCo’s largest investment and is funded through the Tanzania Blended Partnership. It is a 5000 ha. dryland rice farm in the Kilombero Valley of Tanzania. AgDevCo has committed $10m for the construction of a gasification plant and the expansion of up to 3000 ha of irrigation. To date $2.4m has been disbursed in the form of convertible debt. KPL has received the majority of its financed from a social impact private equity investor and Norfund; and has received some finance from a commercial private equity fund and several DFIs. The funds required for expansion would not have been available locally or from other purely commercial sources and there is clear financial additionality in AgDevCo funding.

Mechanisation on part of the 5,000ha KPL rice farm	Construction of the gasifier: waste rice husks will be used to reduce the energy bill

The business encountered significant difficulties last year with a drop in rice prices and issues with smuggling of imported rice from Pakistan, thus avoiding high EAC tariffs. As a result much of the last 12 months has been spent trying to ensure the sustainability of the core business. The agricultural advice provided by AgDevCo is highly valued.

In collaboration with USAID, KPL has provided resources to train local farmers to grow rice using the ‘sustainable rice intensification’ method. Discussions with local farmers highlighted that this has significantly increased yields and profitability; however, most farmers only farm a small proportion of their land using this technique due to the increased costs of production and unaffordability / lack of finance to fund further increases. KPL has tried to initiate a partnership with a local bank to pre-finance the inputs required. The form of this partnership has changed a number of times. But the nature of the paddy purchase contract (as well as an offer from a trader which did not then materialise) last year resulted in a significant reduction in the number of farmers participating. As a result the bank providing the finance withdrew its support.

KPL is the largest employer in the valley and positive impacts in the local community were seen as a result of job creation. KPL currently employs 190 people and this will increase slightly as a result of the expansion. Many are from the locality. Farmers met spoke positively about supplementing their income with casual work at the farm.

KPL has enormous potential to act as a key buying point for farmers in the valley – offering a reliable and fair price for smallholder rice. At present farmers sell mainly to traders who travel from Dar es Salaam. Farmers spoken to had mixed views of selling to KPL – some preferred to sell to traders as the price was the same, others did not want to incur the cost of transporting their rice to KPL, others thought the buying window was too small. On the positive side famers reported that KPL is more likely to buy without question the variety of rice they grow.

Looking forward, KPL is again working with a local bank to arrange a pre-finance deal for next season for local farmers. To work this will require sustained effort by both AgDevCo and KPL and further work is needed to ensure that a transparent, easily understood mechanism is put in place. At present AgDevCo did not appear to have the specialist resources on the ground to support this and further additional support could be provided through the newly established smallholder unit in AgDevCo HQ.

Recommendation 14: AgDevCo to focus on the development of the smallholder development model including at Kilombero Plantations Ltd. and to share and discuss with DFID.

Equity for Tanzania

Equity for Tanzania is a leasing business based in Moshi, Tanzania. It provides leasing finance for small pieces of equipment, with approximately 50% being in the agricultural sector. They fill a gap in the formal commercial banking market, providing lease finance of $2,000 to $50,000 to small businesses in the locality without the need for formal collateral (the leased equipment acts as collateral). Current AER is 32% (vs. a local bank rate of 24-26% AER and 150% collateral) and the default rate is 12% (partly driven up by early investments). The business is not yet at breakeven point and needs to expand its loan book significantly to fully cover overhead costs.

AgDevCo will take a 49% equity stake in EFTA through a $2.5m investment. At present all EFTA’s ’s investors are DFIs or social impact investors, this includes IFC, Cordaid, Lundin and FMO amongst others. However, they have all invested in an LP Fund structure which would not result in the establishment of a permanent Tanzania leasing business. AgDevCo is valued in providing capital to allow EFTA to invest of its own balance sheet. AgDevCo’s investment is taking considerably more risk than most DFIs and impact investors are likely to be willing to take at this point. AgDevCo is also valued for its agricultural expertise and is also bringing a leasing expert onto the Board to provide strategic guidance.

Businesses visited were across the portfolio and included a poultry feed producer, private clinic and brick maker. Businesses reported the value added the leased equipment had provided, increasing profitability and allowing them to keep up with competitors. The additional advice provided by EFTA on running their businesses was also valued.

Rungwe Avocado Company

Rungwe Avocado Company (RAC) is a commercial avocado producer based in the south-west of Tanzania, established in 2009. Its business model focuses on export of avocados grown on a 101ha commercial farm and by 3,700 smallholding out-growers. A total of $1.5mln in funding was committed in early 2014 ($1.22mln debt / $0.28mln equity), with AgDevCo taking a 20% stake in the company. The financing is partly disbursed and has funded an irrigation scheme covering the commercial farm (installed Q4 2014) and ongoing operations.

Outgrowers would only segment some of their land for avocados	Smallholder plot, including avocados

Although 3,700 farmers have signed contracts to supply RAC with avocados, only 300 or so farmers sold produce to the company in 2014. Avocado trees take circa 6-7 years before they produce a full yield at a commercial export quality, and most of the smallholders are yet to produce a full commercial crop. Over the next couple of years, available produce from smallholders for export should dramatically increase. In the meantime, inputs are supplied to a small subset of farmers and extension workers work at the village level to market to new farmers. Average farm size is about 0.5 acres (0.2 ha) for current participants; due to the costs of working with smallholders, RAC is aiming to only target farmers in the future with around 12 acres (5 ha) or more of land available to avocado production.

Margins are currently tight, as the company initially struggled to meet strict export quality standards, which resulted in high wastage. As a result, returns to smallholders were reported to be lower than the farmers expected. No real local market exists for avocados though, so farmers can only sell a minority of produce in the area. Any product that is not suitable for export is currently returned to the farmers (used for consumption, and some sold locally), which provides a small extra income stream. Looking forward, RAC aims to increase the price paid to smallholders, although it first priority is to turn a profit and stabilise the commercial business.

RAC struggled financially before the AgDevCo investment. The company reported that financing may have been possible elsewhere. RAC’s current cost of debt is estimated at approximately 11%, with AgDevCo charging 8% on their loan, with upside expected through its equity investment. It is unlikely RAC would have been able to access further commercial debt, although a soft loan from the Tanzanian government is currently in application stage, for 1Tsh billion (approx. $550,000). When combined with agricultural knowledge and support provided by AgDevCo to the business, it is considered that AgDevCo financing meets additionality requirements.

The company has several other grants/soft loans, including $200,000 form USAID under the TAP initiative, $80,000 from the Danish government and $1,400,000 from AECF ($200,000 is grant) for a new warehousing facility. The AgDevCo loan is secured against the AECF-funded warehouse.

During the field visit, smallholders were generally pleased with RAC and avocado production. The crop requires minimum effort (some pruning and fertilising), and RAC provides staff to conduct the harvesting. This made it suitable for older farmers who were happy to receive a fairly stable yearly payment (it seemed to function a bit like a pension). Avocados were generally part of a farmer’s portfolio that included bananas and tea. Several farmers wanted to increase their avocado production; with care and a mature tree base, yield can reach 20mt /ha, however a more realistic yield is around 7.5mt/ha. The price last year was 369Tsh/kg ($0.20/kg). With a 0.2ha plot, a conservative income is around $300 per farmer/year.

Suma Hydro Power Project

Suma Hydro Project is a 1.54 MW planned hydro power plant, currently in the early stages of project development. AgDevCo have funded $250,000 to cover initial scoping costs, with a further $3,500,000 (debt) planned for Q3 2015. Rift Valley Energy (RVE) was awarded the design, build and operate contract after a tendering process. TATEPA (a local tea production company) contributed $450,000 to the investment, and AECF has provided $850,000. Once complete, TATEPA will control 49% equity and RVE 51%.

The main beneficiary of the Suma Hydro project is the Wakulima Tea Company. Wakulima was visited as part of the review, and a representative from RVE was present to answer queries. Wakulima is owned by TATEPA (70%) and a smallholder organisation (30% equity) that represents approximately 13-15,000 tea farmers. The price of tea has been decreasing, and high energy costs have been putting pressure on Wakulima margins, resulting in no recent dividends to farmers, with Wakulima absorbing some of the price drop at the detriment of its balance sheet (they should be paying 176Tsh per kg, but are keeping the price to farmers at 231Tsh/kg), which is not sustainable.

Wakulima will benefit from Suma Hydro by a reduced energy price, as well as a more consistent power supply. Due to frequent power cuts by TANESCO, the Tanzania state power company, Wakulima have to run two diesel generators for approximately ¼ of operating time. The power is required to run the tea processing factory, which processes approx. 160mt of tea per day. The factory uses roughly 266MWh / month, which will be about 1/3rd of Suma’s output (dependent upon water levels and operating time). Although the price of the power from Suma to Wakulima will be higher than TANESCO charges ($0.18/KWh vs. $0.13/KWh), once the cost of operating the generator is priced in, the hydro plant should work out marginally cheaper, and more stable.

Suma Hydro will supply the excess power to the grid and to households in the area. The company currently has one other hydro project running, and is piloting a payment model that is affordable to low-income households. Under their ‘D1’ basic tariff pricing for households that use less than 30KWh/month (enough for very basic utilities), the charge is currently $0.04KWh – less than $1/month. Connection fees are approximately $70.

With an anchor customer taking a proportion of power output, and an agreement with TANESCO under the feed-in tariff, it is possible Suma Hydro could have sourced commercial funding. However TANESCO is not known for on-time payments, thus it is possible that either the terms of the commercial funding would have been too steep, or not possible to source.

Freshly picked tea leaves drying for 48 hours at Wakulima – part of the 160mt/day	Chopped tea leaves sifted and heading for the dryers

Wakulima Tea Company will benefit from likely cheaper and more consistent power; this should translate to stronger profit margins and a greater return to shareholders (30% smallholder organisation) in the longer-term. Households should also benefit from a power connection, although it is not known how this project sits with recent TANESCO expansion in the area.

Annual Review process

The review was undertaken by Suzanne Parkin (PSD Adviser Private Sector Department), Tim McNeill (Private Sector Development Adviser, DFID Southern Africa), and Marco Serena (PSD Adviser, Africa Regional Department). The review took place between April 6th and 29th April 2015. Fieldwork was undertaken in Tanzania only from 13th to 20th April 2015. The following people were met / interviewed:

Name	Position	Email/Phone/Skype
DFID
John Overton	Team Leader, Energy and Infrastructure Team, PSD	j-overton@dfid.gov.uk
Harry Hagan	DFID ARD Wealth Creation Team Leader, Chair AgDevCo Steering Committee	H-Hagan@dfid.gov.uk
Martin Alsop	PSD Adviser, DFID Zambia	m-alsop@dfid.gov.uk
Vincent Langdon-Morris	Livelihoods Adviser, DFID Ghana	V-Langdon-Morris@dfid.gov.uk
Gillian Rogers	PSD Adviser, DFID Tanzania
Richard Boulter	Growth Team Leader, DFID Tanzania
Tiago De Valladares Pacheco	PSD Adviser, DFID Mozambique	T-Valladares@dfid.gov.uk
AgDevCo
Daniel Hulls	CEO, AgDevCo	dhulls@agdevco.com
Alex Simuyandi	Operations Manager, AgDevCo	asimuyandi@agdevco.com
Rui Sant' ana Afonso	Mozambique Country Director, AgDevCo	rafonso@agdevco.com
Rosanne Whalley	Mozambique Country Manager, AgDevCo	rwhalley@agdevco.com
Nick Jones	Tanzania Country Manager, AgDevCo	njones@agdevco.com
Chris Isaac	Malawi Country Director, AgDevCo
Jim Henderson	Commercial Agriculture Adviser (Malawi), AgDevCo	jhenderson@agdevco.com
Siobhan Franklin	Zambia Country Manager, AgDevCo	sfranklin@agdevco.com
Tom Phillips	Ghana Country Manager, AgDevCo	tphillips@agdevco.com
Keith Palmer	Chair, AgDevCo	kpalmer@agdevco.com
Sean Carey	Investment Manager, AgDevCo	scarey@agdevco.com
Rebecca Sankar	Portfolio Manager	rsankar@agdevco.com
Alice Chapple	Senior Impact Advisor	achapple@agdevco.com
AgDevCo Investees or Representatives
Graham Anderson	General Manager, Kilombero Plantations Limited, Tanzania	graham.anderson@agricatz.com
Chris Nichols	Finance Director, Kilombero Plantations Limited, Tanzania	chris.nichols@agricatz.com
Association Chair and Vice-Chair (also farmers)	Smallholder rice association, Mngeta, Tanzania	-
4 x rice farmers	Mngeta, Tanzania	-
Bennett	USAID Coordinator for smallholder/KPL rice project, Mngeta, Tanzania	-
Michael Timmerman	Director, Equity for Tanzania, Moshi, Tanzania	mtimmerman@equityforafrica.com
Coy Buckley	CEO, Equity for Tanzania, Moshi, Tanzania	cbuckley@equityforafrica.com
Tim Ellis	Strategy Manager, Equity for Tanzania, Moshi, Tanzania	-
James de la Fargue	Leasing expert	Jamesdlf@africancentury.co.zw
3 x SMEs	Moshi, Tanzania	-
Rob Clowes	Director, Rungwe Avocado Company	rob.clowes@rungwe-avocado-company.com
2 x avocado outgrowers	Rungwe area, Tanzania	-
Engineer	Rift Valley Energy (Suma Hydro)	-
John Mhagama	Agricultural Operations Manager, Wakulima Tea Co.	-
Robert Shedafa	Financial Controller, Wakulima Tea Co.	-

Additional recommendations from 2013 reviews

A number of additional recommendations were made in the 2013 annual review; these are difficult to capture within the new annual review format. The table below includes commentary on how these have been addressed:

Recommendation	Update
The independent Evaluation Manager should review AgDevCo’s M&E strategy and examine and validate AgDevCo’s central and country data collection and reporting processes and systems	Throughout the term of the contract for the AgDevCo evaluation the Evaluation Monitoring Unit will conduct annual reviews of the monitoring and evaluation data in order to ensure its appropriateness. Feedback to AgDevCo and DFID will include suggestions to improve the accuracy and comprehensiveness of data where necessary. / The first of these reviews has taken place in April 2015.
As part of its investment appraisal process, AgDevCo should evaluate the options for managerial competence building in investees or beneficiary FBOs to improve the chances of long-term contractual sustainability	AgDevCo proposed and the SC approved in October 2014 a re-organisation of their provision of business development services, which includes the establishment of a small holders development unit which will consolidate learning in this area and deliver tailored solutions to the challenges identified by this recommendation.
AgDevCo should plan a properly resourced marketing campaign for finding and securing investments in agribusinesses owned and managed by indigenous businessmen and business women in the five countries	AgDevCo recognizes the need expressed in this recommendation, although it does not apply to all countries in which it operates. This issue is relevant mainly in Mozambique (where many farmers moved from Zimbabwe), and marginally in Zambia and Tanzania, but little in Malawi and Uganda, and not at all in Ghana. / Rather than a marketing campaign, AgDevCo is deliberately targeting indigenous business men and women in countries where its investees are principally from neighbouring countries.
AgDevCo should collaborate systematically with agribusiness stakeholders to exploit synergies for the benefit of investees and smallholders	Ongoing through national level steering committees
AgDevCo country offices should investigate the possibilities for commissioning baseline research studies into qualitative development change	DFID had a tentative agreement with AgDevCo that they could manage part of the evaluation and research budget (initially approved as up to £2.5 million) for activities like this, but we then faced cuts and decided to only have an independently managed evaluation. / In light of this AgDevCo proposed and the SC approved in October a minor budget re-allocation from the business development services budget to resource this element. In addition to the minor budget re-allocation, AgDevCo has committed its own (additional) resources to this. / We are content that they still found budget for this type of research activity. The costs associated with this kind of locally procured activity are not too high (they will usually pay 1 or 2 researchers from a local university and have students doing much of the field work) so overall we have reached a good compromise.
AgDevCo should continue to apply its investment appraisal criteria rigorously to ensure that additionality in its widest interpretation is present in all investments	AgDevCo already applies its investment appraisal criteria rigorously. DFID and AgDevCo have agreed that financial additionality be included as one of the investment appraisal criteria starting from the next financial year. / To be clear, there are 2 parts to AR recommendation 12. The first is about ensuring additionality of funding. As mentioned, this is part of their Main Operational Policies and is reflected in required sections of the investment appraisal templates. / The second part is about ensuring that AgDevCo provide appropriate TA especially to weaker businesses and producers organisations. AgDevCo has taken this seriously and asked to re-arrange the TA budget to create a smallholder development unit which the Steering Committee has approved as a desirable step. Mastercard Foundation is on the verge of providing additional finance to the smallholder development facility.
The Independent Evaluation Manager commissioned by DFID should make proposals for attribution of development impact of results	The EMU is currently considering approaches to measuring the development impact of AgDevCo initiatives in the design of the evaluation strategy. Final proposals will be presented in the final Evaluation Design Report. This will be submitted to the SEQAS for scrutiny and validation shortly thereafter.
AgDevCo should rationalise their DFID reports and propose a more streamlined reporting process to reduce the burden to both parties	A new quarterly report format has been agreed.
Outcome Indicator 1 should be improved, as follows: / Volume should be replaced by value, capital replaced by finance / Planned results should be added for 2013-2016 / Millions should be deleted from all indicators	Included in the revised logframe.
Outcome indicator 5 should be added, as follows: Value of loans repaid to AgDevCo by investees ($m)	Ditto
The following assumptions should be added at Outcome level: The failure rate of investments including both outright insolvency and failure to achieve development impact results will not exceed 25%	Ditto
The high risk of failure to achieve development impact results should be added to the risk register	The programme risk matrix has been updated as part of the new business case.