Annual Review - Summary Sheet

Title: Africa Enterprise Challenge Fund (South Sudan Window)
Programme Value: £3.9m		Review Date: October 2015
Programme Code: 202848	Start Date: September 2011	End Date: December 2015

Summary of Programme Performance

Year	2012	2013	2014	2015
Programme Score	B	A	B	B
Risk Rating	Medium to High	Medium	Medium to High	High

Summary of progress and lessons learnt since last review
The South Sudan Window (SSW) of the Africa Enterprise Challenge Fund (AECF) has had another challenging year. The programme started in 2011 and DFID’s agreement with the Alliance for a Green Revolution in Africa (AGRA) to manage the programme ended on 31 December 2015. The small size of the window operating in a recently formed independent country (ranked the most fragile state in the world) which has been in conflict since mid-December 2013 has affected results. The window has done well in disbursing almost 60% of the contracted commitments to projects in this difficult environment, but suffers from limited reporting and verification of the results. Only three out of five active projects (Century Seeds, Honey Care and South Farmers Co. Ltd.) are currently reporting results and most of those results come from one project (Century Seeds). While the DFID project currently ends in December 2015 it was always expected that the SSW would be a seven year window (the same as other windows within the AECF) and therefore extended until 2017.

While the conflict continues in only 3 out of 10 states (and not the ones the AECF projects are operating in), AECF grantees have still been severely impacted by the effects of the conflict throughout the country, including difficulties in obtaining foreign exchange (due to devaluation), economic downturn, increased insecurity (e.g robberies/theft) and fuel shortages.

The key issues identified during this annual review are:
- The window relies on one project for nearly all of its development results. Although it is common for AECF windows to be dominated by 1-2 projects, in the case of SSW nearly all the reported development results come from Century Seeds. The heavy reliance on one project for success increases the risk of failure.
- The pro-poor nature of the development results reported may be overstated. Century Seeds has changed its original project in response to market demand to work more with larger farmers as seed-outgrowers than it had originally intended. The development results reported for this component of the project therefore include a proportion of results which do not relate to the target rural poor population (living on less than $2 per day). More detailed verification work on these results is required.
- The value for money of the window is worse than other AECF windows. The reduced size of the window has increased the proportion of management fees paid when compared to other windows. From a DFID perspective, the management time required by the country office team to oversee an AECF window has not reduced with the size of the window and is therefore proportionately more than other windows.

Decisions need to be made about the composition of the SSW: whether to merge it with another window or to run a mini competition to utilise potential uncommitted funds. The progress of the five projects, advancement of the Peace Agreement and the status of the cessation of hostilities and any easing of the current issues in South Sudan will play a crucial role in this decision process.

Summary of recommendations for the next year
Recommendations are listed in full in section H. They focus on: (i) improving the value for money of the window by streamlining management, ensuring projects that won’t deliver are closed and considering options for utilising uncommitted funds; and (ii) revising the logframe targets for future years to ensure they remain challenging but also realistic.

A. Introduction and Context
Outline of the programme
The African Enterprise Challenge Fund (AECF) is a US$245m challenge fund for the benefit of rural households in Africa, established in 2008. The Fund provides support to the private sector for new and innovative business ideas in agribusiness, rural financial services and renewable energy/adaptation to climate change that will benefit Africa’s small farmers and rural households.

In September 2011, DFID committed £6m to the Africa Enterprise Challenge Fund South Sudan Window (SSW). An Accountable Grant of £6m was signed between DFID and the Alliance for a Green Revolution in Africa (AGRA) in December 2011, covering the period December 2011 to December 2014. A no-cost extension was then granted for one year to December 2015 and the initial £6m budget reduced to £3.9m, to account for a reduced number of businesses supported (initial target of 11 projects but only 6 awarded and 5 contracted).

Expected Results
The Project Goal is promoting pro-poor growth in South Sudan with the expansion of innovative and commercially viable agricultural and agribusiness sector that benefits the rural poor.

The Project Purpose is to improve the livelihoods of at least 50,000 farmers/ out-growers and clients who will directly benefit from the provision of AECF support for innovative private sector initiatives in agricultural, agribusiness and other enterprises impacting on the rural areas of South Sudan.

The programme achieves this through a combination of grants and 0% interest loans to innovative agribusiness companies. The SSW target was to support 11 companies - 6 projects were approved but only 5 were contracted. Following the outbreak of conflict the DFID office reduced the overall budget (to focus resources on the humanitarian crisis and assess changes to the operating context) which meant the AECF did not run another window to identify other businesses. The five companies contracted are: Honey Care, Southern Farmers, Century Seeds, Frontier Microfinance and Garden of Eden.

Context
The context in which the UK support is provided remains unchanged. The Secretary of State (SoS) made economic development one of her top priorities for DFID. A new economic development strategic framework has been published to guide DFID’s approach to working with private sector to increase investment and trade with Africa. In South Sudan the SoS asked that DFID do more to support an increased private sector and the agricultural sector is a clear priority for such support. South Sudan is currently heavily dependent on oil revenues (which are primarily spent on security) and would benefit by diversifying into other sectors.

However, the context in South Sudan has changed significantly since the programme was implemented, a conflict erupted in December 2013, insecurity (criminality) has increased, the economy is in decline especially in the last year (with the consumer price index showing inflation at 118%).

Agriculture in South Sudan has enormous potential. It accounts for about 80 percent of employment, with traditional livelihood systems involving various combinations of livestock rearing, crop production, fishing, wild food collection and trade[1]. The country has the largest arable land area per capita in the world, yet only 5% of arable land is currently cultivated. South Sudan’s abundant land and water resources could help to meet massive unmet local and regional demand in all areas of agriculture, forestry and fisheries. There is significant potential for regional trade. South Sudan plans to join the East Africa Community (EAC) and is bordered by countries with which there is significant trade potential, including Kenya, Uganda, Ethiopia, Sudan and the Democratic Republic of Congo (DRC).
[1] FAO Plan of Action for Southern Sudan, 2010

Nevertheless, agricultural knowledge and capacity in South Sudan remains very low. Investment by the Government of South Sudan, whose budget is dominated by security spending, is extremely limited. The economy is highly dependent on imports, more than 2 million people have been displaced by conflict and an estimated 3.9 million people (34% of the population) are severely food and nutrition insecure at September 2015[2]. This is an 80% increase compared to the same period in 2014. Insecurity, ongoing conflict, lack of infrastructure and natural hazards have been major contributing factors to this, as well as low productivity and institutional weaknesses in the agriculture sector.
[2] Integrated Food Security Phase Classification (IPC)

The conflict and violence that erupted in mid-December 2013 has had a significant detrimental impact on all sectors and caused a major humanitarian crisis. In response to the changed context, DFID South Sudan undertook a review of all programmes in 2014 and given the vast scale of the humanitarian needs, some funds were reallocated to the humanitarian crisis response and a decision was taken that no new investments would be made in businesses beyond the existing five supported. A ceasefire came into effect in late August 2015 but violations continue.

## B: PERFORMANCE AND CONCLUSIONS

Annual Outcome Assessment
The intended outcome of the SSW is the creation of jobs and an increased income for the rural poor, along with the improvement of wider market systems.

Indicator(s)	Milestones	Progress
1 Cumulative Development Impact: / total net benefit (US$) / total net wages (US$) / development rate of return (DRR) = ratio of development impact (a+b) to funds disbursed (4.5f)	2,000,000 / 260,000 / 1	688,431 / 239,157 / 0.5
2 Cumulative (US$): / (a) grantee matched funding (sum of grantee: cash, in-kind, re-invested profits); / (b) third party funding (sum of actual third party: equity investments, loans, in-kind, supplier credit, grants from other funders, bank loans, bank overdrafts); and / (c) funding successfully facilitated by AECF Connect[3].	No target / No target / No target / TOTAL: 3,500,000	2,000,000 / 446,000 / 0 / TOTAL: 2,500,000
3 Number of ongoing projects: / (a) bringing a new technology or business model; / (b) replicated by other market players in some way; or / (c) that have led to other systemic changes (regulatory, factor and other markets).	1 / 2 / 1	0 / 2 / 5
[3] AECF Connect is part of the AECF which supports AECF grantees in raising capital from private investors and lenders.

The SSW is not yet meeting expectations on cumulative development impact. The development rate of return (DRR) is lower than that of other AECF windows of a similar age, including those in post conflict environments such as the Post Conflict Window (PCW) which has DRR of 3.5. A higher DRR indicates strong development returns for every $1 invested by the AECF. For the SSW every dollar invested has created $0.50 of benefit. However, the business environment has proven to be particularly challenging and although the cumulative development rate of return to date remains below 1 it is expected to at least exceed this threshold in the medium term. Single-country windows like SSW are inherently more risky than multi-country windows such as the PCW and this is reflected in the development returns.

Matched funding in the SSW comes slightly under the target of $1 for every $1 provided by the AECF with a total matched funding raised of $2.5m, against a target of $3.5m. This is understandable given the environment where access to finance is very limited but remains below the already low target.

The SSW has achieved a degree of wider market system change. There have been some examples of replication of business models using improved seeds by some farmers and among Non-Governmental Organisations (NGOs). The SSW has created additional business opportunities for input suppliers and other projects have positively changed regulatory procedures: Honey Care became the first company to obtain a certificate of origin to export their product, a process which took them four months first time round but is now only taking one week.

Overall, with such a low development rate of return the SSW cannot be considered to be achieving its intended outcome.

SSW Project Summary
The development results for the SSW grantees are summarised below. Outcome Indicator 1, as well as Output 1 (both of which focus on the development impact of the portfolio) reference the results achieved up until the end of December 2014. The remaining Outcome and Output indicators (that are more concerned with the operation and management of the business and funding windows) use data as of the end of June 2015[4]. There has been limited and sometimes incomplete reporting from grantees and it has therefore been difficult for the Fund Manager (FM) to verify impact to the same extent as for other windows:
[4] This is due to differences in reporting periods by the AECF, businesses and donors.

Company	2014 Net Number of Households	2014 Average Net Benefit per HH ($)	2014 Total Net Benefit ($)	Cumulative Total Net Benefit as at Dec 2014 ($)
Century Seed Co.Ltd	2,612	171	446,652	646,652
South Farmers Company Ltd	-[5]	-	-	23,300
Honey Care Africa Ltd	284	64	18,176	18,479
Frontier Microfinance Ltd	-	-	-	0
Garden of Eden Co. Ltd	0	0	0	0
[5] Where a ‘-‘ is recorded there are no results available.

As can be seen from the table above, the development impact for SSW is heavily dependent on Century Seeds. There have been delays in starting the Frontier Microfinance and Garden of Eden projects, including due diligence concerns regarding the latter. A brief summary of the progress and position of each grantee is at Annex 2.

Recommendation
R1 - The FM should continue to review the Frontier Microfinance and Garden of Eden projects and should determine by end March 2016 whether it is likely they will be in a position to progress in the next year. If these projects will not progress sufficiently they should be closed. If the projects do proceed, the FM should report to DFID on the outcome of any outstanding due diligence findings prior to proceeding with disbursements.
Action by: Funding Manager	Timeline by: 31 March 2016

Key Lessons
South Sudan is a complex and difficult environment to run a business. A key lesson that has been learned is that the AECF must take a longer term planning horizon and increase the flexibility in the way it provides support to businesses in these environments. It has not been possible for the original business plans to be implemented as planned due to the impacts of the first oil shut down in 2012 which affected currency and fuel, it was further compounded by the fighting which started in December 2013.
- Businesses should continue to review their business plans in light of the new operating context in South Sudan.
- DFID should review the logframe indicators on the SSW to ensure they provide realistic measurable targets in the current fragile/uncertain SS context.
- The risks inherent in a single country post-conflict competition window are very high, as the success of the project is dependent on the condition of one fragile economy. The PCW, for example, supports 18 projects across four countries and its results are therefore less susceptible to economic problems in one country.
- Finally, the cost of managing a small programme such as SSW is relatively high, both in terms of management fees and staff time. DFID should look at ways to streamline the management of the AECF as a whole and in particular the SSW, for example management alongside another window.

Has the logframe been updated since the last review?
New logframes have been put in place for all windows in the AECF. There is now one logframe for all windows with the same outcomes/outputs with country specific indicators; milestones have been identified for each window based on their specific context.

Actions from 2014
Action taken on recommendations from last year’s review are summarised in Annex 1.

## C: DETAILED OUTPUT SCORING

Output Title	Business initiatives supported by the AECF generate development benefits with high outreach, in particular to: those in rural areas; very poor; women; and youth.
Output number per LF		1	Output Score	B
Risk:		High	Impact weighting (%):	40%[6]
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes
[6] This output is currently weighted as 40% as output 2 is not relevant at this stage. It will revert to 30% weighting in 2016 when output 2 goes live.

Indicator(s)	Milestones	Progress
1.1 Net number of primary beneficiaries benefitting from ongoing AECF funded projects, by year, expressed as number of: / (a) households; and / (b) people.	15,000 / 75,000	2,896 / 14,480
1.2 Average net benefit per household / per year (US$).	80	161
1.3 Percentage of direct primary beneficiaries that live in rural areas.	60%	-
1.4 Percentage of direct primary beneficiaries that are poor (i.e., earn less than US$2 per day).	50%	-
1.5 Percentage of direct primary beneficiaries that are women.	50%	-
1.6 Net additional jobs created (FTE[7]) through/in enterprises supported by AECF: / (a) men; / (b) women; and / (c) youth (18-35 years).	38 / 37 / No target / TOTAL: 75	19 / 10 / 19 / TOTAL: 29
[7] FTE: Full Time Employee

Progress against Output 1, which measures the development impact of SSW, has seen mixed results during 2014.

1.1	The number of beneficiaries[8] is significantly lower than expected and the reported results are largely attributable to one project (Century Seeds). The number of beneficiaries for Honey Care could be higher than the 284 that were verified however, Honey Care records were not adequate to demonstrate this. South Farmers has potential to reach many beneficiaries, but has faced issues sourcing foreign exchange due to the fragile economy. Furthermore, South Farmers has not submitted its most recent report meaning the full development results are not included here. The development results for this year are therefore probably understated. There is potential for the number of beneficiaries to increase as projects develop, as better reporting is provided and as the continued effect of the current fragile ceasefire is felt.
[8] Beneficiaries can be outgrowers or clients: Honey Care and Century Seeds beneficiaries are the producers that supply the raw honey and seeds, whilst South Farmers beneficiaries are the customers of the company.

1.2	The net benefit per household is the only indicator in this output that exceeds its target. This is due to the high net benefit attributable to Century Seeds’ and may be impacted by the fact that this project has worked with larger farmers than originally intended and the benefit per farmer is therefore higher. This brings into question the impact on poverty results (e.g. indicator 1.4) as a proportion of beneficiaries (at least) are not poor, smaller farmers.

1.3 – 1.5	The verification studies for these milestones have not yet been completed so it is not possible to report on their progress. Verification work will be needed if these projects are not in the scope of the final evaluation.

1.6	The number of jobs created has reduced from 76 in 2013 to 29 in 2014. The reduction has been explained in part due to the challenging context in South Sudan and the conflict that started in December 2013. It is also down to the poor reporting with only two projects providing reports to the FM in time for the annual review process. Limited capacity of the partners that are operating has limited the reporting of results. South Farmers have struggled to keep the project moving and did not have the time to complete the reports. Honey Care need to improve their reporting to ensure all attributable results are counted.

Recommendations
R2 – The milestones for output indicator 1.1 on households should be reduced to 10,000 in 2015, 12,500 in 2016 and 18,750 in 2017. These figures are based on an appropriate proportion of the PCW milestones. We measure a household in South Sudan as six people so the number of people (x6) should also be updated in line with these revised figures. These targets still represent a challenge for SSW but one that it may be able to meet when full reporting is provided by the projects.
Action by: FM	Timeline by: 31 March 2016

R3 – The FM should work with Honey Care and South Farmers to ensure they are report all their results in a timely fashion next year.
Action by: FM	Timeline by 31 March 2016

R4 – Progress against output indicators 1.3-1.5 needs to be verified. A verification study is required for the Century Seeds to understand its development impact and the poverty status of beneficiaries. The FM and DFID will need to discuss potential budget sources for this work.
Action by: FM	Timeline by: 31March 2016

R5 – The log frame needs to be updated taking into account the operating context and milestones populated for future years. In particular, future milestones for jobs created should be included beyond the total 50% men and 50% women with youth accounting for 80%.
Action by: FM	Timeline by: 31 March 2016

Output Title	The business initiatives supported by AECF (and the products and services delivered through them), are sufficiently commercially viable that the associated development impacts are sustainable.
Output number per LF		2	Output Score	N/A
Risk:		High	Impact weighting (%):	0%[9]
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes
[9] Output 2 is not relevant at this stage.

Indicator(s)	Milestones	Progress
2.1 Ongoing projects that are profitable 36 months from date of contract: / (a) total number; and / (b) percentage	N/A	Contracts for the five companies were signed in 2013; this indicator will not be reported against until 2016.
2.2 % repayable funds due for repayment / that are repaid. / (a) = cumulative total repayable / grants due (US$); and / (b) cumulative total repayable / grants repaid (US$), / (c) = percentage.	N/A	First loans are not due to be repaid until the end of 2016.

This output is not yet applicable for the SSW so it is currently weighted as 0% and not scored. It will be weighted as 25% from 2016 and will be reviewed in the 2017 annual review.

Future milestones are in line with contractual agreements for repayable. The 2016 milestone for profitable companies (two companies) is in line with the PCW logframe. However the expectation that 4/5 projects will be profitable by 2017 is considered to be too high given the operating environment and when considered against the milestone for the PCW which is for 60% of projects to be profitable.

Recommendations
R6 - It is recommended the milestone for output 2.1 in 2017 is revised down to 3 projects (60%) in line with PCW.
Action by: FM	Timeline by: 31 March 2016

Output Title	AECF identifies and supports business initiatives which generate sustained and positive development impacts and which are innovative.
Output number per LF		3	Output Score	B
Risk:		High	Impact weighting (%):	33%[10]
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes
[10] This weighting will reduce to 25% when output 2 goes live.

Indicator(s)	Milestones	Progress
3.1 Total number of ongoing projects.	5	5
3.2 Ongoing projects that are marked 3 or above on the AECF innovation scale: / (a) total number; and / (b) percentage.	3[11] / 60%¹¹	4 / 80%
3.3 Ongoing projects achieving high development impact: / (a) total number; and / (b) percentage.	2¹¹ / 40%¹¹	1 / 20%
3.4 Ongoing projects where innovation is recognised: / (a) total number; and / (b) percentage.	2¹¹ / 40%¹¹	1 / 20%
[11] Milestones were not included in the approved logframe. The GW, AAW and PCW milestones were used for consistency.

Output 3 looks at the sustainability and innovation of the projects within the window and overall, the SSW has broadly met expectations.

The number of ongoing projects (3.1) has met target and remained the same which is probably unsurprising given the early stage of this window. Projects within the SSW score higher on the AECF innovation scale (output 3.2) than other windows because many practices which are common elsewhere remain innovative in South Sudan. South Farmers and Century Seeds are not innovative business models compared to other AECF windows but in South Sudan they are the first companies of their kind and therefore scored more highly on the AECF innovation scale. However, there has been less external communication and discussion of these innovations than anticipated (output 3.4) and fewer projects than expected have had a high development impact (output 3.3)

This output (3) does not include a measure of country risk which would more accurately quantify the overall risk of a project. In South Sudan the country risk is high. This indicator should be a composite of both innovation risk and country risk in order to fully capture the risk involved and therefore the justification for making a public subsidy to support these businesses.

Recommendations
R7 – The log frame should be updated, the indicators reviewed to ensure they are consistent with other windows and the local environment.
Action by: FM	Timeline by: 31 March 2016

R8 – This output should include a measure of country risk of the projects, for example by using the World Bank Doing Business ratings. A composite measure of innovation and country risk can then be used to measure the risk of each project and window. Changes to logframe should be pursued centrally so all logframes are consistent.
Action by: FM	Timeline by: 31 March 2016

Output Title	AECF identifies, selects, contracts and provides managed support to business initiatives.
Output number per LF		4	Output Score	B
Risk:		Medium	Impact weighting (%):	27%[12]
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes
[12] Output 4 weighting will reduce to 20% when output 2 goes live.

Indicator(s)	Milestones	Progress
4.1 Cumulative number of: / (a) competitions closed; / (b) registrations completed; / (c) applications received; and / (b) eligible concept notes marked.	(a) 2 / (b) No target / (c) 200 / (d) No target	1 / 493 / 187 / 116
4.2 Cumulative number of: / (a) full applications (i.e. business plans) submitted; / (b) approved; and / (c) approval rate.	20 / 11 / 55%	15 / 6[13] / 40%
4.3 Cumulative number of projects successfully contracted.	5	5
4.4 Cumulative number of contracted projects that closed before their original contract end date.	0	0
4.5 Cumulative project funding pipeline metrics: / (a) new funds available to projects (US$); / (b) funds committed to projects at IC stage, pre-contract signature (US$), / (c) % available funds committed; / (d) funds contracted to projects (US$); / (e) % available funds contracted; / (f) funds disbursed to projects (US$); and (g) % available funds disbursed	No target / No target / 100% / No target / 100% / No target / 30%	4.5m / 3.964m / 88.7% / 3.4m / 75.6% / 1.8m / 40.4%
[13] 6 projects were approved at the investment committee but only 5 went on to be contracted and are active projects.

The SSW has not held the expected second round competition for new projects. The programme has not met expectations against this output and revisions should be made to the logframe for future years.

It is worth noting that $670,000 in disbursements have not yet been made to two projects which are under review. Frontier Microfinance has struggled to raise matched funding and it is not clear whether the current management has the capacity and drive to implement the business plan that has been agreed with AECF. Garden of Eden has been the subject of local press reports regarding a conflict of interest of government officials. The Fund Manager is investigating both these issues. In the event that this money is not disbursed it may be available for reinvestment in existing grantees or new competitions or a further reduction in the SSW budget. It would be possible to inject new funds at a low cost to the AECF as management fees have been incurred on a proportion of funds withdrawn earlier from the window.

While not all the available funds have been contracted there has been good progress on disbursing the contracted funds to projects, when considered against the original seven year competition period, with 40% disbursed by the end of 2014, despite two projects having barely started. The disbursement position at June 2015 had further improved with only 42% of commitments yet to be disbursed (see below):
Company	Grant Approved	Loan Approved	Total AECF Funds Approved	Amount disbursed	Balance to disburse
South Farmers Company	300,000	500,000	830,000	535,000	265,000
Honey Care Africa Ltd	500,000	750,000	1,250,000	851,892	398,108
Garden of Eden Co. Ltd	75,000	225,000	300,000	80,000	220,000
Century Seed Co. Ltd	200,000	300,000	500,000	450,000	50,000
Frontier Microfinance Ltd	249,600	250,400	500,000	50,000	450,000
Total	1,324,600	2,025,400	3,380,000	1,966,892	1,383,108
%			100%	58%	42%

Recommendations
R9 – indicator 4.1 should reduce the number of competitions planned for future years to 1 and indicators 4.3 and 4.4 should be updated in future to reflect the likelihood of project closures, to the anticipated 20%.
Action by: FM	Timeline by: 31 March 2016

R10 – the DFID South Sudan team or alternative administrator (see section D below and recommendation 11) should consider how any funds which are not expected to be disbursed to current grantees should be used. Options for the use of these funds include: top ups to existing business (which may have additional management cost implications), running a small competition for other projects to apply for in South Sudan; or using the funding for other agribusiness related projects within the PCW or Agribusiness Window.
Action by: DFID	Timeline by: 31 March 2016

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The competitive nature of the AECF ensures funds are provided to the most commercially viable ideas that offer a large development impact. Management fees of the fund are fixed at 20% of the funds allocated for businesses, which is less than many other Challenge Funds. The original management fees (20%) are split: 4% to AGRA who manage all fiduciary and legal matters; and 16% to the Fund Manager, KPMG, who conduct the day-to-day operations of the fund. However, following the reduction in the amount committed to the window by DFID South Sudan, the effective overhead rate for this window increased to 35%. This reflects the fact that higher management fees had already been charged for the first two years of the window on the assumption that the value of the window was £6 million and not the eventual £3.9 million. These management fees cannot be reclaimed. A reduction of £82,000 of management fees was agreed with effect from 1 January 2015 based on the reduced budget but, it is probable that the total overhead cost will exceed 35% as not all of the remaining funds will be dispersed to businesses due to anticipated project failures.

VfM performance compared to the original VfM proposition in the business case
No specific measures on Value for Money (VfM) were set when the programme was originally designed. VfM indicators were agreed for Agribusiness Africa Window (AAW) and were reviewed in the 2014 annual review. The same method has now been used for all AECF windows. Benchmarks have been included based on the AECF oldest window (the General Window-GW); two closely aligned but separate programmes; and the Post Conflict Window (PCW) has been used for SSW given the similar contexts they operate in.

Assessment of whether the programme continues to represent value for money
Economy
The economy indicators focus on fund management costs and SSW is currently reflecting lower costs than the benchmarks at present, except PCW where it is 1.5% higher. The total fund management costs as a percentage of amounts disbursed to grantees against the revised budget is now 46.1%. Eventual management costs should be in the region of 35%-40%. There will not be additional grantees contracted for the SSW so the management costs will remain disproportionately high.

Efficiency
Private sector leverage for the SSW is lower than other windows but at a similar level to the PCW, at 1.91 it is also higher than the minimum level agreed in the business case for AAW (1.08). Considering the fragile and conflicted environment the SSW is working in (South Sudan is the most fragile state in the world) this is considered to be reasonable.

The management fee to grant disbursement ratio shows that the SSW has a much higher ratio than the benchmark programmes; it is more than double the benchmarks and other windows within the AECF at 85.29%. This is a concern, though it is recognised that the management fees are front loaded in the AECF and should decrease proportionately over time as the portfolio matures.

Effectiveness
The total development rate of return (DRR) shows the SSW is delivering some development impact; however, it is substantially lower than all other windows, including PCW which started the year after SSW.

Overall it is considered that the SSW as a stand-alone window does not represent good VfM. The VfM indicators need to be tracked carefully to ensure there is no further deterioration in economy and efficiency indicators, particularly in the area of management fees to DRR. To maximise this, the fund manager should be encouraged to disperse all of the funds within the window as early as possible (not in advance of need).

A further issue on value for money relates to DFID's management of this window. It does not appear to be good value for money to have separate teams managing each individual window and this is particularly true for a small window such as South Sudan. DFID should look to consolidate the SSW with another window to improve VfM.

Quality of financial management
The quality of the financial management of the portfolio by AGRA has been poor but has improved during 2014/15. It was identified as a major risk to the project in the 2014 annual review and a financial due diligence (FDD) of the AECF was commissioned. The FDD didn’t identify any fraud but did highlight problems with AGRA’s accounting treatment of funds, inaccuracies and poor systems. Some of the issues identified had led to cash balances building up in some of the AECF competition windows. AGRA have invested in the capacity of their staffing since then and have completed a reconciliation of the net cash position on each window. Donors are continuing to monitor the implementation of the FDD recommendations through the AECF Committee.

After the 2014 annual review DFID put on hold all disbursements to AGRA pending the FDD results and confirmation of the true financial position of each fund. The overall net cash position has now been received from AGRA and DFID have confirmed they will again make disbursements on receipt of quarterly reports which demonstrate the need within that window for DFID funds. DFID programme managers have been working closely with AGRA to ensure the quarterly reports they provide are accurate, confirming all expenditure to date and have realistic forecasts for the next quarter.

Date of last narrative financial report	15 August 2015
Date of last audited annual statement	15 August 2015

Recommendation
R11 – DFID should consider managing the South Sudan window as part of another, larger programme. This could be achieved through SIDA who would manage the window along with their investment in the Post-Conflict Window in which case DFID’s project would effectively end. However, this could only occur once all disbursements have taken place according to SIDA. Alternatively the window could be managed by another DFID team such as Africa Regional Department (ARD) or Tanzania who have significant agribusiness investments and engagement with the AECF and have teams already managing these windows.
Action by: DFID	Timeline by: 31 March 2016

R12 – DFID should continue to monitor the VFM to ensure the management fee to grantee disbursement ratio does decrease
Action by: DFID	Timeline by: 30 September 2016

E: RISK

Overall risk rating: High

Overview of programme risk
The programme risk was updated at the last annual review to high given the conflict in South Sudan; the situation has remained challenging and made an already weak system even worse. The risk register has been updated.

The FM detailed their risk assessment process as part of this annual review, which was updated in 2014. Improvements include a detailed 1-page summary of risks and progress that is submitted to the Investment Committee. This contains a summary of progress, challenges and future direction, as well as assessments on the following risks: business model, cash flow, development impact, reputational, compliance and character. A detailed window risk and conflict of interest register is also maintained by the FM; risks are updated at least every 6 months and conflicts of interest as they occur.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
As noted in previous years the number of grantees that signed contracts in the first round was just under 50% of the target and disbursements to grantees under those contracts has also been slower than anticipated, this can be attributed to the conditions in South Sudan but has also been a feature of other windows within the AECF and has an impact on the costs to run the challenge fund and therefore the value for money of the programme.

Performance of partnership
The partnership is performing adequately. However more work needs to be done to institutionalise AECF knowledge and experience beyond high level management and to increase longevity of AECF beyond current partners.

Asset monitoring and control
Reporting by the Fund Manager and AGRA on DFID’s capital is deemed as adequate.

Recommendation
R13 – the DFID Accountable Grant arrangement with AGRA ends on 31 December 2015. The agreement should be extended for one year to allow time for DFID and the AECF to reduce the management burden of this window. If this can be achieved then a further extension should be granted to the end of the seven year lifespan of the window.
Action by: DFID	Timeline by: 31 December 2015

G: MONITORING & EVALUATION

Evidence and evaluation
The mid-term evaluation of the AECF has recently been completed by Ecorys and a draft of the report's conclusions was available for the annual review team along with case studies performed for 32 projects across the portfolio. The final evaluation will take place in 2018 and will be based on a continuation of the case studies already undertaken along with 10-15 quantitative studies.

The mid-term evaluation confirmed the generally positive development benefits of the AECF but raised questions regarding the additionality and sustainability of a proportion of the investments made by the AECF. These concerns and the other general findings from the evaluation will be built into the design of a strategic framework for the next phase of the AECF which will be completed by March 2016.

Enhanced monitoring work has been commissioned for existing projects to undertake verification studies on the top 25% of the projects within the whole portfolio. The AECF Committee has approved a proposal from the Fund Manager but there are uncertainties regarding how the project will be funded. AGRA is continuing to work with donors to resolve the source of funds issue so that enhanced monitoring work can be undertaken for the projects which account for the majority of the AECF’s development claims. If this is not resolved, targeted verification work on the high performing projects should be commissioned by DFID South Sudan and the Fund Manager. A decision will need to be taken about how to fund this.

Monitoring progress throughout the review period
A new harmonised logframe has been agreed with standard indicators across all windows in DFID to enable better monitoring. This review has drawn out some recommendations for future milestones.

Field visits have continued to be restricted. The Fund Manager’s normal schedule is to visit in April/May and at the end of October. However the conflict has impacted on monitoring reducing access to more insecure locations. The FM has visited all projects twice in this period but has only visited 2/5 projects in the field because it has been too volatile for extensive travel outside of Juba. Partners are required to report to KPMG in January and July and KPMG also conducts informal monitoring and conversations with partners on a regular basis.

Recommendations
R14 – DFID South Sudan to keep in view whether targeted verification work will be needed.
Action by:	DFID	Timeline by: 31 March 2016

H: ACTIONS

A summary of the proposed actions arising from this review is provided below.

Action	Responsible	Deadline
R1 - The FM should continue to review the Frontier Microfinance and Garden of Eden projects and should determine by end March 2016 whether it is likely they will be in a position to progress in the next year. If these projects will not progress sufficiently they should be closed. If the projects do proceed, the FM should report to DFID on the outcome of any outstanding due diligence findings prior to proceeding with disbursements.	FM	31 March 2016
R2 – The milestones for output indicator 1.1 on households should be reduced to 10,000 in 2015, 12,500 in 2016 and 18,750 in 2017. These figures are based on an appropriate proportion of the PCW milestones. We measure a household as five people so the number of people (x5) should also be updated in line with these revised figures. These targets still represent a challenge for SSW but one that it may be able to meet when full reporting is provided by the projects.	FM	31 March 2016
R3 – The FM should work with Honey Care and South Farmers to ensure they are report all their results in a timely fashion next year.	FM	31 March 2016
R4 – Progress against output indicators 1.3-1.5 needs to be verified. A verification study is required for the Century Seeds to understand its development impact and the poverty status of beneficiaries.	FM	31 March 2016
R5 – The log frame needs to be updated taking into account the operating context and milestones populated for future years. In particular, future milestones for jobs created should be included beyond the total 50% men and 50% women with youth accounting for 80%.	FM	31 March 2016
R6 - It is recommended the milestone for output 2.1 in 2017 is revised down to 3 projects (60%) in line with PCW.	FM	31 March 2016
R7 – The log frame should be updated, the indicators reviewed to ensure they are consistent with other windows and the local environment.	FM	31 March 2016
R8 – This output should include a measure of country risk of the projects, for example by using the World Bank Doing Business ratings. A composite measure of innovation and country risk can then be used to measure the risk of each project and window. Changes to logframe should be pursued centrally so all logframes are consistent.	FM	31 March 2016
R9 – indicator 4.1 should reduce the number of competitions planned for future years to 1 and indicators 4.3 and 4.4 should be updated in future to reflect the likelihood of project closures, to the anticipated 20%.	FM	31 March 2016
R10 – the DFID South Sudan team or alternative administrator (see section D below and recommendation 11) should consider how any funds which are not expected to be disbursed to current grantees should be used. Options for the use of these funds include: top ups to existing business (which may have additional management cost implications), running a small competition for other projects to apply for in South Sudan; or using the funding for other agribusiness related projects within the PCW or Agribusiness Window.	DFID	31 March 2016
R11 – DFID should consider managing the South Sudan window as part of another, larger programme. This could be achieved through SIDA who would manage the window along with their investment in the Post-Conflict Window in which case DFID’s project would effectively end. However, this could only occur once all disbursements have taken place according to SIDA. Alternatively the window could be managed by another DFID team such as Africa Regional Department (ARD) or Tanzania who have significant agribusiness investments and engagement with the AECF and have teams already managing these windows.	DFID	31 March 2016
R12 - DFID should continue to monitor the VFM to ensure the management fee to grantee disbursement ratio does decrease	DFID	30 September 2016
R13 - the DFID Accountable Grant arrangement with AGRA ends on 31 December 2015. The agreement should be extended for one year to allow time for DFID and the AECF to reduce the management burden of this window. If this can be achieved then a further extension should be granted to the end of the seven year lifespan of the window.	DFID	31 December 2015
R14 - DFID South Sudan to keep in view whether targeted verification work will be needed.	DFID	31 March 2016

Review Process
The review process was completed by Simon Calvert and Katie Wambui.

The review team also spoke to the AECF funded projects - Honey Care Africa (see annex 2); the Fund Manager; and the DFID Livelihoods Adviser and Programme Manager in DFID South Sudan.

The main sources of information for this Annual Review are:

- How to Note: Reviewing and Project Scoring.
- AECF Fund Manager Year 2013/14 Annual Performance Assessment
- South Sudan Window Annual Report July 2014 –June 2015 (Quest 5194503)
- AECF MTE Case Studies Report (Quest 5194502)
- AECF Portfolio Report (http://aecfafrica.org/windows/south-sudan-window/portfolio)
- AECF Annual Report (Quest 5194503)
- South Sudan Window Business Case equivalent (Quest 3286490)
- Due Diligence Report by Nathan Associates (Quest 4153345)
- AECF Revised Logframe (Quest 5194500)
- 2014 AECF Annual Review (Quest 4798855)

## Annex 1: Actions from previous Annual Review

Recommendation	Action
A no-cost extension should be granted in recognition of the fragility of the environment, the lack of time the businesses have had since signing contracts, the average time taken for SMEs to become profitable in neighbouring, less fragile states, and the negative impact of the outbreak of conflict upon the enterprises. The review finds that DFID should also give itself more time to assess the impact and value of the AECF SSW programme in a fragile state context. Additionally, non-extension would likely mean that several of the businesses supported over the past two year would fail. The no-cost extension should also enable greater flexibility in relation to achievement of targets and milestones.	A no-cost extension was granted for one year, to December 2015, to allow the grantees more time to develop but ensure that DFID could take a further view on the VFM of this window before deciding whether to extend further. / The logframe was updated with standard indicators across all DFID windows, further recommendations on the future milestones have been made as part of this review.
With grant disbursements having only reached the half-way point, this factor should be considered when determining the duration of any no-cost extension for the programme, including accepting that the ability of business partners to provide matched funding may require an extended time period. This review recommends a no cost extension of at least another full reporting year.	See above.
Fund Manager to continue to follow up on consistent valuation of in-kind assets, addressing concerns from business partners who have been unable to complete this exercise, particularly when cash-flow has been problematic.	The AECF relies on local capacity (valuation experts, auditors etc.) to prepare valuation reports of assets to be used as in-kind contributions as part of the matching funds. The grantee is responsible for sourcing the valuation expert, however the AECF approves the final valuation report.
KPMG and AGRA to resolve the question on the use of the ring-fenced budget for dissemination of best practice. This is still action pending from the recommendations of the last Annual Review.	Overall, the AECF is looking at improving its monitoring and learning through the discussions of Monitoring and Results Measurement assignment. These discussions are led by DFID centrally. In addition, the FM has worked with a researcher from Durham University looking at the poverty profile of beneficiaries.
The AECF innovation ratings system to be reviewed to allow for amendments during the lifetime of the project rather than as a fixed one-off rating.	The ratings are updated in the 6 -monthly Site Visit Reporting. The synthesis of the changes in the innovation scale might not have been sufficient in the reporting regarding the South Sudan Window which the FM has worked on improving.

## Annex 2: AECF Funded Project

Honey Care Africa
Business model and development impact
Honey Care is a honey purchasing business based in Kenya which has expanded into South Sudan, they support work with communities to improve the productivity of their existing hives, supporting: hive management, processing and marketing.
- The number of households reported to have benefited in 2014 is 284 (discussions with Honey Care suggested the households benefitting is a lot higher, they claim to have 1,200 households that they work with, unfortunately the FM was not able to verify those figures and have asked Honey Care to improve their record keeping of purchases from households in terms of volume). Based on the verified figures the cumulative net benefit at December 2014 was $18,479. However, as noted above the actual benefit is likely to be substantially higher.
- The company have faced a number of challenges:
  - Working in a new country with very small manufacturing and export industry, in many cases they have found they are testing the systems the country will use for other companies: becoming the first company to receive a certificate of conformity and origin South Sudan which took 4 months (now only takes 1 week) and finding out what the export tariffs would be. 90% of the honey they buy from their farmers is exported.
  - The conflict which started in December 2013 has restricted their progress and plans to expand, they have now developed a new strategy which involves diversifying their products, creating peanut butter and other products.
  - The MTE highlighted: (i) other buyers coming in and offering higher prices affecting Honey Care, the company felt that other buyers may come in once with higher prices but they wouldn’t be able to afford to keep those prices high with the export tariffs etc. and Honey Care are planning to be there for the long term; and (ii) trees used to make traditional hives in decline, Honey Care explained that there are large quantities of traditional hives already in existence and they are helping the farmers utilise them all while also trying to encourage modern hives.
AECF experience and financing
- In last year annual review it was noted that Honey Care expected to break even in 2015 with their projected volumes. Their full year report has not yet been received but from discussions on progress it is unlikely they will have achieved the level required. Honey Care is not yet profitable in either South Sudan or its original operation in Kenya which started 15 years ago. In South Sudan, they believe they will need to buy 85 metric tonnes of honey to break even and the original projection they expected to achieve that level in 2017.
- They have been able to get other funding including debt funding from Root Capital, this is for the operation as a whole, not just for the South Sudan project. They are continuing to face difficulties obtaining funding for the South Sudan activities.
- The company is very happy with the support received from the FM, they have appreciated their understanding of the context in South Sudan and flexibility agreeing the new strategy that Honey Care have developed to adapt to the situation in South Sudan.
- They did raise the number of reviews taking place (Fund Manager monitoring, evaluation, donor annual review) at the moment and while they understand why they are taking place it does place considerable burden on the company.

Century Seeds
This project was set up to provide farming communities with high quality seed varieties to promote food security – multiplying seed (for seed not grain). They originally intended have smallholders as outgrowers but this has proved not possible due to lack of capacity / professionalism. The inclusion of larger farmers as outgrowers is likely to have negatively affected the poverty impact of this project. In 2014 they managed to shell, clean and treat 92MT of seed (93 MT in 2013, reported in the 2014 annual review). Century Seeds have been distributing locally which will deliver impact but this hasn’t been captured in the way they are reporting at the moment, the FM believes they could get secondary data from the NGOs who are their clients and will work with them on this. The project is already profitable and it believed to be a viable business model with lots of opportunity given large areas of uncultivated land but in order for them to scale up they would need more fiscal investment (they are currently cleaning the seeds by hand).

South Farmers
This project aimed to establish a day old chick hatchery for commercial chicken rearing. They have suffered with difficulties sourcing foreign exchange, being dependent on imports of fertilised eggs and chicken feed. South Farmers are trying to set up a parent facility to fertilise the eggs and reduce the imports. Some NGOs are now starting to make orders and they are also exploring other markets in discussion with the Ministry of Defence and opportunities in Rwanda where there is a deficit. The project is trying to balance benefitting the poor in South Sudan and keeping the business alive. Results to date are not fully reported as the project has not had time to complete their report while trying to keep the business afloat. The FM is closely monitoring the situation.

Frontier Microfinance
This company was set up to launch an agriculture based micro-finance product, in a second tier town in South Sudan called Torit. They have only succeeded in attracting 500 clients in 2 years of operation and have struggled to raise matched funds. The organisation has been faced with capacity constraints and no reporting has been submitted in June 2014. It is possible that the AECF will withdraw funding.

Garden of Eden
Garden of Eden proposed to produce maize on its farms and also buy from smallholder farmers trained and supported by the company to feed its proposed milling facility. The company intends to process, package and take the finished products to the market. The project has been delayed following the conflict which led to the need to relocate the proposed maize mill. The new site has raised some due diligence concerns to do with inappropriate political links, until they are resolved the AECF will not be able to provide any further funding to them.