ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Strengthening Public Financial Management, Anti-Corruption and Accountability Institutions in Sierra Leone
Country or region targeted	Sierra Leone
Type of cost extension (if applicable)	Time and cost extension
Original project budget	£15m
Original project start and end dates	September 2018 – September 2023
Cost extension value (if applicable)	£7m
New project end date (if applicable)	March 2024
Business Case Vault Document No.	39975011

INFORMATION
What is the project’s purpose?
To improve Sierra Leone’s ability to raise, allocate and account for the use of public funds, so that they can be invested in services such as education, health and economic growth.
What is the objective of the cost extension or other changes?
The original Business Case was for a five year programme, but split into two phases: a short, initial 18 month phase to test political commitment to reform; and a second, longer 3.5 year phase. Before proceeding to Phase II, Ministerial approval was required: this was received in September 2019. DFID contracting requirements mean that we have to undertake separate procurements for implementing partners for Phase I and Phase II. We therefore do not expect to have an implementing partner in place for Phase II until approximately September 2020. / The six-month time extension will allow us to have a 3.5-year implementation period for Phase II. We judge that this slightly longer implementation period is necessary because the time taken for technical assistance to build relationships and establish trust with Government counterparts in order to effectively influence and accelerate their reform agenda. We are therefore likely to see greater results achieved if we have a longer period of continuous support. The time extension is also critical because the programme end date is currently shortly after when the next Presidential elections are due to take place. This is problematic for two reasons. Firstly, having a break in programme support at this juncture will mean we are unable to respond to the immediate needs and priorities of the newly elected Government at a pivotal point in time when commitment to reform and delivery is often highest and we have the greatest chance of influence and impact. Secondly, trying to design a successor programme when there is, potentially, a changeover of administration on the horizon would be very challenging as we will have less clarity on their long-term plans and priorities and will therefore be less able to design a robust programme that responds to the context and political economy. / The cost extension is partly to reflect the extended programme duration but it is primarily to enable an increase in the annual programme budget from £3.3m to £5m. This reflects the high level of commitment we have seen so far under this Government to strengthening public financial management, increasing revenue and combatting corruption, which has meant there is greater need and justification for support in these areas. The proposed cost extension reflects learning from Phase I about the level of support required to achieve the programme’s intended outcome-level results. This has given us a strong basis on which we have determined the level of support the government needs and can absorb going forward in both existing areas, and new areas as set out in the section below.
What is the additional and total support the UK will provide?
The additional £7m of funding will bring the total programme value to £22m. There will be three primary forms of UK support provided in Phase II: / Strategic and Technical Assistance to Government institutions, in particular the Ministry of Finance, National Revenue Authority, Anti-Corruption Commission and Anti-Corruption Court, National Public Procurement Authority and Audit Service Sierra Leone. The additional funds from this cost extension will enable us to also provide targeted support for strengthening public financial management and public procurement in key line ministries, in particular the Ministry of Basic and Secondary School Education and Ministry of Health, to improve the efficiency of spend on basic services. / Support to Sierra Leonean civil society organisations to maintain public pressure for reform and hold the Government to account for delivery. We will provide grants to these organisation to enable them to collect data on corruption, raise awareness of audit recommendations, gather information on attitudes to revenue to inform better targeted revenue collection, advocate for the interests of women and disadvantaged groups to be considered in the budgeting process, and assess whether spending commitments have been met. / Research, monitoring and learning. DFID will set aside funds to support robust collection of evidence, political economy analysis, and learning alongside programme implementation. This will potentially include contributing to the World Bank’s research and analysis of the landscape for public financial management reforms, in particular in relation to local government PFM systems and decentralisation.
What are the expected results?
The expected outcome-level results from Phase II of the programme include: / Government of Sierra Leone remains on track against the IMF ECF programme. / Improvements in budget credibility and PFM controls, ensuring resources are available for service delivery. / Further increase in revenue to 16.7% of GDP in 2023, which contributes to improved fiscal position of the Government of Sierra Leone. / Increase in number of grand corruption cases investigated, prosecuted and completed by Anti-Corruption Commission from a baseline of less than 5 grand corruption cases investigated, prosecuted and completed in 2017. / Improved public perception on ability to fight corruption against the baseline survey being conducted under Phase I. / To support and accelerate the achievement of these outcome-level results, the cost extension will allow us to extend our support and delivery of results in the areas of: / Budget execution and public financial management in key service delivery Ministries and Agencies. To date, our PFM support has been focused on the Ministry of Finance but to ensure improvements in PFM systems effectively translate into improved service delivery we want to extend our technical assistance to cover the Ministries of Education and Health, and key related Agencies. We will define specific PFM results for this additional support during the inception phase. / Public procurement. Under Phase I we have had insufficient resources to provide dedicated support to improve government procurement systems, improve value for money and reduce opportunities for fraud and corruption, despite this being an area for potential support identified in the original Business Case. The cost extension will enable us to include this in the scope of the Phase II contract. / Audit. Similarly, we have not been able to provide support to the Audit Service Sierra Leone (ASSL) under Phase I in part due to resource limitations. ASSL has a key role to play in PFM improvements and using the additional resources under the Phase II cost extension we intend to provide targeted support to ASSL to improve its capacity in key areas like IT audits, as well as exploring the potential for support to the Parliamentary Accounts Committee to improve their oversight of implementation of Audit Reports. / Anti-Corruption Court. The Government only took the decision to establish a dedicated anti-corruption division of the High Court after the original DFID Business Case was approved. We have managed to find resources to support this in Phase I but to sustain support to this under Phase II is dependent on this cost extension. We expect that with DFID support, the newly functional Anti-Corruption Court will result in an increase in the number, speed and robustness of corruption cases. / Working with Civil Society. During Phase I we have learnt that civil society is better able to engage the Government on follow-up when they can base this engagement on high quality research and analysis. The scale (and cost) of this during Phase I is slightly higher than that originally envisaged in the Business Case. Given the importance of developing accountability mechanisms to support reforms and influence political economy we assess that this support should be maintained at this level in Phase II to enable civil society to engage across all programme areas (PFM, revenue, anti-corruption). / It will also enable us to provide funding to the World Bank for an externally funded output, to deliver research and analysis that will inform the design of donor support on PFM and guide the Government’s own future reform plans. This is crucial as strengthening donor coordination and World Bank performance in this space is a key strategic objective of the programme. / The uplift will strengthen the value for money of the programme by maintaining principles of economy and equity whilst delivering improvements in efficiency and effectiveness through: / Delivering additional output-level results and activities that will increase the level and likelihood of achieving outcome-level results. / Creating greater complementarity with other DFID interventions, as noted above, improving results delivery across the portfolio. / Strengthening the overlap between technical assistance to improve government capacity and civil society / parliamentary oversight, for example through the work on audit. In Phase II VFM will be enhanced by consolidating support under one contract. This will increase complementarity between the two workstreams, something that has been found to work well in Phase I. This will also help to streamline management structures, freeing up DFID staff time for policy engagement and influencing and reducing overhead costs. / Improving the quality of design of the World Bank’s future programme, and strengthening its value for money.
What is the approach to implementation?
A full competitive procurement process will be launched in late 2019 / early 2020 for a service provider(s) to implement the programme. They will provide technical assistance to Government, and manage a fund providing grants to Sierra Leonean civil society organisations for agreed activities. We also anticipate that an Externally Financed Output (EFO) agreement will be signed with the World Bank for joint analysis and research on PFM. Finally, DFID will manage the small remaining amount of funds for research, monitoring and learning, potentially using a DFID framework to contract a service provider to deliver this across the programme’s lifecycle. / The considerations relating to gender equality remain the same as in the original Business Case. Our support will empower women, girls and other vulnerable groups to participate in, for example, budget processes, and advocate for their needs so that resource allocation and spending decisions take into account their requirements. By increasing government revenue and enhancing the efficiency and effectiveness of spending in sectors like education and health, we will help ensure women, girls and the disabled benefit from improved access to and quality of services, supported by efforts through our complementary bilateral investments to address equity in the provision of these services. / The risk of aid being diverted for terrorist purposes through this programme remains low, as set out in the original Business Case. DFID will conduct due diligence on all direct recipients of UK Aid funding in this programme, and implementing partners will be required to conduct their own thorough due diligence on any downstream partners.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
There have been no key changes to the theory of change guiding the programme. As part of the inception phase for Phase II of the programme, we will review the theory of change and revise the programme outputs to ensure they better capture the results and influence intended to be delivered under the programme. / In the year since the Business Case was written, the most important new evidence relates to the sustained level of commitment to reform by the new Government and the opportunities this presents for our support. This evidence has directly informed this time and cost extension, and the areas of focus for Phase II of the programme. The CSO consortium funded under Phase I is also producing a range of research products that will help to inform future technical and political engagement in the areas of revenue, PFM and anti-corruption. / The other key change from the original business case was the decision not to provide direct support in Phase I to the World Bank, as had been envisaged in the original Business Case. With the World Bank’s Public Financial Management Improvement and Consolidation Project coming to an end soon, it was decided that further DFID support to the project’s Trust Fund would not be sensible at this late stage. We have, however, continued to engage closely with the World Bank and, as outlined above, plan to work closely together over the coming year on the design of their future support to public financial management in Sierra Leone to ensure this complements rather than duplicates existing support from DFID and other donors, in particular the EU.