Somalia Monitoring Programme

Business Case

Business Case and Intervention Summary

Intervention Summary

## Title: Somalia Monitoring Programme

What support will the UK provide?
The UK will invest £6.5 million over the next four years from its Governance and Peacebuilding programme in Somalia to: / verify results reported by partners / collect data to determine baselines, results and impacts of interventions / build partner capacity to monitor results and impact / collate, analyse, package and present governance and peacebuilding information / The UK will partner with USAID for elements of this intervention, investing in USAID’s MEPS (Monitoring and Evaluation Programme for Somalia) to deliver bullets 1, 3 and 4. Bullet 2 will be delivered by supporting data collection exercises including UNDP’s Safety and Security Assessments, and the UNFPA-led Somalia Population Calculation.

Why is UK support required?
DFID and other donors are funding programmes across Somalia – in Puntland, Somaliland and South Central Somalia. But it is extremely challenging for DFID and other donors and partners effectively to monitor and evaluate the delivery and impact of these investments across their complete range of operation in Somalia. DFID staff are unable to access almost all of Somalia (the exceptions being occasional visits to Mogadishu and visits in preparation of the Secretary of State’s January 2012 visit to Somalia). As a consequence, throughout 2011 DFID staff undertook no monitoring visits. Other donors experience similar constraints to accessing parts of Somalia, though UK travel regulations for Somalia are amongst the most restrictive. / However, the results promised and reported by implementing partners for our programmes are substantial. It is currently difficult for DFID to verify such claims, or to assess whether its programmes are having the intended outcome and impact. Instead DFID has to rely on the reports of implementing partners. The challenge is particularly acute for DFID’s governance and peace building programmes, which are currently under design. The activities, outputs, outcomes and impact of these programmes have not yet been approved, but assessment of their progress will require data collection, surveys, process evaluations and other methods that will need extensive information gathering in the field, which DFID staff and others falling under DFID’s duty of care are unlikely to receive security clearance to do. / Other data is also lacking about Somalia – there is little or no reliable population, income, economic, social or governance data, and what data is available is often not well packaged or made accessible for decision makers to use. There is no MDG for which Somalia has adequate data, and as a result there is no current MDG report for Somalia. There is not even a reliable sampling frame that could be used for nationwide surveys. Instead of relying on data, programme design and decision making to date has been made based on qualitative assessments of the situation in Somalia combined with research on what has worked in other contexts. The limited data about Somalia – and about governance and peacebuilding in Somalia – that is available is difficult to access. It is widely dispersed, based on inconsistent methodologies and not packaged nor presented in a form that makes it accessible and usable by policy makers, including by the DFID Governance and Peacebuilding team. / In addition to the security and access challenges of data collection and project monitoring in Somalia, several implementing partners, particularly on governance and peace building are weak at determining and reporting the results of their interventions. There is clearly a need for implementing partners to improve their capability to monitor and demonstrate their results – and there are few alternative implementing partners in Somalia to whom donors can turn if existing partners continue to fail to demonstrate results.
[note] Map of current DFID support in Somalia - Quest document 3383084
[note] According to British High Commission Nairobi Head of Security
[note] Fritz, V, and Menocal A. 2007. Understanding State-Building from a Political Economy Perspective: Report for DFID’s Effective and Fragile States Teams, ODI, London

What are the expected results?
This intervention is designed to produce and package information so that DFID can design its Governance and Peacebuilding projects to deliver better results, and so that we can know what those results are with confidence. The impact is expected to be more effective DFID Somalia policy and programmes. The outcome will be better monitoring, evaluation and evidence for DFID-funded governance and peacebuilding programmes in Somalia. / The exact results of this intervention are not yet known, as they depend on decisions about the rest of the DFID Somalia Governance and Peacebuilding programme, which have not yet been taken. But based on current estimates, by 2016 we expect this programme to have delivered or contributed to: / 150 field verification visits per year covering 20 projects / 5 project evaluations / 90 district-level Governance and Security assessments per year / Determination of the population of Somalia, by community, district and zone / 20 projects with clear theories of change, logframes and that report on impacts, outcomes and outputs / In addition we expect that the Somali administrations in Somaliland, Puntland and South Central Somalia will use the data generated by this programme to inform their planning and decision making, as will DFID and other donors. / We will work to clarify the precise results of this intervention during a 6-month inception period.

Strategic Case

A. Context and need for a DFID intervention / Evidence of the need for an intervention / Donors are making significant investments in Somalia. In 2010 (the latest date for which figures are available), the total investment from OECD countries in Somalia was £305 million. As political attention shifts towards Somalia – for example with the February 2012 London Conference – investment levels are liable to increase. DFID’s own programme in Somalia is indicative of this shift – it has increased from £35 million in financial year 08-09 to £113 million in 11-12. It is expected to be up to £80 million in 14-15. / DFID and other donors are funding programmes across Somalia – in Puntland, Somaliland and South Central Somalia. But it is extremely challenging for DFID and other donors and partners effectively to monitor and evaluate the delivery and impact of these investments across their complete range of operation in Somalia. DFID staff are unable to access almost all of Somalia (the exceptions being occasional visits to Mogadishu and visits in preparation of the Secretary of State’s January 2012 visit to Somalia). As a consequence, throughout 2011 DFID staff undertook no monitoring visits. Other donors experience similar constraints to accessing parts of Somalia, though UK travel regulations for Somalia are amongst the most restrictive. / While it is possible that security may improve in parts of Somalia, or UK and other donor travel restrictions may change to parts of Somalia, there is no evidence to suggest that access for DFID staff will improve substantially for much of the country over the next few years, so access for monitoring and evaluation by DFID staff is set to remain a major obstacle. However, it is possible for DFID’s implementing partners to access much of Somalia, so although DFID staff cannot conduct monitoring or evaluation there, others can. / The results promised and reported by implementing partners for our programmes are substantial. For example, by December 31 2011, the DFID-funded Sustainable Employment and Economic Development Programme (SEED) reported construction of 280 km of irrigation canals in Somalia. It is currently difficult for DFID to verify such claims (though some results from this project were verifiable), or to assess whether it is having the intended outcome and impact. Instead DFID has to rely on the reports of implementing partners. Similar examples exist for DFID’s health investments and governance and peacebuilding investments in Somalia. The challenge here is to verify results reported by partners. / The challenge is particularly acute for DFID’s governance and peace building programmes, which are currently under design. The activities, outputs, outcomes and impact of these programmes have not yet been approved, but assessment of their progress will require data collection, surveys, process evaluations and other methods that will need extensive information gathering in the field, which DFID staff and others falling under DFID’s duty of care are unlikely to receive security clearance to do. The lack of good data for governance and peace building programmes in Somalia is already evident in DFID’s own programming documents – the Strategic Case for DFID’s Governance and Peace Building in Somalia programme includes just two pieces of quantitative evidence for the effects of conflict in Somalia – the number of internally displaced people (a disputed figure) and the proportion of the population living on less than US$ 1 a day (more than 10 years old). This demonstrates that good information about governance and peace building in Somalia is critically lacking – both to inform the design of DFID and wider donor programmes, and to assess their delivery and effect. Other data is also lacking about Somalia – there is little or no reliable population, income, economic, social data or conflict, and what data is available is often not well packaged or made accessible for decision makers to use. There is no MDG for which Somalia has adequate data, and as a result there is no current MDG report for Somalia. There is not even a reliable sampling frame that could be used for nationwide surveys. Instead of relying on data, programme design and decision making to date has been made based on qualitative assessments of the situation in Somalia combined with research on what has worked in other contexts. The challenge here is to collect data to determine baselines, results and impacts of interventions. / In addition to the security and access challenges of data collection and project monitoring in Somalia, several implementing partners, particularly on governance and peace building are weak at determining and reporting the results of their interventions. A spot check of logframes of three UK-funded security, peace building and stabilisation programmes on 7 February 2012 revealed that despite extensive effort from DFID staff, none of them meet the DFID logframe guidance, and none of them demonstrate clear, tangible, reliable results. There is clearly a need for implementing partners to improve their capability to monitor and demonstrate their results – and there are few alternative implementing partners in Somalia to whom donors can turn if existing partners continue to fail to demonstrate results. The challenge here is to build partner capacity to monitor results and impact. / The limited data about Somalia – and about governance and peacebuilding in Somalia – that is available is difficult to access. It is widely dispersed, based on inconsistent methodologies and not packaged nor presented in a form that makes it accessible and usable by policy makers, including those working on stabilisation and in the DFID Governance and Peacebuilding team. This intervention will produce more data, making the potential benefits of packaging and presenting information even greater. The challenge here is to collate, analyse, package and present governance and peacebuilding information. / There are two challenges that this intervention will not try to address, but which will remain the responsibility of individual projects in the normal way: / Annual reviews and project completion reports will continue to be the responsibility of the programme teams. / Evaluations will continue to be designed, funded and implemented by programme teams and individual programmes. / However, both of these would be very likely to depend on the information generated by this intervention. / Why will intervening make an important contribution to addressing conflict and/or fragility? How will doing harm be avoided? / The main contribution of this intervention in addressing conflict and fragility in Somalia will be to inform the design of and monitor the effect of the wider DFID governance and peace building programmes (and possibly also the health and wealth programmes – should this programme expand to cover health and wealth at a later date) all of which have conflict and fragility objectives. In a fragile, complex and shifting situation such as exists in Somalia it is essential continually to monitor programmes and their effects and to be able to adapt programmes in response to emerging information. It is currently very difficult for DFID to do this due to lack of quality and timely information, and due to remote management of the programme from Kenya. / Somalia is a conflict-prone environment and there remain further risks that data collection or additional monitoring of donor-funded programmes on the ground could have unintended and negative consequences on conflict and fragility in Somalia. These risks have previously materialised in Kosovo. Careful and sensitive design of the intervention details will be essential to mitigate these risks. In particular, the intervention will promote inclusion and ensure broad and meaningful participation; act in a transparent and accountable way; consider the timing, sequencing and location of interventions for their potential conflict impact; and be responsive and flexible to changing requirements. We will also ensure that DFID’s ethical principles on research and evaluation are employed in all relevant activities under this intervention. / Why is it right for DFID to intervene, and the consequences of not doing so? / As set out above, DFID is a major and growing donor in Somalia. It is making an investment of at least £250 million over the financial years 10-11 to 14-15. It is currently unable reliably and regularly to monitor, evaluate or collect data on its projects in Somalia. This makes project design difficult and fraught with risk, and makes it difficult to determine project impact with confidence. Unless DFID intervenes, there is little prospect of this situation improving. It is possible other donors may intervene and improve matters for their programmes, or that some implementing partners will increase their own capability to determine their results. DFID would stand to benefit from these, but at most only for a portion of its programme. / What difference will intervening make to reduce poverty and for poor people’s lives, including women and girls? / Lack of data from the field is hindering design and effective monitoring of all DFID’s programmes and those of the wider donor community, making it difficult to be confident that they are having the intended impact on poverty and poor people’s lives. Data for the impact on women and girls is even scarcer. Unless an intervention is made to improve the quality of information about the progress and impact of projects – and to disaggregate and provide gender-specific data where appropriate – they are likely to provide limited (and unknown) value for money. / It is hard to prejudge the extent to which an intervention would reduce poverty – as this will depend on the improvements to project design and impact as a consequence of better data being made available by the intervention. We have a baseline of available, reliable and trusted information about projects (very little), but no baseline of the effectiveness of those projects beyond that provided by the implementing partners themselves. / What are the political incentives behind the intervention, including relevant factors and stakeholders that are for or against reform? / The international community – as was expressed in the February 2012 London Conference – has a strong political will to see Somalia’s stability, prosperity and human development levels improve. Donor-funded development programmes are a major instrument to help deliver that improvement, and there is some appetite for them to be evidence-based and to increase their effectiveness, though DFID is largely in the lead on this. We therefore anticipate support for an intervention to improve project monitoring and evaluation – especially in a time of constrained aid budgets and the need to demonstrate results to wary taxpayers – but DFID will need to build this further. / As set out above, some implementing partners in Somalia have been slow to respond to DFID’s push for better monitoring and evaluation of their programmes. We assess that this is in large part due to their lack of capacity and ability to change without support, and anticipate that they would respond positively to an intervention. This was backed up by the findings of a consultation of UN and NGO implementing partners on the wider DFID governance and peace building programme, which found that “many flagged the need for a local, context-driven approach, and the need to differentiate between environments within Somalia and set associated, appropriate benchmarks” and “we need a robust analytical model…. [that incorporates] mapping on what works in building peace”. It also flagged the importance of “link[ing] what is learned out of monitoring and evaluation to programming. It was recommended that this programme be expanded to include research and learning, as well as to promote knowledge exchange to encourage collaboration”. / Consultations with Somalia government partners in this intervention elicited the following responses: / TFG: M&E programme is good but also support government institutions, eg Auditor General and the Joint Monitoring and Evaluation Board. / Somaliland: M&E programme is good but also support government institutions, eg M&E policy in Ministry of Planning. Donor need to (sic) coordination is needed over M&E. Requested support for the Statistics Service. / In addition, informal discussions with the Somaliland Minister of Planning found that donor support for better data and statistical analysis of the situation on Somaliland was amongst his top priorities. / There is therefore substantial interest in the intervention from Somalia government, and it will be important that the intervention makes appropriate links with the Somaliland Ministry of Planning, Puntland Ministry of Planning and International Cooperation and Transitional Federal Government Ministry of Planning and International Cooperation. In particular, an objective of this intervention will be for the Somali administrations in Puntland, Somaliland and South Central Somalia to use the data generate by the intervention as part of their planning processes and for decision making. / Link to DFID/wider HMG objectives and priorities. / The intervention links closely to several DFID and wider HMG objectives and priorities: / DFID ministers and senior management have set out their focus on evidence, results and evaluation – of knowing what DFID money is buying, whether it is being delivered, what impact it is having and whether it is delivering excellent value for money: “We will make UK aid work better by focusing on: Results and impact – getting value for money from every pound of aid we spend”. The intervention will help DFID to meet this objective for its governance and peacebuilding programmes in Somalia. / The DFID Somalia Operational Plan 2011-2015 sets out how DFID will deliver a step change in monitoring results. In particular it says: / There will be a much sharper focus on partners’ results frameworks, ensuring robust monitoring and evaluation plans are in place, there is a clear evidence-base for their interventions, underpinned by clear theories of change, or evaluation of innovation where the evidence base is weak. / A minimum of 10% rising to 20% of all our programme funding will be allocated to monitoring and evaluation. / We will invest in our partners to scale up efforts to provide on-going monitoring of wider impacts... as well as monitoring of sector outcomes. / We will ensure that partners’ M&E frameworks have clear plans on establishing baselines, and logframes set realistic targets and milestones… / We will also invest in third party monitoring to verify or triangulate results and support independent evaluations… / An intervention is required to meet these objectives. / An intervention is also essential to inform, monitor and evaluate the wider DFID programmes set out in the DFID Somalia Operational Plan in governance and peace building, and will be needed if DFID is to report results against these programmes as set out in the operational plan. Consideration will also be made of whether an intervention is required to do the same for DFID’s health and wealth creation programmes also. / An intervention would also support the UK Strategy for Somalia by providing information that could be used to determine progress and inform activities for four of the key objectives (ii) A broad-based national government, with limited power… discharges its national… responsibilities, iii) Regional administrations in Somaliland and Puntland enabling delivery of security, the rule of law, economic development and services, iv) stability at local level, and v) economic and social development). It is also an essential element of enabler three: Building a stronger evidence base, to enable us to understand where and how to focus efforts and to help us measure progress. / In many contexts in other countries, DFID would meet most of these objectives by incorporating strong M&E within individual programmes and through actions taken by DFID staff – for example programme monitoring. However, as set out above, in Somalia this approach is not working. Security constraints mean that DFID staff are often unable to undertake some programme management tasks, the weaknesses of many implementing partners mean that theories of change and M&E systems are weak, and the lack of data or capability to collect data mean that information is often simply unavailable. For these reasons, an intervention is necessary if DFID is to deliver the DFID and wider HMG objectives set out above. / How does the intervention work in partnership with others? / Much of the intervention is primarily and initially aimed at measuring and improving DFID-funded programmes, but there would naturally be spill-over benefits for other donors and for the Somalia regional governments who co-finance or are otherwise involved in DFID-funded programmes. However, once the intervention is established we would look to bring other partners, including other donors, into the intervention to help them monitor and evaluate better their own programmes – this would have a wider impact on the overall aid effort in Somalia. / We are also aware of other interventions – existing and planned – by others. We will consider building on these initiatives as options in the appraisal case of this business case: / USAID has contracted International Business & Technical Consultants Inc (IBTCI) to monitor USAID programmes in Somalia. / UNDP has developed a Monitoring and Assessment Toolkit for its community security and peace building work in Somalia, which includes Safety and Security Assessments. / DFID is funding the NGO Saferworld to develop a conflict and governance mapping pilot, which may be useful to provide baseline and trend information in some areas. / DFID has established a regular, informal meeting of parties conducting or interested in perception and other governance and peacebuilding surveys in Somalia. This includes UNDP, Albany Associates, ORB, Bell Pottinger, USAID, IBTCI, Saferworld, UNSOA, Mercy Corps and the World Bank, which is planning a household survey and an enterprise survey in Somaliland. This group is enabling the different parties to share methodologies, capacities and questions, and to work through shared problems. It has also identified the need to collate, analyse, package and present information in a way that will get traction with policy makers. DFID is currently working with USAID and UNSOA on a more formal event aimed at strengthening methodologies. / The UN Statistics Working Group re-formed in January 2012. Led by UNDP it is currently working to: / Compile a draft 2012 MDG report for Somalia. The UN will decide whether there is sufficient data of sufficient quality to make publication worthwhile this year. If it goes ahead, publication will probably be after July. / Estimate the Somali population. Puntland and Somaliland governments are bought into the method of calculation. UNDP and UNFPA are working with the Somali administrations on it now. If this is successful, the UN is likely to look to generate further data about Somalia, for example by completing household surveys or possibly a census. / Pull together a list of all statistics capacity building and data collection work in Somalia. Subsequently the group is likely to try to harmonise and bring coherence to this work / Pilot a system to make UN data on Somalia publically available. / Both the informal perception surveys group and the UN Statistics Working Group are highly relevant for this intervention. Whichever option is chosen for the intervention, the detailed design will need to support, work with and complement these initiatives.
B. Impact and Outcome that we expect to achieve / Expected impact. / The expected impact is “More effective DFID Somalia policy and programmes”. / Expected outcome. / The expected outcome is “Better monitoring, evaluation and evidence for DFID-funded governance and peacebuilding programmes in Somalia” / How and why does the outcome lead to the impact? / DFID’s governance and peacebuilding programmes in Somalia are aimed primarily at increasing stability. Until they are monitored, evaluated and evidenced better, DFID will be unable to determine with confidence whether they are achieving the intended impact, and will not be able to design them to be as effective and as good value for money as they can be. / However, the main assumption linking the outcome statement to the impact statement is: DFID’s programmes in Somalia must be adaptable and able to respond to emerging data, results and changing circumstances on the ground that come to light inter alia as a result of this intervention.
[note] OECD, DAC, Creditor Reporting System, February 2012
[note] DFID Annual Report and Resource Accounts 2008-09
[note] 10 February 2012 estimate by DFID Kenya/Somalia Budget Monitor
[note] DFID Somalia Operational Plan 3 May 2011
[note] Map of current DFID support in Somalia - Quest document 3383084
[note] According to British High Commission Nairobi Head of Security
[note] SEED Summary of Progress Fourth Quarter Report
[note] Stage 1 Business Case – Governance and Peacebuilding in Somalia – 2012-2015
[note] Fritz, V, and Menocal A. 2007. Understanding State-Building from a Political Economy Perspective: Report for DFID’s Effective and Fragile States Teams, ODI, London
[note] The three logframes were: Community Driven Recovery & Development (CDRD), Transitional Initiatives for Stabilisation (TIS) and UN Joint Programme on Local Governance (JPLG)
[note] http://www.fundforpeace.org/global/?q=states-somalia
[note] 'Peace at Any Price: How the World Failed Kosovo', Hurst Publishing, 2006, Iain King and Whit Mason
[note] DFID Somalia Operational Plan, 3 May 2011 – the DFID investment in Somalia is likely to be considerably higher than £250 million due to increases in the DFID humanitarian programme in Somalia.
[note] Consultation report: DFID governance and peacebuilding programme 2012-2015 – 3 Feb 2012
[note] http://teamsite/sites/Somalia/CAP/default.aspx?RootFolder=%2fsites%2fSomalia%2fCAP%2fWorking%20Documents%2fGovernance&View=%7b3A50D3A0%2dB522%2d4D6B%2dB386%2dEEB8B9F3DD34%7d
[note] Donor meeting with Somaliland Minister of Planning – 25 Jan 2012
[note] UK Aid: Changing lives, delivering results, March 2011
[note] DFID Somalia Operational Plan (Annex A: Step change in monitoring results), 3 May 2011
[note] UK Strategy for Somalia, May 2011
[note] Details of the USAID programme can be found in “Somalia: Monitoring and Evaluation Project Technical Proposal – USAID/EA/LPC/Somaliua
[note] A Community Safety & Security Approach to Grass Roots Peacebuilding Monitoring and Assessment Toolkit, 15 Sept 2010

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The need set out in the strategic case is summarised in the following four statements for DFID’s governance and peacebuilding programmes: / to verify results reported by partners / to collect data to determine baselines, results and impacts of interventions / to build partner capacity to monitor results and impact / to collate, analyse, package and present governance and peacebuilding information / These form the basis of outputs for the final intervention, and will be considered output statements for the purpose of this appraisal. / The outcome statement is: Better monitoring, evaluation and evidence for DFID-funded governance and peacebuilding programmes in Somalia / The impact statement is: More effective DFID Somalia policy and programmes / This business case appraises five possible interventions for how they would address each of the four output statements, the outcome statement and the impact statement, and determine which would deliver best value for money. The options to be appraised are: / Co-finance and expand the existing USAID Monitoring and Evaluation Somalia (MEPS) programme, implemented by US consultancy firm IBTCI. / Tender a contract for a company to deliver the services required. / Finance and expand the existing UNDP Monitoring and Assessment Toolkit, and support other UN data collection exercises. / Provide additional, direct finance to existing and new implementing partners to increase their own monitoring and evaluation capacity and build it into their programmes. / A hybrid intervention comprising either option i) or ii) to deliver output statements 1, 3 and 4, and option iii) to deliver statement 2. / Options i) and ii), and consequentially elements of option v), are similar in many respects except for differences in procurement, DFID control over the intervention, and the level of donor harmonisation. Options i) and ii) will therefore be appraised together except for these three issues. The appraisal of option v) will draw on this and on the appraisal of option iii). / Theory of change for intervention (including assumptions), and process through which outputs would be converted to expected outcome and impact (including theoretical foundations) / The theories of change for each of the options are similar. Figure i) shows the project cycle and how various data about Somalia and donor-funded programmes there feed into and inform all parts of the project cycle. Data from the field in Somalia is essential to: / Identify a problem, evince it, and describe what success or progress would like for an intervention that aims to address this problem. / Design an intervention, appraise design options and make evidence-based choices. / Assess implementation of an intervention; know whether it is happening and what results it is delivering. / Determine what impact an intervention has, and identify lessons to inform adaptation of the intervention or design of new interventions. / Figure i) Project Cycle Management – How Data About Somalia Should be Used / However, as illustrated in figure ii), the four challenges identified in the output statements: / inability to verify results reported by partners; / insufficient data to determine baselines, results and impacts of interventions / insufficient partner capacity to monitor results; / inability to collate, analyse, package and present governance and peacebuilding information / are hindering effective project and programme management and thereby decreasing the impact of DFID and other donor-funded programmes in Somalia. / A fifth challenge is also hindering progress / insufficient reliable, accurate, timely and appropriate data to ensure the quality and utility of evaluations / Figure ii) Project Cycle Management – Effect of the four lacking statements / The theory of change is that by tackling the four challenges identified in the output statements, DFID governance and peacebuilding programme teams would have the information available to answer the questions in figure i) (What is the problem? What would success look like? Are project design choices evidence-based and suitable? Is implementation happening as intended? What impact is the project having?). The theory of change is completed by the four following assumptions: / DFID governance and peace building programme teams use the information about Somalia made available to them to inform programme identification, design, implementation and evaluation. Within this is a further assumption that the information gleaned about Somalia by the intervention meets programme teams’ requirements. / DFID’s governance and peace building programmes in Somalia are adaptable and able to respond to emerging data, results and changing circumstances on the ground that come to light inter alia as a result of this intervention. / Governance and peace building Programmes that are based on better evidence, that are monitored better and that are evaluated better deliver better outcomes. / DFID programmes will be rigorously evaluated and include mechanisms to collect reliable, accurate, timely and appropriate data to ensure the quality and utility of evaluations (the fifth challenge in figure ii)). / The theoretical basis of this theory comes from DFID’s programme management guidance: ”Regular and effective monitoring, reviewing and lesson learning are key to how DFID measures the performance of its aid programme and demonstrates Value for Money (VfM). Monitoring and reviewing provide a means of ensuring that important practical lessons are captured from current operational projects so that these can be applied and shared across DFID for future project management. This will ensure continuous learning and quality control for DFID, partners and other donors both during the implementation of specific projects and in the design and development of new initiatives.” A similar basis is used by other government departments, such as the MOD. / The key to converting the outputs of the intervention into the outcome and impact is in how the information is used by the DFID team and implementing partners. If the data is ignored, is used selectively to confirm previously-held viewpoints, or is used slowly, then it will be very unlikely that it delivers the desired outcome and impact. Instead, DFID programmes must be adaptable to emerging information, the programme teams must be prepared to have their assumptions and prejudices challenged and changed, and they must be able to react quickly. This will be a major challenge for the DFID team. / To meet this challenge, the DFID Governance and Peacebuilding team has given the commitment that it and its programmes will be flexible and will use the available information. We will establish a DFID Somalia Monitoring Programme Steering Team, which will include staff from the Governance and Peacebuilding team, to oversee this information (more on that in the Management Case). We will incorporate monitoring, evaluation and evidence agenda items into the quarterly DFID Somalia Governance and Peacebuilding pillar reviews to create a regular forum to hold the Governance and Peacebuilding team to account for their use of the information provided by this intervention. The Governance and Peacebuilding team will also look to design new programmes with ‘learning breaks’ at which points there will be genuine opportunities to shift focus and resources towards well-performing programmes and areas, and away from poorly-performing ones. Output 4 is also intended to help meet this challenge, by packaging and presenting the information gleaned from the other outputs and elsewhere in a way that is accessible and useable by the DFID team and others. / Evidence that this intervention can deliver the Outcome and Impact statements / There is some evidence that evaluation can result in redesign or adaptation of programmes to deliver better results: / 1.) Impact evaluation of NORAD's farm input subsidy programme (coupons to farmers to obtain cheap fertiliser and seeds) in Malawi in 2010 established that the programme had significant problems in targeting and leakages. Households headed by females were less likely to gain access to the subsidy, while fewer coupons reached the households than intended due to leakages from the administrative system to an illegal market. As a result of the impact evaluation, adjustments were made to the farm input subsidy programme to reduce leakage and improve targeting. / 2.) An impact evaluation by Kremer and Miguel in 1998 showed that de-worming was one of the most cost-effective ways to increase school participation in Kenya. Since then, a global de-worming project has been launched in 26 countries. Furthermore, DFID facilitated an evidence session where the State Government of Bihar in India was presented with the evidence of impact of de-worming children. The Bihar government scaled up the programme in the state and by March 2011, it had reached 17 million children. It is estimated that for every USD100 spent on this programme, additional 13.9 school years are gained (Baird et al 2004, Kremer & Miguel 2004). / 3.) An impact evaluation of DFID Zambia’s social cash transfer programme showed that improved targeting of poor households through categorical (households with children under the age of five) and geographical methods was more effective than original plan to target all labour constrained households. This led to more effective programming and an acceptance from the Government, whose mandate has been to focus on the poorest, that the programme was indeed efficient and effective and reached the poorest. / However, the evidence that better evaluation and evidence delivers better results is far from conclusive. A World Bank Independent Evaluation Group assessment of nutrition impact evaluations found that “Impact evaluations in two of the eight countries plausibly had an impact on policy”. Similarly, the Abdul Latif Jameel Poverty Action Lab (J-PAL) has found that of the 317 impact evaluations in its database, as of 5 March 2012, just 5 had resulted in project scale ups. / The evidence therefore suggests that it is possible for evaluations to have an impact on policy and programmes, and improve their effectiveness in some contexts, but we have found no evidence for this in fragile states, and none in Somalia. Furthermore, we have found no evidence that better monitored projects produce better outcomes. / In order to identify evidence of whether any of the proposed options can deliver the outcome statement, the business case considers whether there is evidence that they can deliver the output statements. Overall therefore, the evidence that the outcome of this intervention will lead to the impact is limited. As set out above, significant effort will be required to ensure that DFID Somalia Governance and Peacebuilding programmes are designed to allow them to adapt to emerging data and information about their implementation and impact on the ground, and that programme managers take account of that data and information and are prepared to make those adaptations. / Options i) and ii) / Co-finance and expand the existing USAID Monitoring and Evaluation Somalia (MEPS) programme, implemented by US consultancy firm IBTCI. / Tender a contract for a company to deliver the services required. / verify results reported by partners / The USAID MEPS programme is designed to verify results reported by implementing partners. The implementing partner, IBTCI, has a clear methodology and strong systems for doing this, and has begun to do so in Somalia. IBTCI is also successfully performing the same function for USAID in Yemen. Similarly in Afghanistan, the World Bank has contracted third-party M&E to verify implementation of the Afghanistan Reconstruction Trust Fund. There is good evidence therefore that at least one company (IBTCI) is able to fill this role in Somalia, and there is also evidence from Afghanistan that other companies would also likely be in a position to bid for such work in Somalia should we put it to tender. / collect data to determine baselines, results and impacts of interventions / In Afghanistan DFID has contracted a company to deliver the Helmand Monitoring and Evaluation Programme. This is being implemented successfully to provide baselines and measure progress of the Helmand Plan and is evidence that it is possible to fulfil this role in fragile states. IBTCI is also attempting to fulfil this role for USAID in Somalia by conducting a perception survey in several districts. At time of writing, this appears to have been unsuccessful, though that has not been formally confirmed. Other companies are fulfilling similar functions in Somalia – Bell Pottinger and Albany Associates have successfully conducted three comprehensive opinion polls in Mogadishu, and Opinion Research Business has also conducted a poll in Hargeisa and plans to repeat the exercise in Somaliland. However, these have been limited to one location – there is no evidence that any company has the capacity to conduct surveys nationwide across Somalia, though the capability required to do this is similar to that required for outputs 1. and 4. so it is possible that some companies may be able to deliver this. / build partner capacity to monitor results and impact / This requires workshops, training and technical guidance to implementing partners – particularly NGOs and UN agencies, but possibly also Somali administrations. There is good evidence that private companies are able to do this. IBTCI has demonstrated its ability to perform this function in Yemen and in Somalia, and it has also been done in Afghanistan under the Helmand Monitoring and Evaluation Programme. / collate, analyse, package and present governance and peacebuilding information. / There is some evidence that private companies can fulfil this role to some extent. In particular IBTCI’s ‘Clearinghouse’ system for USAID presents results information to USAID staff in a very clear and accessible way. USAID staff report that it has significantly improved their ability to track results as well as highlighting any problems within projects that need resolution. / In a very different context, Bell Pottinger has packaged its polling information in a very usable format, and has invested time and effort in communicating that information to interested parties. Despite this however, Bell Pottinger’s research has not had any traction in DFID and has not been used to inform decision making. This suggests that Bell Pottinger and companies like them might need to take a different approach to make the information stick. / Option iii) / Finance and expand the existing UNDP Monitoring and Assessment Toolkit and support other UN data collection exercises / verify results reported by partners / There is no evidence that the UNDP toolkit or parts of the UN can objectively verify partner results. In fact, as the UN is one of the main implementing partners (over 60%) of the DFID Somalia programme, it is difficult to envisage how it could objectively and independently verify its own results. / collect data to determine baselines, results and impacts of interventions / There is good evidence that UNDP can do this in Somalia using its Safety and Security Assessments under its Monitoring and Assessment toolkit. In August 2011, UNDP and the Somaliland-based Observatory of Conflict and Violence Prevention produced five Safety and Security baseline reports for Bossaso, Burao, Galkayo, Las Anod and Mogadishu using guidelines developed by OECD-DAC, UNDP BCPR and DFID. / Other parts of the UN system are collecting other data on Somalia. For example, FAO’s Food Security and Nutrition Analysis Unit – Somalia (FSNAU) is collecting data from across Somalia, though at the time of writing it had suspended field work in several areas of South Central Somalia since December 2011. Similarly, UNICEF carried out its Multiple Indicator Cluster Survey (MICs) in 2006, and is repeating the exercise at the time of writing. / UNDP and UNFPA are currently leading the Statistics Working Group to calculate the population of Somalia, broken down by community, district, region and country-wide. Progress so far suggests some weak evidence that UNDP/UNFPA will be successful in generating this data. If it is successful, that will create a platform for further data collection exercises by the Statistics Working Group. / build partner capacity to monitor results and impact / There is little evidence that UNDP has built implementing partner capacity to monitor results and impact in Somalia. The limited progress made in monitoring the UN Somalia Assistance Strategy (UNSAS) outcome 3 on good governance and human security, which requires effective working with other UN agencies to demonstrate progress against this part of UNSAS, is evidence of the difficulties UNDP would face to fill this role in Somalia. There is currently little evidence of whether the UN can build Somali government capacity in this regard – the upcoming UNDP/UNFPA Somalia population calculation will provide some evidence of whether this will be possible, and we will re-consider the merits of such an approach when that process is substantially underway or complete. / collate, analyse, package and present governance and peacebuilding information / While the UNDP and wider UN data collection capability appears strong, there is not good evidence that the UN can package it and publicise it in a way that will be accessible and used for decision makers. The UNDP security baseline data for example, does not appear to have made a big impact on donor decision making, despite it being thorough and of high quality – we judge that this is down to relatively technical and dense presentation of the survey results. / Option iv) / Provide additional, direct finance to existing and new implementing partners to increase their own monitoring and evaluation capacity and build it into their programmes. / verify results reported by partners / There is no evidence that DFID’s implementing partners can successfully employ independent parties to verify the results that they report. In Somalia, there is some evidence that they cannot do this. A recent example of an implementing partner’s failure to do this in Somalia is the SEED annual review, which was conducted by independent consultants, but failed to provide confidence that the results claimed by the implementing partners were delivered. / collect data to collect data to determine baselines, results and impacts of interventions / There is limited evidence that existing implementing partners can provide the data to determine baselines, results and impacts of their interventions. The February 2012 UNSAS M&E matrices demonstrates this clearly – many of the indicators have no baselines and over 20 have no data for 2011 available at the time of publication. There are exceptions to this in the UN however – UNDP, FAO, and UNICEF are all collecting useful data of this type in Somalia, and DFID is funding the NGO Saferworld to develop conflict and governance mapping pilot, which may be useful to provide baseline information in some areas. While this intervention may not fund NGOs such as Saferworld to do this work, it will aim to incorporate and package information provided by them and others through output statement 4. / build partner capacity to monitor results and impact / DFID’s approach to date has been to invest in implementing partners, and require that they have strong systems for monitoring and evaluation. Business case guidance requires that each project has a monitoring and evaluation plan, which would typically require collection and assessment of data by implementing partners, or on their behalf by independent parties contracted by the implementing partner. DFID Somalia’s policy of allocating 10-20% of all programme funding to monitoring and evaluation demonstrates that the resources are available for implementing partners to do this already. But the Strategic Case of this business case is evidence that this approach is not having sufficient effect – DFID has tried this approach and it has not worked in Somalia. / collate, analyse, package and present governance and peacebuilding information / There is no evidence from Somalia on whether DFID’s implementing partners can package and present information in an accessible way that can wider inform decision making beyond their own individual projects. Furthermore, there may be a conflict of interest or credibility challenge as many of DFID’s implementing partners also have political or advocacy functions. / Option v) / A hybrid intervention comprising either option i) or ii) to deliver statements 1, 3 and 4, and option iii) to deliver statement 2. / As set out above, the evidence is strongest for this hybrid option. There is good evidence that private companies including the USAID contractor IBTCI can fulfil outputs statements 1 and 3 in Somalia, and that UNDP is well placed to deliver output statement 2 – possibly in conjunction with a private company (with UNDP doing the enumeration and the private company combining that information with other sources to produce analysis as is done in Afghanistan). The evidence for output statement 4 is weaker as it has apparently not been done in Somalia, but it is certainly feasible. / Feasibility / Criterion for assessing feasibility / The theory of change requires all four output statements be met if the outcome is to be delivered. The criterion for assessing feasibility is therefore: / Is there evidence that the option may be able to address all four output statements? / Feasibility assessment of each option / Having assessed the evidence for each of the five options above, options iii) and iv) include evidence that these options cannot deliver all of the output statements. In particular: / Option iii) – there is evidence that this option cannot deliver output statement 3, and there is no evidence that it can deliver output statements 1 and 4. / Option iv) – there is evidence that this option cannot deliver output statement 3, and there is limited or no evidence that it can deliver output statements 1, 2 and 4. / Options iii) and iv) will therefore be discarded at this stage. / The do nothing counterfactual / We will look at what may happen with regards to each of the output statements if no intervention is pursued: / verify results reported by partners / It seems likely that the current situation would continue and DFID would be unable to verify the results reported by partners. It is possible that some partners may successfully procure independent assessments of their results or that the security situation would improve to the extent that DFID staff will be able to access project sites to verify results. But there is no reason to be confident that either of these will happen. / USAID is pursuing its own independent 3rd party monitoring system – and it is possible that DFID may benefit from verification of results from any co-funded projects. However, at present this appears to be limited to one project, and most of DFID’s results in Somalia would remain unsatisfactorily verified. / collect data to determine baselines, results and impacts of interventions / This is an area where the UN and others (such as Saferworld, International Republican Institute, though the former is with DFID funding) are starting to engage. For example, the UNDP monitoring and assessment toolkit covers many of the types of data that this intervention might seek to investigate. However, coverage of this initiative to date is limited to a small number of Somali towns – it is unlikely to expand its coverage in the absence of an intervention. It will also be unlikely to tailor its data collection to cover the specific issues required by DFID without a DFID intervention. / Similarly, while the UN is seeking to calculate the population of Somalia, it is doing so with DFID support and the prospect of some DFID funding from within this intervention. While we do not envisage that DFID will be a major donor to this intervention, we judge that DFID is a politically important one that can help level a broad base of support from other donors. Our assessment therefore is that without this intervention, this Somalia population calculation would be at severe risk of failing due to lack of donor financing. / build partner capacity to monitor results and impact / Again, it is likely that the current situation would continue and many of DFID’s partners would remain largely unable to monitor their results and impact. It is possible that some partners may improve their capability or respond better than they have done so far to guidance from DFID staff on monitoring and results. But there is no reason to be confident that either of these will happen. / Similar to that mentioned above under output statement 1, it is possible that DFID may benefit from increased implementing partner capability to demonstrate results and impact as a result of the USAID 3rd party monitoring system, but overlap between DFID and USAID implementing partners is limited and the benefit to DFID likely to be small. / collate, analyse, package and present governance and peacebuilding information / There is little to suggest that the current situation would not continue. Different surveys, analysis and research – such as perception surveys – would continue to be conducted in Somalia, and would likely continue to fail to get any traction on policy. / Likelihood of any displacement effect / The likelihood of any significant displacement effect is small. The only possibility seems to be expansion of the USAID programme to make its data and activities more relevant and more available to other donors including DFID. There is no indication that USAID would consider doing this, and the displacement effect is considered minimal. / Costs and benefits over time / The cost to DFID of doing nothing will be defined as zero. As set out above, the benefit would likely be small. There may be some spill-over benefits accrued to DFID from the USAID programme, or through further work by UNDP with its monitoring and assessment toolkit, but this is unlikely and in any case would probably be very small. The benefits over time will therefore be rounded to zero. / Implementation / Evaluation / Design / Identification / Sufficient, well accessed / data about Somalia / What is the problem? What would success look like? / Are project design choices evidence-based and suitable? / Is implementation happening as intended? / What impact is the project having? / Implementation / Evaluation / Design / Identification / Insufficient, inaccessible / data about Somalia / What is the problem? What would success look like? / Are project design choices evidence-based and suitable? / Is implementation happening as intended? / What impact is the project having? / Insufficient partner capacity to monitor results / Unable to verify results reported by partners / Insufficient reliable, accurate, timely and appropriate data to ensure the quality and utility of evaluations / Unable to determine baselines, results and impacts of interventions / Unable to collate, analyse, package and present governance and peacebuilding information
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / I Limited / Ii Limited / iii Limited / iv Limited / V Limited / As described in section A of the Appraisal Case, the evidence for the theory of change and for each of the interventions is limited. The Management Case sets out the monitoring and evaluation plan for this intervention / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / None of the options are likely to have a direct climate change or environmental impact. However within each option there are opportunities for enhancing our approach to environment and climate change. For example, it may be valuable to collect data to inform analysis of the impact of climate change on conflict in Somalia, such as perceptions of the consequences of environmental degradation. Furthermore, we will consider ways to minimise the carbon footprint of the intervention, which will likely be mainly due to emissions from transport. These will be further explored during programme implementation alongside the development of the DFID Somalia Strategic Programme Review. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C / 3 C C / 4 C C / 5 C C
C. What are the costs and benefits of each feasible option? / Expected resource costs of the intervention / Up to £6.5 million over four years has been allocated to this programme from the DFID Somalia Governance and Peacebuilding pillar budget. This figure of £6.5 million was allocated to the M&E component of the £80 million DFID Governance and Peacebuilding programme as it is around 10% of the total budget. DFID Somalia policy is that a minimum of 10% rising to 20% of all our programme funding will be allocated to monitoring and evaluation. It is anticipated that the remaining funding for M&E will be channelled directly to implementing partners in the normal way. / The human resource cost of the intervention to DFID Somalia is also relevant. Option ii) is likely to have a higher management cost than option i), as under option i) some of the management burden would fall to USAID. We estimate that option i) would cost 0.1 full time staff equivalents less than option ii). The intervention is also likely to reduce the burden on DFID staff compared to continuing to incorporate M&E into programmes in the normal way – we estimate this will reduce the burden on DFID staff by 1 full time equivalent. / The main drivers of the cost of the intervention will be: / the unit costs for project monitoring visits / the number of projects covered by the intervention / the unit costs and number of districts subject to surveys under the UNDP programme / the number and nature of other data collection and analyses supported (such as the Somalia population calculation, or bringing together and presenting governance and security data) / the unit cost and number of partners benefitting from training/capacity building sessions. This is also a function of the nature of the partner (Somali government and big UN organisations and programmes are likely to be higher cost than niche NGOs) / the level of investment in packaging and presenting the information. / Other drivers will be overhead costs, the security costs of operating in Somalia, and the human resource cost to DFID Somalia. / The cost of delivering output statement 2 through the UN is likely to be of the order of £3,000 per district. This compares favourably with the estimated $600,000 paid to a private company to conduct a similar survey in 6 districts across Somalia (estimate $100,000 per district). While it is not clear whether this is a perfect like-for-like comparison, the UN approach appears more successful and lower cost, which makes option v) appear potentially good value for money compared to options i) or ii). / The approach to reducing costs is largely a function of the option selected, and is set out below. If through reducing and managing the costs, we manage to deliver this intervention for less than the £6.5 million allocated to it, DFID Somalia will re-invest the remainder of the money in the wider Governance and Peacebuilding programme. / Expected benefits of the intervention / Some of the expected benefits are largely the same for the intervention whichever option is selected. There are other benefits that are particular to one or other option. These are set out at the end. / Benefits of all options / The biggest benefit of this intervention will be seen through DFID’s wider Governance and Peacebuilding programme. As set out in the strategic case, the lack of data and information about Somalia and DFID’s programme makes it difficult to design evidence-based interventions and to know whether they are having the intended effect and whether they needed to be adapted in order to deliver better results. If DFID Somalia can successfully use the information provided by this intervention, and make good decisions based on that information, then the Somali people and government institutions stand to benefit from a much more effective £80 million UK Governance and Peacebuilding programme. / This information will be made widely available and will be a public good which may be used by the Somalia government, the international community, academics and others. This will accrue benefits through the other donors’ programmes – estimated at a further £80 million. It was also accrue benefits to the Somali administrations. This would be a substantial and positive impact on conflict and fragility in Somalia. / DFID will directly benefit by knowing whether implementing partners of the £80 million Governance and Peacebuilding programme are delivering the results that they claim. / Other donors (including the EU, USAID, and Nordic countries) that co-fund programmes with DFID will similarly benefit from knowing whether our shared implementing partners are delivering. We estimate that this will benefit a further £80 million of investment in Somalia. / Implementing partners will benefit from improvements in their ability to determine and monitor their results and impact. This will benefit £80 million of DFID investments and an estimated further £80 million of other donor investments. / Additional benefits of option i) / The systems and methodologies established by IBTCI under the USAID contract are strong and high quality. IBTCI has demonstrated its ability to deliver against output statements 1 and 3, and as shown potential to deliver against output statement 4. Joining this programme would have the benefit to DFID of reducing the risk of selecting an implementing partner that does not deliver. / By joining with USAID, option i) would have an aid effectiveness benefit. It would harmonise DFID and USAID M&E, and may create a critical mass to attract other donors to also join in – further improving harmonisation and further improving the results capacity of other donors. / Additional benefits of option v) / UNDP’s approach to gathering data about Somalia is to invest in and use the Hargeisa-based Observatory of Conflict and Violence Prevention. The Observatory in turn will use the universities of Hargeisa, East Africa and Mogadishu to enumerate its surveys. This will have the effect of further building indigenous Somali capacity to conduct surveys, analyse data and produce reports on Safety and Security. / The intervention will contribute to generating wider information about Somalia, initially including population data, but which could be expanded to household surveys and other MDG data if the population calculation is successful. This is a further public good which may be used by the Somalia government, the international community, academics and others (all data produced by this intervention will be made publically available). / Risks and sensitivity analysis / The biggest risk to this intervention, and the key assumption for sensitivity analysis, is that DFID programmes and programme managers may be unwilling or unable to take decisions based on the evidence this intervention produces. If this happens, then programmes will not be adapted to take account of the emerging information about their effectiveness and the intervention will not deliver many of the benefits set out above. It will be essential to manage this risk carefully – how this will be done is set out in the Theory of Change section above. / Other risks include: / Security – for security or duty of care reasons, the implementers may be unable to access some parts of Somalia where we would need them to travel. This would reduce the impact of the programme. There are also security risks for individuals working in Somalia. / Political – it is possible that some of the outputs under the intervention, particularly output statement 2, will be politically sensitive in Somalia and beyond. This data will need to be managed carefully, and collection and analysis methodologies will need to be robust and able to withstand scrutiny and challenge. / The Management case includes a risk matrix. / Balance of costs and benefits / The expected costs and benefits are set out above. For all options, the cost is capped at £6.5 million over four years plus DFID staff time. The benefits are difficult to quantify with any confidence. However, given the expansion of DFID’s Somalia programme to £80 million per year, the development of a £80 million Governance and Peacebuilding programme, and the expect spill-over effects to other donors and beyond, this investment has the potential to lever impact many times its own value. It would need to improve the effectiveness of the £80 million DFID programme by just over 8% in order for the benefit to outweigh the cost. Without an intervention, we will remain largely unable to determine whether our programmes are having an impact and what that impact is. With the intervention we will be able to make better decisions, to stop the things that don’t work and expand the things that do. The cost also falls comfortably within DFID Somalia’s commitment to spend between 10 and 20 percent of its programme budget on M&E. This intervention is not without risk, and it will need to be monitored carefully to ensure it is having the desired effect. But the risk for the rest of the DFID Somalia programme of not investing is considerably higher. / Preferred option / On the basis of the information set out above, the preferred option is option v), with output statements 1, 3 and 4 delivered through USAID and IBTCI, and output statement 2 delivered through UNDP, UNFPA and others. / The reason for choosing USAID for output statements 1, 3 and 4, rather than going to tender are as follows: / The additional benefits of partnering with USAID as set out under ‘Expected benefits of the intervention’ above. These include the aid effectiveness benefits and the high quality of IBTCI’s products. / The reduced management costs to DFID of partnering with USAID as set out under ‘Expected resource costs of the intervention’ above. / The fact that USAID has already conducted a competitive tender process to select IBTCI for this work. / The reduced start-up costs for the intervention that DFID would incur, as these have already been borne by USAID. / Our confidence in USAID’s contract management capability to manage and reduce costs and ensure strong implementing partner performance. USAID has a full time staff member dedicated to managing the IBTCI project, who is backed by considerable legal and project management expertise – things that DFID would be unable to replicate.
D. What measures can be used to assess Value for Money for the intervention? / The key measures for assessing value for money are as follows: / Economy: The costs of project monitoring visits, training/capacity building sessions for partners, enumeration visits and surveys. At time of writing we do not know what these costs will be. / Efficiency: The quality of reporting and presentation of the data. Does the organisation managing the programme present the data in a clear, concise, accessible format that enables DFID staff and others to absorb it? / Effectiveness: Do DFID staff and others use the data produced by this intervention as evidence to make decisions about wider DFID programming. / The trigger which would determine whether the intervention would no longer represent good value for money would be if the data and information produced by the intervention is not used by DFID staff for decision making – either because it is not presented in a suitable way, or because they are unable or unwilling to use it.
E. Summary Value for Money Statement for the preferred option / This £6.5 million programme has the potential to lever huge change and improvement in effectiveness of DFID’s £80 million Governance and Peacebuilding programme, and other international community interventions in Somalia beyond that. The evidence that this programme can produce its outputs is strong. The challenge to deliver value for money, and where evidence is weak, is to turn this information into changes on the ground through better evidence-based policy and programme decision making.
[note] Details of the USAID programme can be found in “Somalia: Monitoring and Evaluation Project Technical Proposal – USAID/EA/LPC/Somaliua
[note] Community Safety & Security Approach to Grass Roots Peacebuilding Monitoring and Assessment Toolkit, 15 Sept 2010
[note] This diagram is based on the DFID ‘Stages of Project Lifecycle’ diagram, which can be found here: http://dfidinsight/MoneySight/Managingprogrammes/Businesscase/PUB_031140
[note] http://dfidinsight/MoneySight/Managingprogrammes/Monitoringevaluation/Evaluationlessonlearning/index.htm
[note] Joint Doctrine Note (JDN) 01/12Assessment: (Within a Stabilisation Context)
[note] Examples courtesey of Anna Hentinnen, DFID India Evaluation Advisrer
[note] World Bank IEG report: What can we learn from Nurtition Impact Evaluations?, 2010
[note] http://www.povertyactionlab.org/scale-ups
[note] Emily Poskett Yemen BTOR – 23/2/12
[note] Afghanistan Reconstruction Trust Fund Monitoring Agent For The Investment Portfolio Terms Of Reference
[note] Helmand Monitoring and Implementation Programme. Annex A
[note] Mogadishu Opinion Poll – 13 March 2012
[note] IRI Hargeisa Poll Presentation – 6 December 2011
[note] DFID Somalia Deputy Head, February 2012
[note] Peace and Security Monitoring Assessment toolkit
[note] http://www.fsnau.org/
[note] http://www.unicef.org/somalia/media_1360.html
[note] reference 29 Feb 2012 UNSAS meeting papers
[note] DRAFT FINAL 6 Jan 2012 Sustainable Employment and Economic Development Programme SEED Annual Review Report
[note] M&E Matrices Outcomes 1, 2 and 3 – February 2012
[note] Peace and Security Monitoring Assessment toolkit
[note] http://www.fsnau.org/
[note] http://www.unicef.org/somalia/media_1360.html
[note] DFID Somalia Operational Plan Annex A: Step change in monitoring results – May 2011
[note] Transition Initiatives for Stabilisation (TIS)
[note] DFID Somalia Operational Plan Annex A: Step change in monitoring results – May 2011.

Commercial Case

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / B. Value for money through procurement / Our intention is to fund this intervention through the following funding mechanisms: / Output statements 1, 3 and 4 will be funded through investing in USAID’s existing Monitoring and Evaluation Programme for Somalia (MEPS). / Output statement 2 will be funded through investing in UNDP (for the Safety and Security Assessments under its Monitoring and Assessment Toolkit) and through UNFPA (for the Somalia Population Calculation). Decisions on how to fund further analysis and data collection in Somalia will depend on the outcome of the Somalia Population Calculation and further proposals to be developed by the UN Statistics Working Group. / Taking each of these in turn: / Output statements 1, 3 and 4 / USAID has conducted a competitive tender for its MEPS programme, and has contracted IBTCI to implement its MEPS programme. The MEPS programme performs a near identical function for output statements 1 and 3 as is required by DFID under this intervention. USAID has strict project management procedures designed to ensure IBTCI delivers excellent value for money, and has offered to manage the DFID contribution to this programme on our behalf – subject to agreement to: / an MOU between DFID and USAID / a scoping document setting out DFID’s requirements from USAID / Formal negotiations on these with USAID will commence once this business case is approved. / We therefore rely on USAID to ensure value for money through application of its procurement procedures. / Output statement 4 is not identical to the existing USAID MEPS programme. However, we will work with USAID to determine whether the MEPS programme can be adapted and expanded to include this output within USAID’s procurement regulations. If this is deemed not possible, we may wish to put output statement 4 to competitive tender and direct procurement. In this case we will follow DFID procurement guidance and regulations, and complete a ‘Direct Procurement’ section for this business case. / Output statement 2 / Both the UNDP Safety and Security Assessments, and the UNFPA-led Population Calculation are unique programmes – there is no choice for DFID to procure the services they will supply elsewhere given the evidence set out in the Appraisal Case. DFID’s main foci will therefore be: / to negotiate a maximum 7% administration fee when agreeing funding MOUs with UNDP and UNFPA / to check via due diligence assessments and project reporting that the procurement of these agencies is delivering value for money. / The DFID multilateral aid review found that UNFPA “Has a good track record on procurement. Its procurement strategy considers value for money related principles”. This gives some confidence in UNFPA’s procurement for this programme. / For UNDP, the Multilateral Aid Review found that “While UNDP has sound procurement policies, little evidence was available of the extent to which they are used to drive the achievement of value for money.” We will therefore focus our efforts on ensuring UNDP’s procurement under this programme delivers value for money.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The total budget available for this programme is £6.5 million over four financial years as set out below: / FY12-13 FY13-14 FY14-15 FY15-16 / Budget £0.5m £2m £2m £2m / This money has been allocated from the DFID Somalia Governance and Peacebuilding budget and is within DFID Somalia’s resource allocation. The programme is designed to extend beyond the current spending round and is within guidance set out by FCPD. / The paragraphs below set out the estimated unit costs for the programme against, and the number of each unit we expect this project will purchase. At this stage, both the unit costs and the number of each unit to be purchased are estimates based on discussions with the DFID Somalia Governance and Peacebuilding team, and partners involved in implementation of similar programmes. These prices unit costs and numbers of units purchased will be determined by: / negotiation with IBTCI through USAID. / the precise format and requirements of the DFID Somalia Governance and Peacebuilding programme, which is currently under design. / However, if unit costs are higher than those specified, the number of units will be reduced to keep the total budget of £6.5 million. / to verify results reported by partners / The cost of this output statement is estimated at £30,000 per project per year, plus £3,000 per field visit. / FY12-13 FY13-14 FY14-15 FY15-16 / Number of projects 3 15 20 20 / Number of field visits 10 50 50 40 / Total cost £120k £600k £750k £720k / Examples of projects in this context include the UNDP Rule of Law programme, consultants implementing public sector reform and various NGOs such as PACT, IRC, Care or Danish Refugee Council implementing programmes across several communities in Somalia. In the case of the Somalia Stability Fund, or the Somaliland Donor Fund, this intervention would work at the level of individual projects under the fund rather than at the level of the funds themselves. / Examples of field visits include to the site of the prison that will be built with DFID funds in Mogadishu, inter-clan conflict resolution sessions and community-based development project sites. Care will be taken to minimise costs by grouping nearby project sites and visiting several of them during a single mission. / to collect data to determine baselines, results and impacts of interventions / The cost of this output statement is estimated at £3,000 per district for UNDP, plus analysis and presentation of findings, plus other analysis (such as contributing to the UNDP Somalia population calculation). / FY12-13 FY13-14 FY14-15 FY15-16 / Number of districts 10 30 60 90 / Other analysis 1 3 4 3 / Total cost £230k £690k £980k £870k / to build partner capacity to monitor results and impact / The cost of this output statement is estimated at £30,000 per project per year / FY12-13 FY13-14 FY14-15 FY15-16 / Number of projects 5 20 5 5 / Total cost £150k £600k £150k £150k / As under output statement 1, in this context and implementing partner might be an NGO project management team – such as Saferworld or Mercy Corps. Or it might be the particular part of a UN agency or programme managing a DFID project, such as the programme management for the UN’s Joint Programme on Local Governance (JPLG). / to collate, analyse, package and present governance and peacebuilding information / The cost of this output statement is estimated at £200,000 per year (less in the first year due to an anticipated late start date) / FY12-13 FY13-14 FY14-15 FY15-16 / Total cost £50k £200k £200k £200k / The total estimated costs per year are therefore as follows: / FY12-13 FY13-14 FY14-15 FY15-16 / Output 1 £120k £600k £750k £720k / Output 2 £230k £690k £980k £870k / Output 3 £150k £600k £150k £150k / Output 4 £50k £200k £200k £200k / Total cost £0.55m £2.09m £2.08m £1.94m / More accurate forecasting will be possible once final unit costs, the precise nature of the DFID Somalia governance and peacebuilding programme, and the priorities of the DFID governance and peacebuilding team within that programme are known. These will be determined during the initial 6-month inception period of this programme, and will be kept under regular review.
B. How will it be funded: capital/programme/admin? / Funding will come from programme resources.
C. How will funds be paid out? / Funds will be paid to different entities as follows: / Funds to UNDP or other UN agencies will be based on an MOU on a reimbursable basis in line with DFID guidance on managing payments to multilaterals. / Funds to IBTCI will be channelled through USAID on the basis on an MOU with USAID. The details of how this will be done including terms, frequency, reporting, assets, admin costs will be determined in the MOU. We will seek guidance from the DFID Nairobi Accountability and Results Team (ART) to ensure this MOU meets DFID standards.
D. What is the assessment of financial risk and fraud? / Our assessment of financial risk and fraud risk is that they are low. UNDP, UNFPA and USAID have strong systems in place to guard against financial risk and fraud within their own organisations and within their sub-contractors. We will conduct due diligence assessments of implementers in line with DFID Somalia guidance.
E. How will expenditure be monitored, reported, and accounted for? / For all implementing partners, we will require annually audited statements that separately report receipt of DFID funds and associated disbursements, together with unspent funds. Partners will also submit expenditure reports with budget breakdowns to monitor actual spend and adherence to original proposed budget lines. / If partners purchase assets, we will require them to maintain an asset register, and to seek a decision from DFID on what to do with the assets at the end of the project. / We will include in any agreement we sign with any partners for this programme an exit strategy, which will set out the process, and give DFID appropriate authority, to withhold/suspend any future disbursements, reclaim all or part of the funds already disbursed and/or cancel the agreement and project.
[note] http://dfidinsight/MoneySight/Managingprogrammes/Howweworkwithotherdonors/Workingwithmultilaterals/PUB_020280

Management Case

A. What are the Management Arrangements for implementing the intervention? / The different components of the intervention will be managed in different ways: / The funding to UNDP, UNFPA and any other implementing partners for output statement 3 will be managed by DFID. The UNDP/UNFPA-DFID relationships will be defined by MOUs. / The remainder of the programme (i.e. output statements 1, 2 and 4) will be managed by USAID. The USAID-DFID relationship will be defined by an MOU. / We will establish a DFID Somalia Monitoring Programme Steering Team, comprising the DFID Somalia Results Adviser and advisory and programme management staff from the DFID Somalia Governance and Peacebuilding team. This Steering Team will: / Oversee and provide guidance on MOU negotiations, in particular with USAID / Agree priorities for each of the outputs, and oversee and provide guidance on negotiation of these priorities with USAID / Monitor performance of the intervention including the logframe / Agree any changes to the intervention within the scope of this business case / Meet with UNDP to agree next steps on the Safety and Security Assessments / Decide on further analysis and data collection exercises to be funded under this intervention / Monitor the extent to which the intervention is supporting the wider DFID Governance and Peacebuilding Programme and make recommendations both to the intervention and the DFID Governance and Peacebuilding Team on improving this if necessary. / Ensure the timeline for implementation of this intervention, and the timeline for the other DFID Somalia Governance and Peacebuilding interventions are aligned. / Perform any other functions regarding this intervention as may be required. / The MOUs with UNDP and UNFPA will be based on standard DFID templates as provided by DFID’s United Nations and Commonwealth Department. / The MOU with USAID will be based on an existing DFID-USAID MOU for the Transitional Initiatives for Stabilisation (TIS) programme. However, we aim for the following elements to be included within the final MOU (though these will require negotiation with USAID): / A requirement that IBTCI submits quarterly and annual progress reports, including progress against the logframe. / A requirement that IBTCI employs a second senior programme manager of similar rank to the existing programme manager. / Scope for USAID to recruit a second programme officer to help manage the programme / A clause setting out a requirement for annual reviews of the programme, and linking funding disbursements to implementation of annual review recommendations / A 6-month inception period during which any outstanding issues such as staffing, IBTCI or USAID capacity, unit costs or management arrangements can be resolved. / A joint DFID-USAID panel to oversee management of the programme. / Other financial issues as set out in the Financial Case
B. What are the risks and how these will be managed? / Risk Probability Impact Management / DFID programmes and programme managers may be unwilling or unable to take decisions based on the evidence this intervention produces. Medium High DFID Somalia Results Manager to use pillar reviews to challenge programme team on their use of evidence emerging from this intervention. / Output 4 is designed to mitigate this risk. / Security – for security or duty of care reasons, the implementers may be unable to access some parts of Somalia where we would need them to travel. Medium Medium We will work with the implementers to encourage them to use local partners who are better able to access insecure areas. It is likely that if it is possible for a DFID-funded project to operate, then it will be possible for the implementers to access it. / Monitoring donor-funded programmes on the ground could have unintended and negative consequences on conflict and fragility in Somalia Low Low We will ensure the implementer adopts DFID conflict-sensitivity methods. / We will encourage implementing partners to use the NGO SSAFE training. / Focussing implementing partners on the measurable the intervention causes them to miss the important. Low Low We will ensure that theories of change do not exclude non-measurable elements, if they are necessary. / Implementation of much of the programme will rely on USAID. USAID may decide to cancel or alter the programme in a way the does not suit DFID Medium Medium This will be handled in the MOU with USAID
C. What conditions apply (for financial aid only)? / n/a
D. How will progress and results be monitored, measured and evaluated? / Monitoring Plan / The logframe sets out the data requirements and sources for this intervention. Progress against all indicators will be monitored annually, with the exception of the impact indicator, which will be monitored at the start and end of the intervention. / While the baselines for each indicator are correct, the targets and milestones are not as these are in most cases a function of decisions about the DFID Somalia Governance and Peacebuilding programme, which have not yet been taken. The milestones and targets will therefore be updated as those programmes and the projects under them are approved over the next 6 months during the inception period. / Evaluation Plan / As set out in the appraisal case, the evidence for this intervention is limited. However, the nature of this programme does not lend itself to a rigorous impact evaluation as there is no control group with which to compare results in the treatment group. It would also be impossible to match DFID-funded Governance and Peacebuilding projects (or projects from other pillars) for inclusion/exclusion in the treatment group due to the diversity of the programme and the spill-over effects between projects. / There is an ongoing evaluation prioritisation exercise ongoing across DFID Somalia to allocated scarce evaluation capacity in the office. If evaluation of this intervention is prioritised we will look to conduct a process evaluation which considers: / Is the project operating as intended and influencing DFID Governance and Peacebuilding and wider donor decision making? / Does better data and better monitoring deliver better projects? / To answer these questions, we would develop a more detailed evaluation plan for a process evaluation that: / 1 – compares the pre-intervention set of logframes with a post-intervention set for the same projects, and establish whether they align better with DFID corporate guidance, whether they use more and better data, and whether they are more fully completed. / 2 – determines whether there are changes in the use of data in DFID business cases after the intervention. / 3 – looks qualitatively for effects on the wider development community of more data availability. / 4 – compares the percentage of verified and un-verified partner results before and after the intervention / 5 – determines whether decisions are taken to change programme design or shift resources when intervention data shows that projects are being successful or not. / 6 – assesses the extent to which Somali administrations are using the data generated by this intervention.
Lograme / Quest No of logframe for this intervention: 3493189