Annual Review – post April 2018

Title: Supporting the Africa-led Movement to End FGM: Phase II
Programme Value £ (full life): £35Million		Review Date: February 2020
Programme Code: 204768	Start Date: April 2019	End Date: March 2024

Summary of Programme Performance
Year	2020
Programme Score	B
Risk Rating	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204768/documents
DevTracker Link to Log frame:

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

DFID will provide up to £35 million over a period of 5 years for a second phase of support to efforts to end Female Genital Mutilation (FGM).
[note] The practice is known as Female Genital Mutilation (FGM), Female Genital Cutting (FGC) and (with decreasing usage) female ‘circumcision’. In this AR we use the term FGM, to reflect the extreme harm done by the practice and the fact that it violates girls’ and women’s human rights and bodily integrity. FGM is also the term used in international negotiations. The term ‘cutting’ is used to reflect understanding that the practice is not carried out with the intention of harming girls but because in communities where it is practiced, they cannot be married – and would therefore be isolated and stigmatised - without it. The term is not intended to question that it is an extremely harmful practice; we respect this position but we do not use it in this AR. Practising communities all have their own words for the practice.

Building on the foundations of our first five year investment (2013 – 2018), Health: Toward Ending Female Genital Mutilation/Cutting in Africa and Beyond (hereafter referred to as Phase I FGM Phase I) https://devtracker.dfid.gov.uk/projects/GB-1-203024, this programme will focus on accelerating the pace of change and achieving results at scale to contribute to the vision in the Sustainable Development Goals of a world free of the practice of FGM by 2030.

The programme will do this through three complementary and mutually reinforcing approaches:

- Supporting and building the capacity of the Africa-led movement to end FGM at multiple levels and at scale (ALM component);
- Getting laws, policies and systems at multiple levels to work effectively to end FGM – through the WHO and the Joint UNFPA/UNICEF to Eliminate FGM (UNJP);
- Generating the right data to guide interventions and measure change through a Data and Measurement (DM) component.

Summary supporting narrative for the overall score in this review (1/2 page)

The ‘B’ score reflects the fact that the laws, policies and systems component is signed and implementation has begun, but also reflects significant delays in the procurement of the ALM and DM components.

The procurement process for both are near completion and it is anticipated that the winning consortia will be announced in March 2020.

This project is not scored against specific logframe indicators because, as set out in the business case, a more detailed logframe or results framework will be designed during the co-creation phase of the main Africa-led movement component.

The outputs below therefore refer to 1) the ALM and DM components and 2) the laws, policies and systems component (UNJP/WHO), which has begun. Next year’s Annual Review will reflect the outputs agreed in the results framework for the whole programme.

Recommendations for the year ahead (1/2 page)

1. Work closely with Procurement and Commercial Department (PCD) to ensure the two contracts are well designed and awarded to maximise programme effectiveness and efficiency (DFID)
2. Proceed with the co-creation phase to design a range of evidence-based interventions and a robust results framework (DFID and Implementing Partners).
3. UNJP and WHO to proceed with implementing agreed activities to improve the enabling environment to end FGM.
4. Design and utilise a separate results framework for the laws, policies and systems component in the next 3 months (DFID and Implementing Partners).
5. Bring the date of the next annual review forward, to October 2020.
6. Establish a mechanism in the co-creation phase for the ALM and DM components to learn from evidence generated by the research programme.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Procurement and mobilisation of three programme components
Output number per LF			Output Score	B
Impact weighting (%):			Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress

Provide supporting narrative for the score

The procurement of the main Africa-led Movement (ALM) and Data and Measurement (DM) components was delayed due to vacancies and change in personnel at various levels, although once these were filled, the process was prioritised and moved efficiently from the invitation to tender onwards.

The Early Market Engagement (EME) was held on 15 May 2019. The programme’s Terms of Reference were then worked up and the invitation to tender (ITT) was launched on 23 October 2019, with a closing date of 27 November 2019.

These factors also caused some delay in implementing the laws, policies and systems component. Once the Project Completion Report (PCR) for Phase 1 of the programme was complete in June 2019, we sought and reviewed proposals from the UNJP and WHO for renewed interventions to improve the enabling environment to end FGM. A formal Contribution Arrangement was drawn up with WHO and was signed off in November and work has commenced. The focus activities are:

- Develop and initiate implementation of health sector action plans
- Introduce and assess health sector interventions on FGM
- Monitoring and evaluation activities
- Finalise and launch the health economics measurement tool including a website established for hosting an FGM cost calculator and a tool for calculating costs in 30 high prevalence countries

A Standard Administrative Arrangement for the UNJP was signed in January. The focus activities are:
- Implementation of the AU continental-wide ‘Saleema’ initiative promoting the elimination of FGM
- Implementing cross-border initiatives on FGM in five countries in Africa
- Development and implementation of framework for addressing the medicalisation of FGM in at least two countries
- At least two countries to develop costed national action plans for the elimination of FGM
- Implementation of legislation criminalising FGM in Burkina Faso and Kenya
- Following up on global and country level actions on the ICPD25 commitments

Lessons identified this year, and recommendations for the year ahead linked to this output

1. Work closely with Procurement and Commercial Department (PCD) to ensure the two contracts are well designed and awarded to maximise programme effectiveness and efficiency (DFID)
2. Proceed with the co-creation phase to design a range of evidence-based interventions and a robust results framework (DFID and Implementing Partners).
3. UNJP and WHO to proceed with implementing agreed activities to improve the enabling environment to end FGM.
4. Design and utilise a separate results framework for the laws, policies and systems component in the next 3 months (DFID and Implementing Partners).

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

This is a generic Theory of Change, suitable for a centrally managed programme with many different country contexts. Suppliers will be required to produce a country-specific Theory of Change for each context in which they are working. Given the flexible nature of the programme, there will also be a need to regularly review and test the theory of change in each context.

The working Theory of Change shows that to reduce the practice of FGM there needs to be a positive change in social attitudes towards ending FGM. This reflects that FGM is a social norm, and a change in behaviour around FGM therefore requires a change in social attitudes and the creation of a new norm.

The Theory of Change also shows how a multipronged approach is needed to bring about these changes in social attitudes. It shows how community-level commitment to ending FGM, the right enabling environment for change to happen, and diffusion and amplification mechanisms come together to change social attitudes.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The programme’s expected contribution to the outcome of improving the enabling environment for ending FGM is on track, through work that has started with WHO and the UNJP. The programme is off-track in terms of contributing to the overall outcome and impact of reducing FGM prevalence in focus countries, due to a delay in procurement and therefore implementation. We are working closely with PCD to ensure the remainder of the procurement process is completely smoothly and we are able to award contracts and start the co-creation phase imminently.

Explain major changes to the logframe in the past year (1/2 page)

The results framework for the ALM and DM components, which may be a logframe or an alternative, will be designed in the 6-8 month co-creation phase, with input from the implementing partners and with oversight and ultimate sign-off from DFID.

Describe any planned changes to the logframe as a result of this review (1/2 page)

N/A

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

As set out in the Business Case, the available evidence shows that for ending FGM interventions to be successful, a combination of approaches, which include targeted community-level social change, the creation of a supportive enabling environment, and interventions that catalyse and diffuse change, are needed. Investing in a programme that delivers all of these interventions is therefore the best approach from an economy, efficiency, effectiveness or cost-effectiveness perspective.

The UN Joint Programme and the WHO are the most cost-effective mechanism to deliver the work on laws policies and systems, given their experience and normative role working with governments and sectors. There have been no set up costs to this component, as both partners are building on their existing presence and activities.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The UK is a global leader in its support to the Africa-led movement to end FGM, and already invested significant resources. Ending FGM is a key part of our wider ambition to end violence and against women and girls and gender inequality. This remains a high priority programme, and the Value for Money justification has not changed since the Business Case.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

A full risk matrix is set out in the Business Case. The overall risk profile is likely to remain ‘Major’ given the delivery risks inherent in working on ending FGM. Working to change social norms is extremely difficult with many factors outside a programme’s control, but working to end the social norm of FGM is particularly challenging given it is a sensitive, complex and taboo practice that is extremely deep-rooted. The practice is carried out in different ways and for different reasons in different communities – programming must therefore be highly context-specific. In addition, measuring social norms change is challenging, and the programme will have to test new thinking on how best to do this. On top of this, the programme will work across multiple countries with potentially long results chains giving rise to challenges around monitoring. All partners in Phase I faced varying degrees of delivery challenges.

Implementing partners will compile their own risk matrices, approved by DFID, in the co-creation phase.

The main risk now is operational: any further delay in implementation risks achieving the planned results in the timeframe set out. We are working closely with PCD to ensure that the procurement is finalised and contracts awarded as soon as possible.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Commercial and Financial

Both the UN Joint Programme and the WHO are funded through indirect procurement, through Memoranda of Understanding, for the Laws, Policies and Sectors component of the programme. Memoranda of Understanding are the established method of providing funding to the UN, using templates agreed centrally for each agency.

UNICEF, UNFPA (UNJP) and WHO have regular assessments centrally by DFID on financial management. Within both organisations, there are procedures to deal with financial mismanagement and fraud. These are under constant review, including through Multilateral Aid Reviews.
Funds disbursed to UN agencies are subject exclusively to the internal and external auditing procedures laid down in the agencies’ financial regulations and rules.

To date the overall spend to date for this financial year is £2,493,946.00 against a total approved budget of £2,500,000.00 for this financial year which is practically on target for the WHO and UNJP components.

Component	Year	Approved Budget in £s	Spend in £s	Commitment in £s
WHO	2019/20	1,000,000.00	993,946.00	1,000,000.00
UNJP	2019/20	1,500,000.00	1,500,000.00	1,500,000.00
		2,500,000.00	2,493,946.00	2,500,000.00

Both UNJP and WHO have provided requests for the contribution on time as specified by their respective Memorandum of Understanding/Agreements.

Date of last narrative financial report(s)	WHO October 2019 / UNJP January 2020
Date of last audited annual statement (s)	Too early (UNJP – June 2019 for year ending December 2018 for Phase1)

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

The results framework for the ALM and DM components will be designed during the co-creation phase. We suggest bringing the date of the next annual review forward, to October 2020, to monitor progress of the co-creation and mobilisation phase.

We have an indicative results framework for the UNJP component, with proposed indicators to measure progress towards the overall outcomes of improving the enabling environment for ending FGM and girls and women receiving appropriate FGM prevention, protection and care services. We will finalise this shortly. We will have quarterly calls with the implementing partner to discuss progress, and they will produce a report, to be approved by DFID, to summarise achievements and learning from the current piece of work.

We are also working with the WHO to develop a set of indicators to measure progress against the overall outcome of enabling health systems in six countries to respond adequately to FGM. We will have quarterly calls with the implementing partner to discuss progress, and they will produce a report, to be approved by DFID, to summarise achievements and learning from the current piece of work.

Evidence (1/2 page)

The research component of Phase 1 – Evidence to End FGM – which was essentially managed as its own programme, has continued to produce research to answer some key questions around where, when, and why FGM/C is practiced, and whether it’s changing?; what is working, where, and why?; what are the wider impacts of FGM/C? and; looking at methodological approaches to FGM/C measurement, including in particularly the factorial focus group analysis.

The research programme has been extended to 2022 and will continue to provide evidence that should inform Phase 2 of the main FGM programme. In the last year studies have included analysis of FGM prevalence among 0-14 year old girls in Kenya; shifts in the practice in Sudan; medicalisation in Egypt and associations between FGM and HIV. It will be important to ensure that evidence from these informs interventions as relevant in the co-creation and implementation phases of the ALM and DM components. To do this DFID should ensure that the SRO and implementing partner (Population Council) are brought into early discussions and that they have an established mechanism for feeding in as the programme develops.

Learning (1/2 page)

The main lesson we have learned from the procurement process is that there can be delays in procuring a complicated programme and these should be accounted for in advance planning.

Progress on recommendations from previous reviews (1/2 page)

N/A

Recommendations

1. Design and utilise a separate results framework for the laws, policies and systems component in the next 3 months (DFID and Implementing Partners).
2. Bring the date of the next annual review forward, to October 2020.
3. Establish a mechanism in the co-creation phase for the ALM and DM components to learn from evidence generated by the research programme.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided