Business Case

Summary Sheet

Title: DFID Support to National Malaria Programme 2
Purpose: To improve the planning, financing and delivery of sustainable and replicable pro-poor services for malaria in supported States
Programme Value: max £50m		Country/ Region: Nigeria
Senior Responsible Owner: Ebere Anyachukwu
Project Code: 202979	Start Date: 2017	End Date: 2022
Quest Number:5506112

# Intervention Summary
## What support will the UK provide?
The UK will provide upto £50m for a 6 year programme (2017 – 2022) to reduce Nigeria’s malaria burden through more efficient and effective use of available resources. The programme will strengthen the Government of Nigeria’s malaria control programme to ensure long-term sustainability.
Building from the success of the Support to National Malaria Control Programme (SUNMAP) programme (2008-2016), the new programme will:
- help address current malaria programmatic and technical gaps,
- complement and secure the effectiveness of the Global Fund’smalaria efforts in Nigeria,
- reduce the risk of malaria resurgence,
- provide a structured path into integrating malaria management into broader health systems strengthening efforts.
- build long term sustainability,
- make possible an eventual responsible exit from DFID bilateral malaria support in Nigeria.

The programme will be delivered by a service provider, selected through competitive procurement in compliance with OJEU regulations.
## What are the main programme activities?
SUNMAP2 will support interventions against five outputs as follows:
- Under the first output ‘strengthened government stewardship at national level and in state supported states’, SUNMAP2 will build the capacity of the national and supported states malaria programmes in the formulation and dissemination of evidenced based policies and annual operational plans development and monitoring. It will put a new emphasis on malaria expenditure tracking, financial management strengthening and domestic resources mobilisation. Working closely with DFID Nigeria’s state level governance, health systems and engagement platforms, SUNMAP2 will support the Global Fund to develop and implement its new state-level grant model, which aims to increase direct operational oversight and commitment at state level allowing greater visibility over delivery and risk. SUNMAP2’s work on public financial management and domestic resource mobilisation will also support the Global Fund’s efforts to incentivize domestic funding through its New Funding Model. Considerable efforts will go in supporting the development and implementation of public private partnership strategies. .
- The second output will aim at increasing the sustainable availability of antimalarial commodities. For the public sector distribution channels, this will entail integrating, where appropriate, the current vertical antimalarial commodities procurement and supply management systems into broader health commodities management systems as well as supporting the design and roll-out of sustainable supply systems to support non-health facility based interventions. Working with the Nigerian government and a range of partners, including the Global Fund, USAID and Gavi, SUNMAP2 will support the implementation of the National Supply Chain Integration Project, which will increase the availability of basic health commodities, improve transparency and help minimise corruption. For the commercial sector distribution channels, the programme will help the national malaria programme to identify the constraints to developing high quality antimalarial commodities retail markets as well as develop and support action plans to address a selection of them.
- Falling under the third output, ‘More efficient and equitable malaria prevention and treatment services delivery’ will be a set of selected interventions aimed at strengthening malaria services delivery and supervision. The programme will continue UK’s commitment to building the capacity of health providers, including those in the private sector, in up-to-date malaria management knowledge and practices. Emphasis will be put on the newer interventions included in the National Malaria Strategic Plan 2014-2020 (e.g. seasonal malaria chemoprevention, integrated community case management and severe malaria management) with the aim to test delivery models in supported states and inform cost-efficient roll-out of these interventions across the country with non-DFID or non bilateral DFID resources (particularly domestic funding and the Global Fund).
- The fourth output ‘Better engaged citizens and institutions in the country’s malaria response’ will support a better understanding of the gap between awareness and use of malaria interventions, and reviewing accordingly the national and supported states Advocacy, Communication and Social Mobilisation (ACSM) strategies and plans in pursuance of their respective malaria targets. SUNMAP2 will further build the capacity in ACSM interventions implementation, supporting selected ones for demonstration purposes. Efforts under this output will contribute to advocacy for social accountability and domestic resource mobilisation.
- The fifth and last output’s objective is to embed at national and supported states an evidence based learning environment. This cross-cutting output will, on the one hand, strengthen systems for results measurement at national, supported states and programme levels; this will range from routine data to surveillance systems and surveys and operational research. It will, on the other hand, support the use of generated evidence for decision making. A six year longitudinal study will be undertaken under this output with the aim of testing the programme theory of change and understandingthe key drivers for sustainable development aid.
## Why is UK support required?

The UK is committed to combating malaria, and supports the new global malaria target to, by 2030, eliminate or reduce malaria incidence by 90% in endemic countries. With 25% of the global burden of malaria, a reduction in malaria cases and deaths in Nigeria is urgently needed if the 2030 global malaria targets are to be achieved. Major progress has been recorded in malaria control in the country in the past 15 years thanks to an unprecedented mobilization of mainly external resources. DFID played a criticial role in this success by providing quality technical assistance that supported the scale-up of interventions well beyond its directly supported 10 states. There are however serious outstanding programmatic and technical gaps that threaten these gains. To reach the malaria pre-elimination phase, Nigeria needs advanced technical capacity to respond to the changing epidemiology of the disease. DFID is well placed to strengthen that capacity at institutional level.

The UK is a major financial supporter of the Global Fund to fight Aids, TB and Malaria (the Global Fund), which provides the bulk of external financing for malaria in Nigeria. The Global Fund has contributed substantially to the scale up of malaria control in Nigeria through the provision of large numbers of commodities such as long lasting insecticidal nets (LLINs). However, a number of weaknesses in the delivery of Global Fund grants in Nigeria have been identified (as detailed in the a recent audit report of the Office of the Inspector General), particularly with fiduciary controls, supply chain systems, and service delivery. There are currently concerted efforts by the Nigerian Government and the Global Fund to address these weaknesses. However, these efforts will require complementary support from other partners who are able to deploy extensive governance, health systems and malaria control expertise, particularly at state level. Progress in all these areas will be required to drive sustainable malaria reduction in the post 2015 period.

DFID’s existing bilateral malaria programme SUNMAP has been the key provider of technical assistance and catalytic support enabling the recent scale up of malaria control in Nigeria. DFID’s extensive portfolio of health systems, governance and private sector programming and expertise in Nigeria confers a distinct comparative advantage, which will enable SUNMAP2 to complement and optimise the Global Fund’s efforts; build sustainability into malaria programming, and help secure a responsible exit from DFID bilateral malaria support.
## What are the expected results?

At impact level, SUNMAP2 will contribute to a reduction in all causes under-five mortality rate from 128 per 1,000 in 2013 to 80 in 2022 and a reduction in the proportion of children aged 6-59 months infected with malaria parasites from 27% in 2015 to 16% by 2022. It is further anticipated, under very conservative assumptions, that the programme will directly save 7,500 lives and avert 209,000 disability adjusted life years (DALYs).

The programme will build sustainable capacity, systems and financing sources, and hence it is expected that the gains made during the project lifetime will be sustained after its closure. At an horizon of 20 years, this would bring the total lives saved to 40,000 and DALYs averted to 915,000 within the population targeted with commodity support during the programme.

The programme represents good value for money, with an estiamted cost of £226.24 per DALY, decreasing to £51.73 per DALY if longer term benefits are included.
## How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

SUNMAP2 will support DFID Nigeria’s 2016 – 2020 business plan vision “As part of a flagship partnership between the Government of Nigeria and the Government of the United Kingdom, DFID Nigeria will work at the federal and state level to support Nigeria to use its own resources to address the causes of and eliminate poverty ensuring no Nigerian is left behind”. It will contribute to DFID Nigeria’s Business Plan Strategic Objective 4 for bilateral programmes: Build the systems, public and private, to deliver basic services of health care, education, water and sanitation and nutrition to the poorest in the country while fostering social protection. Build the resilience of the poorest to ensure they can adapt to the impact of climate change; which is aligned with the UK Aid Strategy and DFID Single Departmental Plan (SDP) Objective 4: Tackle extreme poverty and help the world’s most vulnerable, with commitments to save 1.4 million children’s lives, and invest to save lives from malaria. SUNMAP2 will also align with DFID Nigeria business plan geographical targeting in fewer states and will actively collaborate with other DFID programmes, particularly those addressing governance, accountability and health systems strengthening, to facilitate long term institutional and transformational change .
## How does the programme fit with the Government of Nigeria’s strategy?

DFID, through SUNMAP, provided significant support to the development of the latest Nigeria National Malaria Strategic Plan covering the period 2014 to 2020. SUNMAP2 has been designed to strengthen the management and technical capacity of the government and other key actors to drive the implementation of this plan and achieve its ambitious targets. This will translate in technical support embedded in the National Malaria Elimination Programme in the first years of the programme in the key areas of programme management and evidence generation and use and capacity building across all programme outputs.

# Strategic Case
## Context and need for a DFID intervention

The Health Context
Nigeria has poor health indicators including: higher than average rates of under-five mortality and the highest number of maternal deaths in Sub-Saharan Africa.

Nigeria is Sub Saharan Africa’s second largest economy; it has a population of about 170 million, large reserves of oil and gas resources and a growing economy. In 2014, the Gross Domestic Product (GDP) was 568.5 billion USD[1]; with a GDP growth rate of 6.3% (this fell to 3.3% in 2015)[2]. More than 50% of the population live below the poverty line of less than $1.25 per day and the average life expectancy at birth is 52 years[3].
[1] World Bank, 2014 http://data.worldbank.org/country/nigeria
[2] World Bank, 2014 http://data.worldbank.org/indicator/NY.GDP.MKTP.KD.ZG/countries/NG?display=graph
[3] World Bank, 2014 http://data.worldbank.org/country/nigeria

Nigeria is ranked 152 out of 187 countries in the 2013 United Nations Human Development Index. Maternal mortality is estimated at 630 per 100,000 live births -the highest in sub-Saharan Africa - and under-five mortality is estimated at 124 per 1,000 live births so that approximately one in eight children die before their fifth birthday[4].
[4] United Nations Development Programme 2015 Human Development Reports http://hdr.undp.org/en/countries/profiles/NGA
Malaria is a major cause of ill health, mortality and poverty in Nigeria

97% of Nigerians live in areas of malaria transmission and are therefore at high risk of infection. Malaria related illnesses overburdens the already-weakened health system with nearly 110 million clinical cases of malaria diagnosed each year. Malaria accounts for 60% of outpatient visits and 30% of hospital stays. The Malaria Indicator Survey (MIS) of 2010 indicated that 42% of under-fives harboured malaria parasites (infection prevalence estimate at the time of the survey). Malaria related deaths account for up to 11% of maternal mortality, 25% of infant mortality, and 20% of under-five mortality resulting in 300,000 childhood deaths annually[5]. Malaria in Nigeria costs an estimated US$ 835 million per year, including prevention, treatment and loss of income[6]. Looking at expenditure, 68% of anti-malarials for under-fives were sourced from private sources (ACTwatch 2012) and among all members of the household who presented with fever, the largest group (35.5%) sought chemists and patent medicine vendors as the first place for treatment, while additional 3.5% sought advice or treatment from other private sector outlets and 47.8% got their treatment at home (ACTwatch 2012[7]).
[5] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[6] Malaria No More, 2015 http://www.malarianomore.org.uk/our-work/protecting/nigeria
[7] ACTwatch Group & SFH/Nigeria, 2013. Household Survey, Nigeria, 2012 Survey Report. Washington, DC: Population Services International. Available at: www.actwatch.info
A fragmented and weak health system contributes to the high burden of malaria in Nigeria

The public health care system is divided into three tiers, each associated with one of the administrative levels of government: federal, state, and local government area (LGA). While the 774 LGAs and the National Primary Health Care Development Agency oversee the provision of primary health care, the state government organises the provision of secondary health care through the state general hospitals and the federal budget covers tertiary care and disease control programs, including malaria control. The amount of government spending on health and malaria is difficult to determine, as funding levels vary and actual spend against budget is difficult to ascertain.

The private health care system consists of formal tertiary, secondary, primary care health facilities, as well as pharmacies, informal patent medicine vendors and drug sellers. They account for 40% of registered health facilities. The outcome is generally a greater density of provision of care in urban areas compared to rural areas except in the case of the informal patent medicine vendors and drug sellers, who are as well distributed in rural areas as in urban areas.

There are a number of weaknesses in Nigeria’s public health system that exacerbate the burden of malaria, including:

- Inadequate, inaccessible, and poor quality service delivery, particularly at the periphery, where most primary health care facilities offer only a limited package of services
- Lack of necessary referral linkages between the different levels of health care.
- Weak logistics systems for commodities, with as many as six separate vertical commodities management systems with little or no coordination between them.
- Poorly maintained infrastructure with many buildings and equipment in need of repair and/or maintenance.
- Weak institutional capacity with inadequate supervision of health services and health information systems
- Lack of political commitment and incentive to invest in health leading to inadequate domestic budgetary provision and release for the health sector coupled with weak absorptive capacity (e.g. at federal level, 89%, 59% and 61% of the allocated annual budgets were released for 2009, 2010 and 2011, respectively, while released budget utilisation rates stood at 50%, 98% and 67% for the same years[8])
  [8] The Global Fund to Fight aids, Tuberculosis and Malaria, Standard Concept for Nigeria, 2014
- Poor governance resulting in poor donor coordination, lack of accountability and endemic corruption.

Furthermore, due to unstable security conditions in the north eastern region of the country, delivering key malaria interventions especially mass campaigns for the delivery of Long Lasting Insecticidal Nets (LLINs) is severely compromised[9].
[9] The Global Fund New Funding Mechanism Concept Note (2014)
Key malaria interventions have been significantly scaled up in Nigeria over the past decade, saving hundreds of thousands of lives.

A number of interventions are available to limit the spread of malaria and reduce the human impact of the disease. There is strong evidence that preventive measures such as insecticide treated nets (ITNs) and indoor residual spraying (IRS) with insecticides are highly effective in preventing malaria in settings similar to Nigeria. ITNs, and the newer version, LLINs, are the most prominent malaria preventive measure for large-scale deployment in endemic areas and the evidence for their efficacy is strong. A systematic review of 22 randomised controlled trials concluded that the use of ITNs reduced under-five mortality in malaria-endemic areas in Sub-Saharan Africa (SSA) by about a fifth, and halved clinical episodes of uncomplicated malaria in areas of stable malaria transmission in Africa[10]. There is also evidence that IRS is effective in reducing the incidence of malaria. Similarly, improvements in diagnosis of malaria using Rapid Diagnostic Tests (RDTs) and highly effective drug treatment (known as Artemisinin Combination Therapy – ACT) are also available to reduce illness and illness duration and to prevent its progression to severe life-threatening disease.
[10] UK Department for International Development, 2010. Malaria Framework for Results. Breaking the Cycle. Evidence Paper

Between 2007 and 2015, the Nigerian Government and partners procured and distributed more than 100 million LLINs and large numbers of other antimalaria commodities to millions of households. This scale-up, in turn, led to significant increases in the coverage and use of key malaria control interventions across the country. Table 1 shows progress from 2008 to 2013 of key malaria interventions coverage.

Table 1: Coverage of key malaria interventions, 2008 -2013
Malaria intervention coverage	2008 / NDHS	2010 / MIS	2013 / NDHS
% of households with at least one ITN	16.3%	41.5%	49.5%
% of children <5 who slept under ITN night before the survey	5.5%	30.5%	25.4%*
% of pregnant women who received IPT during ANC visits	8.0%	13.2%	22.6%

* Smart survey 2014

This scale-up has been possible thanks to unprecedented external funding commitment.

Between 2004 and 2010, nearly US$600 million in external funding was allocated to scale up the country’s malaria control programme. In 2009, donor disbursements reached a peak of around US$325 million, two thirds of which were provided by the Global Fund; however, that represented less than half of what was needed that year to effectively tackle the disease. Between 2008 and 2010, the Nigerian government spent at least $80 million on malaria control[11].
[11] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
Progress made in the last 15 years has translated into malaria incidence reduction and lives saved

Recent modeling using malaria point prevalence in children aged 2-10 to predict malaria risk across Nigeria for the years 2000, 2005 and 2010 showed that all states in the country have experienced a reduction in transmission intensity. None the less, in 2010 all states had risks of infection that exceeded 20%. [12]. Figure 1 shows malaria endemicity patterns in Nigeria 2000 – 2010.
[12] Snow RW, Mundia CW, Kinyoki D, Linard C, Baba ES, Adegbe E, Ozor L, Mohamed AB, Amratia P, Kabaria CW, Noor AM (2013). A description of the epidemiology of malaria to guide the planning of control in Nigeria. Report prepared by SunMAP, WHO-Country Office Nigeria and the KEMRI-Wellcome Trust-University of Oxford Programme, Kenya for the Federal National Malaria Control Programme, Abuja, Nigeria. February 2013.

Figure 1 - Malaria endemicity patterns in Nigeria

Legend:
 light brown <10%, mid-brown 10-49% and dark brown >=50%

Similarly, between 2010 and 2015, malaria prevalence among children under five (microscopy) reduced from 42% to 27%[13]. Although the basis for these dramatic changes may be multifactorial, they mirror the period after the Roll Back Malaria RBM Abuja declaration in 2000 and progressive increase in available resources and the large scale deployment of malaria control materials (LLINs and ACTs) in the country, providing a plausible link between the scale up of malaria interventions and the changing malaria epidemiology in country.
[13] 2015 Nigeria Malaria Indicator Survey

According to estimates using the Lives Saved Tool (LiST model), the lives of 166,000 children under-five were saved by malaria control interventions in Nigeria between 2001 and 2010. Approximately 136,000 (or 82%) of the lives saved occurred in 2009 and 2010 alone.[14] Furthermore, it is estimated that the malaria-related mortality rate in children under five for 2010 is 15% lower than it would have been, had the Government of Nigeria not expanded malaria control intervention coverage[15].
[14] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
[15] World Health Organisation, 2012. Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership.
DFID contributed significantly to the progress made in Nigeria and to saving 48,200 lives

Since its inception in 2008, the £89 million SUNMAP project, although representing a relatively minor contribution to the total malaria funding in Nigeria, has repeatedly been recognised for its abilityto provide crucial technical assistance and for its outstanding contribution to malaria control in Nigeria. Some important achievements of the SUNMAP programme include[16]:
[16] DFID 2015. SuNMaP Seventh Annual Review report.

- Establishing a mechanism to develop a coordinated malaria response through federal and state Roll Back Malaria partners.
- Supporting the development and implementation of national and state malaria control plans which have increased partner coordination and enhanced harmonization of efforts in malaria control.
- Orchestrating and contributing to the successful nationwide distribution of LLINs to every household. About 100 million nets were distributed through mass campaigns since 2009, of which 7.5 million were DFID funded through SUNMAP.
- Developed and implemented the first large scale routine distributions of LLINs (4.1 million nets in total) through ante-natal clinics and other context relevant routine distribution channels.
- Development of training modules for management, planning and malaria case management that have been used across the health sector and training roll-out reaching close to 22,000 health workers in 13,000 different service delivery points.
- The scale-up of effective malaria diagnosis and treatment in supported States, with 7.3 million of ACTs doses and RDTS, respectively distributed.
- The development of sustainable private sector markets for malaria commodities through a facilitative approach known as Making Markets Work for the Poor (M4P)
- Generation of evidence and support to evidence based policymaking at federal and state level.

Between 2008 and 2015, the lives of 96,000 children under five are estimated to have been saved in the ten DFID SUNMAP supported states, of which around 48,200 are estimated to be directly attributable to DFID programming[17].
[17] Estimates based on modelling using the Lives Saved Tool (LiST model), DFID 2015, SuNMaP Seventh Annual Review report.

However, current progress is particularly fragile, and a number of serious outstanding programmatic and technical gaps threaten further improvement with malaria control in Nigeria

The current national malaria strategic plan has the ambitious aim of achieving pre elimination status and reduction of malaria related deaths to zero by 2020[18]. The seven year strategic plan estimates that US$4.1 billion is required to achieve its goals. According to the latest national gap analysis, only 36% of the needs - not inclusive of larviciding interventions - are funded from 2014 to 2017, leaving a gap for these four years only of US$1.7 billion. Figure 3 below shows the increasing needs and funding gap during this period.
[18] National Malaria Elimination Programme 2014 National Malaria Strategic Plan 2014-2020

Figure 3: Estimated funding coverage and gap for Global Fund prioritised interventions, 2014-2017

The scale up in malaria control in Nigeria so far has generated significant results from implementing “low hanging fruit” interventions such as universal LLIN distribution campaigns. However, these improvements are fragile, and can quickly be reversed if not sustained. A failure to sustain or intensify control could lead to a resurgence of malaria with significant increases of malaria relayed morbidity and mortality.

In 2012, a systematic review of malaria resurgence events in 61 countries[19] showed almost all resurgence events were attributed at least in part to the weakening of malaria control programmes primarily due to resource constraints. It is vital that current progress is sustained, improved upon and extended to ensure sustained impact and achieve national and global malaria and wider health goals.
[19] Cohen et al. Malaria Journal 2012, 11:122 http://www.malariajournal.com/content/11/1/122

An additional challenge is presented by increasing levels of insecticide resistance of the malaria-transmitting mosquito. In response to these challenges more stratified interventions and increased technical specialist skills will be needed to lead Nigeria on the path towards pre-elimination and eventually elimination of malaria.

The increased technical capacity that will be required to implement the next phase of malaria control in Nigeria is still lacking. Without these technical resources it is unlikely that the available funding will be used effectively.

# Why should DFID intervene?
Malaria control is considered to be a good development strategy

There is evidence that a high malaria burden is related to depressed economic growth[20] and regions that have decreased malaria have seen substantial economic gains, with economic growth more than five times higher than in endemic regions. Investments in malaria prevention and control by ACTs in sub-Saharan Africa have been shown to yield a benefit cost ratio of 20:1[21] With over 50% of the population living on less than $1.25 per day, investment in malaria control can not only increase overall economic prosperity but also contribute to the alleviation of poverty.
[20] See, for example, Gallup JL and Sachs J. The economic burden of malaria. American Journal of Tropical Medicine and Hygiene, 2001, 64:85-96.
[21] Jamison, DT, Jha, P, and Bloom, D. Disease Control Copenhagen Consensus, 2008.
The UK is committed to combating malaria, particularly in the worst hit countries, and Nigeria accounts for 25% of global malaria cases and deaths

The UK is committed to combating malaria, particularly in the worst hit countries. While DFID’s 2016-2020 business plan is currently under development, the UK’s commitment to the achievement of the 2030 Sustainable Development Goals (SDGs) directly translate into an engagement to tackling malaria control and elimination. Table 2 below shows the anticipated key contributions of malaria support towards the attainment of the SDGs.

Table 2: Malaria and the 2030 SDGs, key anticipated synergies[22]
[22] World Health Organization, 2015. Lessons learned from fifteen years of responding to malaria globally. A prototype for sustainable development
SDG Goal	Key anticipated synergies with malaria
1: No poverty	Sustained investment in health and malaria unlocks the potential of human capital to generate growth. A 10% reduction in malaria has been associated with a 0.3% rise in annual GDP. At household level, reducing malaria protects household income from lost earnings and the costs of seeking care.
2: Zero hunger	People who do not suffer from malaria can work their fields more consistently, resulting in better harvests and improved food security. Well-nourished people, especially children, are better able to fight malaria.
3: Good health and well being	The scale-up of malaria averted at least 670 million malaria cases and 4.3 million malaria deaths between 2001 and 2013. Preventing malaria in pregnancy reduces maternal mortality and gives newborn a far healthier start of life. Lowering the burden of malaria makes a susbtantial contribution to improvments in child health.
4: Quality education	Reducing malaria enables children to attend school regurlarly and learn more efficiently. This significantly improves their later wage-earning capacity. As a caregiver’s level of education increases, so do the chances that their children will access malaria prevention and treatment services and survive childhood.
10: Reduced inequalities	A context relevant and targeted response to malaria actively improves the health of the poorest, enabling vulnerable families to break the vicious cycle of disease and poverty.
13: Climate action	Given that climate change is predicted to increase the range and intensity of malaria transmissions, plans to mitigate the effects of climate change are likely to include an increased commitment to controlling and eliminating malaria, and vice versa.
17: Partnerships for the goals	The many multisectoral partnerships in place to reduce and eliminate malaria have a positive collateral effect, and also bring progress to other domains of development.

The UK also supports the WHO Global Technical Strategy for Malaria 2016-2030 that sets ambitious yet feasible global targets, including a further 90% reduction in malaria incidence and mortality rates by the year 2030[23].
[23] World Health Organization, 2015, Global Tehnical Strategy and Targets for Malaria 2016-2030 Sixty-Eighth World Health Assembly WHA68.2

WHO estimates that 198 million cases of malaria and 584,000 deaths occurred around the globe in 2013[24]. Nigeria is one of three countries that account for over 40% of the global malaria burden, with about 25% of global cases and deaths occurring in Nigeria alone[25] as demonstrated in Figure 2 below.
[24] World Health Organisation 2015 Action and Investment to defeat Malaria 2016-2030 (AIM) http://www.rollbackmalaria.org/about/about-rbm/aim-2016-2030
[25] World Health Organisation 2015 Action and Investment to defeat Malaria 2016-2030 (AIM) http://www.rollbackmalaria.org/about/about-rbm/aim-2016-2030

Figure 2: Estimated proportion, and cumulative proportion, of the global number of
malaria cases and (b) malaria deaths in 2015 for countries accounting for the highest share of the malaria disease burden

With 25% of the global burden of malaria, it is recognised that if the 2030 global malaria targets are to be achieved, a reduction in malaria cases and deaths in Nigeria is urgently needed.
A new bilateral programme will build on DFID’s comparative advantages, and complement DFID’s multilateral investments, particularly the Global Fund

The UK is a major financial supporter of the Global Fund to fight Aids, TB and Malaria (the Global Fund), which provides the bulk of external financing for malaria in Nigeria. The Global Fund has contributed substantially to the scale up of malaria control in Nigeria through the provision of large numbers of commodities such as long lasting insecticidal nets (LLINs). However, a number of weaknesses in the delivery of Global fund grants in Nigeria have been identified (as detailed in a recent audit report of the Office of the Inspector General ), particularly with fiduciary controls, supply chain systems, and service delivery. There are currently concerted efforts by the Nigerian Government and the Global Fund to address these weaknesses. These efforts include the strengthening of fiduciary controls within key health institutions, the implementation of a new public/private supply chain distribution system, and initiatives to reform primary health care delivery. In addition, the Global Fund is developing a new state-level grant model to increase direct operational oversight and commitment at state level allowing greater visibility over delivery and risk; and its New Funding Model will incentivize increased domestic funding. Successful delivery on these initiatives will require complementary support from other partners on institutional strengthening, governance and health systems at state and federal levels.

DFID’s existing bilateral malaria programme SUNMAP has been the key provider of technical assistance and catalytic support enabling the recent scale up of malaria control in Nigeria. DFID, through its extensive portfolio of health systems, governance and private sector programming and expertise in Nigeria is well placed to complement and optimise the Global Fund’s malaria efforts; and help secure a responsible exit from bilateral malaria support. Key programmes that will work closely with SUNMAP2 include the Public Sector Accountability and Governance Programme (£100m, 2016-2021), now known as the DFID Partnership to Engage, Reform and Learn (PERL), which will support ‘more accountable, effective, and evidence informed governments, that prioritise the sustainable delivery of public goods and services that meet citizens’ needs’. The programme will strengthen government systems to reduce opportunities for corruption and make them better able to respond to public demand. It will also strengthen the capacity of citizens to hold government to account and provide robust evidence and lesson learning on public sector reform.

SUNMAP2 will support DFID Nigeria’s objective of assisting Nigeria to use its own resources to address the causes of and eliminate poverty.

The new programme will emphasize providing technical assistance to support the mobilisation and effective use of domestic and external resources while providing limited resources in the form of commodities and activity support to meet ongoing need in the short-term and for demonstration purposes where new interventions are required to achieve the Nigeria Malaria Strategic Plan 2014-2020.
Specifically, the bilateral malaria programme will
- help address current malaria programmatic and technical gaps,
- complement the efforts of the Global Fund for malaria,
- reduce the risk of resurgence,
- provide a structured path into integrating malaria management into broader health systems strengthening efforts.
- build long term sustainability,
- make possible an eventual responsible exit from DFID support.

Gender Equality

There is no evidence to suggest that people of a particular gender encounter systematic barriers to access for malaria services in Nigeria. However, it is well known that biological roles and gender norms mean women are disproportionately affected by the impact of malaria on the Nigerian population. Pregnant women and their unborn babies are particularly susceptible to the effects of malaria; and malaria is responsible for poor pregnancy outcomes such as low birth weight, pre-term deliveries, stillbirths, abortions, and anaemia in pregnancy. Malaria is known to contribute up to 11% of maternal mortality in Nigeria. In addition, women are the primary caregivers of children in Nigeria and have to sacrifice their time and stay away from work when children – who are the principal sufferers of malaria – fall ill.

A number of the interventions promoted by SUNMAP2, such as intermittent preventive treatment for pregnant women, and routine LLIN distribution through ante-natal clinics, will help protect pregnant women and their babies from the effects of malaria. Behaviour change efforts will target care-givers, primarily mothers, on the best ways of protecting their families from malaria and handling it when it occurs. SUNMAP2 will also ensure that health workers of either gender have equitable access to training and skill building opportunities provided through the programme. By reducing the incidence of malaria among children and pregnant women, SUNMAP2 will help reduce the impact of the disease on mothers and increase the time women have to pursue income generation opportunities.

## Impact and Outcomes that we expect to achieve with the Programme
The anticipated impact of the programme is a reduction of Nigeria’s malaria burden through more efficient and effective use of available resources.

This will be measured by:
- Reduction in all causes under-five mortality rate (number of children who die before the age of five, per thousand live births) from 128 in 2013 to 85 by 2022.
- Reduction in proportion of children aged 6-59 months infected with malaria parasites from 27% in 2015 to 16% by 2022.
The outcome of the programme will be an improvement in the planning, financing and delivery of sustainable and replicable pro-poor services for malaria in supported states.

This will be measured in supported states by:
- Proportion of population with access to an ITN who used it in the previous night (target: 75%)
- Proportion of eligible children receiving Seasonal Malaria Chemoprevention in states where rolled-out (target: 80%)
- Proportion of children 6-59 months with fever in last two weeks who receive a diagnostic test (target: 45%)
- Proportion of children under five with any malaria treatment who received ACTs (target: 95%)
- Proportion of total annual malaria expendiure that comes from domestic sources

# Appraisal Case
## Options appraised
Two options for the DFID malaria programme in Nigeria are considered as described below with a third option of doing nothing being first discussed.

Option 1: No new DFID bilateral malaria support after the closure of SUNMAP and consequences of not intervening

This option would mean an end to DFID bilateral support for malaria control after the closure of SUNMAP in 2016. It would allow DFID to allocate potential money for malaria control to other priorities in its development strategy in Nigeria. Essentially, DFID support to malaria control in Nigeria would be limited to that provided through multilateral sources, particularly the Global Fund.

If DFID does not intervene with a bilateral support intervention, it is unlikely that the Nigerian Government and other donors supporting malaria control in Nigeria will be able to cover the shortfall in technical and commodity support. The loss of technical support currently provided by DFID could mean that the available resources from other sources (including UK support through the Global Funds) will not be used effectively. While there are some other donors which provide technical support for malaria control in Nigeria (such as the US Government’s Presidential Malaria Initiative PMI), their resources and coverage are limited and already stretched (for instance, US-PMI’s geographical focus excludes most DFID focus States), and none has the distinct comparative advantage provided by DFID’s longstanding investments in governance and health systems development in Nigeria. There is a risk that progress so far in malaria control will not be sustained, and that malaria resurgence will occur. In addition, an abrupt stop in DFID bilateral support for malaria in Nigeria, particularly if this is followed by resurgence, also carries a reputational risk that could undermine the credibility of the UK’s commitment to malaria control in the worst hit countries.

Option 2: A new three-year bilateral malaria programme after SUNMAP in up to three partner states

This option would be a relatively short and small size project. It would entail mostly technical assistance with limited commodity support. It would mostly rely on the commodities provided through the Global Fund and could focus on:

1. Improving malaria programme management, integration with the health system, and value for money of malaria expenditure.
2. Improving diagnosis and treatment at community level
3. Facilitate the provision of commodities through the commercial markets
4. Improve the treatment of severe malaria.
5. Expand seasonal malaria chemoprevention (SMC) in Nigeria’s Sahel region.
6. Build capacity to monitor and manage insecticide and drug resistance.
7. Promote behaviour change.

This option would continue the provision of technical assistance in a small number of states (up to three) to consolidate the progress of institutional capacity building started under SUNMAP and provide limited commodities for prevention and control. It will help sustain the pressure on malaria, address some of the current malaria programmatic gaps, complement multilateral efforts through the Global Fund and allow DFID enough time to engage with its Nigerian partners to ensure that its intended exit from bilateral funding in malaria is well understood.

This option will focus on a few states to develop and demonstrate what works and prime the pump for scale up across the country, with a focus on extending capacity development in those states in new areas such as the treatment of severe malaria and SMC. The monitoring and management of insecticide and drug resistance is becoming an increasingly urgent issue to address and will receive technical support from the programme.

Option 3: A new five-year bilateral malaria programme after SUNMAP in six states

This option would be a major programme focused on developing policy and managament capacity with a clear objective of sustainability and with substantial efforts towards increasing mobilisation of domestic resources for malaria control and eventual elimination. DFID’s intended exit from bilateral funding for malaria at the end of the five years will be clear from the start, and the programme’s activities will be directed to that end.

In broad outline, this option would have five components:
1. Strengthening government stewardship at national level and in supported states
2. Increased sustainable availablity of anti-malarial commodities (AMCs)
3. More efficient and equitable malaria and prevention services
4. Better engaged citizens and institutions
5. Embedding an evidence-based learning environment in both National and State Malaria Elimination Programmes (N/SMEP).

The last component will be a cross-cutting component and is intended to provide many of the factors required for sustainability after the end of DFID’s involvement. In particular, it will address the issue of the capacity of the Nigerian health system to generate data which are current, reliable and appropriate for policy-making and programmatic decision-making.

Such interventions containing substantial levels of technical assistance have been shown to optimise and complement support provided through the Global Fund, and are more suited to delivery through a bilateral programme. The DFID SUNMAP2 programme will therefore complement the Global Fund by providing technical assistance and capacity building, leveraging DFID’s extensive experience in governance reform and malaria control in Nigeria.

Under this option, some antimalaria commodities will continue to be provided directly by DFID in order to demonstrate the value of developing new or reviewing existing approaches, to roll them out at scale as well as to adjust the danger of resurgence.

In addition to the merits of option 2, this option will also explicitly address the medium-term sustainability of Nigeria’s malaria elimination programme by supporting the institutions in such a way that they can take on more responsibility for this work. Finally, it will provide a more realistic timeframe to explore ways in which malaria can be integrated more closely into the health system as a whole.

This option will cost more than option 2. However, the continuing relationship with six states over five years provides potential for providing them with the tools not only to continue their work without further DFID bilateral intervention but also to demonstrate to other states the power of this approach.

Summary of options appraisal and conclusion

The three options are reviewed in the Table 3 below using three criteria of: i) costs, ii) protection against resurgence and iii) potential for sustainability.

Table 3: Options appraisal summary
Option	Merits	Demerits
1. Do Nothing (the counterfactual)	Funds would be available for use elsewhere.	Investment in Global Fund potentially at risk due to institutional weaknesses / Some benefits gained through SUNMAP are unlikely to be sustained. / There is a high risk of resurgence / DFID’s sudden exit from bilateral malaria support may present a reputational risk.
2. Three-year bilateral malaria programme in up to three states	Relatively low cost. / The activities of SUNMAP – widely acknowledged to be successful – will be continued albeit at a smaller scale / There will be a modest contribution to sustainability.	Three years may be too short to firmly embed the gains in a way required for sustainability. / Investment in Global Fund potentially at risk due to institutional weaknesses which will not be fullly addressed in the lifetime of the programme / The scale of the project and the geographic scope are likely to reduce (relative to the first phase) its ability to influence broader reform at national level, and address the possibility of resurgence.
3. Five-year bilateral malaria programme in six states	Will have sustainability at its heart and will embed increasing Nigerian responsibility for results / Will strengthen systems such that institutional weaknesses are addressed and stewardship of Global Funds is improved. / Will avoid a reversal of the gains made under SUNMAP and reduce the risk of resurgence. / Will provide DFID with a clear exit strategy from bilateral vertical malaria programmes.	Requires more resources but still provides value for money.

Therefore, on the basis of delivering sustainabilit, strengthening systems and reducing the risk of resurgence, Option 3 is considered to provide greater developmental benefits than option 1 and 2. This option is considered in more detail with a full cost benefit analysis below as well as some sub-options.
## Full appraisal of preferred option and sub-options

The preferred option is fully appraised below as well as a slight variation of it presented as option 4 as follows:

- Option 3:	A new five-year bilateral malaria programme in six states
- Option 4:	Option 3 + one additional year for completion of a longitudinal study to address evidence gaps

Option 3: A new five-year bilateral malaria programme in six states

This option consists of a five-year programme that will allow DFID to exit responsibly from bilateral malaria funding in Nigeria. While contributing to further reducing illness and deaths due to malaria in the country, it will, as importantly, prepare the relevant government institutions and other key stakeholders to drive indepedently the country’s response to an evolving malaria burden as an integral part of the Nigerian health system. The project will build from the success of SUNMAP and work towards four interrelated outputs and a fifth cross-cutting output.
## Output 1: Strengthened government systems and stewardship at national level and in supported states

SUNMAP made major progress in strengthening government stewardship. In terms of policy development, the programme has made significant contributions to malaria policy reviews during the past eight years, particularly the Nigeria malaria policy, integrated vector control policy, the diagnostic and case management policies.

At national level, the intense support provided by SUNMAP to the malaria programme review in 2012 paved the way and provided the evidence for the development of the latest National Malaria Strategic Plan (NMSP), 2014-2020. In supported states, the annual operational planning process is consistently cited by benefiting states as the catalyst intervention that improved state ownership over malaria interventions and enhanced coordination of efforts for malaria control.
‘SUNMAP positions us to take care of ourselves’
Permanent Secretary, Ministry of Health, Kano State, Oct. 2015

SUNMAP built the foundations for stronger programme management with the development and adoption of context specific malaria programme management frameworks in the areas of integrated supportive supervision, procurement and supply chain management, advocacy, communication and social mobilisation as well as monitoring and evaluation. These frameworks further contributed to the harmonization of implementation but they have not all been developed in all supported states and, where available, they have not been all fully institutionalised yet.

In close collaboration with other DFID programmes, particularly those concerned with governance and health systems strengthening, SUNMAP2 will take the stewardship strengthening agenda to the next level by:

- Working closely with DFID’s governance and health systems programmes, strengthen financial planning, management and expenditure tracking in the public and private sectors at federal and supported states level; integrating expenditure reviews into operational plan implementation review processes. SUNMAP2 will also work on domestic resource mobilisation which will support the Global Fund’s efforts to incentivize domestic funding through its new funding model.
- SUNMAP2 will leverage DFID’s extensive experience in state level working to support the Global Fund to develop and implement its new state-level grant model, which aims to increase direct operational oversight and commitment at state level allowing greater visibility over delivery and risk.
- Increasing the use of evidence in the development of context specific malaria policies and ensuring that national policies are cascaded down at lower levels;
- Equipping the National Malaria Elimination Programme and supported states with decision tools for stratification of interventions where most cost effective considering the increasing variations in the malaria burden in the different parts of the country;
- Building the capacity of national and supported states to develop and monitor progress of evidence based malaria operational plans fully aligned with the overall health sector annual planning and budgeting process;
- Documenting and sharing learning from public private partnership initiatives to guide the design and implementation with the support of the programme of interventions in this area;
- Facilitating the development and implementation of domestic resources mobilization for malaria strategies, including private sector contributions;
- Facilitating the development and implementation of policies and other tools to maximize the functioning of the commercial segment of anti malaria commodities markets in the interest of malaria control objectives.
- Assessing and strengthening general institutional management and stewardship capacity, including improved accountability, to drive the implementation and review of progress against the ambitious NMSP 2014-2020 at federal and state level. At national level, this will include the secondment to the NMEP of a health governance and management expert during two years followed by periodic short term support;
- Providing contributions to other DFID governance and health systems programmes, including but not limited to the development of human resources management systems and health workforce training tracking.
##
## Output 2: Increased sustainable availability of antimalarial commodities

SUNMAP2 will strengthen both public sector and private sector procurement and distribution channels to ensure a sustainable supply of malaria commodies, and ensuring that these reach the poorest and most marginalized. The free public distribution of nets is important to ensure equitable high coverage and control of malaria, so there is no intention to replace this with the commercial market at this time. However, there is significant demand that is not met by free distributions, and there is significant concern regarding their long term financial sustainability.

Non commercial sector distribution

The predecessor SUNMAP programme contributed 33% of its resources towards commodities support; this generally went to supporting 25% of the LGAs in each supported state.

SUNMAP provided key contributions to the USAID led design and implementation of a single procurement and supply system (PSM) for anti malaria commodities. While this resulted in all malaria partners using the same system both for distribution and logistic information, it remains a parallel vertical system which requires a high amount of resources to run. SUNMAP created a few exceptions to this system where, in collaboration with the DFID funded Partnership for Transforming Health Systems 2 (PATHS2), they facilitated the integration of the malaria PSM into broader health sector PSM.

Beyond its lead role in developing robust distribution systems for LLIN through mass campaigns, SUNMAP pioneered the scale-up of continuous LLIN distribution to build more sustainable mechanisms to routinely target most vulnerable groups, pregnant women and children under five years old. These are channelled through antenatal care clinics as well as immunization services or are context specific school, and community based distribution systems.

Building on the successes above, and to ensure sustainability, SUNMAP2 will focus on:

- Supporting the integration of malaria PSM into the supported state’s main PSM systems in close collaboration with other DFID health programmes;
- Working with the Nigerian government and other partners such as the Global Fund, USAID and the Gates Foundation, support the implementation of the Nigerian Integrated Supply Chain Project, which is deploying a range of innovations to improve the effectiveness and efficiency of supply chain systems for health products. This will also help improve transparency and reduce opportunities for corruption.
- Providing technical assistance to further strengthen assessment of malaria commodities needs at all levels including routine quantification at service delivery points;
- Documenting the cost effectiveness of various mass and routine LLIN distribution systems and support the country with decision tools based on the NetCALC[1] tool for deciding on most appropriate and sustainable context specific distribution channels; supporting implementation where appropriate for demonstration and lessons learning purposes.
  [1] NetCALC is an excel-based modeling tool developed under the USAID funded Networks project with contributions from SUNMAP that allows a user to model different continuous distribution scenarios based on a country's LLIN data and specific situation
- With the increase of community based interventions (i.e. integrated community case management, seasonal malaria chemoprevention, LLIN routine distribution), exploring early in the programme ways of integrating commodities supply systems of these interventions into the main state PSM systems.
- Providing limited quantities of commodities to meet commodity gaps in supported states and develop scale-up arrangements for interventions which are yet to reach optimum scale or maturity, such as routine net distribution, rapid diagnostic testing with ACT treatment, seasonal malaria chemoprophylaxis, and severe malaria treatment. The following quantities of commodities have been quantified to be provided under the programme (these take account of the gaps after planned supplies by the Nigerian government and the Global Fund, as well as the expectation of increasing quantities provided through domestic funding).

Commodity Units	2017	2018	2019	2020	2021	Total
Routine LLIN	207,110	550,983	487,916	424,432	200,626	1,871,067
SMC (Jigawa only)	724,198	1,862,998	1,744,493	1,578,095	811,930	6,721,714
RDT	1,347,033	2,522,807	1,894,415	1,453,012	640,847	7,858,114
ACT	600,042	1,177,310	918,063	726,506	320,424	3,742,344
Injectable Artesunate	28,045	54,439	42,078	33,044	14,471	172,076
Rectal Artesunate	3,913	4,415	5,465	6,576	7,752	28,121
Total	2,910,342	6,172,951	5,092,429	4,221,665	1,996,050	20,393,437

Commercial sector distribution
## In recognition of the sustainability problems posed by the heavy dependence on donor funded commodity supplies, SUNMAP has also been working with the commercial sector to develop sustainable retail markets for LLINs, ACTs and RDTs. Using a facilitative “Making Markets work for the Poor (M4P)” approach, the project is helping address key constraints to the bednet retail market. Important interventions in the LLIN market include improving access to finance for net distributors; improving branding, marketing and distribution of net products; interventions to improve the desirability of nets and generate demand, and supporting the development of new products which better meet the needs of the population. An important part of this work includes efforts to improve the targeting of free net distributions in order to create more space for the commercial sector. Initial successes include facilitating the development of LLIN manufacturing capacity in-country by linking an international LLIN manufacturer with a domestic net manufacturer. Important lessons have been learnt from SUNMAP work in this area, including that there is significant demand (for non-standard or replacement nets) that is not being met by public distributions, and that the way and manner free or subsidized distributions are planned and implemented by the public sector has a profound impact on business confidence and investing decisions taken by commercial distributors.
## Interventions in the ACT and RDT markets have focused on addressing constraints in the market for malaria diagnosis and treatment that have hindered the scale up of appropriate treatment for malaria. Specifically, SUNMAP faciliated mutually beneficial partnerships between AMFm first line buyers and networks of rural patent medicine vendors, which will help ensure that commodity supplies are widely available in rural areas, adequately targeted to the poor, and that prices are kept at an affordable level.

SUNMAP2 will continue to play a catalyst role in the management of essential malaria commodities markets by:

- Contributing to the creation of an enabling environment characterized by public-private dialogue and coordination.
- With regard to the net market, SUNMAP2’s goal will be to facilitate the eventual development of a sustainable commercial market in bednets that is able to respond to consumer demand which is not addressed through the public distribution of free, standardised nets, and that is able to respond to any gaps in public distribution. The intention is to enable a mixed, healthy market where (1) the distortionary impact of free public supplies are minimised – free distribution is well planned and predictable in size and scope, the commercial value of the free nets are minimised, distribution channels are more routine than campaign based, leakages along the supply chain are minimised, and distribution systems target the poor and vulnerable. (2) Commercial distributors and local manufacturers recognize the commercial opportunity presented by unmet needs for nets, and invest in developing retail markets to meet them. (3) Consumers who have net needs unmet by the public distribution system are able to access them from the commercial market.
- Supporting federal and state partners to comprehensively analyse and monitor all market segments identifying the constraints to the development of high quality anti malarial commodities retail markets.
- Facilitating development of action plans for government and public sector players to better manage the commercial markets and help define the programmes contributions to these plans. Possible actions will include strengthening of quality assurance mechanisms that prevent sub-standard products reaching the markets and crowding out of products detrimental to malaria control such as untreated mosquito nets or artemisinin monotherapy. It will also include ensuring that the current legal, regulatory (taxes and tariffs, norms, quality standard) and financial (licensing, contracting, tendering) environments and tools do not inhibit developments of the commercial sector that would be in the public interest.
- Building capacity of key market players at all levels including consumers to better function within the market operations by providing information and transferring skills.
- Increasing advocacy to FGN and the public regarding the security of nets procured for public sector distribution to minimize leakage to the commercial markets.

## Output 3: More efficient and equitable malaria prevention and treatment service delivery

SUNMAP developed a large malaria service delivery improvement programme in line with the latest national malaria policies. In supported states, close to 22,000 health workers received competence strengthening training in the areas of malaria prevention, diagnostics and treatment at the different levels of the health system, i.e. facility level, secondary and primary, and at community level, targeting community care givers and PMVs. The training approach and materials, including up to date job aids, have been adopted by the national malaria programme and used by other partners in non DFID supported states. These efforts have been complemented by the development and roll out of integrated supportive supervision systems in each supported state to continuously develop health workers using on the job mentoring approaches and ensure quality of services.

The areas of diagnostic, training and advocacy have only slowly started to shift the old paradigm of all fevers to be treated with antimalarial medicines to ‘test before treating’, with the ratio of tests done to treatment being on a slight increase in supported states (from 0.9 in 2014 to 1.17 in 2015[26]). SUNMAP also initiated support to malaria diagnostic quality assurance from 2012 onwards.
[26] DFID 2014. SuNMaP Sixth Annual Review report and DFID 2015. SuNMaP Seventh Annual Review report.

More recently, SUNMAP developed implementation models for new interventions such as Seasonal Malaria Chemoprevention (SMC) and support to management of severe malaria. SMC is a community intervention providing a full course of antimalarial medicine during the malaria season to children in the Sub-Sahel where malaria transmission is highly seasonal. In these settings, SMC has been to shown to be 75% protective against uncomplicated and severe malaria in children under five years of age[27]. In Nigeria, nine states fall within that region and are eligible for SMC implementation[2]. SUNMAP has piloted the intervention with impressive results in a few LGAs in Jigawa and Katsina.
[27] World Health Organization, 2014, Global Malaria Programme
[2] Gombe, Jigawa,Kebbi, Sokoto,Zamfara, Katsina, Kano,Bauchi,and Borno

To reduce the fatality rate due to complications of malaria, SUNMAP provided support to the management of severe malaria. It intensified the training in this area and distributed injectable artesunate as first line treatment before referral.

SUNMAP2 will strengthen further malaria services delivery by:

- Supporting NMEP and states to lead the intensification of training activities, with a new focus on initial professional training in medical schools, nursing schools, health technology colleges in addition to continuous professionsl development using on the job training approaches;
- Institutionalizing integrated supportive supervision systems;
- Providing maintenance technical assistance for scale-up of routine malaria prevention, including malaria in pregnancy, and case management services;
- Supporting the design and roll-out of context specific LLIN continuous distribution systems;
- Expanding SMC coverage to 80% in Jigawa state;
- Driving changes in approches to and building capacity in malaria diagnosis and link this to well-managed quality assurance and control programme for RDT and microscopy
- Supporting training and commodities for severe malaria management;
- In collaboration with other health programmes, building the capacity to roll out and monitor integrated community case management (ICCM) for malaria, pneumonia, diarrahoea and neonatal illnesses[3]..
  [3] ICCM is a community based intervention aimed at reducing the service delivery gap between the households and health facilities when hard to reach populations have limited access to the latter. Community health workers provide life saving interventions for the preventable and treatable infections that account for 75% of deaths in children under 5 years old, i.e. malaria, pneumonia, diarrahoea and neonatal illness. The ICCM strategy was adopted by the Government of Nigeria in 2012 and will be a critical step towards integration of vertical disease programmes into the Nigeria health system

Output 4: Better engaged citizens and institutions in the country’s malaria response

Considerable resources under SUNMAP went towards advocacy, communication and social mobilization (ACSM). Beside the support to developing a national ACSM strategy for malaria control, the last annual SUNMAP review found that actual communication support during the programme often seemed to have been managed as “campaigns” rather than as an on-going activity.

These efforts have yielded progress in increases in awareness of key malaria messages; for example, there has been an increase of 29 percentage points between 2008 and 2013 in the proportion of women in child bearing age in supported states who know the preventive benefits of intermittent preventive treatment in pregnancy (IPTp). This has however not translated in commensurate behavior change with an increase of only 15 percentage points, from 8% to 23% of women who received IPTp during ANC visits in the same period. Also use of nets in some parts of the country is not yet optimal . The Figure 4 below shows the ITN ‘use gap’ per region during the rainy season in 2010 (MIS) indicating that while in the North almost all people with access to a net also used it, this was not the case in parts of the South where only slightly more than half of those who could have used a net did so.

Figure 4: Percent population that used an ITN last night versus percent population with access to ITN that used it by zone, all ages, MIS 2010

SUNMAP2 will build on the investment made by SUNMAP in the area of ACSM by

- Understanding better the causes of the gap between awareness and use; this should include careful analysis of evaluation data on communication campaigns related to timing and content of advertisements to understand their impact;
- Supporting the revision of the national ACSM strategy to support the latest NMSP and the achievement of its targets by 2020; this should include strategies of social mobilization for increased accountability by the government and service providers;
- Intensifying communication activities, both locally and nationally, including through social media and using innovative approaches;
- Working with other malaria partners in country to coordinate their efforts by using a single and harmonized approach on advocacy for domestic resource mobilisation for malaria funding;
- Supporting NMEP in developing communications capacity, especially for advocacy purposes (e.g. reviewing and maintaining website, growing social media presence).

Output 5: An evidence based learning environment embedded in NMEP and supported states

SUNMAP has invested in operational research into key areas of prevention and treatment to provide the evidence for more effective strategies. It also focused on building local capacity for operational research and use of evidence into decision making process. SUNMAP played a leading role in growing the interest amongst national stakeholders towards evidence generation and use by supporting the establishment of a national operational reseach agenda as well as an operational research unit with the NMEP M&E department. SUNMAP supported research led to some policy decisions, for instance on the methodology of LLIN distribution campaigns to achieve universal coverage, granting permission to patent medicine vendors to use RDTs or on the continued use of sulfadoxine-pyrimithamine for IPTp.

The programme implemented a regularly reviewed monitoring and evaluation strategy that involved the use of different methods and data sources for assessing progress of the programme at output, outcome and impact levels. At output level, regularly collected data, either through existing systems such as the national health management information or through programme specific parallel data collection set-up (e.g. to monitor the number of LLIN sold by commercial partners or to track health workers training), were used. Assessing progress at outcomes and impact levels, relied on national and project specific surveys (e.g. the national demographic and health survey, the national malaria indicator survey, net tracking surveys, health facilty assessment survey, market and provider surveys). Monitoring areas representing the different strata of the malaria epidemiology in the country as well as sentinel drug testing sites were supported. Through the monitoring areas, malariometric variables are assessed in various age groups of asymptomatic children and adults before and at the end of the main malaria transmission season. This allowed for a clear picture of the malaria epidemiology as well as trends over time which in turn allowed estimation of changes in burden of transmission, infection and morbidity. While the programme showed a strong commitment in developing the NMEP M&E capacity and much progres has been made over the years with the use of data at NMEP level, some of the above M&E efforts and results have been limited to the project and not always been fully utilized to inform decision making (both at project and NMEP level).

SUNMAP2 will build a stronger evidence based learning environment by

- Building the capacity of the NMEP and supported states to collect and analyze the necessary evidence to adapt the national and local responses to changing vector composition and behaviour and disease epidemiology; strengthening capacity to review and feed appropriate national and international evidence into practices, plans, strategies and policies review;
- Supporting the NMEP in the development of performance dashboards regularly published on its website; latest versions of key national data and documents (policies, framework, training manuals, job aides) should equally be systematically managed and available on line;
- Giving high prioirity to the support and expansion of entomological and resistance surveillance sites and systems that can provide timely evidence needed for the critical responses to the threat of vector and parasite resistance; ensuring that local capacity is built and domestic funding secured by the end of SUNMAP2 for these to be sustained post project;
- Supporting efforts to strengthen comprehensive, timely and accurate routine health information management systems that integrate malaria as much as possible; strengthening the capacity of NMEP and state staff to analyse and interpret results from this routine data and take action based on the findings where needed;
- Strengthening capacity to undertake secondary and metanalysis of data to triangulate evidence (e.g. of the Malaria Indicator Survey 2015);
- Strengthening capacity to undertake context relevant surveys and operational research to assess the efficiency and cost effectiveness of interventions including those targeting the private and commercial sectors;
- Strengthening generally reporting and accountability of the malaria programme at national and supported states level; supporting reviews of progress against national and subnational malaria targets.

Similar to the approach used for output 1, an evidence and learning expert will be seconded to the NMEP for the first two years of the programme, which will be followed by gradually decreasing short term technical assistance.

In addition, in a bid to fulfill DFID’s commitment to increased evidence use and transformational approaches, a five-year longitudinal study as part of output 5 will answer the following questions:

- What is the cost-effectiveness of selected interventions in different contexts of Nigeria?
- What constraints hinder the translation from awareness to behaviour change and use of malaria interventions among various population groups, and what measures are likely to be effective in tackling them?
- What are the key factors that have driven positive and less positive progress? (ie not only measuring results but understanding the why).
- What has been the role of softer support in the areas of governance and health systems strengthening in the achievements of the programme?

This study will be carefully designed jointly with NMEP, key malaria partners as well as DFID and apply a mix of methodologies (quantitative and qualitative) and a multi-disciplinary team. In addition to outcomes, emphasis will be on inputs and processes and interim results will be made available at several time points during the programme in order to inform improvements in interventions and/or their implementation.

The study will be implemented by the programme but will be guided by an external review committee comprising of national and international experts.

Option 4: same as 3 + with an additional year for the longitunal study only

Option 4 is the same as Option 3 but with the study running for six years instead of five. During that additional year, no DFID support at all will be extended for technical assistance and interventions implementation. The final round of assessment of the study will thus in this scenario be undertaken one year after the exit of DFID technical and programmatic support. This will allow the study to deepen the understanding on sustainability factors to address the following additional questions.

- To what extent have the successes achieved during the interventions been sustained after the discontinuation of the external support?
- To what extent are they likely to be continued in the future?

For both options 3 and 4, the following engagement approaches will be followed to ensure a strong sustainability focus across the board:

Supported State selection and engagement
DFID Nigeria has developed a new state level geographic footprint strategy for the 2016 – 2020 operational plan, which focuses DFID transformational engagement in a more limited set of three partner States (Kano, Kaduna and Jigawa), complemented by issue based or regionally focused work in other parts of the country. SUNMAP2’s strategy for state selection and engagement is closely aligned with this. The programme footprint has been reduced from 10 States (SUNMAP1) to up to six states. Selection of the supported states will be finalised before the programme inception period, but is likely to consist of the three partner states at a minimum, and up to three additional states. Criteria for additional state selection include the following – need, as measured by malaria parasite prevalence or resurgence risk; the presence of complementary programming, such as DFID health systems or governance programming as well as Global Fund and other donors; state or regional level political commitment; and the presence of distinct opportunities such as private sector malaria commodity markets. Given the variety of context, there will be at least two distinct models of state engagement. In partner states this will be based on the DFID partner state engagement model, with a high level compact with the state, a large complementary DFID portfolio, and support from a DFID state representative. In other states, engagement models will be tailored to the range of opportunities available in that particular state, but based around an issue-based partnership with the state and the Global Fund.

Agreeing an exit strategy with the Nigerian government
In order to support the sustainability agenda of this new programme, DFID will enter into memoranda of understanding with the NMEP and supported states in which all parties will recognize that the DFID support is extended with the expectation that, where appropriate, counterpart funding will increase year on year as DFID funding will be gradually decreased from the third year of the programme. Consideration and selection of states for counterpart funding will be based on an in-depth assessment of fiscal position, political will/economy, sustainability etc. The amounts expected as counterpart funding will be agreed upon and documented each year.

While DFID is not moving into binding counterpart funding per se, SUNMAP2 will explore the possibility to adopt results based financing approaches. The Global Fund has recently reviewed its funding approach moving away from unsynchronized diseases specific grants to single country proposal to tackle the three diseases supported by the Fund together with some resources to build management systems. The new funding approach also has a provision for two types of grants, one as standard Global Fund contribution and an Incentive Fund, with commitments from the latter for additional activities being made upon satisfactory performance of the activities in the standard grant. The World Bank is also embarking on a results based funding approach. SUNMAP2 will learn lessons from these new approaches and consider with DFID the potential adoption of such mechanisms for the latter years of the programme, when it is planned that DFID support will decrease.

Continuing DFID leadership role in malaria partners harmonization efforts
SUNMAP2 will renew DFID’s commitment towards development aid coordination and efficiency in the country. Nigeria’s share of the global malaria burden means that a lot of global attention and resources are focused on the country, which translates to a significant level of co-ordination required in support of the NMEP and Nigeria’s 36 states to meet the country malaria targets. SUNMAP2 will continue to be a close and trusted partner among the malaria community in the country and will persistently promote harmonization of strategies, support, implementation approaches and results monitoring for all malaria interventions. DFID, through SUNMAP2, will play a leading role in rallying all partners around the sustainability agenda and the need to mobilize domestic resources and to recognize the role of the private sector in the fight against malaria. DFID will use its influential voice both at global and national level to support the programme in that direction.

Providing commodity support mainly for demonstration purposes
In a bid to gradually reduce Nigeria’s dependence on external funding for commodities provision, DFID will target commodity support under SUNMAP2 towards demonstration purposes. This could either be to test ways to make existing routine distribution mechanisms more efficient or to trial the roll-out of newer interventions such as SMC, Integrated Community Case Management or severe malaria management.

Promoting where relevant and feasible integration of malaria management with broader health systems
Throughout the above description of the preferred option, there are several references to the need to integrate malaria management into broader health systems. While there are specific aspects of the disease that will require specialist attention and support towards the disease elimination, there are key aspects of the malaria control that would be more efficiently managed as an integral part of the core health system. These are, for example, human resources planning and training information systems, routine malaria information, procurement and supply management, integration of routine LLIN distribution in ANC and EPI services, ICCM. SUNMAP2 will work closely with the NMEP, FMOH and other health systems strengthening initiatives to plan and support that integration and coordination.

Coordinating efforts closely with other DFID programmes
DFID will maximize the use of its funding by ensuring that the suite of its programmes work together in supported states. The costing for the programme has been estimated on the premise that the programme will operate in six states. SUNMAP2 will be required to report on and show results for coordinating its governance, advocacy and health systems strengthening activities with other DFID programmes. The new Nigeria Public Sector Accountability and Governance (PSAG) Programme (2016-2021) will use a problem-driven iterative adaptation approach to drive reforms; DFID will support both programmes to identify specific interventions on which they will actively collaborate, likely in the areas of political economy analysis, political engagement, planning, budgeting, financial tracking, accountability and domestic resources mobilisation towards sustainable stream of government funding. The Maternal, Neonatal and Child Health 2 (MNCH) programme (2014-2019) operates in Jigawa, Kaduna, Kano, Katsina, Yombe and Zamfara. Areas for demonstrating the feasibility to integrate malaria into broader health systems management will be identified; the two programmes will be required to work and report jointly on them in addition to collaborate more generally on governance, health systems strengthening and demand creation efforts. DFID will include in the all programmes logframes an indicator to track the performance of DFID programmes synergy and hold all service providers equally accountable for it.

Delivery options

DFID considered the following delivery options to implement this programme. In considering the options, note was taken of the fact that this is a complex programme requiring the delivery partner to deploy a mix of skills and expertise, such as governance, health systems development, malaria control, and private sector development. It is likely that very few organisations will be able to deliver it on their own, and a consortium approach may be required. The following options were considered:

- Through funding a multilateral organisation (via an MOU): Given this project is explicitly intended to complement the efforts of the Global Fund by focusing on activities to which the fund is not particularly suited, this is not a viable option. Funding through other multilateral organisations, such as WHO or UNICEF, are also not optimal options because their operations in Nigeria are currently stretched by other priorities, such as nutrition, girls education and polio eradication. These organizations are also likely to experience difficulty assembling the mix of expertise required to deliver this programme.
- Directly through DFID staff: Given the large amount of short term specialised expertise of different kinds required for this programme; DFID’s limited staffing and presence in supported States; and the large amount of risks (for instance fiduciary and security), which would have to be retained and managed by DFID, this is not a viable option.
- Through an accountable grant to a civil society organization: Given the size of this programme, this option is unlikely to provide sufficient assurance that DFID is obtaining value for money. In addition, it is unlikely that a civil society organisation will be able to, on its own, assemble the mix of expertise required to deliver this project.
- Through financial aid to the Nigerian government: This is not a viable option because, as a matter of policy, no DFID funds can be channelled through Nigerian government systems at the moment.
- Partnership with another donor: The option of delivering this programme through the US President’s Malaria Initiative (PMI) was considered. The option was considered not optimum because (1) US-PMI has a different geographic focus in Nigeria from DFID, in line with USAID geographic targeting (2) While some of the interventions to be supported by this programme are common to the US-PMI project, many of the key interventions specifically targeted at governance, public finance improvements and private sector development, do not appear to be major priorities within the PMI project. (3) If the project were delivered by US-PMI it might have difficulty leveraging on DFID’s extensive governance and political investment in Nigeria, which is expected to underpin the project. (4) It would make attribution to and visibility for DFID relatively difficult.
- Direct procurement through a contract with a private supplier: This is the delivery route for the existing SUNMAP project, and is still thought to be the optimum option because (1) It would enable the required skills to be assembled through a consortium of organisations (2) Open competition would help ensure value for money for DFID; and (3) Commercial contracts would allow an appropriate level of risk to be transferred away from DFID, with strong provisions to manage and incentivise performance.

Climate change and environment

Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation.

Option	Climate change and environment risks and impacts, Category (A, B, C, D)	Climate change and environment opportunities, Category (A, B, C, D)
2	C	C
3	C	B
4	C	B

Possible effects of SUNMAP2 on climate and the environment
Possible effects on the environment arise from SUNMAP2’s limited procurement and promotion of the use of Long Lasting Insecticidal Nets (LLINS). However, SUNMAP2 focus on LLINs will be much less relative to SUNMAP. It will focus relatively more on technical assistance and promoting diagnostics and appropriate malaria treatment. WHO recently undertook a preliminary research study[28] focusing on identifying preferred options for LLIN End of Life management, and provide evidence to make policy recommendations. The main recommendations[29] of this study include the following:
[28] World Health Organization, 2010. Inception meeting for the pilot-study project on sustainable management of long-lasting insecticidal nets throughout their life-cycle: REPORT
[29] Aurelie Bottelin. Sustainable Lifecycle Management of LLINs: Project findings and recommendations. World Health Organisation Global Malaria Programme.

- Proper disposal of LLIN packaging material to reduce their environmental impact.
- Net distribution should be accompanied by education on the proper use and disposal of LLINs.
- Net distribution workers should wear Personal Protective Equipment.
- LLINs should not be retrieved from the community at their end of life.

SUNMAP2 will promote the increased use of rapid diagnostic tests for malaria, including in non-clinical settings such as by patent medicine vendors and caregivers. Given that these tests involve the collection of tiny amounts of blood, which may involve biological hazard, it is important that SUNMAP2 ensure proper training and education on the proper use and disposal of biological waste.

There is no immediate impact on climate change anticipated.

Possible effects of climate change on SUNMAP2
Global temperature and precipitation changes alter the location, rate of breeding and the migration range of disease-bearing vectors including mosquitoes. In fact while many infectious diseases are affected by changes in the climate, vector-borne diseases, such as malaria and dengue fever are known to be particularly sensitive to climatic variations. Available research indicates that the combined effects of changing temperatures, precipitation and humidity are in most cases likely to lead to a more suitable environment for the spread of malaria. Analysis of malaria morbidity data in a number of other tropical countries, eg Ethiopia, indicates that higher minimum temperatures correlate with increased instances of malaria outbreaks (Confalonieri et al., 2007). The effects of increased temperature can be further multiplied by a simultaneous increase in precipitation (Confalonieri et al., 2007). Climate changes also affect the density of vectors in a particular area and increases the likelihood of infection up to significant thresholds (WHO, 2004). Bite frequency generally rises with temperature and atmospheric CO2 content (DeLucia, 2008). If climatic changes increase the rate of spread of malaria in Nigeria to new significant level, the obvious implication will be that a far greater percentage of the population than anticipated by SUNMAP2 will be at risk of malaria infection.

Opportunities
Some opportunities exist to make SUNMAP2 more resilient. Firstly, SUNMAP2 managers would need to be sensitive to the possible ways through which climate changes can impact the epidemiology of malaria in Nigeria. Future malaria modeling in SUNMAP2 active states and indeed the country will need to involve a prediction of the scope, geographical distribution and characteristics of malaria over a period of time. These models must incorporate a variety of factors including projected changes in temperature, precipitation, and humidity as well as other environmental factors such as drought and deforestation. For example some existing models suggest that people living in developing countries at the risk of malaria will increase 5-15% by 2100 due to climate change.  In Africa alone, according to the MARA Project (Mapping Malaria Risk in Africa) there is a projected increase of 16-28% in person-month exposures to malaria by 2100. These models are crucial in preparing an effective public health response to future disease outbreaks. In 2012, SUNMAP funded the most recent mapping of trends in malaria epidemiology and climate in Nigeria, and SUNMAP2 will support the NMCP to continue to update the model and improve environmental targeting of malaria interventions. The wide distribution and usage of effective malaria control commodities supported by SUNMAP2, as well as the scale up of seasonal malaria chemoprevention and severe malaria treatment will help to improve resilience of susceptible communities to climate change induced malaria resurgence.

There are additional opportunities to minimise the impact of SUNMAP2’s activities, particularly the distribution of long–lasting insecticide treated nets, on the environment. The project will:

- Continue to promote the use of pre-treated LLINs rather than other types of nets which require treatment by the user, and have much higher environmental risks.
- Continue to ensure proper disposal of LLIN packaging according to WHO guidelines, including specifying the use of biodegradable packaging materials in net procurement.
- Continue to provide information to consumers and communities regarding the use and safe disposal of long lasting insecticide treated nets.
- Encourage practices (e.g appropriate washing, drying and stitching of holes) to extend the useful life of LLINs.
- Collect data from programme beneficiaries and other users regarding net preferences, alternative uses and net disposal practices to enable better targeting of net types and information, as well as inform policy. Share the data collected with WHO and other relevant organisation which are conducting studies in this area.
- Ensure net distribution workers and RDT users wear personal protective equipment.
- Measure the implementation of the above measures as part of its monitoring and evaluation processes

Gender and poverty

Malaria accounts for 25-30% of infant mortality in Nigeria. This rate however represents the national aggregate. There exist significant differentials in infant mortality at national and state levels, between rural and urban, and even city-wide differences between the rich and poor.
# Malaria is responsible for poor pregnancy outcomes such as low birth weight, pre-term deliveries, stillbirths, abortions, and anaemia in pregnancy. Malaria is known to contribute to 11% of maternal mortality in Nigeria.

Indirect and social costs of the disease are enormous. It leads to an increased sickness absence rate in children with consequent low educational attainment and to absenteeism from work in adults leading to low capacity to earn. The resulting loss of income aggravates poverty and contributes substantially to maternal mortality and reduced life expectancy.

Characteristics of the poor include low income, poor access to health services, poor housing conditions and high incidence of under-nutrition and parasitic diseases. In the urban areas by contrast, there is increased general awareness on health issues, access to primary education and a source of income of some sort. However, poor housing and sanitation and increased environmental degradation lead to increased vector breeding sites, increased malaria transmission, increased frequency of malaria episodes and its sequelae on the household.

As in many developing countries, women in Nigeria are more likely to be poor. They also have fewer options than men for escaping poverty. Women are the primary caregivers in Nigeria and should be targeted for education in malaria prevention and treatment especially as it affects children. Women are unable to contribute to the household income when they fall ill, as they have to stay away from work. They also have to sacrifice their time and stay away from work when any member of the household falls ill - be it the husband or the children.

SUNMAP2 will contribute to ensuring a positive social impact by supporting improvements in the quality of service delivery, particularly among rural primary facilities and informal health workers used primarily by the poor. The provision of preventative commodities such as LLINs and SP are expected to have a substantial effect on reducing malaria incidence. The distribution of these commodities has been carried out in such a manner as to ensure access by the poorest and vulnerable groups. A recent study investigating the effects of the SUNMAP 2009 net distribution campaign in Kano State[30] concluded that “The campaign had a significant impact by increasing ITN coverage and reducing inequity in ownership and use”. Between 2008 and 2015, wealth inequities in access to malaria prevention were dramatically reversed. Insecticide treated net ownership among the poorest households increased from 4% to 86%, compared to an increase from 11.2% to 58% in the richest households. The focus on approaches which address equity will continue during SUNMAP2.
[30] Ye et al.: Can universal insecticide-treated net campaigns achieve equity in coverage and use? The case of northern Nigeria. Malaria Journal 2012 11:32

Routine distribution of LLINs through ANC and EPI channels will target the most vulnerable groups – women and children under five - thus reducing the risks of malaria related mortality and increased opportunities for income generation and reduced number of school days missed. Provision of case management commodities, will not only assist health facilities in improved treatment relating to malaria, but enable the opportunity for prompt and effective treatment of malaria and, it is anticipated, reduce malaria related mortality.

Behaviour change interventions will also work towards developing a more knowledgeable community with particular regards to malaria prevention who know how to protect themselves and generate a demand for quality services.

Conflict and fragility

In spite of steady economic growth, Nigeria has witnessed an increasing trend towards rising conflict and fragility, particularly in the last few years. Key hotspots include Northern Nigeria, where a religious insurgency has disrupted families, economic activities and social services. Environmental degradation in the Niger delta, as well as dispute over the control of oil resources has also fuelled conflict in that region.

The roots of conflict appear to lie in widening social inequality, exacerbated by poor governance, high levels of impunity and unresolved ethnic and religious differences. Low levels of accountability and delivery of public services have weakened the government’s ability to successfully address these issues. DFID’s strategy for helping address this challenge in Nigeria includes (1) helping improve the capability, accountability and responsiveness of Nigerian governance at all levels; (2) working with communities to develop sustainable and peaceful means of resolving conflict, including police and justice reforms; (3) helping to address poverty, improve employment, and foster inclusive economic growth; and (4) helping improve institutional means of citizen participation in governance, such as fair elections, civil society and legislative representation.

97% of Nigeria’s population are at risk of malaria, and it is a condition that affects nearly every household in the country. Interventions, such as bednets and treatment that help address malaria are highly valued by families and political leaders. The universal bednet campaigns (2 nets for each household) between 2009 and 2013 were seen by many rural poor as probably one of the few tangible benefits they have received from public services.

SUNMAP2 is not a conflict programme, but will embed conflict sensitive principles in its operations. It will contribute to reductions in conflict and fragility in Nigeria by helping address some of the root causes, for instance, by improving the capacity of public health services to plan and deliver malaria interventions in equitable ways; helping reduce the burden of malaria which is expected to improve household incomes; and improving the ability of households to protect themselves from malaria and other diseases.

## How will the programme address corruption?

Corruption is endemic in Nigeria including in public services such as the health service. Manifestations of this in the health services range from diversion of funds at administrative levels, particularly through poor procurement practice; to informal user fees and theft or leakage of commodities from health facilities into private markets. A lack of transparency and accountability around budgeting, expenditure and service level expectations facilitates this scourge, and makes it difficult for citizens and civil society to hold officials accountable for delivery. The result is available funding that does not readily translate into acceptable levels of service delivery; stock-outs of key preventive and lifesaving commodities at public facilities leading to avoidable illness and death; the loss of confidence by the population in the health service leading to poor health seeking behaviour; and the loss of confidence from international donors, such as the Global Fund, who may be forced to either reduce investment or institute costly, unsustainable parallel delivery mechanisms.

DFID Nigeria’s approach to tackling corruption in Nigeria is to combat the problem on several fronts, and is part of a broader effort working across HMG and involving international partners. DFID has been providing technical assistance to increase transparency in revenue collection (in particular oil sector transparency); building more accountable systems in delivering services, promoting governance processes that close down spaces for corruption; supporting anti-fraud efforts, helping the enforcement agencies to have capacity and ability to sanction those that break the rules; and increasing citizen voice on policies and service delivery, and ability to hold Government into account. DFID Nigeria is stepping up its engagement in these areas and planning an additional standalone anti-corruption programme.

SUNMAP2 will contribute to this effort in two ways. First, working closely with DFID’s governance and health systems programmes as well as the Global Fund, the programme plans to strengthen financial planning, management and expenditure tracking for malaria, and procurement and supply chain systems for malaria and other health commodities. Expenditure reviews of malaria spending will be undertaken, with engagement of civil society; state and federal malaria control programmes will be supported to implement improved procurement practices, with outcomes benchmarked with other partners; and improved supply chain information systems will help increase the visibility of commodity flows and reduce stock-outs, shrinking opportunities for corruption . These measures will help promote better financial management and accountability, and reduce the risk of funds being misused through weak administration or corruption. Secondly, SUNMAP2’s push for more domestic malaria financing and better engaged citizens and institutions in the country’s malaria response through support for advocacy, communication and social mobilization; will promote the strengthening of domestic accountability.

The costs and the benefits of the three sub-options are presented below. Annex A details the methodology and assumptions made for their estimation.

Costs

Costs for option 3 have been estimated using a similar budget structure as used by SUNMAP and costs against budget categories and sub-categories are presented in the financial case. The Table 4 provides a breakdown of anticipated costs per output per year where cross-cutting personnel, operations and DFID retained direct costs have been distributed across the outputs using a weighting allocation formula, as per the weight proposed for each output in the logframe

Table 4: SUNMAP2 anticipated costs per output including DFID retained direct costs
Output	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Output 1 - Stewardship	£1,292,980	£1,787,130	£1,393,230	£1,077,055	£695,075	£6,245,470
Output 2 - Commodities	£2,932,204	£5,894,386	£4,922,094	£3,861,791	£1,745,833	£19,356,308
Output 3 - / Service delivery	£1,778,077	£3,268,858	£2,625,499	£2,041,530	£919,882	£10,633,846
Output 4 - Awareness	£1,068,448	£1,950,988	£1,597,756	£1,065,616	£603,300	£6,286,108
Output 5 - / Evidence	£1,411,648	£1,997,248	£1,633,036	£1,284,096	£846,100	£7,172,128
Total	£8,483,358	£14,898,610	£12,171,615	£9,330,088	£4,810,191	£49,693,861

The total Option 3 costs funded by DFID are estimated at £49,693,861, which discounted at 3% per year comes to £47,233,086.

In addition to the costs funded by DFID, there will be an increasing counterpart contribution. This contribution will be negotiated and justified to counterparts as a component of sustainability, involving increasing ownership of and responsibility for the malaria programme by all Nigerians. The expected counterpart contributions are shown in Table 5.

Table 5: SUNMAP2 expected counterpart funding from domestic sources
in Year 3 to 5 of the programme
Output	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Output 1 - Stewardship			£105,000	£175,000	£280,000	£560,000
Output 2 - Commodities			£1,555,359	£2,997,434	£5,543,632	£10,096,426
Output 3 - Service delivery			£549,910	£1,035,774	£1,903,930	£3,489,614
Output 4 - Awareness			£150,000	£250,000	£400,000	£800,000
Output 5 - / Evidence			£210,000	£350,000	£680,000	£1,240,000
Total	£0	£0	£2,570,269	£4,808,208	£8,807,562	£16,186,039

The total expected contribution from domestic resources, assuming that all states will be selected for such arrangement, is estimated at £16.2 million but over half of this contribution is not expected to be provided before year 5.

Option 4 attracts an additional £50,000 for the longitudinal study (with reduced cost from £75k to £50k in year 5 and £100k in year 6), making a total of £49,743,861, which discounted at 3% per year comes to £47,274,922.

Benefits

The principle quantifiable benefit of SUNMAP2 is expected to be lives saved both now and in the future. Using a LiST model like approach the number of lives saved (deaths averted) and Disability Adjusted Life Years (DALYs) averted was estimated for option 3. Simulations with the model estimate that the increase in coverage of malaria interventions attributable to the SUNMAP2 programme might be expected to prevent approximately 7,500 deaths among children under five years of age over the first five years of the programme. Most deaths prevented would be expected to be among children under the age of five years and most would be prevented though preventative interventions such as LLINs or SMC rather than curative and treatment interventions. Figure 5 represents the annual number of deaths averted in each year of the project assuming that the comparison is simply maintenance of current coverage levels for the set of interventions included (ACT treatment, LLINs, SMC, IPTp).

Figure 5 - SUNMAP2 estimated lives saved - Year 1 to Year 5

In addition, the current expected number of DALYs averted for each child death prevented in Nigera is approximately 31. Applying this to the estimates produced here gives an expected number of DALYs averted over the first five[31] years of the project of about 230k (95% CI 102k – 359k). The present value of these DALYs, again discounted at 3%, is 209k.
[31] The effects are assumed to be lagged by one year.

These quantifiable benefits come from the commodities to be provided by the project. In addition, there will be gains from improving information to health facilities and households in terms of using these commodities but we do not have estimates of the size of this impact.

However, the real focus of this programme is to promote sustainability by developing Nigerian national and state capacity so that they no longer need DFID support in this area. It is critical that this capacity is firmly embedded so that Nigerian actors at national and state levels can and will take responsibility for their own malaria programmes. Therefore, we propose that the real impact of sustainability will be the continuation of the scale of the provision at the end of the programme. In this case, we expect to be able to attribute the continuing benefits for another fifteen years. Figure 6 shows this expectation.

Figure 6 - SUNMAP2 estimated lives saved - Year 1 to Year 20

This would add a further 1.04 million DALYs averted, albeit with very large confidence intervals (95% CI 463K-1.6 million). The present value of these DALYs, again discounted at 3%, is 705k.

Options 4 offers additional unquantifiable benefits in terms of learning about the medium-term impact of this type of programme while involving relatively little additional cost (£50k) over the five or six years. This learning can provide a formal complement to learning on similar DIFD projects to support sustainable institutional development such as the recent SPARC and SAVI projects, PATHS2, MNCH2 and the PSA. In this way, it will assist DFID to strengthen its practice in measuring and valuing “hard-to-measure” benefits. It will as importantly provide NMEP currently missing evidence about future malaria programming in the Nigeria context.

The summary of the costs and benefits of options 3 and 4 can be found in Table 6 below.

Table 6: Summary of costs[4] and benefits of the options fully appraised (present value)
[4] The costs presented here are only those funded by DFID as are the DALYs for the first five years. It is intended that, by year 5, there will be a substantial contribution from domestic resources that will be sustained after the end of the project and we have shown the DALYs that might be expected to accrue from that sustainability. We have not included the expected domestic contribution because the increase in domestic contribution is a key objective of the programme and, therefore, have excluded it from the estimation of costs so that it can more readily be compared with other DFID programmes.
Option	Cost	Benefits in # of DALYs averted / Years 1-5	Cost per DALY averted / Years 1-5	Benefits in # of DALYs averted / Years 1-20	Cost per DALY averted / Years 1-20
Option 3 - five-year bilateral malaria programme	£47,233,086	208,956	£226.04	913,865	£51.68
Output 4 - Option 3 + one additional year for the planned longitudinal study only	£47,274,922	208,956	£226.24	913,865	£51.73

The conclusion on full appraisal of options 3 and 4 is that option 4, including a 6-year longitudinal study is preferred because it offers the potential for substantial learning for the Nigeria malaria programme and DFID programmes for a very modest increase in costs. In particular, it offers the opportunity to learn in more detail about the drivers and constraints for sustainable outcomes in complex programmes.
## Theory of change of the preferred option

The theory of change of SUNMAP2 is presented in Figure 7.

Assumptions underpinning the theory of change

Assumptions detailed in the logical framework

Evidence underpinning the theory of change

In essence the theory of change stipulates that:

1. Malaria is a significant health problem in Nigeria and addressing it will reduce mortality and disease burden resulting in a healthier population which is the desired impact of the project
2. Achieving the outcome of increased coverage (availability/ownership and use) through SUNMAP2 of key malaria specific interventions such as ITN, SMC, IPTp and effective diagnosis and treatment of clinical malaria (including severe cases) will – in conjunction with measures possibly implemented by other stakeholders – result in reduced morbidity, case fatality and malaria transmission and thereby reach the desired impact on mortality
3. The increase in quantity and quality of malaria interventions can be achieved by a variety of activities that – given the inputs are sufficient and external assumptions are met – will result in the necessary outputs at three levels: the public sector (government and health services); the private sector (malaria-relevant commodity markets); and the population (behaviour of individuals, households and communities). These activities, if effectively implemented, will lead to sustainable gains including lives saved beyond the project timeline.

Evidence of the disease burden of malaria in Nigeria

There is strong evidence from Nigeria on the epidemiology and burden of malaria in Nigeria, dating as far back as 1951 (Bruce-Chwatt 1951[32]). In recent years the most comprehensive summary of malaria in Nigeria was compiled in 2013 by a collaboration between the National Malaria Control Programme, SUNMAP, the INFORM project and WHO (NMCP 2013[33]). Using Bayesian geo-statistical modelling based on environmental, climatic and parasite survey data the report on the one hand shows the significant burden and high level of endemicity of malaria in Nigeria, but also the declines in parasite rates in the past 15 years.(see also paragraph 6).
[32] Bruce-Chwatt LJ: Malaria in Nigeria. Bulletin of the World Health Organization, 1951, 4:301-327
[33] National Malaria Control Programme, SUNMAP, World Health Organization and the INFORM Project (2013). A description of the epidemiology of malaria to guide the planning of control in Nigeria. A report prepared for the Federal Ministry of Health, Nigeria, the Roll Back Malaria Partnership and the Department for International Development, UK. November, 2013

Evidence that effective malaria control will reduce mortality

The evidence base demonstrating that comprehensive malaria control leads to dramatic reductions in transmission, morbidity and mortality is strong, including evidence from Nigeria (Molineaux & Gramiccia 1980[34]). The 2015 World Malaria Report (WHO 2015a[35]) provides good evidence that the scale-up of malaria control in recent years has had the expected impact. World-wide malaria incidence has declined by 37% since 2000 and malaria specific mortality by 60%. In Africa reductions are somewhat smaller and Nigeria and DRC together still contribute approximately 80% of malaria burden in Africa. However, estimations on malaria control induced reductions in under-five mortality using the Lives Saved Tool (LiST model) suggest that the lives of 166,000 children under-five were saved in Nigeria between 2001 and 2010 (WHO 2012[36]). This coincides with the beginning of a pronounced reduction in all-cause under-five mortality for Nigeria which is estimated to have reached 109/1,000 live births in 2015 (Inter-agency Group on Child Mortality Estimation 2014[37] - see Figure 8).
[34] Molineaux L, Gramicca G: The Garki project : research on the epidemiology and control of malaria in the Sudan savanna of West Africa, World Health Organization 1980, http://apps.who.int/iris/bitstream/10665/40316/1/9241560614.pdf
[35] WHO (2015a): World Malaria Report 2015, Geneva 2015. http://apps.who.int/iris/bitstream/10665/200018/1/9789241565158_eng.pdf
[36] WHO: Progress and impact series: Focus on Nigeria. Roll Back Malaria Partnership, Geneva , 2012 http://www.rollbackmalaria.org/microsites/ProgressImpactSeries/docs/report11-en.pdf
[37] IGCME: Inter-agency Group on Child Mortality Estimation, 2015, http://www.childmortality.org/

Figure 8: Estimates under-five mortality from the Inter-agency Group on Child Mortality Estimation

Intervention specific evidence

ITN
The systematic review of Lengeler (2004[38]) was the first to compile the clear evidence that ITN are highly effective and can reduce child mortality by 17%, episodes of uncomplicated malaria by 50% and severe malaria by 43%. Nigeria-specific data are more limited but using the 2010 Nigeria MIS data and a methodology that allows control of ITN ownership at community level (mass-effect) it could be shown that parasite prevalence was significantly lower in areas with high ITN coverage following the campaigns (34% vs. 41%) (Kyu 2013[39]).
[38] Lengeler C.: Insecticide-treated bed nets and curtains for preventing malaria. Cochran review, 2004, CD000363
[39] Kyu HH, Georgiadis K, Shannon HS, Boyle MH: Evaluation of the association between long-lasting insecticidal nets mass distribution campaigns and child malaria in Nigeria. Malaria Journal 2013, 12:14

SMC
A systematic review of the impact of seasonal malaria chemoprevention is also available (Meremikwu 2012[40]) and shows that SMC can prevent approximately 75% of clinical and severe malaria episodes in children under five. Malaria Consortium recently also presented their evidence from a pilot in Katsina State, Nigeria (Baba 2015[41]). After the first year of four rounds of SMC malaria cases during peak of transmission season (September) reduced by 66% and in the second year by 78% at a cost of close to USD 4.00 per child covered.
[40] Meramikwu MM, Donegan S, Sinclair D, Esu E, Oringanie C: Intermittent preventive treatment for malaria in children living in areas with seasonal transmission. Cochrane review, 2012, CD003756
[41] Baba E, Katsina State SMC Project: Summary of Results & Implications for Wider Roll – Out, Malaria Consortium, Presentation 11. November 2015

IPTp
An analysis of 32 nationally representative surveys which included Nigeria showed that IPTp could be attributed a 18% protective effect for neonatal mortality and 21% increase in birth weight (Eisele 2012[42]). Since these were not intervention studies or trials, the findings suggest that these effects can be achieved under programme implementation conditions.
[42] Eisele TP, Larsen DA, Anglewicz PA, Keating J, Yukich J, Bennett A, Hutchinson P, Steketee RW. Malaria prevention in pregnancy, birthweight, and neonatal mortality: a meta-analysis of 32 national cross-sectional datasets in Africa. Lancet Infect Dis. 2012 Dec;12(12):942-9

Case Management
The 2015 World Malaria Report (WHO 2015a[43]) states that 17 studies in the therapeutic efficacy of ACT have been carried out in Nigeria with strong evidence that they are efficacious. In addition, there is as yet no evidence that the artemisinin resistance in Southeast Asia has emerged in Africa (WHO 2015b[44]). Furthermore, there is good evidence that the use of RDTs for malaria diagnosis is cost-effective (Lubell 2008[45]).
[43] WHO (2015a): World Malaria Report 2015, Geneva 2015. http://apps.who.int/iris/bitstream/10665/200018/1/9789241565158_eng.pdf
[44] WHO (2015b): Update on artemisinin and ACT resistance, September 2015, http://www.who.int/entity/malaria/publications/atoz/status-rep-artemisinin-act-resistance-sept2015.pdf
[45] Lubell Y, Hopkins H, Whitty CJM, Staedke SG, Mills A: An interactive model for the assessment of the economic costs and benefits of different rapid diagnostic tests for malaria. Malaria Journal 2008, 7:21

Evidence that planned activities will increase quantity and quality of interventions

Public sector
The effect of strengthening governance interventions in the malaria sector have not been systematically documented. There are however several indications that strengthening planning and management of government capacity leads to improved stewardship, programme implementation efficiency and increased resource. For example, SUNMAP contributions towards malaria operational planning has meant that state governments had for the first time a tool to lead the implementation and monitor a coordinated plan for malaria control, avoiding duplication of efforts as experienced in the past. It also provided them with a strong basis for domestic and international resources mobilisation. In terms of domestic resources mobilisation, in Kano State for example, which has been supported by SUNMAP since the inception of the programme in 2008, registered a steady increase in budget allocation for malaria from 15 million Naira in 2011 to N600m in 2014.,;)[46].
[46] SUNMAP, presentation from Kano State Manager for 7th DFID annual review, 2015.

Similarly, under its harmonization agenda, SUNMAP adopted an issue based approach to provide evidence that a well managed and coordinated programme can lead to increased resource mobilization and performance. The best example has been the role that the programme played in the rapid scale-up of LLIN coverage. SUNMAP facilitated the agreement of all partners on mass distribution campaigns using common planning, implementation and reporting tools. SUNMAP then supported the national programme to design and lead a central technical assistance facility to ensure the quality and consistency of all campaigns in terms of advocacy, trainings, implementation, surpervision, trouble shooting and reporting. This single and clear government led plan rallied development partners together and resulted in the mobilization of enough resources to cover all states with one mass LLIN distribution campaign distributing close to 100 millions LLINs in approximately two years. The agreement that a state campaign would only take place when enough nets and operational costs were secured to cover the entire state meant that the partners supporting a given state had to closely coordinate their efforts and that a single campaign event led to economies of scale in aspects like advocacy, training, logistics and training.

Private sector
The experience from SUNMAP in Nigeria as well as other countries has shown that it is possible to stimulate the ITN/LLIN markets as long as the role of the public sector as a direct distributor of free product is limited (Malaria Consortium 2013[47]). Similarly, experience from the AMFm implementation has shown that also the ACT market can be steered towards supplying quality ACT at affordable prices and that these even could reach remote areas in Kenya and Ghana (Ye 2015[48]). On the side of the application of RDT in the private sector a cluster randomized trial in Ghana demonstrated that introduction of RDT was feasible and compliance with test results was significantly better if RDT and training were provided with 70% of negative patients NOT receiving ACT compared to 12% in the control arm (Ansah 2015[49]).
[47] Malaria Consortium: Development of the commercial Insecticide Treated Net sector in the face of free public sector distributions and options for support. A Learning Paper, October 2013 http://www.malariaconsortium.org/media-downloads/220/Insecticide%20treated%20nets:%20the%20role%20of%20the%20commercial%20sector
[48] Ye Y, Arnold F, Noor A et al.: The Affordable Medicines Facility‑malaria (AMFm): are remote areas benefiting from the intervention? Malaria Journal 2015, 14:398
[49] Ansah EK, Narh-Bana S, Affran-Bonful H, Bart-Plange C, Cundill B, Gyapong M, Whitty CJM: The impact of providing rapid diagnostic malaria tests on fever management in the private retail sector in Ghana: a cluster randomized trial. British Medical Journal 2015, 350:h1019 doi: 10.1136/bmj.h1019

BCC
A recent study from Nasarawa State, Nigeria showed that exposure to messages on net care and repair through various communication channels led to a significantly improved attitudes of households towards net care and repair which in turn resulted in better condition of the nets and an almost one year longer median survival of the ITN (Koenker 2015[50]). Similar effects could be demonstrated for net use: a secondary analysis of 10 post-campaign surveys from Nigeria showed between 8% and 17% impact of BCC on net use (Kilian 2015[51]). Evidence on the side of case management is less strong. A recently published cluster-randomized trial of interventions to improve diagnostic (RDT) uptake by health care providers and the community only resulted in a 34% testing rate in the control arm, 37% for the provider training plus school-based BCC and 48% for the arm with provider training only (Onwujekwe 2015[52]).
[50] Koenker H, Kilian A, Hunter G, Acosta A, Scandurra L, Fagbemi F, Onyefunafoa EO, Fotheringham M, Lynch M: Impact of a behaviour change intervention on long-lasting insecticidal net care and repair behaviour and net condition in Nasarawa State, Nigeria. Malaria Journal, (2015), 14:18
[51] Kilian A, Lawford H, Ujuju CN, Abeku T, Okoh F, Baba E: The impact of behaviour change communication on the use of insecticide treated nets – a secondary analysis of ten post-campaign surveys from Nigeria, 2015 (manuscript in preparation)
[52] Onwujekwe O, Mangham-Jefferies L, Cundill B, Alexander N, Langham J, Ibe O, Uzochukwu B, Wiseman V: Effectiveness of Provider and Community Interventions to Improve Treatment of Uncomplicated Malaria in Nigeria: A Cluster Randomized Controlled Trial. PlosOne, 2015, DOI: 10.1371/journal.pone.0133832 http://journals.plos.org/plosone/article?id=10.1371/journal.pone.0133832

Programme performance
SUNMAP had a strong track record of successfully implementing its activities leading to meeting and in some cases exceeding its output targets. The last two DFID annual reviews rated the programme performance as moderately exceeding expectations. This provides a high level of confidence that SUNMAP2 outputs can be achieved too. While the results measurement and evidence generation and use output 5 is clearly presented as a cross cutting output, SUNMAP2 outputs have been designed to achieved in a fully integrated and coordinated manner, internally and with other relevant DFID programmes and malaria partners.
## Proposed Value for Money Assessment measures for SUNMAP2

SUNMAP2 will build on the approach to Value for Money developed under SUNMAP, taking a 4Es Approach as shown in Figure 9 below

Figure 9: The 4Es Approach to Value for Money

Economy

Economy is usually measured by the unit costs of inputs. Most projects are able to provide a great deal of detail on this subject but this information needs to be treated with care. It is usually thought that the lower the unit costs, the better. That is certainly true as long as like is compared with like. However, project inputs can vary a good deal in terms of quality. It is not clear, for example, that a project that uses a lot of relatively inexperienced technical assistants has better economy than a project that uses fewer days of more experienced technical assistants. Certainly, the unit cost of technical assistance for the former will be lower than that of the latter but, until we compare efficiency, we do not know which set of technical assistants would be better for the project. Of course, we can collect data on different levels of experience (for example, more than fifteen years, ten to fifteen years, five to ten years, under five years) but this does not really tell us about their experience relevant to the project. Indeed, in a malaria project, it may be that technical assistants with fewer years of experience have more recent knowledge to apply. For these reasons, we do not intend to use either the unit costs of technical assistance or the proportion of the funding used for operational costs as metrics for economy. Instead, we propose to monitor the unit costs of inputs that are unambiguous in terms of quality. The key inputs to be monitored in this way will be those shown in Table 7.

Table 7: Unit Costs to be Monitored for Economy
Input	Monitoring methods
LLINs distributed to the Health Facility (HF)	Benchmarked against: (i) international data; (ii) SUNMAP / Monitored within the project over time
ACT doses distributed to the HF	Benchmarked against: (i) international data; (ii) SUNMAP / Monitored within the project over time
RDTs distributed to the HF	Benchmarked against: (i) international data; (ii) SUNMAP / Monitored within the project over time
SMC treatment distributed to the HF	Benchmarked against international data / Monitored within the project over time
Inj AS distributed to the HF	Benchmarked against international data / Monitored within the project over time

The benchmarking against international data will be essential in order to prevent distortion as a result of exchange rate changes. During the first phase of SUNMAP, the unit cost per LLIN distributed (procurement & distribution) reduced from £3.19 to £2.49, and; the cost per ACT distributed fell by 12% to £0.52 between years six and seven. These figures fall comfortably within the NAO benchmarks of £2.43-£2.92 per LLIN distributed and £0.98 per ACT distributed. The cost per LLIN distributed via continuous distribution fell by 61% between years three and seven to £0.82 per net distributed.

Efficiency

Efficiency is measured by the unit cost of the expected outputs of the programme. Ideally, the output would be straightforward to measure and its unit cost easy to derive and interpret. However, in a complex programme such as this, outputs can only be measured by a number of indicators, many of which measure various aspects of the output. In the case of this programme, we have five outputs each to be measured by three indicators to measure progress against the project logframe and by more indicators for internal monitoring purposes. While this is inevitable for performance management, 20-25 value for money metrics for efficiency would be difficult to interpret. We have, therefore, identified a set of a maximum of two indicators for each output. Where outputs are very complex to produce, we have used only one value for money indicator for which either the individual costs are easy to identify or where it summarise the entire output to which the full costs of the delivering that output’s activities can be allocated. We have chosen value for money indicators that fulfil the following criteria:

- The indicator has an unambiguous quantitative measure
- It is key to the achievement of the Output
- It is possible to allocate spending clearly to its delivery.

The proposed value for money metrics for efficiency are shown in Table 8.

Table 8: Unit costs to be monitored for efficiency
Output	Indicator	Monitoring methods
1. Stewardship	Cost of obtaining an increase of N1000 in domestic contribution to malaria control and prevention / $ saved/recovered through anti-corruption measures	Measured and compared at national and state level / Tracked over time / Audit reports
2. Availability of Commodities	Cost of reducing by one stock-outs of any AMCs in HFs reporting by DHIS or LMIS	Measured and compared at national and state level / Tracked over time
	Cost of reducing % market share of non-recommended AMCs (eg non-ITN, chloroquine)	Measured and compared at national and state level / Tracked over time
3. Service Delivery	Cost of an additional service delivery point (public and private sectors / facility and community) with adequate number of health workers trained on malaria prevention, uncomplicated malaria treatment and referral of severe malaria	Measured and compared at national and state level / Tracked over time
	Cost of an additional service delivery points with adequate number of health workers trained on severe malaria treatment	Measured and compared at national and state level / Tracked over time / Possible international benchmarking
4. Better informed citizens and institutions	Cost of increasing by 1 percentage point percentage of people with access to LLIN within the household compared to proportion of people using it last night	Measured and compared at national and state level / Tracked over time / Possible international benchmarking
	Cost of increasing by one the number of facility and non-facility based health committees established and trained in their role in malaria prevention and treatment	Measured and compared at national and state level / Tracked over time
5. Evidence-based learning environment	Cost of a malaria surveillance site functional and using nationally agreed protocols and reporting system	Measured and compared at national and state level / Tracked over time / Possible international benchmarking
	Cost of achieving annual operational plan evidenced by appropriate amount and relevant malaria data analysed	Measured and compared at national and state level / Tracked over time

Cost Effectiveness

The indicators of outcome as reflected in the logframe can be used to estimate the expected DALYs averted by the programme at each point. Divided by total programme costs, effectiveness can then be measured by cost per DALY averted. The first phase of the programme is estimated to have averted 1 998 912 (approximately 2m to date) DALYs at a total cost of £89m. This equates to approximately £44.52[53] (or $70.6[5]) per DALY averted, which is highly cost effective relative to international benchmarks.
[53] SUNMAP Programme Completion Review 2016
[5] Using the average £/$ exchange rate of £1/$1.585 between 2009 and 2014

Equity

Equity can be interpreted in a number of ways including both treating individuals equally and addressing existing inequalities. With poverty being so widespread in Nigeria, it is important that this programme tracks the extent to which it affects the poor. This is a new issue in value for money analysis and further research and analysis are required. In the absence of a definitive approach, the following metrics for equity are proposed as shown in Table 9.

Table 9: Metrics for equity
Equity ratio	Monitoring methods
Ratio of household bed net ownership in the lowest to the highest socio-economic status (SES) groups	Measured and compared at DFID supported state level / Tracked over time
Ratio of ACT treatment for children under five for lowest to the highest socio-economic status (SES) groups	Measured and compared at DFID supported state level / Tracked over time

During the first phase of the programme, wealth inequities in access to bed nets were dramatically reversed. Between 2008 and 2015, insecticide treated net ownership among the poorest households increased from 4% to 86%, compared to an increase from 11.2% to 58% in the richest households.
## Summary Value for Money Statement for the preferred option

SUNMAP was widely considered to have provided the UK taxpayer with good value for money. It appeared to have obtained antimalarial commodities at competitive and falling prices – although this latter factor was facilitated as much by favourable exchange rate changes as by careful purchasing. Generally, the unit cost of outputs such as training courses showed a decline in costs over the life of the project – probably as a result of learning by experience. Finally, the unit cost of the prime outcome - a DALY averted – was estimated[54] at £44.52 per DALY averted, comfortably lower than the other benchmarks considered. The seventh annual review concluded “SUNMAP continues to show good VfM”.
[54] SUNMAP Programme Completion Review 2016

For SUNMAP2, the present value of costs to DFID is expected to be £47,274,922. The present value of DALYs generated during the life of the project is expected to be 208,956, resulting in a unit cost per DALY directly attributable to DFID of £226.24. This is a high unit cost compared with SUNMAP and somewhat high in terms of international benchmarking. This can be explained by following reasons:

1. Very conservative assumptions have been used to generate the DALYs, including the assumption that:
    1. DALYs can only be generated by the use of antimalarial commodities and i) the programme itself does not improve the efficacy of these commodities and ii) since the commodities are targeting a small portion of the population (around 10%) for demonstration purpose only, the calculations does not take the extended positive effect of the technical assistance to the rest of the population in each state
    2. Deaths averted have been converted into years of lives saved by using an age-weighted and discounted factor of 30.9 rather than the more generous factor, which is often used, of 82.5 that is unweighted and non-discounted.
2. Only 25% of the programme budget is used to purchase commodities (over 33% in SUNMAP)
3. The low-hanging fruit of mass provision of LLINs has already been plucked by SUNMAP. SUNMAP2 will be focusing more on treatment – particularly of severe malaria – and on diagnosis, both of which areas are less “productive” in terms of DALYs averted.

However, in spite of the high unit cost resulting from these very conservative assumptions, this figure remains good value for money. GDP per capita is usually considered a reasonable proxy for the value of a DALY. In Nigeria in 2014, GDP per capita was estimated by the World Bank to be $3,203[55] or £2,112. So in these terms, the new programme is still very worthwhile in the Nigerian context.
[55] http://data.worldbank.org/indicator/NY.GDP.PCAP.CD

It is worth noting that a major reason for the conservative assumptions is that we are now engaged in an ex ante evaluation. We will not know until the programme is underway whether the wider benefits attributed to SUNMAP will also be generated by SUNMAP2, although there is no reason why they should not be.

Finally, when the potential benefits from sustainability are included, the unit cost of a DALY drops to £51.73 even under the conservative assumptions and the less favourable environment. Although higher than SUNMAP, this figure is more than acceptable.

# Commercial Case
A. Clearly state the procurement/commercial requirements for intervention

The Appraisal case (see para 32) has set out the delivery options and concluded the preferred route for the management of the programme will be through a competitive tender governed by the EU Public Procurement Directives.
The commercial requirement in this case is to obtain technical services and programme management to the highest possible standard at the least possible cost.

Other planned direct procurement/employment activities over the life of the programme are:

Procurement of health commodities, vehicles and equipment through DFID’s new procurement framework
Procurement of consultancy services: Annual reviews conducted by DFID Nigeria through in-house/HMG resources in accordance with new guidance on self-employed individuals or if no solution can be found through the Professional Evidence and Applied Knowledge Services (PEAKS) framework agreement.
Procurement of independent programme audit and assurance services again subject to the guidance on self-employed individuals .
# B. How do we expect the market place will respond to this opportunity?
The large number of development actors operating in the country suggests that the market place will respond well to this opportunity and international providers will be incentivised to work with local organisations to maximise local content.
It is considered highly likely that serious competitors will bid. The health programme Service Providers’ market in the international development sector in Nigeria is fairly large as funding for basic health services is available within the resource envelopes of most bilateral and multilateral partners.
DFID Nigeria will carry out a pre-procurement early market engagement in order to openly and transparently discuss the design of the programme and the draft Terms of Reference The early market engagement will help us to gauge interest and understand market capacity, capability and trends.

C. How does the intervention design use competition to drive commercial advantage for DFID?

DFID Nigeria does not propose to utilise one of its frameworks under which pre-qualified suppliers stand ready to supply services. The use of tendering for the procurement of technical assistance will ensure that commercial advantage will be achieved for DFID through competition.

The Terms of Reference will include some ‘outcome’ focused specifications. Proposals will compete on the basis of delivering the services required, accounting for the level and quality of inputs proposed, and the cost, which represent the most economically advantageous tender.

To enable DFID to effectively assess the different bids and determine which offers best value for money, detailed information will be requested on the bidder’s ’ approach, and the costs associated with it. This should detail, as a minimum:

- The approach taken to deliver outcomes and outputs;
- A breakdown of costs associated with delivery, including detail of the role of the SP in delivery, i.e. which outputs the SP expects to deliver directly vs those they expect to buy-in externally;
- The inputs the SP expects to be attached to delivery of outputs e.g. consultants time; grade and cost of consultants; material costs;
- The method by which payment is expected by DFID, with an emphasis on output based payment and a strong case for any areas where this is not believed to be possible Where output-based payment is used, a proposed approach to generating milestones and clearly specified results by which DFID can assess successful delivery will be expected.
- Their Payment by Results offer on risk and reward

Management fees to be included in commercial bids will be evaluated to ensure that costs are set at an appropriate level for the programme and benchmarked against other similar fund management arrangements.

The contract will be agreed for a period of five years with an option for extension. Value for Money reviews of supplier performance by DFID Nigeria will be conducted annually using criteria that will be elaborated by DFID Nigeria in consultation with the lead service provider. the SRO will have lead responsibility for managing the Service Provider’s performance, including quality in delivery of outputs, cost control and innovative solutions.

While quality, technical expertise and innovation will be key considerations in selection of the service provider, DFID Nigeria will give high priority to efficiency and the ability to deliver the intervention at the lowest reasonable cost. We envisage that commercial considerations will attract a significant weighting.
Commodity Procurement

Commodity procurement will be carried out through the new Procurement Service Provider who will ensure all DFID’s requirements are met including, transparency, Value for Money. There are a number of manufacturing sources for the commodities required. We will look for opportunities to procure collaboratively with other donors particularly GFATM where it is possible to do so, to leverage better prices for quality products. We will also explore the range of services on offer eg to include last mile delivery. The procurement of commodities will also be discussed with the current Nigeria Supply Chain Integration Project (NSCIP) to ensure it is part of the drive for an integrated approach.

DFID Nigeria’s commercial adviser will provide support to SUNMAP2 and the SRO to determine the best model for the procurement of commodities. With the appointment of DPSA under a global procurement framework,  DFID Nigeria has options to contract them or all DFID Nigeria requirements or for specific sectors or as a potential sub-contractor to programme suppliers. At this point it is too early to say if contracting DPSA for all requirements would be advantageous. For SUNMAP2 a decision will be taken in advance of the tender on the other two options available, namely requiring potential suppliers to demonstrate their procurement capability eg by sub-contracting DPSA or another procurement organization, or , depending on DPSA’s performance on other programmes,.to exclude the procurement capability and award a separate contract to DPSA. In either scenario DFID Nigeria’s Commercial Adviser and PCD will work closely with both parties to ensure procurement processes use best practice and secure value for money for DFID.

D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?

The key underlying cost drivers in this intervention will be the cost of services, because much of the delivery of the programme will be through technical assistance. By this we mean the consultancy fee rates of the international specialist skills required for the delivery of the various aspects in the project. We will ensure that we are able to negotiate Service Provider fee rates and endeavour to get VfM. Living costs are high in Nigeria, and this will be a major driver of consultancy costs, as is the perception of Nigeria as a difficult environment to operate in. Our ability to influence these factors is, and remains, quite limited.
Several elements affect the price. Management costs are spread between salaries, direct overhead costs relating to the provision of staff and brought-in consultancy (e.g. medical insurance, visas, etc.), indirect overhead costs to contribute to the costs of being in business, such as corporate operations, managed costs, recruitment, back office administration, and the profit margin.

The key cost elements, therefore, will include:

- The Service Provider’s staff costs, which are a function of the quantity and unit cost of staff time deployed by the implementing firm including the core team who will manage the programme and any sub-contractors;
- Security costs
- The cost of securing suitable work premises;
- Rent and office equipment cost
- The Procurement Service Provider’s costs

Competitive tendering should ensure value-add in that accredited staff and consultants with sufficient capacity to perform the tasks required to a high standard are expected to be chosen. We will consider if the Competitive procedure with Negotiation is the most appropriate route for the tender process where DFID would have the opportunity to negotiate on both technical and commercial aspects of bids. The Terms of Reference will be used to define the framework within which the providers are expected to operate. Contract continuity will be subject to performance and satisfactory delivery of agreed milestones/outputs.

Evaluation of bids will ensure these costs are at an appropriate level and benchmarked against similar programmes in Nigeria. Proposals received from potential applicants will be judged against the VfM criteria of economy, efficiency and effectiveness. Elements that will be considered include: competitive fee rates, total cost to deliver the programme, provision of a clear and effective financial plan, their risk and reward offer under Payment by Results, and proportion of local input to costs.

Commodity Procurement cost drivers

Commodity procurement costs are largely dependent on international market conditions, with limited ability for DFID to influence this. However, measures that have been applied in the project include consolidating procurement volumes to achieve economies of scale, and ensuring, as much as possible, that standard product specifications are ordered. Market information (particularly for LLINs) reveals that costs have fallen through successive procurements when expressed in £ sterling. A key variable has been the £ to US$ exchange rate, given that most nets are procured in US$. These factors alongside for example using hedged pricing will be discussed with DFID’s newly appointed procurement service provider to establish how they will reduce costs. We will also fully explore the potential to join up with other donors and partners, particularly those involved in the Nigeria Supply Chain Integration Project (NSCIP) programme, who may be buying similar commodities.

# E. How will the contract be structured and how will contract and supplier performance be managed through the life of the intervention?

The DFID Nigeria Health Adviser Lead Adviser/SRO) and the Project Officer will have regular management meetings to discuss progress against Key Performance Indicators (KPIs) and, if agreed, progress against outputs. Contract and supplier performance management will be undertaken using existing established mechanisms in DFID including support from DFID Nigeria’s Commercial Adviser and DFID Procurement and Corporate Performance Department where necessary.

Payments will be authorised against satisfactory performance of the work plan and specific objectives/milestones/outputs. Tenderers will be evaluated on their proposed payment processes, and negotiations will be held with the chosen supplier to maximise the amount of the contract price that is pegged to acceptable delivery.

The supplier will maximise value for money throughout the life of the project, actively benchmarking and testing how to reduce the cost per beneficiary or widen the number of beneficiaries for the contract value. Non-fee expenditures will use existing benchmarks for hotel and subsistence costs, and reviewed regularly. The contract will reflect the levels of insecurity, and enable the supplier to enhance security if it considers this necessary.

The performance of contracts will be measured and managed by:

- Outputs achieved, as reported in quarterly and annual reports, and monitored by the SRO (and the Project Officer); including quarterly meetings with the programme.
- Independent and in-depth annual audit. This will be commissioned by DFID and focus on internal controls, procurement, finance, inventory and asset management. A clear time frame will be agreed with the SP on implementing agreed recommendations;
- An inception period review commissioned by DFID and conducted by an external reviewer.
- The contract will be delivered in phases. A business plan will be produced annually by the Service Provider setting out the planned profile taking into account risk and potential opportunities and agreed before proceeding to the next phase of the implementation plan.

We expect the main Service Provider to sub-contract other providers over the course of the programme or source from within if they have a range of diverse services at their disposal. Interventions to be sub-contracted are likely to include studies/research, training, and specific interventions. DFID will work with the prime Service Provider to ensure that DFID procurement principles are applied, due diligence of sub-contractors is undertaken and audits are conducted. DFID will under-take regular monitoring/spot-checks of these contracts and of the relevant reports.

There will be separate contracts. The first contract will be the technical assistance component for which a consortium of firms will be selected and the second contract would be the programme procurement which will be contracted under the new procurement framework. Results-based terms of reference that include SMART deliverables and outputs, and clear delineation of responsibilities will be used as the basis for a contract with the technical assistance service provider. The Service Provider will be required as part of their tender bid to set out clearly their implementation plans. DFID will seek the use of appropriate service level agreements and KPIs on output based contract. DFID will expect regular reporting against agreed indicators
DFID will include defined milestones, and reserve the right to scale the programme up or down based on performance, and to terminate the contract if performance is unsatisfactory.
In addition to outcomes, emphasis will be on inputs and processes and interim results at several time points during the programme in order to inform improvements in interventions and/or their implementation.

F. Corruption and fraud assessments in the procurement processes
Corruption and Fraud will be managed through the following mechanism
- Reinforcing ethical behaviour in the tender process and bidders will be asked to declare conflict of interest.
- Ensuring separation of duties in procurement processes and due diligence assessment will be conducted.
- Annual programme and financial audits to get assurance that the processes and procedures specified by the service provider are complied with.

# Financial Case
## Overview of cost

The key costs categories are technical assistance, including personnel fees and the operational costs related to the technical assistance, activities costs, procurement costs and retained funds to cover direct DFID management and oversight costs. The total expected costs to DFID for these four categories and including the six years longitudinal study are shown in Table 10 below.

Table 10: SUNMAP2 estimated costs by budget category and sub-category - 6 years
Budget category and sub-category		Total 6 years	% 6 years
Technical assistance
	Long term technical assistance fees
	Central - technical project	£4,407,660
	Central - technical seconded to NMEP	£603,720
	Central - management and finance	£1,738,920
	States - technical and management	£4,218,120
	Short term technical assistance fees
	Output 1 - stewardship	£1,080,000
	Output 2 - commodities	£1,788,000
	Output 3 - service delivery	£2,388,000
	Output 4 - awareness	£1,668,000
	Output 5 - evidence	£1,200,000
	Operational costs	£3,643,000
		£22,735,420	46%
Activities support costs
	Output 1 - stewardship	£1,015,000
	Output 2 - commodities	£1,896,976
	Output 3 - service delivery	£5,131,678
	Output 4 - awareness	£1,300,000
	Output 5 - evidence	£2,310,000
		£11,653,654	23%
Procurement costs
	Operational	£353,200
	Commodities	£12,501,587
		£12,854,787	26%
DFID retained costs
	DFID direct costs	£2,500,000	5%
Total		£49,743,861	100%

In some of these budget categories, activities and procurement costs, we will be expecting the programme to generate additional counterpart funding as part of the its sustainability agenda. The expected counterpart funding was shown earlier in Table 5, it will increase over time in preparation for the DFID exit at the end of five years.
## Cost profiling

Annual costs have been estimated as per Table 11 below. Costs are low in year 1, taking into account project start-up. We expect the project to be fully functioning in year 2, which has the highest annual costs of the five years. Thereafter, costs decline in each subsequent year both because of increasing counterpart contribution and because the technical assistance input is declining in preparation for exit.

Table 11: SUNMAP2 estimated annual costs by budget category - 6 years
Budget category	Year 1	Year 2	Year 3	Year 4	Year 5	Year 6	Total
Technical assistance	£4,248,480	£6,807,440	£5,649,320	£3,996,880	£2,033,300	£0	£22,735,420
Activities support costs	£1,704,719	£3,789,900	£2,859,765	£2,198,194	£1,001,075	£100,000	£11,653,654
Procurement costs	£2,030,158	£3,801,270	£3,162,530	£2,635,014	£1,225,815	£0	£12,854,787
DFID retained costs	£500,000	£500,000	£500,000	£500,000	£500,000	£0	£2,500,000
Total £	£8,483,358	£14,898,610	£12,171,615	£9,330,088	£4,760,191	£100,000	£49,743,861
Total %	17%	30%	24%	19%	10%	0%	100%

## Draft input sector codes
Component 1 £36.9m
Funding Type: Procurement of services
Benefiting Country: Nigeria
	Input Sector	Input Sector Code	Percentage Allocation
1	Health education	12261	15%
2	Business Support Services and Institutions	25010	5%
3	Health Policy and Administrative Management	12110	25%
4	Malaria Control	12262	35%
5	Health Personnel Development	12281	15%
6	Health Research	80012	5%
Component 2 £12.9m
Funding Type: Procurement of goods
Benefiting Country: Nigeria
	Input Sector	Input Sector Code	Percentage Allocation
1	Malaria control	12262	100%

## What is the assessment of financial risk and fraud?

There are four key financial and fraud risks:
- Risk of funds being misappropriated or not being used as intended.
- Risk of diversion of DFID funded commodities.
- Risk of loss due to reduced financial management and oversight in conflict areas.
- Risk that expenditure does not represent value for money for DFID.

The following is an assessment of the key risks:

Table 12: SUNMAP2 financial risk assessment
Risk	Likelihood and impact	Mitigation	Residual risk
Risk of funds being misappropriated or not being used as intended.	Likelihood – Possible; Impact - Moderate	No SUNMAP2 funds will be passed through government systems. / Payment will be made in arrears, following standard DFID Nigeria procedures for inspecting invoices to ensure value for money and compliance with agreed fees and reimbursement costs. / A Due Diligence Assessment of the service provider will be carried out prior to any disbursement of funds. / DFID will commission regular independent audits of the SUNMAP2 programme.	Minor (within fiduciary risk appetite)
Risk of diversion of DFID funded commodities.	Likelihood – Possible; Impact - Minor	i) MOUs with supported states will stipulate some SUNMAP2 oversight, joint management and independent monitoring of the use of commodities. / ii) DFID will be providing assistance to improve the management of health commodities in supported States, and SUNMAP2 will support greater transparency and availability of supplies through the Nigeria Supply Chain integration Project. / iii) Independent audits will perform verification and reconciliation of commodity utilisation and stock.	Minor (within fiduciary risk appetite)
Risk of loss due to reduced financial management and oversight in conflict areas.	Likelihood – Unlikely; Impact - Moderate	i) Develop the ability of local staff, particularly in conflict zones, to monitor SUNMAP2 financial operations in their areas. / ii) DFID will ensure, as much as possible, that independent audit teams visit all SUNMAP2 locations, including those in conflict locations, if any. / iii) Only one (Yobe) of the 6 states that may be possibly be supported by SUNMAP2 is seriously affected by conflict.	Minor (within fiduciary risk appetite)
Risk that expenditure does not represent value for money for DFID.	Likelihood – Unlikely; Impact - Moderate	All commodity procurement under the SUNMAP2 project will be conducted using DFID’s contracted procurement agent using EU procedures. Assessment of procurement costs under SUNMAP indicates that unit costs can be competitive relative to international benchmarks. / The cost effectiveness of SUNMAP’s major interventions were well established. And there is no reason to expect this situation not to continue under SUNMAP2. / Value for money assessments of the project will be conducted as part of its annual reviews.	Minor (within fiduciary risk appetite)

## How will expenditure be monitored, reported on and accounted for?

Monitoring and accounting of expenditure will take place using the DFID’s ARIES financial management system and standard DFID Nigeria procedures for inspecting invoices to ensure value for money and compliance with agreed fees and reimbursement costs. DFID will rely on:

•	Quarterly progress reports covering programme and financial issues
•	Year-end statement of actual expenditure
•	Independent annual audits of the programme
•	Monthly invoice checks before payment.

Quarterly narrative and financial progress reports to DFID will include reports against the logical framework and agreed results. Expenditure will be monitored/validated against quarterly financial and progress reports. Progress and financial reports will be submitted within 30 calendar days of the end of each quarter.

DFID will conduct annual financial audits of the programme and ensure that SUNMAP2 maintains up to date asset registers. DFID will decide on the disposal of assets at the end of the programme.

# Management Case
## What are the management arrangements for implementing the interventions?

Programme management will primarily be the responsibility of SUNMAP2 and the service providers selected to deliver it, in close collaboration with DFID. Technical coordination and direction of the programme will be provided by DFID Nigeria’s Health Adviser and Senior Responsible Owner for the project. DFID project management support will be provided by a Programme Officer and Programme Manager within the Human Development (HD) Team. The DFID and SUNMAP2 senior team will form a Programme Management Committee, which will meet at least on a quarterly basis to review progress and discuss broader issues affecting the programme performance, including budgetary performance and risk.

The service provider will be required to propose a management structure that offers high value for money to DFID and allows for activities roll out and capacity building of government institutions and other actors at both federal and supported states levels. The programme central team will be able to report on both programmatic and financial progress at all levels.

It is envisaged that the programme will hire a pool of technical staff at central level to support the delivery of each output of the programme at federal and state levels. Two technical assistants will be seconded to the NMEP in the first years of the programme as part of the focus of the programme to build capacity in the areas of malaria programme management and evidence generation and use. The specific roles and tasks of these staff will be agreed between NMEP, DFID and SUNMAP2. Progress against periodic milestones and broader engagement review will guide the performance of this focused technical assistance. Similar to other programme inputs, by the middle of the programme, these long term technical assistants will first be replaced with periodic short term assistance, with the frequency of the latter gradually decrasing as the programme advances until its end.

Flexibility to respond to the rapid changing malaria landscape in Nigeria will be required. Priorities will be reviewed with the DFID Health Advisor annually based on progress and evidence gathered by the programme and other partners in the country. The possibility to adjust interventions during the course of each year will be considered by DFID based on technical and/or management justification provided by SUNMAP2.

The responsibility for coordination between designated DFID programmes, specifically those working in the health and governance sectors, will be shared between, on the one hand, DFID Nigeria Health and Governance Advisors and, on the other hand, the respective programme leaderships and their prime contractor. DFID State Representatives will also liaise closely with SUNMAP2 at state level to ensure robust political dialogue and engagement with state governments and other counterparts; as well as to coordinate and assist DFID programmes in their work. DFID will provide the service providers a clear coordination framework indicating what type of issues are to be discussed and agreed between DFID and the programmes at which level, national and states, and how that decision process will take place. All programmes will requested to report against coordination milestones agreed by all at the beginning of SUNMAP2.

DFID will support SUNMAP2 in the area of coordination and harmonization with other malaria funding partners in the country. The programme will sit on key partner coordination forums such as the Nigeria Roll Back Malaria Partnership. It will also help operationalize a new strategic partnership between DFID and the Global Fund, which will support efforts to improve government financial management, domestic funding and logistics. The programme will also join relevant committees of the multi-donor National Supply Chain Integration Project, and at a minimum, serve as an observer in Global Fund Country Coordination Committee (CCM) meetings. DFID Nigeria’s health adviser and SRO for SUNMAP2 will also leverage support from DFID’s Global Funds Department and the Global Fund Secretariat in Geneva.

Procurement for the operations of the technical assistance and for commodities will be undertaken in compliance with DFID procurement guidance. DFID Nigeria’s commercial adviser will provide support to SUNMAP2 and the SRO to determine the best model for the procurement of commodities. With the appointment of DPSA under a global procurement framework,  DFID Nigeria has options to contract them or all DFID Nigeria requirements or for specific sectors or as a potential sub-contractor to programme suppliers. At this point it is too early to say if contracting DPSA for all requirements would be advantageous. For SUNMAP2 a decision will be taken in advance of the tender on the other two options available, namely requiring potential suppliers to demonstrate their procurement capability eg by sub-contracting DPSA or another procurement organization, or , depending on DPSA’s performance on other programmes,.to exclude the procurement capability and award a separate contract to DPSA. In either scenario DFID Nigeria’s Commercial Adviser and PCD will work closely with both parties to ensure procurement processes use best practice and secure value for money for DFID.

As reported throughout the business case, SUNMAP2 builds on the signifcant successes of the eight year £89m SUNMAP which is coming to an end in March 2016. The latter has shown very good value for money to DFID. In, the 2012 National Audit Office (NAO) value for money audit of DFID’s malaria control work, a case study of the SUNMAP project was included. The design of the SUNMAP programme was commended and so was its responsiveness to changing malaria priorities in Nigeria, its efforts on capacity building and harmonisation and the value for money efforts within the project. The concerns raised regarding insufficient usage of nets, the provision of malaria treatment without prior diagnosis and the sustainability of malaria control efforts have largely informed the design of SUNMAP2 with a focus on closing the gap between ownership/awareness and use and on sustainability of DFID’s investment.
## What are the risks and how these will be managed?

Overall the level of risk affecting the programme is judged to be medium. Risks have been assessed against six categories: context; delivery; operational; safeguards; fiduciary and reputational . They are summarized together with the mitigation measures in the Table 13 below.

Table 13 - SUNMAP2 political economy, security and programmatic risks assessment
Identified Risk	Likelihood(1-5)	Impact (1-5)	Mitigation Measures	Residual risk
Context
Malaria fails to gain traction as an issue at a political level with the new Administration post 2015 elections	4-Likely	3-Moderate	i) Potential to mitigate through high level advocacy, as DFID has successfully done regarding family planning. Explore scope to engage at Presidential / bilateral political level to raise malaria as a potential political issue in active collaboration with other DFID programmes in assessing political economy and using transformational approaches for changes. / ii) Strong monitoring of SUNMAP MOUs with State Governments using DFID State engagement mechanisms.	Major. (Within context risk appetite)
Political interest in inappropriate interventions diverts resources from more cost effective measures	3-Possible	4-Major	i) Continue high level advocacy / ii) Support better malaria surveillance and epidemiological mapping to enable better targeting of interventions to epidemiological and climatic patterns (e.g.: larviciding and IRS) / iii) Support improved use of evidence in planning malaria interventions	Moderate (Within context risk appetite)
Domestic fiscal difficulties due to oil price crash does not improve, limiting the ability to mobilize increasing domestic resources for malaria funding	4-Likely	4-Major	i) Monitor potential effect and plan for alternative approach should the situation worsen much more; assess potential opportunities. / ii) Assumptions of counterpart funding from government sources have been kept moderate and placed toward the latter years of SUNMAP2, when the fiscal situation is expected to have stabilized. / iii) Improve value for money of available malaria expenditure and support government efforts to demonstrate the effective use of available resources. This is likely to encourage sustained funding from other sources. / iv)Escalate to DFID Nigeria portfolio level – and support government efforts to address fiscal difficulties by improving financial management, tackle corruption, and improve tax collection. / v) Leverage private sector investment.	Major (Within context risk apetite)
Weaknesses in the delivery of Global Fund grants not addressed leading to withdrawal of international funding and resurgence of malaria	3-Possible	5-Severe	i) Support strengthening of financial management systems in government health institutions / ii) Support improvements in procurement and supply chain systems and other health delivery systems / iii) Support improvements in domestic resource mobilisation.	Major (Within context risk appetite)
Operational
Increased insecurity affects ability to implement the project.	3-Possible(in some states)	3-Moderate	i) Monitor closely; / ii) Avoid overloading programmes in insecure States; or operate from more secure states / iii) Develop low profile but frequent programme monitoring to ensure checks and balances are maintained in fragile states. / iv) Encourage effective recruitment and training of local project staff with high local credibility. / v) DFID State representatives, advisers and DFID risk management office (RMO) proactively address potential security risks and mitigation responses. / vi) Escalate to DFID Nigeria portfolio level	Minor (Within operational risk appetite)
Delivery
Commodity quality is not adequately assured.	2-Unlikely	3-Moderate	i) Reduce time pressure by avoiding procurement at the end of the financial year. / ii) Ensure independent testing. / iii) Procure from WHO prequalified suppliers. / iv) Contribute to strengthening national quality assurance mechanisms	Minor (Within delivery risk appetite)
Malaria commodities cannot be marketed through the retail sector in the face of competition from public sector free commodities distribution and leakages from the public into the private sector	4-Likely	3-Moderate	i) Address security of public sector distributed commodities; / ii) Increase evidence and understanding of malaria commodities markets potentials and targets interventions to most relevant value chain level and market segments. / iii) Support government to develop and implement agreed guidelines for free commodity distribution - e.g no branding and targeted distribution - to minimise market distortion	Moderate (Within delivery risk appetite)
Malaria parasites develop resistance to SP and ACTs and mosquitoes develop resistance to insecticide	3- Possible	3- Moderate (within project timeframe)	i) Provide significant technical support to build national and sub-national capacity for effective resistance surveillance / ii) Ensure adequate technical advice is timely available in case of evidence of resistance	Moderate (Within delivery risk appetite)
Safeguards
Malaria control interventions reduce biological immunity to malaria, leaving population more susceptible to resurgence, serious outbreaks and severe malaria	2-Unlikely	3-Moderate	i)SUNMAP2 is not designed to support interventions such as Indoor Residual Spraying, which have a known high risk of rebound effects. / ii) Continue to promote the availability and use of long acting prevention methods such as insecticide treated nets even after malaria prevalence has reduced. / iii)Provide support to improve malaria outbreak surveillance and response; and the treatment of severe malaria.	Minor (Within safeguards risk appetite)
Fiduciary (Please see financial case)
Reputational
Withdrawal from commodity support over the later years of the programme and possible exit from bilateral support at the end triggers complaints that threaten DFID’s reputation	2 - Unlikely	3 - Moderate	Develop and implement a clearly agreed and understood exit strategy and plan from the start of the programme – formalised through MOUs with supported governments and shared with civil society.	Minor (within reputational risk appetite)

Risks will be managed in line with DFID’s current risk management framework. Risks will be captured in the risk register and delivery plan, and will be tracked, managed and updated through the project cycle. The contract with the service provider will be used to allocate an appropriate level of risk away from DFID. Risks will be monitored through various methods, including through regular engagement and programme management committee meetings between DFID and SUNMAP2 management. The risk register will also be reviewed during each annual review. Risks may be escalated as required to portfolio level and to DFID senior management.

## Partnership Principles and other conditions

In Sept 2014 DFID Nigeria conducted an assessment of the Federal Government of Nigeria’s (FGN) commitment to the Partnership Principles. This reconfirmed the UK’s declared policy that that no UK aid money should go directly to the Government of Nigeria: as an anti-corruption measure and to avoid substituting for the country’s own resources. In line with this policy, SUNMAP2 will not provide funding through government channels.

However, the programme will work at both national and state level to strengthen institutional capacity and government commitment towards the partnership principles. Firstly the programme objective of supporting Nigerian authorities to scale up efforts to reduce illness and death due to malaria will help promote ‘a commitment to reducing poverty and achieving the Millennium Development Goals’ (Partnership Principle 1). Secondly, working closely with DFID’s governance and health systems programmes as well as the Global Fund, the programme plans to strengthen financial planning, management and expenditure tracking for malaria, and procurement and supply chain systems for malaria and other health commodities. This will help promote “better financial management and accountability, and reduce the risk of funds being misused through weak administration or corruption” (Partnership Principle 3). Thirdly, SUNMAP2’s push for more domestic malaria financing and better engaged citizens and institutions in the country’s malaria response, will promote the strengthening of domestic accountability (Partnership Principle 4).

The programme will not use the Partnership Principles as a formal conditionality in programming as no UK aid money goes directly to the Government of Nigeria. However, MoUs with supported states will set out mutual expectations, such as the state’s responsibility for stronger political leadership, embedding improved management systems and progressively increasing domestic financing. Decisions on the depth of DFID support and possible entry/exit to/from certain states will largely be informed by performance on MoU expectations.

## How will progress and results be monitored, measured and evaluated?

An indicative logframe for SUNMAP2 is provided in Annex B. This is provided for illustration only and will be reviewed as part of the programme inception and regularly throughout the life of the programme to provide flexibility to adapt to changing malaria burden. Output and outcome targets will be set at state level and impact targets at national level. Targets will be agreed with DFID based on evidence gathered prior and during the inception phase. The progress against these targets will be reported upon on quarterly basis by the service provider and verified on annual basis during annual reviews organised by DFID.

SUNMAP2 will develop a robust monitoring and evaluation framework, including detailed strategy to monitor the value for money offered by the programme. It is anticipated that the programme will rely on a combination of routine data, survey data and qualitative review to monitor its progress. The programme is designed to emphasise the development and use of national data collection systems which are collected and used by the government and other partners and not specific to SUNMAP2. To minimise the tendency for suppliers to exaggerate progress, the majority of indicators to be measured in the logframe and used to assess programme performance come from such independent sources. All indicator data provided by the programme, for instance at annual reviews, and for the purpose of milestone payments, will be verified from the data source. Operational research relevant to both NMEP and SUNMAP2 will be supported under the evidence output and will serve at the same time as an opportunity to build the capacity of NMEP to design, implement and/or oversee operational research independently in the future.

A formal evaluation has not been proposed because (1) there is already strong evidence for the key interventions; (2) the facilitative nature of the programme would make attribution very difficult, and (3) evaluation capacity within the DFID Nigeria office is already overstretched. The longitudinal study planned under the project, which will entail periodic assessments, will contribute to testing the theory of change of the programme across all outputs and thus the pathway of change from outputs to outcomes and from outcomes to impact. It will provide a unique opportunity to research what are the key drivers that make DFID support being sustained beyond a programme life time. Hence, it is not envisaged that a separate evaluation be commissioned.

DFID will arrange annual reviews following its latest agreed procedures. These reviews will document progress against the logframe and the value for money obtained from the programme. To ensure consistency, indicator data will be triangulated with other sources. Reviews will make recommendations for corrective actions where performance is lagging or for setting more ambitous targets for the same level of resources in areas where the programme is exceeding its targets. Where feasible, these reviews will be synchronized with the annual reviews of other DFID progammes designated for close collaboration with SUNMAP2.

The commercial case provides more information regarding the management of contract performance, including the use of independent audits, output or milestone based payments, and other contractual provisions.

Glossary

ACT	Artemisinin-based Combination Therapy
ACSM	Advocacy, Communication and Social Mobilisation
APR	Annual Programme Review
CM	Case Management
DALY	Disability Adjusted Life Year
DFID	Department for International Development
DFID-N	Department for International Development – Nigeria
DPSA	Delivering Procurement Services for Aid
FGN	Federal Government of Nigeria
FMoH	Federal Ministry of Health
GBP	Great British Pound
GFATM	Global Fund to Fight AIDS, Tuberculosis and Malaria
IEC	Information, Education and Communication
IPT	Intermittent Preventive Treatment
IRS	Indoor Residual Spraying
ITN	Insecticide Treated Net
LGA	Local Government Area
LiST	Lives Saved Tool
LLIN	Long Lasting Insecticidal Net
M4P	Making Markets work for the Poor
M&E	Monitoring & Evaluation
MDG	Millennium Development Goals
MNCH2	Maternal, Neonatal and Child Health Programme
MoH	Ministry of Health
NMCP	National Malaria Control Programme
PATHS 2	Partnership for Transforming Health Systems – Phase 2
PSAG	Public Sector Accountability and Governance Programme
RDT	Rapid Diagnostic Test
SDG	Sustainable Development Goals
SMoH	State Ministry of Health
SMC	Seasonal Malaria Chemoprevention
SMCP	State Malaria Control Programme
SP	Sulphadoxine pyrimethamine
SPARC	State Partnerships for Accountability, Responsiveness and Capability
SuNMaP	Support to National Malaria Programme
USD	United States Dollar
VfM	Value for Money

# ANNEX A: SUNMAP2 cost and benefit assumptions QUEST 5452476
# ANNEX B: SUNMAP2 draft logframe QUEST 5505981