Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Overseas Development Institute (ODI) Fellowship Scheme 2015-2020
Programme Value: £17,000,000		Review Date: March 2016
Programme Code: 203210	Start Date: 01/04/2015	End Date: / 31/03/2020

Summary of Programme Performance
Year	2013	2014	2015	2016
Programme Score	A	A+	A+	A
Risk Rating	Moderate	Moderate	Minor	Minor

Summary of progress and lessons learnt since last review
In 2015, DFID began a new phase of support to the ODI Fellowship Scheme, continuing a long-running partnership. In the first year of the new phase (2015-16), the programme has continued to meet its expected outputs and continues to provide good value for money. The scheme has met its target on getting Fellows into posts, and is exceeding its targets in relation to support provided to fellows and the contribution of Fellows to capacity building. The programme is also on track with its outcome indicators. / Building on the recommendations of the Project Completion Review of the 2012-2015 phase of support, the ODI has maintained its strong reputation and maintained the systems in place, and has continued to develop the new Statistics stream.

Summary of recommendations for the next year
Main recommendations: / Continue efforts to establish the statistics fellowship scheme and ensure quality postings are available. / Suggest ODI alter the Briefing Week moderately to provide greater focus on civil service skills, thereby ensuring better value for money and responding to feedback. ODI/DFID to discuss how this might be done. / Whilst it is not clear if a capacity building plan exists, ODI should continue the positive trend by giving greater attention to capacity-building at induction, and revisit the detailed recommendations made in the RFS. ODI to continue current capacity building efforts, including gathering feedback for lessons where possible. / Logframe/Survey: It is not always easy to link the logframe to the survey information provided e.g. no direct question exists for Indicator 2.1. Additionally, it is not easy to disaggregate between the statistician and economist streams, and this will become increasingly important as the statistics stream grows. This also applies at times to DFID and non-DFID funded post disaggregation. Finally, drawing lessons for comments is difficult as they are not grouped by category. It is therefore recommended that DFID/ODI work closely to refine the survey to: a) better reflect logframe indicators, and b) make comment information more accessible. / Additional recommendations: / (i) From Fellows and Supervisors: / Supplementation: ODI to investigate the costs, benefits and feasibility of adjusting supplementation to local cost of living (price purchase parity), based on feedback from Fellows / Facilitation of knowledge sharing: Both Fellows and supervisors have suggested that the opportunity to share knowledge and lesson learning would be useful. ODI to consider facilitating the initiation of two groups: one for Fellows, and one for supervisors at the start of each year. This could be done during the Briefing Week and/or by email. / Training/Technical support: Feedback from Fellows suggests that there is demand for some training/technical support from ODI. ODI and DFID should assess the range of options and value in providing a learning and development resource to Fellows during their appointment. / Fellow terms of reference: recommend to partner Governments that Fellow’s terms of reference include a small capacity building component, where both parties benefit. Fellows could consider a capacity self-assessment on particular areas they think can provide support on to colleagues. Fellows are junior staff and so this shouldn’t be too onerous, but forms good practice. / Whilst ODI try to ensure handover periods between Fellows, it is still cited by supervisors as an area for improvement. ODI should consider this going forward. / (ii) For DFID/ODI working: / DFID should work with ODI to formalise the process and deadlines for the information needed for Annual Reviews. Given the FS has been running for a long time with a fairly regular timetable, DFID and ODI should agree on the information needed for Reviews and ensure a timely process. / DFID/ODI to consider making an amendment to the logframe to better align with the theory of change by including output related to Fellows work, or other options. Applying a weighting to an additional output would then reduce the high weighting (80%) on the number of Fellows placed which currently doesn’t seem justified. The output could be measured via the completion survey.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717549.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5042338.xls

What support is the UK providing?
The Overseas Development Institute (ODI) Fellowship Scheme (FS) provides technical support to currently some 28 developing country governments and regional organisations through the recruitment and posting of economists and statisticians at the start of their careers each year to work as civil servants in developing country governments and regional organisations on 2-year postings. / The Fellowship Scheme is a partnership between the employing government overseas, ODI and donors and other agencies. Fellows work in a variety of institutions from Ministries of Finance to Public Investment Agencies. The countries currently covered by the scheme overall are: Djibouti; Ethiopia; Ghana; Guinea-Bissau; Lesotho; Liberia; Malawi; Mozambique; Namibia; Nigeria; Rwanda; Sierra Leone; Somaliland; South Africa; South Sudan; Swaziland; Uganda; Zambia; Zanzibar; Guyana; Haiti; India; Thailand; Solomon Islands; Timor Leste; Vanuatu; Pacific Regional (Secretariat of the Pacific Community). Fellows were recently pulled out of Burundi (political reasons), and reassigned from Madagascar (Fellows weren’t being used effectively). The intention is to return to both countries when conditions allow. / Under the current agreement, DFID funds up to 50 economists and 10 statisticians a year in low, lower middle income, or high poverty countries. Australia’s Department of Foreign Affairs and Trade (DFAT) funds most posts in the Pacific while the Gates Foundation funds up to five Financial Inclusion posts. / The UK Government has supported the ODI Fellowship Scheme almost since it began in the 1960s and remains the largest funder of the FS. Funding has been on a rolling basis with an understanding that DFID would give ODI adequate notice of a significant shift in our funding support, for ODI to manage the implications this would have for selecting and placing Fellows overseas. The current grant commits DFID to provide a 5-year Accountable Grant (AG) to the ODI to support the FS over the 5 financial years 2015/16-2019/20. The agreement is for total grant funding of up to £17,000,000. At the initiative of DFID, an amendment made in early 2014 confirmed agreement to add Statistics Fellows to the Scheme and to expand to providing support in further poor countries with capacity gaps.

What are the expected results?
The intended outcome is: / To provide skilled junior economists and statisticians to work in developing country governments and organisations that need them. Related indicators of this are: / Minimum of 100 (10 being statisticians) and maximum of 120 (20 being statisticians) Fellows in post each year as junior economists or statisticians (DFID-funded posts only); / 90% successful completion of two-year placements; / 75% of Fellows and employers consider ‘somewhat’ or ‘a lot’ of capacity building has been achieved. / The expected outputs to reach this and their corresponding indicators are: / Skilled junior economists and junior statisticians supplied to overseas governments in low-income and high-poverty countries. Measured by: / Number of starters each year: Economists 45/50 (min/max), and Statisticians 5/10 (min/max) / Skilled junior economists and statisticians gain and share valuable professional experience through their Fellowship posting. Measured by: / Fellows are effectively recruited and prepared for, then supported during, their posting: Fellows and employers are 85% satisfied, and 80% satisfied on FS management and admin efficiency. / Fellows contribute, where possible, to sustainable capacity building of colleagues in the government department they are placed in: Economists 70% Fellows and 50% employers agree, Statisticians 60% Fellows and 40% of employers / The overall impact of DFID’s support is, through achieving the above outputs and outcomes, is to increase the capacity and effectiveness of governments in developing countries and the international development community.

What is the context in which UK support is provided?
Global Context / Developing country governments often struggle to attract and retain junior technical staff, or face capacity gaps while letting their staff undertake further study or training, and the Fellowship Scheme helps by placing junior technical staff in those roles. Developing countries face multiple and complex decisions over the assessment of needs, policy and programme effectiveness and resource allocation, which economists and statisticians can contribute to through the technical skills they bring, in terms of good economic management for poverty reduction, and good data to make good decisions. / Whilst this context has changed little over the time of the FS, the countries in which Fellows have been placed have altered for several reasons: countries have developed sufficiently to no longer require Fellows, crises have forced the FS to cease operations there, to follow demand, or where governments are no longer willing to fund foreign nationals. As country governments have also developed, there has been an increase in the number of non-ministerial postings and this has been accelerated by the advent of the Statistics Stream. / ODI and DFID agreed to the introduction of a Statistics stream from 2014 to meet priority capacity gaps in that skill set in developing country governments. This has not impacted on the functioning of the Economics stream. / Annual Review Context / This is the first Annual Review of the current phase of support to the ODI Fellowship Scheme, which will run from 2015 to 2020. However, this is a continuation of support from a previous phase in 2012-2015, and decades of support. We refer back to the Project Completion Report for the previous phase (henceforth PCR), which was completed in 2015, to check on the progress of previous recommendations. DFID also carried out a Review of support to the Fellowship Scheme in 2012-2015 (henceforth RFS), which was completed in January 2015, which informed the design of the current phase and provided recommendations for the programme. / This Annual Review was carried out by DFID staff (including staff who are not engaged in the management of the programme, providing a semi-independent scrutiny). The review is based on management information and surveys completed by the ODI, as well as interviews of current fellows (to provide a sense check of the management data and allow more in depth discussions of any issues and ideas for improving the Scheme).

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual Outcome Assessment
Information is available on all of the outcome indicators for the programme, which are summarised below. Overall, the programme is on track on all three Outcome Indicators, showing that the programme has acceptable number of Fellows, achieved a high completion rate and that Fellows are engaging in capacity building activities during their Fellowship. / Outcome Indicator 1: Total number of DFID-Funded Fellows in post at end of financial year. Target for 2015/16: / Economists: min 90, max 100 / Statisticians: min 5, max 10 / At the end of 2015/16 91 DFID-funded Fellows were in post, 83 economists and 8 statisticians. Two economists dropped out due to extreme health reasons, which was beyond the control of the FS. The number of economists is therefore slightly below the target range, whilst the statisticians are on target. / Outcome Indicator 2: Completion rate (broadly defined, i.e. min 21 months in post including any evacuation) for DFID-funded Fellows due to complete in financial year. Target for 2015: 90% for economists and statisticians. / The completion rate for the most recent cohort of Fellows (2013-2015) was 91% (51 out of 56 fellows). This indicator is therefore on track. / Outcome indicator 3: Fellows and employers consider some capacity building has been achieved. Targets for 2015/16: 75% somewhat or a lot. / In post-completion questionnaires of the 2013-2015 Fellows, Fellows were asked “Would you say you managed to build capacity during your Fellowship posting?” 16.3% of Fellows responded “A lot”, 61.2% “some”, 22.5% “A little”, whilst none reported “None”. This gives a score of 77.5%, and therefore the outcome is on track.

Overall output score and description
The programme is on track on all of its outputs. Output Indicator 1 (number of starters) showed the total number of Fellows within the desired range. Output Indicators 2.1 and 2.2 (Fellows are recruited and supported, and Fellows contribute to capacity building) have exceeded their targets.

Key Lessons
The Fellowship Scheme continues to operate effectively and is meeting its targets. The recommendations of this review seek to continue the progress made and ensure quality in all aspects of the Scheme. / Interviews with current Fellows on the Scheme found that Fellows were generally very happy with the way the Scheme is run and the support that they receive from ODI. In particular, Fellows feel that when there are crises or issues that need to be dealt with, ODI’s response is timely and effective; showing a concerted effort by ODI as part of their pastoral care improvements. / Interviews with supervisors of current Fellows also confirmed that the Scheme is of benefit to their department and valued by the host Government.

Key actions
ODI should focus on maintaining the quality of the scheme and should continue their efforts to build up the Statistics stream, which continues to gradually grow.

Has the logframe been updated since the last review?
This is the first Annual Review of a new phase of funding to the ODI Fellowship Scheme. The logframe was updated alongside the Business Case (BC) for the new phase of support in 2015-2020. The changes included: / Outcome Indicator 3 was re-defined so that it can be measured accurately, rather than the previous indicator which was much less precisely defined. This is done using the post-Fellowship questionnaire which ODI have synced with the DFID logframe / An Indicator based on the proportion of FS posts in low and middle-income countries has been removed. ODI and DFID agreed that Fellows would not be placed in upper middle income countries. There is therefore no longer a need to make the distinction. / An indicator based on the number of starters with “minor” DFID funding has been removed. Originally the indicator was designed to discourage too many Fellows being placed in South Africa. As the point above describes, Fellows are being pulled out of South Africa so this indicator is no longer required.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	1. Skilled junior economists and junior statisticians supplied to overseas governments in low-income and high-poverty countries
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	80%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of starters each year	Economists: minimum 45, maximum 50 / Statisticians: minimum 5, maximum 10	Starters in 2015: / Economists: 44 / Statisticians: 7

Key Points
The number of Fellows in the economist stream starting in 2015 was very slightly below target: 44 rather than the proposed minimum of 45. For the statistics stream, there were 7 new starters in 2015, which is within the proposed range of 5-10. This difference of one Fellow fewer than specified in the economists stream is not of particular concern, given the focus of the programme has been on ensuring sufficient quality of the Fellowship postings and Fellows, rather than posting as many Fellows as possible. Furthermore, it is always difficult to predict the number of candidates who will drop out between the time they accept their offers (in March), and the time they are offered specific posts in specific countries (in June). In 2015, 12 economists and one statistician dropped out during this period before posts were finalised. The total number of starters in the 2015 FS is acceptable.

In terms of regions, the vast majority of DFID-funded Fellows are in Africa, with a minority based in the Caribbean, Pacific and Asia. It is important to note that no new Fellows were placed in upper middle income South Africa, while new Fellows were posted in low income Guinea-Bissau and Somaliland.

DFID-funded ODI FS starters in 2015 by region (economists and statisticians):

Summary of responses to issues raised in previous annual reviews (where relevant)
There were no concerns raised on this indicator in the PCR for the previous phase of support – ODI has been consistently meeting its targets for the number of fellows.

The RFS recommended that ODI “intensify efforts to build up the statistics Fellowship Scheme, reaching a new set of young professionals, and demonstrating the benefit of expanding the FS scheme into the statistics field. The expansion of the statistics scheme has shown steady growth from its slow start of two Fellows in the first year to seven in the second, and there is no danger of over-expansion. Given the statistics stream is still not as widely known as the economists (the economists stream has been running for decades and has built up a strong reputation), ODI should continue to raise awareness of the statistics stream and attract applications. There have been a healthy number of applicants for the 2016 start, and ODI are on track for another modest increase in statistics postings.

Recommendations

Continue efforts to establish the statistics fellowship scheme and ensure quality postings are available.

Output Title	2. Skilled junior economists and statisticians gain and share valuable professional experience through their Fellowship posting
Output number per LF			Output Score	A+
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	Yes (increase 10% due to removal of one output)

Indicator(s)	Milestones	Progress
2.1 Fellows are effectively recruited and prepared for, then supported during, their posting, as evidenced by employer and Fellow feedback	All Fellows: 85% satisfied	100% of Fellows sampled
	Employers: 85% satisfied	95% of employers
	Feedback on FS management and admin efficiency: 80% feedback from Fellows and employers is satisfied	95.9% of Fellows; and 100% of employers sampled
2.2 Fellows contribute, where possible, to sustainable capacity building of colleagues in the government department they are placed in.	Economists: / 70% Fellows and at least 50% employers consider some CB happened for local staff	77.5% of Fellows (100% of statisticians sampled); / 95% of employers
	Statisticians: / 60% Fellows and at least 40% employers consider some CB happened for local staff

Key Points
Overall both Fellows and employers felt that ODI effectively recruited, prepared, and supported Fellows during their posting, with 100% of Fellows and 95% of employers reporting satisfaction with ODI, which is a very positive result. The management and administration efficiency of the ODI FS was also ranked similarly as high, and the majority of related comments made highlighted the quick response time of ODI in both crises and administration issues. Responses overall were very positive e.g. 75.5% of Fellows reported ‘good’ or ‘very good’ when commenting on the ODI administration. It should be noted that accompanying the positive feedback on the running of the ODI FS, most Fellows and employers gave suggestions on how the FS could be improved. Lastly, whilst 49% of Fellows said that the briefing week prepared them well, 51% felt they were neither badly nor well prepared.

In terms of capacity building, 77.5% of Fellows felt they managed to build some or a lot of capacity during their fellowship, whilst 95% of employers felt some or a lot of capacity had been built. Of the statistician stream progress notes that were received in time for this AR, 100% contributed to capacity building, with one Fellow training over 100 people in Excel at a workshop. Whilst a small sample, this may indicate a particular effectiveness of the statistics stream at transferring some capacity.

Summary of responses to issues raised in previous annual reviews (where relevant)
Whilst the PCR had no specific recommendations, the RFS made several recommendations related to Output 2:

- Briefing Week: ‘There is a good justification to expand the briefing to cover issues that cannot be reasonable expected to have learned during a fellows studies, e.g. civil service skills, or areas of economics not well covered in university course, such as PFM’. Whilst PFM has been included in the Briefing Week, civil service skills have not well been covered. Based on feedback, Health Fellows receive special training on health economics which saves time in post. This requires travel and accommodation at York University. It is not clear why this particular sector should be given preference over others.
- Pastoral care: ‘give this area [pastoral care] priority, including monitoring feedback, learning lessons and ensuring they have a good understanding of all the main risks’. This will improve management of the FS scheme. ODI is continuing to improve this, with Country Strategy Notes, and as shown by the positive feedback received.
- Capacity Building: ‘The ODI FS team would benefit from developing a plan of action on increasing the profile of capacity building in the FS across the entire scheme’. The PCR found a 67% positive response to capacity building, compared with 77.5% in this AR indicating that the lessons from the RFS have been taken into consideration

Recommendations

Suggest ODI alter the Briefing Week moderately to provide greater focus on civil service skills, thereby ensuring better value for money and responding to feedback. ODI/DFID to discuss how this might be done.
- Whilst it is not clear if a capacity building plan exists, ODI should continue the positive trend by giving greater attention to capacity-building at induction, and revisit the detailed recommendations made in the RFS. ODI to continue current capacity building efforts, including gathering feedback for lessons where possible.
- Logframe/Survey: It is not always easy to link the logframe to the survey information provided e.g. no direct question exists for Indicator 2.1. Additionally, it is not easy to disaggregate between the statistician and economist streams, and this will become increasingly important as the statistics stream grows. This also applies at times to DFID and non-DFID funded post disaggregation. Finally, drawing lessons for comments is difficult as they are not grouped by category. It is therefore recommended that DFID/ODI work closely to refine the survey to: a) better reflect logframe indicators, and b) make comment information more accessible.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Costs and Cost Drivers / There are two main parts to the ODI FS budget: the central administration costs (17.7%) and the ‘reimbursable’ costs of Fellows’ (82.3%). Of the ‘reimbursable’ costs, almost all are attributed to salary supplementation and rent (81%), followed by the end of fellowship bonus, travel and medical cover. The main administrative costs are staff costs and office space and support systems, followed by placement visits. / The key factor each year for the ‘reimbursable’ cost is the actual postings made, which are known in Q2 of each FY. Therefore the demand for Fellows, and location of that demand are important cost drivers: DFID funded Fellows are concentrated in LDCs, which over time will increasingly be dominated by fragile and conflict states as countries exit poverty. This will drive up the average cost per Fellow through increased insurance premiums, inability of governments to contribute to funding Fellows, more expensive accommodation due to scarcity of safe housing, and security. This is increasingly the case, with recent Fellows placed in Guinea-Bissau, South Sudan, Somaliland, and Haiti. / Additional cost drivers worth mentioning include exchange rate volatility, medical care/emergencies, and in the past have also included wage rate inflation expectations, and changes in staffing. To mitigate exchange rate risk, the ODI FS now revises exchange rates on a monthly basis as opposed to annually. A rare costly serious accident was mitigated through contingency forecasting. Finally, access to private medical clinics was approved for Fellows in South Sudan, Sierra Leone, and Liberia, which was only a minor cost and a requirement and therefore acceptable. / For details on performance of the FS against the original timescale, please refer to Section F.

VfM performance compared to the original VfM proposition in the business case
VFM has been met this year against the expectations set in the business case / The FS overall has met the expected scale set out in the logframe, and has exceeded expectations in terms of Fellow satisfaction and capacity building that has taken place. Support from DFAT in 2013, and the Gates Foundation in 2015 has reduced the financial burden on DFID. The statistician stream is growing well, and early indicators suggest it has slightly higher capacity building impact than the economist fast stream. The country selection process and pastoral care have improved with Country Strategy Notes and risk assessments taking place. Of the employers interviewed and surveyed, almost all were satisfied with Fellows, and their outputs against cost. / The average cost of a Fellow under the DFID grant in 2015-16 was £38,750, which is just below the average cost for the past three years, as set out in the BC: £39,000. The represents good value for money when you consider the cost a consultant per year would be around £127,500 per year (£500 x 225 working days). The average cost should continue to be monitored closely as it is expected to increase slightly over time. The range of the average costs is roughly £43k (£70k in South Sudan, and £27k in Djibouti), which reflects the additional costs of working in a fragile and conflict affected state, against a state with a safe environment and can afford good local salaries and housing. / ODI seeks good VFM through its travel policy of purchasing economy-class charity fares; carefully balancing good-value housing with safety concerns; and rigorously reviews rent and supplementation requirements for each post annually. Whilst the current system is transparent and simple, one Fellow interviewed suggested that wages could be better adjusted to reflect the local cost of living e.g. the cost of living in Nigeria is much higher than in Rwanda. / ODI ensures efficiency of operations through hitting multiple objectives during the annual country visits i.e. to review country suitability, Fellows and employer satisfaction, and pastoral care. The briefing session has seen improvements, but costs have also risen, and will need to be monitored carefully. / The ODI FS prioritises low-income and high-poverty countries, and is reducing its presence in MICs in response to this e.g. through the upcoming closure of the South Africa presence. To ensure quality posts are made, the FS consults with employers, Fellows and development partners in-country. The management team stated in March 2016, that alliances are being formed with development partners in-country. This is welcome, to 1) improve the allocation of Fellows to quality posts 2) improve the information they have on FS countries and 3) improve the access to information and networks for Fellows in post. On the other hand, Fellows interviewed sensed that there was an incentive for the FS to place Fellows first, and that quality sometimes came second. There is an element of luck in how posts turn out, and it may be difficult for the ODI FS to increase quality controls without increasing costs significantly. The nature of the work means that the quality of posts can vary greatly over time e.g. due to frequent changes in supervisors. Lastly, there is a renewed focus on capacity building as shown by survey questionnaires, although the Briefing Week agenda for 2015 did not feature a capacity building component so more focus placed here would benefit the scheme.

Assessment of whether the programme continues to represent value for money
The FS is considered to represent good VFM for DFID and for employing governments. / The Theory of Change still holds, with Fellows assisting governments to make better policy decisions, and builds capacity to do so, helping to reduce poverty. The FS has delivered on expectations at good value for money.

Quality of financial management
The forecasts made seem to be in-line with the cost driver factors mentioned above, such as increased presence in fragile states. Reporting of financial information was done in a clear and transparent manner. If any cases of fraud are found, this would be grounds for ending DFID support. / Is the project on track against the original financial forecasts? / Total spend in 2015/16 is expected to be £3,526,321 (as spend for the current month of March is forecasted), against a forecast of £3,219,972, giving a variance of +9.5%. This variance is high compared with current DFID practices, however relative to previous years of the FS this marks an improvement, suggesting the addition of an additional staff member in 2014 has been of value. The main reasons for the variance are: / Operations (+10%): (i) +£0.25m supplementation (£2.1m to £2.35m), (ii) +£15k briefing week (£15k to £30k), and (iii) +£19k travel (£80k to £99k). / Management and Administration (+6%): (i) +£16k office space, ICT and HR (£229k to £245k), and (ii) +£9k publicity and printing (£6k to £15k). On a plus note the costs of recruitment have fallen by over 50%. / ODI will need to continue to tightly manage budgets to come in on budget at the end of the 5 year period. / ODI shared its financial forecast in March 2016 for the 5 year DFID grant set out in the BC (2015-2020), and forecasted spend was: £3.3m (2016-17), £3.4m (2017-18), £3.5m (2018-19), and £3.6m (2019-2020), making a total of £16.96m over the grant period. The gradual increase in spend each year is reflected in a moderate increase in operation costs each year, and minor increases in management and administration costs.

Date of last narrative financial report	August 2015
Date of last audited annual statement	31st March 2015

## E: RISK (1/2 page)

Overall risk rating: Low

Overview of programme risk
The Fellowship Scheme is a tried and tested approach that has been running for many years with established relationships with its partners in employing Governments. / A highlighted risk in the BC was the volatile and uncertain living and working conditions of the Fellows. Evidence presented so far suggests that pastoral care from ODI is good, and that ODI have responded well to any issues faced by Fellows in-country. According to the management team, in the last year, the ODI FS has increased its response to risk: the ODI FS now makes use of a full-time security manager in ODI (since October 2015), develops risk assessments per country that have to be signed off by Fellows, and have had a fourth member of the team for over two years to cope with moderate expansion. / Regarding the risks of expansion of the Scheme, there is no worry at the moment of the Scheme expanding beyond its means. The expansion into statistics is building up gradually, minimising risks of over-expansion. / Fiduciary risk continues to be assessed as low. Purchases and payments are managed by ODI (for example, for travel, insurance, supplementation and housing), and feedback suggests that these are managed effectively. / The climate and environment risk of the programme is judged to be low.
Outstanding actions from risk assessment
None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The annual recruitment and placement cycle is well established and is on-track to provide junior economists and statisticians to governments and organisations needing capacity support. / The Fellowship Teams Annual Timetable is currently as follows: / November - December ODI accepts applications for the Fellowship Scheme / December Governments requested to indicate their likely requirements for Fellows. / Mid December Closing date for receipt of applications. / Late January Short-listed applicants invited to attend selection board. / Early February Referees contacted for short-listed applicants / Mid-February Selection board and provisional offers of Fellowships. / March - June Placement tours and Pastoral/ Progress visits by ODI team / May - June Requests submitted for new Fellows from partner governments; future job information to current Fellows. / June Fellows informed of results of post allocations and notification of availability sent to governments. / July Briefing session to prepare new Fellows for their posts. / August - October Completion of postings/ Commencement of next postings.

Performance of partnership (s)
Australia’s DFAT is another partner providing support to the FS, and currently funds 16 posts (Papua New Guinea, Vanuatu, Fiji, Solomon Islands, and Timor-Leste). DFAT is therefore a welcome and trusted partner, and broadens the financial base. / In addition to Australia, the Gates Foundation has also started a ‘financial inclusion’ stream pilot, and successfully placed two Fellows in 2015: one in the Reserve Bank of India, and one in the Central Bank of Nigeria. A third Fellow, placed in Bangladesh, was pulled out for safety reasons. The Gates Foundation is hoping to place at least three more Fellows this year. As with the statistics stream, it will take time to build up the stream, and hopefully the Gates Foundation can build on the experience of the long established economist stream and new statistician stream. / Employing governments continue to be the largest group of partners and stakeholders in the FS. They provide feedback during placement tours and other communication such as the new End of Fellowship Questionnaire for Supervisors (2013-2015), and requests channelled via DFID country teams. Feedback suggests that they are satisfied with the service and support provided by the FS, and contribution of Fellows. / Recommendation: / ODI could respond to, and consider, suggestions made by Supervisors in the End of Fellowship Questionnaire for Supervisors could be considered. The main ones include: allowing for greater overlap between Fellows, allowing for a third year, training for Fellows on culture/adaptability, and Fellows being allowed to interview shortlist of candidates for their position. This is not to say any should be implemented.

Asset monitoring and control
The ODI FS has no substantial assets to speak of as it places and supports Fellows. Office space is rented from ODI itself.

G: CONDITIONALITY (½ page)

Update on Partnership Principles (if relevant)
Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
There is no independent evaluation of the programme. Monitoring and evaluation is conducted by DFID using the information provided by ODI and through evidence collected by DFID staff. / Alongside Annual Review, a more thorough review of the ODI FS was completed in January 2015, to cover the period 2012-1015. This included an analysis of previous reviews and interviews with Fellows, ODI staff and DFID staff. This review helped to inform the design of the new phase of the programme (2015-2020).

Monitoring progress throughout the review period
Data collected by ODI has improved a lot over recent years and is sufficient to track progress against the logframe. DFID also work closely with ODI and are informed of any developments at the scheme. Direct interviews with Fellows have helped to provide an additional check on progress.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process