## Logframe
Building a Reliable Investment Climate in Kenya (BRICK) Log Frame- Updated December, 2015
IMPACT | Impact Indicator 1 |  | 2012 | 2013 | 2014 | 2015-12-01 | 2016-12-01 | Assumptions
An expanded private sector, which creates more jobs particularly for the poor, through improvements in the business environment | Poverty headcount rate at official poverty line (%) | Planned
|  | Achieved | 46% 2005 | 46% 2005
Source: KIHBS 2005, KIHBS 2015 and annual household surveys
| Impact Indicator 2 |  | 2012 | 2013 | 2014 | 2015 | 2016
| Annual GDP growth rate (%) | Planned
|  | Achieved | 4.6% | 4.7% | 5.4% | 6.0(Projected)
Source: KNBS, Economic Survey, World Bank
| Impact Indicator 3 |  | 2012 | 2013 | 2014 | 2015 | 2016
| Exports (% GDP) | Planned
|  | Achieved | 27.3
Source: World Development Indicators
| Impact Indicator 4 |  | 2012 | 2013 | 2014 | 2015 | 2016
| Private sector gross fixed capital formation (% GDP) | Planned
|  | Achieved | 14 2009
Source: World Development Indicators
OUTCOME | Outcome Indicator 1 (regulatory burden) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016 | Assumptions
A transformed business environment with lower regulatory burdens, in a more competitive economy with improved infrastructure | Compliance Cost Savings to private sector (direct and indirect) | Planned |  | 0 | 0 | 0 | 0 | (1) That the national government remains committeed to business regulatory reform. (2) County governments, do not undertake revenue raising measures that restrict or raise the cost of business operations. (3) Business take up the opportunities made available by reforms and use these to increase growth, reduce prices and employ more people.
|  | Achieved | 0 | 0 | 0 | 0 | 0
Source: DB Reports, MOIED reports and WBG records
Subnational and national authorities; primary data collection. (WBG target $87m by 2019: regulatory reform $50m; competition policy, 10m; trade logistics $22m and tax $5m). CCS for RR to be recalculated as Nairobi County didn't pick up as planned.
| Outcome Indicator 2 (Regulatory burden) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of investment climate Doing Business reforms implemented at national (N) and county levels (C) (cumulative) | Planned |  | N:0 C:0 | N:1 C:0 | N:3 C:10 | N:4 C:11
|  | Achieved | N:0 C:0 | N:0 C:0 |  | N:3 C:0
Source: IFC National & Sub-national DB reports, MOIED reports
N reforms are: Getting electricity, Registering property, Starting a business & Getting credit. C reforms will be known after SNDB study
| Outcome Indicator 3 (private investment) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Private sector investment generated ($m, cumulative) | Planned |  | 0 | 0 | 0 | $30m
|  | Achieved | 0 | 0 | 0 | 0
Source: KNBS, Treasury, ERC, KenInvest, CBK, commercial banks, MoIED
(WBG target $220m by 2019): PPP $100m; agribusiness $10m; $60m renewable energy; SEZs $50m). $30m is across all the sectors.
| Outcome Indicator 4 (competitiveness) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of sectors with at least one sector-specific reform to the regulatory framework or business practices | Planned |  | 0 | 0 | 1 | 4
|  | Achieved | 0 | 0 | 0 | 1
Source: CNBS, KICP M&E report
Improvements to be judged against private sector investments, increased competitiveness and cost savings from energy audits in agribusiness, leather, textile, furniture, WRS, seeds & Pyrethrum.
| Outcome Indicator 5 (demand for reform) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of PSD champions created in government (disaggregated by gender) | Planned |  | 0 | 0 | M:0 F:0 | 10
|  | Achieved | 0 | 0 | 0 | M:0 F:0 | M: F:
Source: KICP report, project documents & relevant GoK agencies
To be judged against behavioural indicators.
| Outcome Indicator 6 (Business Taxation) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Increase in revenue generated from tax | Planned |  | 0 | 0 | 0 | $10 million
|  | Achieved | 0 | 0 | 0 | 0
Source: KICP M&E report, KRA records
Revenue to be generated from transfer pricing, tax audits
| Outcome Indicator 7 (demand for reform) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Proportion of KEPSA's financial sustainability target achieved (%) | Planned |  | n/a | n/a | 50% | 70%
|  | Achieved | n/a | n/a | n/a
|  |  | Source: KEPSA reports (financial sustainability target agreed in 2014 |  |  |  |  | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | Low
INPUTS (HR) | DFID (FTEs)
Output 1 | Output Indicator 1.1 (National regulatory reform) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016 | Assumptions
Reformed regulatory environment | Capacity score of the Doing Business Unit of MoIED. | Planned |  | n/a | 1 | 3 | 6 | (1) That the national government remains committed to business regulatory reform. (2) County governments, do not undertake revenue raising measures that restrict or raise the cost of business operations. (3) Business take up the opportunities made available by reforms and use these to increase growth, reduce prices and employ more people.
|  | Achieved | n/a | n/a | 0 | 3
Source: IFC & MOIED Reports
Capacity score to be based on the following criteria: Mandate & organizational chart agreed, suitable staff in place, operational procedures agreed, staff trained, staff gained experience, lessons learned used to improve services, DB unit coordinating effectively with stakeholders, budget resources met & DB Unit headed by a reform champion.
| Output Indicator 1.2 (County regulatory reform) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of web-based regulatory portals developed and fully transactional on Construction Permits (CP) Single Business Permits (BP),Investment Portals (IP) and e-citizen portal (e-CP) | Planned |  | CP:0 BP:0 | CP:0 BP:0 | CP:2 BP:2 IP:1 | CP:2 BP:3 IP:2
|  | Achieved | CP:0 BP:0 | CP:0 BP:0 | CP:0 BP:0 | CP:2 BP:2 IP:1 e-CP:1
Source: County regulatory authorities, KICP-II project documents
CP=Mombasa, Kisumu, Kiambu;SBP=Nyeri, Mombasa, Kisumu;IP=Machakos, Nyeri, e-CP=1
| Output Indicator 1.3 (County regulatory reform) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of county officers satisfactorily trained (disaggregated by gender) | Planned |  | 0 | 0 | 85 | 150
|  | Achieved | 0 | 0 | 0 | T:78 M:48 F:30 | M: F:
Source:IFC reports, Sub national reports
Number of county officers trained who report being 'satisfied' or 'very satisfied' in training evaluation forms. T: total number, M: Male, F: Female
| Output Indicator 1.4 (Business Taxation) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of reform memoranda drafted | Planned |  | 0 | 0 | 0 | 2
|  | Achieved | 0 | 0 | 0 | 0
Source: IFC reports, KRA, National authorities
Includes reform memoranda drafted and adopted.
| Output Indicator 1.5 (Trade Logistics) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Percentage of transactions of top 15 government agencies using the KNESWS for permit application | Planned |  | 0 | 0 | 70 | 70
|  | Achieved | 0 | 0 |  | 100
Source: KenTrade, The National treasury, Trade facilitation agencies
| Output Indicator 1.6 (Investment Policy) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of policies recommended for improvement or elimination | Planned |  |  | 0 | 0 | 3
|  | Achieved | n/a | n/a | 0 | 0
Source:GoK documents, Keninvest, KICP-II reports
Policies on 3 areas; entry, incentives and protection. They include; setting up companies, work permits, capital requirements
| Output Indicator 1.7 (Whole Output) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance. | Planned |  | n/a | 70% | 70% | 70%
|  | Achieved | n/a | n/a
|  | Source:DFID interviews on MOIED, County governments, Kentrade | [5 empty] | RISK RATING
IMPACT WEIGHTING (30%) |  | DFID interviews with counterparts as part of Annual Review. Rating scale of Very Dissatisfied, Dissatisfied, Satisfied, Very Satisfied. | [5 empty] | Low
| DFID (£) |  | Govt (£) | Other (£) |  | Total (£)
INPUTS (HR) | DFID (FTEs)
Output 2: | Output Indicator 2.1 (Manufacturing) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016 | Assumptions
Effective competition | Number of industrial sector action plans that meet quality criteria and are adopted by GoK (cumulative) | Planned |  | 0 | 0 | 3 | 3 | 1) CAK becomes fully operational and capable of delivering its mandate and independence in terms of fostering effective competition oversight, nationally and in all sectors. (2) Gains from new competition practices trickle down to firms, consumers and employees in key sectors. (3) crucial competition related reforms and changes to laws are not prolonged or blocked by bureaucracy or self serving political interests.
|  | Achieved | 0 | 0 | 0 | 3
Source:IFC reports, MOIED, KLDC
Quality criteria to be evidence-based through WB peer review; practical with concrete actions and timelines and must incorporate analysis of risks. The action plans are on textiles, garments, furniture and leather.
| Output Indicator 2.2 (Tourism) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of short-term tourism initiatives completed (cumulative) | Planned |  | 0 | 1 | 1 | 1
|  | Achieved | 0 | 0 | 0 | 1
Source:MoEACT,MOIED
Tourism online directory and Tourism contribution macro-economic analysis
| Output Indicator 2.3 (Agribusiness) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of laws and regulations drafted to support agribusiness (cumulative) | Planned |  | 0 | 2 | 2 | 4
|  | Achieved | 0 | 0 | 2 | 3
Source: MOAL& FD, EAGC
WRS entails 3 regulations to be determined after enactment. Seed regulations include: National performance trials, Plant breeders' rights and seeds.
| Output Indicator 2.4 (Seed Reform and WRS) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of farmers reached (disaggregated by Gender) | Planned |  | 0 | 0 | 0 | 5000
|  | Achieved | 0 | 0 | 0 | T:2000 F:654 M:1,346
Source: MOAL& FD, Seed Companies, WRS impact study
| Output Indicator 2.6 (Competition Policy) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of laws and regulations drafted to increase market competition (cumulative) | Planned |  | 0 | 2 | 5 | 6
|  | Achieved | 0 | 0 | 2 | 4
Source: Competition Authority of Kenya
Guidelines generated: mergers, exemptions, restrictive practices and unwarranted concentration of economic power.
| Output Indicator 2.7 (Whole Output) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance (MoIED, MoEAACT, MoA, CAK) | Planned |  | n/a | Satisfied | Satisfied | Satisfied
|  | Achieved | n/a | n/a
IMPACT WEIGHTING (%) |  | Source: DFID interviews | [5 empty] | RISK RATING
30% |  | DFID interviews with counterparts as part of Annual Review. Rating scale of Very Dissatisfied, Dissatisfied, Satisfied, Very Satisfied. | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£)
INPUTS (HR) | DFID (FTEs)
Output 3 | Output Indicator 3.1 (PPPs) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016 | Assumptions
Effective environment for public private partnerships | Number of PPP regulations (R) and Fiscal Commitment and Contingent Liability (FCCL) frameworks (F) drafted through adequate consultation (cumulative) | Planned |  | R:0 F:0 | R:1 F:0 | R:2 F:1 | R:2 F:1 | (1) Essential PPP bill is enacted to law to augment weak regulations in place; (2) Operationalisation of PPP regulations and supporting procedures and structures in not delayed. (3) Specific PPP transactions are carried through to close within agreed timetable and costs. (4) Benefits from private sector participation in infrastructure is felt by firms, and passed to consumers and households
|  | Achieved | R:0 F:0 | R:0 F:0 | R:1 F:0 | R:2 F:1
Source: PPP Unit, National treasury
Final FCCL guidelines approved by PPP committee,PPP regulations drafted
| Output Indicator 3.2 (PPPs) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of GoK officials satisfactorily trained in the PPP Unit (disaggregated by gender) | Planned |  | 0 | 4 | 14 | 14
|  | Achieved | 0 | 0 |  | 14
Source: PPP Unit, National treasury
Number of county officers trained who report being 'satisfied' or 'very satisfied' in training evaluation forms.
| Output Indicator 3.3 (PPPs) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of PPP transaction feasibility studies at national (N) and county (C) level completed and approved by PPP Committee | Planned |  | N:0 C:0 | N:0 C:0 | N:4 C:0 | N:4 C:3
|  | Achieved | N:0 C:0 | N:0 C:0 | N:0 C:0 | N:4 C:0
Source:PPP Unit, National Treasury
Transaction feasibility studies included: Mombasa-Nairobi road, Nairobi-Nakuru highway, Nairobi-Thika road and the 2nd Nyali Bridge.
| Output Indicator 3.4 (PPPs) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of project concept notes for County PPPs finalized and approved by PPP committee | Planned |  | 0 | 0 | 5 | 7
|  | Achieved | 0 | 0 | 0
Source:PPP Unit, National Treasury, County governments
PPP act and PPP regulations require that PPP concept notes are developed and submitted to PPP committee for approval.
Output Indicator 3.5 (Renewable Energy)
| Number of laws, regulations and e-portals drafted to support renewable energy (cumulative) | Planned |  | 1 | 3 | 3 | 0
|  | Achieved | 0 | 0 | 1
Source: ERC
ERC e-portal supported, up and running
| Output Indicator 3.6 (SEZs) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of laws (L), regulations (R), site feasibility reports (F), market demand reports (M), developer requests for proposals (D) and investment targeting strategies (I) drafted to support investments in SEZs (cumulative) | Planned |  | L:0 R:0 F:0 M:0 D:0 I:0 | L:0 R:0 F:0 M:0 D:0 I:0 | L:1 R:0 F:0 M:0 D:0 I:0 | L:1 R:3 F:2 M:2 D:1 I:1
|  | Achieved | L:0 R:0 F:0 M:0 D:0 I:0 | L:0 R:0 F:0 M:0 D:0 I:0 | L:0 R:0 F:0 M:0 D:0 I:0 | L:1 R:0 F:0 M:0 D:0 I:0
Source: SEZ Authority, Keninvest
SEZ regulations subjected to stakeholder review
| Output Indicator 3.7 (SEZs) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Capacity score of the SEZ Authority. | Planned |  | 0 | 0 | 1 | 4
|  | Achieved | 0 | 0 | 0 | 0
Source: SEZ Authority, Keninvest
Capacity score to be measured by: organisational structure and mgt framework; regulatory strategy; capacity assessment; training curriculum and materials; key technical staff have gained experience in applying procedures to deliver services.
| Output Indicator 3.8 (Whole Output) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance. | Planned |  | n/a | Satisfied | Satisfied | Satisfied
|  | Achieved | n/a | n/a | n/a
|  | Source: PPP unit, National treasury, ERC, Keninvest, SEZ authority | [5 empty] | RISK RATING
IMPACT WEIGHTING (%) |  | DFID interviews with counterparts as part of Annual Review. Rating scale of Very Dissatisfied, Dissatisfied, Satisfied, Very Satisfied. | [5 empty] | Medium
30% | DFID (£) |  | Govt (£) | Other (£) |  | Total (£)
INPUTS (£)
INPUTS (HR) | DFID (FTEs)
Output 4 | Output Indicator 4.1 (PSD Champions) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016 | Assumptions
Strengthened demand and evidence base for investment climate reform | Number of GoK officials satisfactorily trained on private sector development (disaggregated by gender) | Planned |  | 0 | 0 | 0 | 10 | (1) PPP bill is enacted to law; (2) Operationalisation of PPP regulations are not delayed. (3) Specific PPP transactions are carried through to close within agreed times & costs. (4) Benefits from private sector participation in infrastructure is felt by firms & passed to consumers and households
|  | Achieved | 0 | 0 | n/a | M:0 F:0
Source: GoK documents, KICP-II project report
Number of GoK officials trained who report being 'satisfied' or 'very satisfied' in training evaluation forms by KICP-II components.
| Output Indicator 4.2 (KEPSA) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Extent that a Change Management Plan is drafted and implemented to help make KEPSA 'fit for purpose' | Planned |  |  | Change Mgt Plan drafted to make KEPSA fit for purpose | Plan approved by KEPSA Board & at least 50% implemented | Plan at least 70% implemented
|  | Achieved | n/a | n/a
Source: KEPSA project reports, KEPSA Board
|  |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Output Indicator 4.3 (Private Sector Consultation) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of BRICK components for which private sector inputs have been received through adequate consultation | Planned |  | n/a | n/a | 7 | 9
|  | Achieved | n/a | n/a | n/a | 7
Source: KICP-II project documents
Evidence: Formal letters with feedback, email correspondence, minutes of meetings, reports on stakeholder consultations & list of attendees at workshops.
| Output Indicator 4.4 (Investment Climate Diagnostics) |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Target 2016
| Number of Investment Climate reports produced (P), formally launched (L) and rated as Satisfactory on average by targeted GoK agencies (S) | Planned |  | P:0 L:0 S:n/a | P:2 L:1 S:n/a | P:7 L:4 S:4 | P:9 L:5 S:6
|  | Achieved | P:0 L:0 S:n/a | P:0 L:0 S:n/a | P:2 L:1 | P:7 L:4 S:4
Source: P&L from BRICK monitoring reports. S from DFID interviews with counterparts as part of Annual Review
IMPACT WEIGHTING (%)10 |  | Rating scale of Very Dissatisfied, Dissatisfied, Satisfied, Very Satisfied. If the counterpart is not aware of the report it will be scored as Dissatisfied.
10% | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | RISK RATING
INPUTS (£) | [7 empty] | Low
INPUTS (HR) | DFID (FTEs)

## Output weighting
Output Weighting Calculation
Component | Original Budget | Extended Budget | Total Budget | DFID Output | Comment
National regulatory reform | 335293 | 0 | 335293 | 1
Subnational regulatory reform | 2404067 | 0 | 2404067 | 1
Trade logistics | 1533887 | 300000 | 1833887 | 1
Manufacturing, tourism & innovation | 1216760 | 400000 | 1616760 | 2
Agribusiness | 2122479 | 0 | 2122479 | 2
Competition Policy | 1002905 | 0 | 1002905 | 2
PPP | 1729321 | 1500000 | 3229321 | 3
SEZ | 609774 | 900000 | 1509774 | 3
Renewable energy | 794554 | 0 | 794554 | 3
KEPSA | 750000 | 1462500 | 2212500 | 4
PSD champions | 0 | 1000000 | 1000000 | 4
Investment diagnostics | 199788 |  | 199788 | 4
Total Programme Cost | 12698828 | 5562500 | 18261328
c£ | 8465885.3333 | 3708333.3333 | 12174218.6667
Output | Output Budget | % Total Prog Cost | Weighting
Total Output 1 | 4573247 | 25.04% | 30
Total Output 2 | 4742144 | 25.97% | 30
Total Output 3 | 5533649 | 30.3% | 30
Total Output 4 | 3412288 | 18.69% | 10