Sub-National Governance (SNG) Programme, DFID Pakistan / Logframe / Revision date: 25 August 2015
IMPACT	Impact Indicator 1		Baseline / (March 2013)	Milestone 1 (March 2014)	Milestone 2 / (March 2015)	Milestone 3 / (March 2016)	Target / (Sept 2017)
More stable democracy in Pakistan	Government Effectiveness / Government Control of Corruption	Planned	a) -0.82 / b) -1.00	Data not available	a) -0.79 / b) -0.95	Data not available	a) -0.77 / b) -0.80
		Achieved		Data not available		Data not available
		Source: World Bank Institute Worldwide Governance Indicators
	Impact Indicator 2		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (March 2015)	Milestone 3 / (March 2016)	Target / (Sept 2017)
	Government Capability	Planned	3.81	Data not available	3.85	Data not available	3.89
		Achieved		Data not available		Data not available
		Source: Bertelsmann Transformation Index
OUTCOME	Outcome Indicator 1		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (March 2015)	Milestone 3 / (March 2016)	Target / (Sept 2017)	Assumptions
Poor people in Punjab and Khyber Pakhtunkhwa report that services are better meeting their needs	Household satisfaction with basic health and education services[1]	Planned for Punjab	a) Basic Health Unit = 29% / b) Schools = 63%	Data not available	a) = 31% / b) = 66%	Data not available	a) = 39% / b) = 73%	Administration has political commitment and capacity to pilot and adopt reforms. / Pilot districts participate in governance reforms to improve health and education services. / Raising the standard of public services improves government legitimacy by increasing trust and confidence in government and contributes to stability. / Government's spending is effective in targeting service delivery gaps. / Conflict does not constrain government reform impact or SNG engagement. / Security-related activities do not reduce government funding available for other public services. / Programme risk matrix and mitigations report awareness of conflict sensitivity.
		Achieved
		Planned for Khyber Pakhtunkhwa	a) Basic Health Unit = 35% / b) Schools = 65%	Data not available	a) = 38% / b) = 68%	Data not available	a) = 45% / b) = 74%
		Achieved
		Source: Pakistan, Social and Living Standards Measurement Survey (PSLM)[2].
	Outcome Indicator 2		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (March 2015)	Milestone 3 / (March 2016)	Target / (Sept 2017)
	Access to improved health and education services:[3] / Immunisation coverage for children below five years of age / Net enrolment rate (girls in primary education)	Planned for Punjab	a) 65% (PDHS) / b) 73%	a) 57% (MICS) / b) 71%	a) 72% (DFID, Nelson) / b) 74%	a) 73% / b) 76%	a) 75% / b) 77%
		Achieved
		Planned for Khyber Pakhtunkhwa	a) 57% / b) 75%	a) 59% / b) 72%	a) 60% / b) 77%	a) 61% / b) 78%	a) 62% / b) 80%
		Achieved		N/A
		Sources: / Punjab: Pakistan Education Statistics, National Education Management Information Systems (NEMIS), DFID/Nelson Bi-Annual EPI Coverage Survey / KP: Education Management Information System (EMIS), Extended Programme on Immunisation (EPI)
INPUTS (£)	DFID (£)	Govt (£)		Other (£)	Total (£)	DFID SHARE (%)
	£ 38,128,120	N/A		N/A	£ 38,128,120	100%
INPUTS (HR)	DFID (FTEs)
	2.2	0.3 x A1 Team leader, 0.7 X A2 Governance Adviser, 0.2 X A2L Economist, 0.5 X A2L Programme Manager, 0.5 X B2 Programme Officer
[1] This indicator captures government and private sector facilities for education (primary, middle, and high), and basic health care.
[2] Assumes government continues to carry out PSLM surveys in districts on alternate years, and SNG districts are included in the surveys. PSLM has changed the denominator for this indicator to include only individuals using services (rather than all respondents). It is therefore a partial measure, but is retained as an indicator for household satisfaction with services.
[3] Indicator and milestones revised August 2015 in response to a change in available data sources.

OUTPUT 1 / (Impact Weighting 30%)	Output Indicator 1.1		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (March 2015)	Milestone 3 / (March 2016)	Target / (Sept 2017)	Assumptions
Decisions by sub-national governments are based on robust evidence	District budgets based on evidence of people’s needs	Planned for Punjab	No population based assessment of needs	2 needs assessments done (one per district) with a focus on women and girls	6 districts have budget proposals based on evidence including needs assessments	Evidence-based lobbying effective in changing budget allocations, including needs of women, girls and marginalized groups in 3 districts	Evidence-based lobbying effective in changing budget allocations, including needs of women, girls and marginalized groups in 6 districts	Administration is responsive to political and community demands. / Local and provincial politicians welcome assistance that helps them connect better to citizens in order to bring about policy changes. / Governments adopt successful pilots without DFID funding. / Increased community involvement in setting local spending priorities. / Government has funding for operationalisation of GIS. / Monitoring and evaluation arrangements are robust and feasible to gauge numbers of beneficiaries. / Federal GIS legislation does not prevent district level GIS activity. / Local government elections are held, with funds transferred to districts for planning, budgeting and monitoring.
		Achieved		Achieved	Achieved: All 6 districts have budget proposal based upon needs assessments
		Planned for Khyber Pakhtunkhwa	No population based assessment of needs	2 needs assessments done (one per district) with a focus on women and girls	6 districts have budget proposals based on evidence including needs assessments	Evidence based lobbying - with a focus on the needs of women, girls and marginalised groups - results in institutionalizing need based planning and budgeting in 3 districts	Evidence based lobbying - with a focus on the needs of women, girls and marginalised groups - results in institutionalizing need based planning and budgeting in 6 districts
		Achieved		Achieved	Achieved: All 6 districts have budget proposal based upon needs assessments
		Source: Observation of committee meetings and analysis of records; budget strategy papers, Aawaz programme data including Policy Analysis Research and Results (PARR)

Output Indicator 1.2		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (March 2015)	Milestone 3 / (March 2016)	Target / (Sept 2017)
Service improvement pilots are evaluated and successful pilots are adopted by provincial governments	Planned for Punjab	No SNG-funded service improvement pilots in place	CF institutional arrangements agreed and Round 1 launched. / Pilots identified and 2 supported with technical assistance in 2 districts	2 pilots operational and 4 additional pilots shortlisted for award; with future benefits for 60,000 people.	2 pilots assessed and recommended for adoption and 4 additional pilots (from Round 2 and 3) made operational benefitting 120,000 people with a focus on women, girls and marginalized groups	4 Pilots (from all 3 rounds) recommended for adoption benefitting 240,000 people with a focus on women, girls and marginalized groups
	Achieved		Achieved	Achieved : 3 pilots operational for round 1 (Education) and 4 pilots (Health) shortlisted for round 2
	Planned for Khyber Pakhtunkhwa	No SNG-funded service improvement pilots in place	CF institutional arrangements agreed and Round 1 launched. / Pilots identified and 2 supported with technical assistance in 2 districts.	2 pilots operational and 4 additional pilots shortlisted for award; with future benefits for 60,000 people.	2 pilots assessed and recommended for adoption and 2 pilots made operational benefitting 120,000 people with a focus on women, girls and marginalized groups	4 Pilots recommended for adoption benefitting 240,000 people with a focus on women, girls and marginalized groups
	Achieved		Achieved	Achieved: 5 pilots operational for round 1 and 8 pilots shortlisted for round 2
	Source: District records; independent audit and evaluation reports

	Output Indicator 1.3		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (March 2015)	Milestone 3 / (March 2016)	Target / (Sept 2017)
	Government uses Geographic Information Systems (GIS) to monitor and plan quantity and quality of services	Planned for Punjab	No GIS in use in SNG pilot districts	2 pilot districts selected for GIS introduction	GIS operational in 2 districts and used for service delivery monitoring	GIS operational in 6 districts for service delivery monitoring, with a focus on health and education, and with gender disaggregated data. Substantial evidence of use of GIS in decision making.	GIS operational in 6 districts for service delivery monitoring and planning, in sectors other than health and education, and with gender disaggregated data. Substantial evidence of use of GIS in decision making.
		Achieved		Achieved	Achieved: GIS cells operational in 2 districts and used for service delivery planning
		Planned for Khyber Pakhtunkhwa	No GIS in use in SNG pilot districts	2 pilot districts selected for GIS introduction	GIS operational in 2 districts and used for service delivery monitoring	GIS operational in 6 districts for service delivery monitoring, with a focus on health and education, and with gender disaggregated data. Substantial evidence of use of GIS in decision making.	GIS operational in 6 districts for service delivery monitoring and planning, in sectors other than health and education, and with gender disaggregated data. Substantial evidence of use of GIS in decision making.
		Achieved		Achieved	Achieved: GIS cells operational in 2 districts and used for service delivery planning
		Source: Implementation reports; impact evaluation reports						RISK RATING = High
INPUTS (£)	DFID (£)	Govt (£)		Other (£)	Total (£)	DFID SHARE (%)
	£ 12,400,000	N/A		N/A	£ 12,400,000	100%
INPUTS (HR)	DFID (FTEs)
	2.2	0.3 x A1 Team leader, 0.7 X A2 Governance Adviser, 0.2 X A2L Economist, 0.5 X A2L Programme Manager, 0.5 X B2 Programme Officer

OUTPUT 2 / (Impact Weighting 30%)	Output Indicator 2.1		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (July 2015)	Milestone 3 / (July 2016)	Target / (Sept 2017)	Assumptions
Sub-national government services are more responsive to peoples' needs	Proportion of budget allocated to primary health and primary education at district level	Planned for Punjab	Share of non-salary recurrent budget allocated to health and education at district level. / Health: 44% / Education: 14% / TOTAL: 58%	Need-based transparent formula for devolution of resources to districts approved by PFC (PFC award)	TOTAL: 60%	TOTAL: 61%	TOTAL: 62%	Indicator 2.1 / Administration and politicians willing to explain spending decisions by reference to publicly available data. / % shift of devolved expenditure to be defined following PFC award. / Indicator 2.2 / World Bank mobile phone pilots deliver according to proposed results framework, and World Bank shares monitoring information on regular basis. / Indicator 2.3 / Government accepts application of OBI as a valid benchmark. / Quarterly narrative reports address programme impact on corruption.
		Achieved		Achieved	Achieved: Allocation of non-salary recurrent budget rose to 60% in the 2014/15 budget
		Planned for Khyber Pakhtunkhwa	Share of non-salary recurrent budget allocated to primary health and education at district level. / Health: 8% / Education: 14% / TOTAL: 22%	Need-based transparent formula for devolution of resources to districts approved by PFC (PFC award)	TOTAL: 24%	TOTAL: 26%	TOTAL: 28%
		Achieved		Achieved	Achieved: Allocation of non-salary recurrent budget rose to 28% in the 2014/15 budget
		Source: Provincial government financial management and budgeting data
	Output Indicator 2.2		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (October 2014)	Milestone 3 / (March 2016)	Target / (Sept 2017)
	Number of Departments / districts using smart information communication technology (World Bank)	Planned for Punjab	0	1 Department (Education or Health) 2 Districts	1 Department (Education or Health) / 6 Districts	N/A	N/A
		Achieved		Achieved	Partially Achieved: A wide range of ICT interventions were piloted (more than 10 interventions across 5 departments) through World Bank EFO with limited emphasis on sustainability and coherence.
		Source: Management dashboards (reported by World Bank to DFID, October 2014)
	Output Indicator 2.3		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (March 2015)	Milestone 3 / (March 2016)	Target / (Sept 2017)
	Provincial Open Budget Index (OBI) score	Planned – Punjab	No score	Baseline established (Score 55)	58 (5% improvement over base)	63 (15% improvement over base)	65 (18% improvement over base)
		Achieved		Achieved	Achieved: OBI score of 61 (10% improvement over base)
		Planned for Khyber Pakhtunkhwa	No score	Baseline established (Score 43)	45 (5% improvement over base)	55 / (25%) improvement over base)	60 / (36% improvement over base)
		Achieved		Achieved	Achieved: OBI score of 51 (16% improvement over the base)
		Source: Open Budget Index (OBI)						RISK RATING = HIGH
INPUTS (£)	DFID (£)	Govt (£)		Other (£)	Total (£)	DFID SHARE (%)
	£ 7,818,000	N/A		N/A	£ 7,818,000	100%
INPUTS (HR)	DFID (FTEs)
	2.2	0.3 x A1 Team leader, 0.7 X A2 Governance Adviser, 0.2 X A2L Economist, 0.5 X A2L Programme Manager, 0.5 X B2 Programme Officer

OUTPUT 3 / (Impact Weighting 40%)	Output Indicator 3.1		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (July 2015)	Milestone 3 / (July 2016)	Target / (Sept 2017)	Assumptions
Strengthened sub-national government capability to deliver basic services.	Sub-national planning is more performance orientated (especially for health and education)	Planned for Punjab	Provincial level / No performance-oriented budgets at district-level	Basis for delegation of health and education budgets to districts agreed	Framework for performance-based budgeting agreed	Performance based budgets with service delivery targets (including targets for women and girls) approved in primary health and education for 2 districts.	Performance based budgets with service delivery targets (including targets for women and girls) approved in primary health and education for 6 districts.	More performance-oriented planning improves service delivery. / Able to identify standard unit costs to inform efficiency saving analysis. / Governments commit to Output Based Budgeting and conditional grants rollout, and that capacity exists for rollout according to plan. / Government of Punjab acts on findings of payroll and pensions audits.
		Achieved		Achieved	Moderately not meeting expectations (B) : SNG has supported the introduction of a performance framework at district level covering Health sector but budgeting is still based at provincial level with limited discretion on budget decisions at District levels
		Planned for Khyber Pakhtunkhwa	District level / No performance- oriented budgets at district-level	Basis for performance-oriented health and education budgets agreed	Framework for performance-based budgeting agreed in 6 districts	District OBB targets agreed for health education in 6 focus districts (including targets for women and girls)	Average 50% OBB targets met in health and education in 6 focus districts (including targets for women and girls)
		Achieved		Achieved	Achieved: SNG has supported the introduction of a performance framework at district level covering six sectors with strong buy in from provincial and the district administrations.
		Source: Cabinet decisions; conditional grant allocations; impact evaluation reports
	Output Indicator 3.2		Baseline / (March 2013)	Milestone 1 / (March 2014)	Milestone 2 / (March 2015)	Milestone 3 / (March 2016)	Target / (Sept 2017)
	% of budget reaching service delivery units	Planned for Punjab	No expenditure tracking	Expenditure tracking for basic health and primary education agreed in SNG districts and % of non-salary budget allocations reaching service delivery units in a timely fashion established	Expenditure tracking survey completed in two districts and baseline established	At least 25% of recommendations from PETS implemented in all 6 SNG districts	At least 50% recommendations from PETS implemented in all 6 SNG districts
		Achieved		Achieved	Achieved: Study has been undertaken in two districts and report received.
		Planned for Khyber Pakhtunkhwa	No expenditure tracking	Expenditure tracking for basic health and primary education agreed in SNG districts and % of non-salary budget allocations reaching service delivery units in a timely fashion established	Expenditure tracking survey completed in two districts and baseline established	Expenditure tracking system established in one pilot district for one sector	Expenditure tracking system established for one sector in 6 focus districts
		Achieved		Partially achieved	Achieved: Study has been undertaken in two districts and report received.
		Source: Public Expenditure Tracking reports; impact evaluation reports

	Output Indicator 3.3		Baseline / (March 2013)	Milestone 1 / (March 2014)		Milestone 2 / (March 2015)	Milestone 3 / (March 2016)		Target / (Sept 2017)
	Increased provincial resources to finance services	Planned for Punjab	N/A	Plan agreed for SNG to support expenditure saving or revenue raising activities		Expenditure saving / revenue raising activities deliver efficiency savings of £2m	Expenditure saving / revenue raising activities deliver efficiency savings of £7m	Expenditure saving / revenue raising activities deliver efficiency savings of £15m
		Achieved		Achieved		Achieved: Efficiency savings of £12m (£8m for flood relief and rehabilitation £4m from education sector payroll audit)
		Planned for Khyber Pakhtunkhwa	N/A	Plan agreed for SNG to support expenditure saving or revenue raising activities		Expenditure saving / revenue raising activities deliver efficiency savings of £2m	Expenditure saving / revenue raising activities deliver efficiency savings of £7m	Expenditure saving / revenue raising activities deliver efficiency savings of £15m
		Achieved		Achieved		Achieved: Improved allocative efficiencies as a result of expenditure rationalisation worth Rs. 1.122 billion (£7m). / Identified efficiency savings of Rs. 143 million (£0.92 million) as a result of IT payroll audit for E&SE Department.
		Source: Provincial government financial management and budgeting data								RISK RATING = Medium
INPUTS (£)	DFID (£)	Govt (£)			Other (£)	Total (£)	DFID SHARE (%)
	£ 17,910,120	N/A			N/A	£17,910,120	100%
INPUTS (HR)	DFID (FTEs)
	2.2	0.3 x A1 Team leader, 0.7 X A2 Governance Adviser, 0.2 X A2L Economist, 0.5 X A2L Programme Manager, 0.5 X B2 Programme Officer