# Addendum to the Business Case: Central African Republic Emergency Response programme
# Costed Extension (DFID Africa Regional Department)
# 1 February 2016

SUMMARY INFORMATION
Project Name	Central African Republic Emergency Response
Country or region targeted	Central African Republic
Type of cost extension	Costed extension
Original project budget	£35 million
Original project start and end dates	Start date: 17 July 2014 End date: 31 March 2016
Cost extension value	£5 million
New project end date	31 December 2016
Programme Document No.	204852

INFORMATION
What is the project’s purpose?
The Central African Republic (CAR) Emergency Response programme was approved in 2014 and provides a package of support totalling £35m. The programme addresses life-saving needs of conflict-affected populations in CAR and of CAR refugees in Cameroon and Chad who have fled the violent conflict since December 2013. The programme supports the Food and Agriculture Organisation (FAO), the International Committee of the Red-Cross (ICRC), the UN High Commissioner for Refugees (UNHCR), the World Food Programme (WFP), the Common Humanitarian Fund (CHF) and NGO consortia that provide the CAR population with access to healthcare, livelihoods support and protection assistance. Activities for refugees focus on providing life-saving food assistance, access to shelter, water and sanitation, and improved protection, including for women and girls. / In September 2015, Minister of State Shapps agreed to release £7m in contingency funding to address urgent humanitarian gaps, bringing the total UK spend under this business case to £35m. The UK humanitarian contribution for CAR and CAR refugees totals £58m since 2013. / This programme’s refugee component was reviewed in July 2015. UK funding has helped agencies provide a successful response to refugee needs and bring assistance up to minimum standards. Significant mortality drivers such as malnutrition have been brought under control thanks to DFID and other contributions. On that basis we assessed that the programme is achieving its outcome. The 2014 CAR programme was reviewed in August 2015 and found to have achieved its intended outcome.
What is the objective of the costed extension/ addendum?
Rationale / Overview / In order to support longer term humanitarian assistance, recovery and resilience, DFID is preparing a new CAR multi-year business case for 2016-2019 involving a switch in DFID’s partnerships. This change in delivery mechanisms will affect humanitarian assistance coverage in 2016 in two sectors in which DFID is a lead donor, healthcare and livelihoods. The requested £5m cost extension will bridge the gap of CAR needs between the current business case (£35m) due to end March 2016, and the upcoming business case to be submitted to the Minister in February 2016 (£75m). / This cost-extension will enable DFID to continue providing essential healthcare to 270,000 people over six months. It will also provide an estimated 170,000 people with essential livelihoods support during the agricultural season. / Long term outlook / An electoral process begun in December 2015 and due to end in March 2016 will end the transition back to democratic governance in CAR. With the support of a UN peace-keeping operation (MINUSCA), the government will begin the painstaking task of rebuilding essential services and launching armed group disarmament and reconciliation initiatives. It will take five years for the foundations of this state to emerge and ten to deliver nascent governance structures and a reformed security sector. In the meantime, humanitarian assistance will remain crucial to address the needs of displaced populations and returnees and provide basic healthcare. The humanitarian community will also need to address the rapidly deteriorating food security situation. In 2015, 50% of people were estimated food insecure, up from 29% in 2014. / To address the challenges ahead, we will submit to Ministers a Multi-year business case that proposes to address key humanitarian priorities in 2016-19. This business case will look in particular at channeling some of our assistance through an EU trust fund to ensure more joined up and predictable aid delivery and technical support to CAR authorities. There will however be a time lag between the end of the current business case and the launch of some of the EU trust fund programmes that DFID intends to support. In two key sectors, health and livelihoods, we estimate these time lags to be highly detrimental to CAR populations and potentially cost lives. DFID is one of the key donors supporting healthcare in country. In the absence of functioning Ministry of Health structures, DFID’s support to health ensured that 340,000 people had access to healthcare in 2015 in CAR. We propose to extend our health support under this cost-extension so that the 270,000 people supported though an NGO consortium led by International Medical Corps continue to receive life-saving health support until the EU trust fund is able to expand its area of operation to encompass those covered by DFID. We do not estimate that other donors or funding mechanisms are likely to immediately step in and cover those needs if DFID support is not provided through a costed extension. / In the field of livelihoods, planning towards the new agricultural season will begin in February and planting will take place between May and August. Agriculture represents close to 60% of CAR’s gross national product and shrank by almost 60% in 2013-14 as a result of the conflict. Insecurity in 2015 means that cereal production has shrunk by a further 14%. 50% of CAR’s population (2.5million people) is estimated moderately to severely food insecure (compared to 29% in 2014). Curtailing the ongoing and rapid deterioration in food security is essential to decrease the risk of a more severe crisis in 2016 (that could see emerging pockets of famine). The new EU trust fund livelihoods programme will only begin in Autumn 2016, so we propose to bridge the needs during this agricultural season under this proposed costed extension. / Our longer term approach will also include advocacy to ensure effective coordination among humanitarian and development donors, early engagement of international financial institutions, and support to the cross-Whitehall CAR strategy in the fields of security, justice and governance through close cooperation with the FCO. / Gender Equality / The scale and length of the current conflict is likely to exacerbate existing inequalities within CAR’s society. / UNFPA reported that more than 60,000 sexual and gender-based violence survivors sought assistance in 2015, demonstrating the scale on which women are victimised. The Central African Republic Emergency Response Business case states that DFID will ensure that all selected projects use gender and protection mainstreaming to understand and start to address inherent inequalities within CAR society. / The business case also noted that within the health sector, gender mainstreaming will take place through comprehensive integrated services which provide treatment and care for gender based violence and specialised services for women and girls’ health. This costed extension will enable the IMC consortium to continue providing referral and treatment of survivors as well as access to essential healthcare for pregnant and lactating women. / Livelihoods assistance will aim to ensure that aid is provided with adequate attention to most vulnerable beneficiaries including in particular women and girls. FAO's partners will select beneficiaries based on targeting criteria, according to the minimum standards outlined by the food security cluster with particular emphasis on the inclusion of gender balance (at least 50% of beneficiaries will be women). FAO will ensure that women are represented in the local committees selecting the beneficiaries. Priority is given to vulnerable farming households with access to land, affected by the conflict and, with specific attention being paid to women's groups, women headed households and specific vulnerable groups (disabled persons, people with HIV/AIDS). FAO aim to monitor disaggregated data to ensure proper vulnerability targeting. Gender equity during livelihoods training will be assured by taking into consideration gender specific tasks and targeting training beneficiaries according to well-known gender specific production tasks. For example, women’s participation will be obligatory during trainings on seeding, pest and disease identification and control, harvesting, marketing, and value added processing trainings. Above all, the first payment to partners will be based on confirmation of gender equality in the choice of beneficiaries (i.e. 50% women) as demonstrated by beneficiary lists provided to FAO and disaggregated by gender. / These measures aim to ensure that groups that suffer discrimination are fully able to contribute to programme design, benefit in equal measure and the humanitarian programmes do not exacerbate discriminations or local conflicts. / Nature of the current response / The current programme aims to provide 692,976 people in CAR with healthcare, livelihood and food assistance and protection assistance. The programme also provides up to 236,000 CAR refugees with food aid, healthcare, shelter, protection and livelihood support. / Programme objective and outcomes / Under the current business case, the programme aims to: / improve the food security and agro-pastoral production of 343,282 people; / provide 340,072 people with access to essential healthcare, / provide 88,960 people with an improved protection environment, and / help improve humanitarian coordination through a better performing Common Humanitarian Fund. / In addition, the programme proposes to: / provide 88,000 CAR refugees in Cameroon with food and nutritional assistance; / provide 30,000 of them with emergency malnutrition treatment; / provide 56,000 refugees in Chad and up to 180,000 refugees and host community members in Cameroon with shelter, water and sanitation assistance, protection, essential household items, access to healthcare and livelihood assistance.
What is the additional and total support the UK will provide?
The UK has provided £35m under the current business case between 2014 and 2016. We propose to provide a further £5m under the existing business case, bringing it to a total of £40m. / Including the current business case, the UK has provided £58 million since 2013 to address urgent humanitarian needs in the Central African Republic (CAR) and among CAR refugees. This costed extension will bring the total UK contribution since the conflict began to £63m. / We will approach Ministers in February to request approval for a new Business case spanning 2016-19. The newly proposed Business Case aims to provide a multi-year support package of £75 million to address humanitarian and recovery needs in CAR and among CAR refugees. / Timeframe / The proposed costed extension will last 9 months, extending the current Business case from 31 March 2016 to 31 December 2016. / Budget breakdown / The budget under the current Business case is presented below in the second column. It includes £7m in contingency funding released in September 2015 to the CHF (£4m) and UNHCR (£3m). The proposed cost extension budget is presented in the third column. / Agencies – CAR response Current business case (2014-16) Proposed cost extension (2016) Total / CHF £6m £6m / ICRC £2m £2m / FAO £3m £3.1m £6.5m / IMC-led consortium* £3m £1.75m £4.5m / SI-led consortium** £3m £3m / Agencies CAR refugees / UNHCR £9.5m £9.5m / WFP £4m £4m / MSF £1m £1m / START network*** £3m £3m / M&E £0.5m £0.15m £0.5m / TOTAL £35m £5m £40m / *NGO consortium led by the International Medical Corps providing healthcare. / **NGO consortium led by Solidarites International providing livelihoods and protection assistance. / ***NGO consortium under secretariat of Save the Children UK. / Value for Money / The business case followed DFID’s approach to VfM, the Efficiency, Economy and Effectiveness (3Es) model. / The project proposed by the IMC consortium will be a continuation of our existing health project. Similar protocols will be applied to purchasing processes. Where possible, partners have sought economies by joining up procurement and transportation between consortium members. They have also shared technical expertise and tools. This partner has performed well throughout the year, meeting most of its quality targets. The response has therefore proved its efficiency. This has translated into child mortality remaining overall below emergency thresholds, demonstrating the effectiveness of the operation. By ensuring that staff, resources and assets remain in use for the benefit of the population under this costed extension, and that health indicators remain below emergency thresholds until the EU trust fund is able to take over, DFID is ensuring that our programme is effective and provides Value for money. / The project proposed by FAO will involve a large proportion of local procurement and where feasible, assistance will be provided through vouchers rather than in-kind. This will stimulate the local economy, decrease transportation costs and increase beneficiaries’ choice. In terms of economy, this strategy is a positive choice albeit more complex than direct procurement. The scope of the programme remains similar to that of 2015, i.e. responding to deteriorating food security by providing agricultural inputs and capacity building in crisis areas. This is an effective response to address the shrinkage of the agricultural sector since 2013. DFID will also advocate with other donors on the need to resource agricultural programmes, to ensure a response at scale that helps curtail rapidly worsening food insecurity.
What are the expected results?
This cost extension will enable 269,354 people to continue accessing healthcare services over a period of six months. It will provide up to 170,000 people with improved access to essential agricultural inputs and training to resume agricultural production.
What is the approach to implementation?
Commercial / The funding will be made available through indirect procurement. A Memorandum of Understanding will be signed with the FAO. An Accountable Grant will be signed with IMC, which will in turn contract its consortium partners. / Partner performance will be regularly monitored through reviews of their reports and quarterly visits to CAR. / Management / The same governance structure of the existing programme will govern the management of this proposed extension. The current SRO will remain SRO for the programme, with support from the existing humanitarian advisor and Deputy programme manager. / The FAO programme will be managed by the FAO country team. The IMC-led programme will be run by IMC and will involve subcontracted partners: CORDAID, MENTOR initiatives and OXFAM. An IMC consortium manager will be in charge of day to day operational management and quality control. IMC will run due diligence checks of its partners. / Reporting and M&E / FAO will report quarterly, with a final narrative report provided a maximum of 3 months after completion of the project, and a final financial report provided 6 months after completion. / The IMC-led consortium will report quarterly and provide a final narrative and financial report a maximum of 3 months after project completion. / Fraud management / Delivering humanitarian assistance in fragile and difficult contexts such as CAR inevitably has a high level of risk associated with it, and DFID is prepared to take on some risk in order to meet the pressing humanitarian needs in these countries.[1] However, DFID has a zero tolerance policy on fraud. / We reported to ministers on instances of loss and fraud cases in 2014-15 in CAR.[2] In 2014-15, DFID partners reported 5 security incidents where funds or assets provided by DFID were stolen, mainly during violent robberies. DFID has agreed £21,711 in write-off costs for lost funds and assets. In 2014-15, partners reported 5 potential and 2 confirmed fraud cases affecting DFID programmes. Cases include the theft of assets and the diversion of funds intended for income generating activities. The value of DFID funds and assets lost to fraud still need full estimation. All identified losses due to fraud will be reimbursed to DFID. / Through engagement with implementing partner organisations’ audit processes, and scrutiny of their financial statements, DFID will ensure all spend under this programme and the future Business Case is accounted for and work with implementing partner organisations to strengthen financial oversight. DFID will also ensure adequate fraud mitigation processes are in place including whistle-blowing mechanisms. If fraud is detected we will demand repayment in full. Continued disbursement of funds will be contingent upon adequate financial oversight mechanisms. / Assistance across CAR is constrained by insecurity and the absence of a DFID office. DFID therefore ensures that partners roll out adequate risk management systems. We will also continue to organise at a minimum quarterly visits to CAR and CAR refugee programmes to review partners’ processes, progress and performance. / Fraud mitigation actions are as follows: / DFID due diligence reviews ensure that partners have adequate processes to mitigate and manage fraud risks. / DFID monitors compliance mechanisms in particular frequency of compliance checks, audits and M&E. / DFID to report all fraud and losses cases to DFID counter-fraud units. / Risk management / The overall risk level of this programme is High. CAR is a very challenging environment for partners to operate in. DFID has a tolerance to risk, but no tolerance to fraud. / Risk Probability Impact Mitigating Actions / Conflict hinders access and delivery and leads to surge in needs High – CAR is still characterised by relative lawlessness and witnesses localised surge in needs and frequent access challenges. High DFID liaises with FCO on MINUSCA performance and monitors other relevant security bodies (UNDSS, INSO, HCT). / DFID is flexible around need to revise/adapt programmes. Bekou Fund and CHF implement programmes with flexibility. / Partners are selected on the basis of scale-up capacity, experience and contingency to rapidly respond to uprising needs. / Internal Risk Contingency Facility to provide rapid funding to address surge in needs. / Insecurity/criminality High Medium to High Due diligence partner review ensures they have suitable security management processes. / DFID checks that partners have contingency plans in place. / DFID ensures that partners conduct do no harm analysis to keep beneficiaries safe. / Lack of conflict sensitivity/Do no harm analysis among partners Medium High DFID reviews do-no-harm analysis at proposal time and during implementation. / DFID ensures that partners implement projects transparently in accordance with humanitarian principles. / DFID advocates with CHF, HCT and Bekou Fund for adequate partner capacity building on do-no-harm. / Underfunding of the refugee response heightens local tensions and criminality High Medium In Cameroon, DFID to closely coordinate with the EU and US to ensure assistance remains commensurate to the needs. / In Chad, CAR refugees are being integrated under DFID’s PHASE programme. In the DRC, DFID’s system-wide assistance to the CHF directly supports the humanitarian community to address gaps. / DFID to ensure that refugee programmes have a solid built-in do-no-harm component and address social tensions. / DFID to ensure refugee assistance include livelihoods assistance that progressively helps rebuild refugees’ self-sufficiency. / Fraud High Medium DFID due diligence review ensures that partners have adequate processes to mitigate and manage fraud risks. / DFID monitors compliance mechanisms in particular frequency of compliance checks, audits and M&E. / DFID to report all fraud and losses cases to DFID counter-fraud units. / Procurement and transportation challenges High Medium to high DFID ensures partners have solid procurement planning and procurement processes in place – including surge support where necessary. / DFID monitors security on main supply roads and advocates with MINUSCA via FCO when necessary. / DFID to show flexibility on transportation and storage costs. / Partner capacity High Medium DFID due diligence to review capacity to deliver including staffing and technical capacity. / DFID to incorporate lessons learnt from Annual Reviews, Project Completion Reviews and quarterly monitoring into programming. / DFID to show flexibility around staffing and training costs. / DFID establishes with partner action plans to address poor performance. DFID to work with other donors and Bekou Fund to ensure similar partner performance monitoring processes are incorporated. / Constraints placed on humanitarian space by CAR authorities Medium to low Low DFID to advocate through HCT, FCO, EU, UN. / Weak humanitarian coordination and strategy Medium Medium DFID to advocate with OCHA (at country, regional and central level), CHF, HC, UNHCR and with relevant agencies. / DFID to support funding mechanisms that empower humanitarian coordination (CHF). / DFID to maintain contacts with key donors, including ECHO, OFDA/PRM, CHF, AFD, SIDA. / Poor linkage between relief and development Medium Medium DFID to coordinate closely with development donors and international financial institutions. / Insufficient management capacity within DFID Medium Low DFID to resort to surge capacity when necessary (through CHASE OT). / DFID to increase frequency of visits to CAR and engagement level. / DFID to plan programmes/partnerships with attention to management capacity. / Sustainability – We do not foresee at this stage a decrease in humanitarian needs over the proposed costed extension. We will submit to ministers in February a multi-year business case that will propose to transition towards channelling UK funding through an EU trust fund and to increase our allocation to the Common Humanitarian Fund. Through these fora, we hope to increase our engagement with other donors, support better coordination between humanitarian and development actors and plant the seeds of essential services reconstruction and economic recovery. We hope that our combined funding and advocacy efforts will contribute to stopping the current trend towards increasing needs and lay the foundations towards a potential recovery process.
Describe any key changes to the original business case?
We propose to extend our agreements with two current partners over a period of 9 months. This additional contribution will total £5m. The proposed costed extension does not entail other major change under the current business case.
[1] http://www.dfid.gov.uk/About-us/How-we-measure-progress/Resource-accounts/Risk-management/
[2] DFID (2015), Central African Republic (CAR): Humanitarian situation and funding submission.