Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	March 2016

Title: : Public Financial Management Reform Programme
Programme Code: 114491	Start Date: 23/01/2010	End Date: 31/01/2016

Summary of Programme Performance

Year	2012	2013	2014	2016
Programme Score	B	A	A	A
Risk Rating	High	High	Medium	Medium

Financial Position

Original Programme Value	£3.6 million / Of which £3.5 million contributed to a World Bank managed Multi-Donor Trust Fund (MDTF) of £15 million[1] in total.
Extensions/ amendments	March 2014 / February 2015
Log-frame revisions (with dates)	October 2012 / August 2014
Total programme spend	£3,566,684
[1] Based on exchange rates at 24 February 2016: £1 = $1.39. Includes contributions commitments from all funders to date.

Enhancing the efficiency, transparency and integrity of public finances has been central to the UK’s aid strategy in Nepal. From 2010 to 2015, the UK supported the Government of Nepal’s (GoN) efforts to strengthen its public financial management through a £3.5 million contribution to a World Bank managed £15 million[2] Multi-Donor Trust Fund (MDTF)[3]. Despite a highly challenging implementation period, this Programme Completion Review (PCR) concludes that the DFID programme, delivered through the MDTF, successfully met its stated objectives. In some areas, impressive technical reforms have been achieved.
[2] Contribution commitments to date.
[3] Other funders to the MDTF during the programme review period include: Norway, Denmark, Australia, Switzerland, the USA and EU.

This PCR documents the progress of the programme since its inception in 2010 and the achievements attained by the end of December 2015. It also draws out a number of key lessons learnt during implementation, which will be shared widely including with GoN, other development partners and DFID’s central PFM team. Finally, the PCR proposes recommendations that could help shape Nepal’s future PFM agenda.

DFID follow-up actions required following closure

As per DFID’s SMART rules, the necessary actions have been taken to ensure that the programme is fully closed. However, this review notes that whilst the DFID programme of support has closed given that all payments have been made and all DFID funds have been spent, the MDTF will continue supporting public financial management reforms using other approved development donor resources until 2018[4]. A couple of actions are therefore outstanding:
[4] Phase 1 of the MDTF: 2010-2015. Design discussions are currently underway for a Phase II MDTF Programme. The administrative arrangement for the MDTF is currently scheduled to end in January 2018. However, this is likely to be extended following approval of a Phase II MDFT Programme.

Action: All required audited accounts and financial statements covering the full duration of the programme have been received: The audited accounts covering DFID funding for the 2015 calendar year[5] are not due until September 2016. Upon receipt, DFID Nepal will scrutinise this audit report and follow-up accordingly;
[5] Audit report due is for the MDTF’s 2015/16 FY

Action: All assets are disposed of in a way that represents value for money with a clear record of decision making: As noted in this review, the MDTF arrangement states that assets will be transferred to recipients, local authorities or to the final recipients in according with the World Bank’s policies and asset management. The World Bank is continuing to monitor assets as part of its bi-annual financial supervision missions. In light of the continuation of the MDTF, there will no clear record on decision making regarding the disbursement of assets until the MDTF actually closes.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3860084.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3717433.docx

Outline of programme and what it has achieved
Sound public financial management (PFM) is an essential ingredient for driving inclusive growth, maintaining fiscal discipline and curbing corruption in the public service. For the UK, it is also essential for protecting and maximising the value-for-money of our aid delivered through Government systems.

Nepal emerged from a lengthy conflict in 2006. A Public Expenditure and Financial Accountability (PEFA) assessment[6] concluded that whilst Nepal’s PFM system has been well designed, “its implementation has been uneven”. Budget preparation did not always adhere to its detailed guidelines and procedures; budget execution faced major challenges including a delayed appropriation of the annual budget, a highly bureaucratic and centralised authorisation process and complex procurement processes; computerised accounting systems did not effectively assist decision making, whilst incomplete computerisation negatively impacted the timeliness and quality of accounting and financial reporting; significant gaps existed in internal and external control systems, and when transgressions occurred credible sanctions, were lacking. Access to information was restricted.
[6] PEFA assessment conducted on the 2005/06 FY and published in 2008. The PEFA assessment was produced by the GoN, with support from the World Bank, and provided a basis for objectively assessing the national PFM system.

Enhancing the efficiency, transparency and integrity of public finances has therefore been central to the UK’s aid strategy in Nepal. From 2010 to 2015, the UK supported the Government of Nepal’s (GoN) efforts to strengthen its PFM through a £3.5 million contribution to a World Bank managed £15 million[7] Multi-Donor Trust Fund (MDTF)[8]. The GoN contributed USD 3.34 million[9] to support the MDTF activities. The programme was composed of two components:
[7] Contribution commitments to date.
[8] Other funders to the MDTF during the programme review period include: Norway, Denmark, Australia, Switzerland, the USA and EU.
[9] SPFM 1 = USD 1.4m; OAG = USD 0.8m; SPMF 2 = USD 1.14m

## Component A focused on strengthening the Government of Nepal’s own PFM systems and was referred to as the supply side component. Under this component, the programme supported the following sub-projects:
The implementation of a Treasury Single Account (TSA);
Improvements in financial reporting and accounting standards, to bring them in line with international accounting standards;
Capacity building and institutional strengthening of the Public Expenditure and Financial Accountability (PEFA) Secretariat in the Ministry of Finance (MoF), which is responsible for driving and coordinating PFM reforms across the GoN;
## Since DFID committed funding in 2010, new areas of support were added to Component A. These included sub-projects to:
Strengthen the Office of the Auditor General (OAG) and the Public Accounts Committee (PAC);
Strengthen the Government’s budget process.

Component B focused on developing the capacities of Nepali civil society organisations (CSOs) to use social accountability approaches to hold the GoN to account and demand better use and management of public finances. This component was delivered via the Programme for Accountability in Nepal (PRAN) and is referred to as the demand side component.

The programme implementation period has been highly challenging. The on-going political instability, which was anticipated at the design stage, has impacted the development of robust institutions. For example, there was no Public Accounts Committee (PAC) for the first two and a half years of the programme[10] and no permanently appointed Auditor General between 2007-2013. These factors, particularly the absence of the PAC, impacted the achievement of originally targeted results under the sub-project to strengthen the OAG and PAC. As a result, the OAG and PAC sub-project was re-designed with a scaled down ambition level. Accountability structures at the local level were also weak with local elections not having taken place since 1997. This review confirmed that this is likely to have negatively impacted the effectiveness of activities under the demand side component.
[10] The sub-project to support the PAC began in February 2012. After elections at the end of 2013, a new PAC was not formed until mid 2014.
Consultations for the PCR also highlighted the unexpected impacts of frequent staff turnover in the public sector, which occasionally halted the momentum of reforms and likely undermined the sustainability of some of the capacity building activities. Finally, the April 2015 earthquake and six month political unrest in the Terai (September 2015 – February 2016) interrupted some sub-projects.

Despite this difficult operating environment and an initial delayed start – the programme started one year later than expected - a number of good, and in some areas impressive, technical reforms have been delivered:
- A Treasury Single Account, implemented a year ahead of schedule, has enhanced fiscal control and expenditure efficiency, and improved the quality, timeliness and transparency of financial reporting, and savings to GoN;
- Accounting and reporting standards have been strengthened, and are feeding through to more robust practices in the public and private sectors and;
- Audit practices and methodologies are being modernised;
- Awareness has been raised throughout the country on GoN’s PFM reforms;
- A GoN-led second PEFA assessment that was completed and disseminated in June 2015, and used as the basis for second phase PFM Reform Strategy.[11]
  [11] PFM Reform Plan II was not formally adopted by the GoN PFM Steering Committee until 24 February 2016 and is therefore not covered within the scope of this PCR.

For the demand-side component, a large volume of Civil Society Organisations (CSOs) have been trained through PRAN social accountability schools; awareness on budgetary issues has been raised amongst journalists; and awareness raising initiatives have directly helped marginalised communities and disadvantaged people to exercise their rights to social security entitlements.

There have also been other important non-tangible benefits delivered through this programme. This review confirmed that the MDTF is widely viewed as a key instrument for change and has provided important traction upon which to build future PFM reforms. The number of development partners (DPs) providing funding to the MDTF has also increased from DFID alone at its start in 2010 to seven as at the end of 2015[12]. Consequently, this review confirmed that the MDTF has been instrumental in terms of improving the alignment and coordination of donor support for PFM reforms in Nepal. Over the years, the increased number of DPs has also strengthened the MDTF’s credibility, influencing and convening power.
[12] In addition to DFID, MDTF funders as at the end of 2015 include the Royal Norwegian Embassy (2011), Embassy of Denmark (2011), the Australian Department of Foreign Affairs and Trade (2011), the EU (2011), Government of the Swiss Confederation (2015), and the US Agency for International Development (2015).

While the second PEFA assessment on the FY 2013/14 does not capture the full reform efforts of the programme, it nonetheless concluded that “Nepal has made substantial progress in deepening the structures and processes of PFM, particularly in the use of information technology”.[13] The evidence in this review confirms that the MDTF has played an important part in this achievement. This assessment is also supported by the awarding of the MDTF with a Vice President’s Award (South Asia Region) of the World Bank in April 2015 which cited the use of analytical work in informing Bank-financed projects and/or advice provided to Governments as a key success criteria.
[13] Public Expenditure and Financial Accountability (PEFA) Assessment II – As at 2013/14 FY. http://www.pefa.gov.np/second-pefa-assessment-report-2015/

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

Outcome Title	A more efficient public financial management system with increased transparency and accountability to citizens

Indicator(s)	2015 Target	Progress
Number of sectors where information of budget allocation and expenditure is made public 3 times a year	A target of 3 sectors was established for 2015. However, information on budget allocation and expenditure has been made public throughout the year for all sectors since 2014. (This was reported as achieved in the 2014 annual review).
Percentage of budget execution reports and financial statements (meeting acceptable standards of quality, completeness and timeliness) prepared by FCGO using the TSA system and published on the FCGO website[14]. (Indicates the mainstreaming of the TSA system)	A target of 100% was established for 2015. However, all budget execution reports and financial statements using the TSA system have been published on the FCGO website since 2014. (This target was reported as achieved in the 2014 annual review).
[14] http://www.fcgo.gov.np/report-publications/daily-budgetray-status/

The programme achieved its outcome in 2014 and was reported as such in the 2014 Annual Review. However, the DFID log frame was not updated to extend the level of ambition for the final year of the programme.

Overall, budget information has become more transparent as confirmed by the second PEFA assessment. All budget documents are published on the Ministry of Finance (MoF) website – www.mof.gov.np – after their submission to Parliament and the budget is published after approval. The Financial Comptroller General’s Office (FCGO) produces daily budget execution reports using the TSA system with the following data available on the FCGO website: a) daily budgetary status b) monthly ministry expenditure status and burn rate and c) monthly ministry and economic head cumulative expenditure and current monthly expenditure classification d) monthly district-wise budget execution and e) yearly consolidated financial statements.

Public access to fiscal reports is therefore good – the second PEFA assessment recorded an improved score to 'A' in 2014 from B in 2008.

However, this review concluded that there are three key outstanding challenges:
- Budget data should be presented in a more disaggregated format to facilitate detailed analysis. This observation was also captured in the mid-term review of the MDTF[15];
  [15] Nepal Public Financial Management Support – Multi-Donor Trust Fund. Mid-Term Evaluation. Clay Wescott 2014; Consultations for the PCR
- As confirmed by the second PEFA assessment, fiscal reports should improve their comprehensiveness. Many autonomous government agencies and donor projects remain outside of the TSA system;
- Budget data should be presented in a format that facilitates policy dialogue and decision making. This review found no conclusive evidence that data generated from the TSA is actively feeding into policy debates. However, this review notes that the poor use of data and evidence to influence policy is a systemic challenge in Nepal – not just a specific PFM challenge. DFID Nepal is actively seeking to address this challenge through an Evidence for Development Programme.[16]
  [16] https://devtracker.dfid.gov.uk/projects/GB-1-203385/documents

Overall Output Score and Description

The overall output score for this programme has been assessed as an ‘A’ – output met expectations. After an initial slow start, the programme has delivered good and in some cases impressive results. The implementation of the TSA, a year ahead of schedule, is widely viewed as the strongest achievement. However, this review notes that there is not a strong linkage between all outputs and the outcome – for example, the outcome indicators do not properly capture the results of achievements from outputs 4 and 5. It is therefore considered that the outputs achieved more than the programme’s stated outcome.

Scoring methodology: In the absence of targets to extend the ambition level for results achieved ahead of schedule (this applies to outputs 1 and 2); and given that DFID’s 2015 log frame targets for PRAN do not reflect a re-design of the project, a judgement was made on progress achieved during 2015 based on a desk review of documents and consultations with stakeholders in order to score the outputs.

Output	Weighting	Score
1. Treasury Single Account (TSA) implemented throughout Nepal	20%	A+
2. Financial reporting and accounting standards improved in Nepal	10%	A+
3. Increased capacity and knowledge of key stakeholders in Nepal on public financial management	25%	A
4. Quality of public sector audits enhanced	15%	A
5. Improved citizen engagement in PFM reform	30%	A

Key lessons
A number of key lessons can be drawn from the implementation of this programme:

The Country Context
Post conflict and politically unstable environments such as Nepal present challenging contexts for PFM reforms. However, this programme has demonstrated that even in such contexts, advancing certain technical PFM reforms is possible if they are aligned with Government strategies and plans;

Capacity Building
In country contexts such as Nepal with frequent staff turnover and no professional PFM related cadres (other than accountants), the focus of a risk mitigating strategy should be on building institutional capacity (alongside individual capacity) to ensure that there is sufficient depth to provide continuity when staff leave;

It is important to establish a capacity building plan from the outset to avoid a piecemeal approach. There is also a need to establish approaches that assess the application of new skills and knowledge, for example through training tracer studies, to assess the impact and value-for-money of capacity building activities and provide evidence to support adaptive approaches;

Financial incentives for staff can provide a powerful motivator for PFM technical reforms as evidenced by the roll-out of the TSA system;

Coordination
An inter-institutional coordination function, such as GoN’s PEFA Secretariat, is essential to drive systemic reforms. It is critical to ensure that this function is properly resourced and empowered.

Communications
Broadening the constituency for PFM reforms is critical to driving its success. It is important to ensure that there is sufficient capacity to communicate effectively on the PFM agenda. It is also important to ensure that there are tailored communication approaches that create broad engagement with PFM reforms. These should target GoN technical staff directly involved in PFM reforms, GoN staff tangentially involved in PFM reforms and GoN senior officials. In addition, communications with the general public is critical for building demand side pressure for PFM reforms.

It is important to be realistic and manage expectations with PFM reforms. Introducing new tools and systems into an environment where old tools and systems are entrenched requires attitudinal and behavioural changes alongside technical capacity building. Communicating the benefits of PFM reforms is key for over-coming resistance;

Demand side initiatives can play a useful role in holding Governments to account, particularly where accountability structures are weak. To sufficiently influence PFM reforms, it is important to ensure a clear linkage between demand side and supply side initiatives;

Demand side initiatives, particularly those engaged on technical areas and working with marginalised communities and disadvantaged people, require long-term funding commitments to ensure that a platform for trust and voice is properly established.

The MDTF
The MDTF has been opportunistic, has focused on technical wins, and has provided good flexibility in responding to well-founded requests from GoN for support. These approaches have clearly been appropriate to the context in which the programme has been implemented i.e. post-conflict with changing political dynamics and a very limited PFM reform agenda prior to the MDTF’s start. However, a more robust strategic approach that fully considers political economy in its design will be required for a new programme going forward;

While the MDTF has been difficult for funders from a programme management perspective given World Bank administrative challenges. However, it has provided good value-for-money as a delivery mechanism for DFID.

Measuring results and value-for-money
DFID Nepal missed opportunities to ensure that the log frame is a credible monitoring tool, both in terms of updating it to accurately reflect the evolving programme design and extending the ambition level when indicators were achieved earlier than expected. For programmes that are flexible and adaptive in nature, it is important to ensure that the log frame is treated similarly;

There is not a strong linkage between the outcome indicators and all outputs in the log frame. When PFM reform programmes are trying to achieve more than one outcome, consideration should be given to using a multiple log frame approach (DFID PFM reform programme guidance), leading to a common impact statement;

It is important to ensure that financial information is disaggregated to allow the achievement of results to be costed. This will enable an objective assessment on the VfM of reform efforts;

DFID and other MDTF funders should align their review processes to enable a more robust monitoring of programme performance and minimise transaction costs of stakeholders that are consulted for reviews.

A re-designed/new programme
A new programme will need to consider the change of Nepal’s structure to a federal system which was mandated in the 2015 Constitution. It will also need to ensure that its design and approaches consider the political economy – and that there is sufficient on-going political economy analytical capacity, ideally provided from the World Bank. With the MDTF having built the momentum for change, a new programme would also provide an opportunity for a more strategic approach to PFM reforms that balances low hanging technical wins with high impact transformational changes.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Treasury Single Account (TSA) implemented throughout Nepal.
Output number per LF		1	Output Score	A+ On the basis of on-going work during 2015 to enhance the functionality of the TSA.
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	2015 Target	Progress
1.1 Number of districts implementing the Treasury Single Account (TSA).	A target of (all) 75 districts was established for 2014. This was achieved and reported as met in the 2014 Annual Review. / A new indicator and target for 2015 to reflect the implementation of initiatives that enhance the TSA was not established.
1.2 Number of Spending Unit Bank Accounts operational.	A target of 500 was set for 2014. This was achieved and reported as met in the 2014 Annual Review. / A new target for 2015 to reflect continued efforts to close bank accounts was not established.

Indicator 1.1: The roll-out of the system to all 75 districts, driven by senior GoN champions and achieved in July 2013 (a year ahead of schedule), is widely viewed as a major accomplishment for the PFM agenda. The system is yielding a number of significant benefits. GoN now has improved control over its cash balances; reduced expenditure on interest payments for internal borrowing and reduced commercial bank commission charges; improved transparency and accuracy in financial transactions, which together with full daily reconciliation between GoN accounting systems and the Central Bank’s cash flow statements have strengthened internal controls and; improved quality and timeliness in financial reporting as detailed under the outcome statement.

During 2015, two other major achievements were noted during this review. The TSA’s Disaster Recovery and Business Continuity Plan proved effective – the TSA system withstood the April 2015 earthquake and, against expectations, was functional through a web-based system the day after. The programme also supported the roll-out of a Revenue Management Information System (RMIS) to 15 districts, which is now providing GoN with on-line real-time access to approximately 90% of its revenue collection.

However a number of actions are still outstanding. An accounting manual to support implementation of the TSA has yet to be finalised and approved; the long-promised on-line reporting access to sector ministries to enable them to conduct analysis and extract TSA data for reports was provided to all ministries in late February 2016[17], supported with a half-day orientation to ministry staff and; IT staff with crucial knowledge of the TSA system remain externally contracted while IT human resource capacity within GoN remains weak. This review also confirmed earlier identified challenges. Field inspections confirmed that TSA IT infrastructure requires upgrading to enhance its speed and functionality. The system also continues to faces infrastructural challenges such as frequent power outages and connectivity issues that are common across Nepal. The TSA does not yet have 100% coverage of public sector funding. For example grants, locally collected taxes, and transactions through public enterprises remain outside of the system.
[17] Due to the timing of this development, it is not counted to the scoring of this output.

Indicator 1.2: The process to consolidate cash resources for TSA implementation commenced in 2010 with GoN identifying 14,000 operational spending unit bank accounts across approximately 4,000 spending units as a baseline for the 2010/11 FY. Alongside TSA implementation, the target of 500 operational accounts for 2014 was also achieved a year ahead of schedule, assisted by buy-in from commercial banks. Over the past year, the baseline estimate has been revised upwards to over 15,000 accounts while the process to close accounts has continued. Currently, there are approximately 600-700 accounts still operational (14,300-14,400 have closed), albeit with their aggregated balances estimated to be low at around 0.5% of the total cash balance[18]. It was noted during this review that GoN regulations require certain accounts to remain open – for example, local revenue collection accounts, special purpose and miscellaneous accounts. The District Treasury Comptroller Office (DTCO) consulted for this review also explained that long distances from Nepal Rastra Bank (Nepal’s Central Bank) branches have kept some accounts open. However, a review has been undertaken and discussions are underway on actions to close more accounts.[19]
[18] World Bank estimate
[19] GoN feedback in the process of this PCR indicated that FCGO do not see the need to close further accounts as the TSA roll out process has closed those accounts which are possible for closure. However, FCGO will seek to continue monitoring accounts to verify closure.

Summary of Responses to Issues raised in Previous Annual Reviews (where relevant)
The 2014 Annual Review recommended:
- That GoN ensure longer tenure of key staff, especially the PEFA Secretariat Coordinator. This recommendation has not been addressed. Staff turnover continues to be a substantial challenge for the continuity of strategic leadership and embedding technical capacity. For example, the PEFA Coordinator has changed 3 times in in the past year and 9 times during the full programme duration.[20] Targeted lobbying for certain positions may assist to some degree. However, this review notes that this challenge can only be sufficiently addressed through public sector reforms which are outside of the direct control of the programme;
  [20] Since 2013, the average duration of PEFA Secretariat Coordinator has been seven months.
- The development of a retention strategy for key IT staff, a needs assessment and a strategy to ensure the development of sufficient in-house IT capacity. It was noted during this review that financial incentives have been used to encourage the performance and retention of staff directly involved in the TSA implementation. These incentives are viewed as a major instrument for change. However, the long-term use of financial incentives has not yet been considered, neither has the financial sustainability of such incentives nor the possibility of using non-financial incentives. On developing sufficient in-house capacity, a plan has been in place for the past two years for external contractors to transfer their knowledge and skills. However, there is still a heavy continued reliance on external support;
- That FCGO and the PEFA Secretariat prepare a strategy on making payments directly by bank transfers instead of handing over cheques to spending units. This has still not been implemented.

Recommendations for future programmes
Nepal’s success at TSA implementation could provide a valuable case study for other countries. A case study should be produced and widely disseminated to assist other countries. This should capture the findings of the 2015 “Impact Study of Implementation of the TSA in Public Finance in Nepal”.[21]
[21] : http://www.pefa.gov.np/study-reports-in-different-pfm-areas/

Efforts should continue to ensure that internal IT capacity is built and retained. The use of both financial and non-financial incentives should be considered.

While there has been significant progress with the implementation of the TSA, a master plan to guide the strategic integration, harmonisation and roll out of all IT based financial management systems to central and local entities is recommended. This will help ensure that synergies are maximised and that incompatibilities do not occur. The master plan should also include a change management plan that addresses change implications from the diverse set of stakeholders that would be involved.

Output Title	Financial reporting and accounting standards improved in Nepal.
Output number per LF		2	Output Score	A+ On the basis of on-going work during 2015 for indicator 2.1 and the achievements for indicator 2.2
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	2015 Target	Progress
2.1 Nepalese Financial Reporting Standards (NFRS) drafted in line with International Financial Reporting Standards (IFRSs) and issued by Institute of Chartered Accountants of Nepal (ICAN).	The 2014 target for the NFRS to be drafted in line with IFRSs and issued by ICAN[22] was achieved in 2013 and reported as met in the 2014 Annual Review. A new indicator and target for 2015 to reflect further activities to support NFRS implementation was not established.
2.2 Number of pilot ministries with consolidated financial statements prepared in accordance with Part 1, Cash IPSAS (Enhanced transparency and qualitative financial reporting leads to better managerial decision making and allocative efficiency)	NPSAS piloted in 2 ministries (current log frame).	8 Ministries[23] (which of the below are considered as “Ministries”) have prepared financial statements on the basis of the NPSAS and have submitted them to the OAGN. / A+
[22] http://www.ican.org.np/nfrs.php
[23] Pilot ministries financial statements

Key Points
Indicator 2.1: The NFRS, in line with the IFRS, was issued by ICAN in 2013, a year ahead of schedule. More recently, 15 guidance notes including guidance on first time adoption of the NFRS, have been completed to assist the corporate sector to improve its financial report preparation. Training of trainer activities on the NFRS has also been undertaken. Furthermore, in June 2015, a Report on the Observance of Standards and Codes Accounting and Auditing (ROSCA) was produced.[24]
[24] Report available on http://mdtfpfm.org.np/reports

Indicator 2.2: Pilots for rolling out the Nepal Public Sector Accounting Standards (NPSAS) commenced with two ministries - Ministry of Physical Planning, Works and Transport Management and the Ministry of Women, Children and Social Welfare – in 2014. These were successful and certified by the International Consortium of Government Financial Management (ICGFM). Further to this positive result, eight further entities[25] prepared statements and submitted them to the Office of the Auditor General Nepal (OAGN), though they have not yet been certified. Overall, there has been high level and rapid buy-in to NPSASs although it was noted during this review that the preparation of the statements required extensive support from an external consultant.
[25] Entities include Minsters: FCGO, Office of the President, National Planning Commission, Ministry of Physical Infrastructure and Transport, and Constitutional Bodies: Commission for the Investigation of Abuse of Authority, Election Commission, Ministry of Foreign Affairs and Office of the Auditor General.

Summary of Responses to Issues Raised in Previous Annual Reviews (where relevant)
The 2014 Annual Review recommended:
- That the ICAN, Accounting Standards Board (ASB) and regulatory bodies of the Government work together to ensure that there are no slippages in the calendar of operations that was issued following the promulgation of the NFRS. The implementation of this recommendation is outside of the influence of the MDTF given that MDTF funded activities ceased once the NFRS had been promulgated. However, this review noted that MDTF activities provided the critical foundation upon which ICAN, ASB and regulatory bodies are working together to roll-out the calendar. The calendar is being rolled out - progress is being made for non-financial sector companies but it was noted that some financial sector companies are having problems adopting the standards;
- That FCGO start orientating respective ministries to ensure that there are no capacity gaps, if the roll-out of NPSAS is decided to be carried out in all ministries by next year. In July 2015, a directive was issued to all line ministries to prepare NPSAS compliant statements. However it has since been agreed that there will continue to be an incremental approach to the roll out to ensure the necessary availability of technical support, adequate capacity building activities and absorption capacity. The new targets are for five additional ministries in each of the 2015/16 and 2016/17 FYs. The MDTF is providing support for this.

Recommendations for future programmes

Support should continue to be provided to roll-out NPSAS across GoN. A strategy should also be devised to ensure that sufficient institutional capacity is built to reduce the level of assistance required from external consultants.

Output Title	Increased capacity and knowledge of key stakeholders in Nepal on public financial management.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	2015 Target	Progress
3.1 Number of districts where awareness raising programmes for GoN financial management staff on PFM reforms are carried out.	56	59 PFM orientation programmes (9 central, 13 regional and 45 district level) were carried out. / A
3.2 Number of analytical pieces of work on PFM in Nepal completed and disseminated.	Based on findings of all studies, national PFM reform strategy revised	A revised strategy was prepared over the course of 2015 and endorsed by the PFM Steering Committee in February 2016. The strategy draws on the recently completed (July 2015) PEFA assessment and other supportive documents. A
3.3 Capacity development plan for key PFM stakeholders in Government of Nepal developed.	Capacity development plan for key PFM stakeholders in Government of Nepal developed	A full plan has not been developed[26] / B
[26] Although a capacity development plan has not been developed during the period of this PCR, FCGO note that in March 2016, PEFA Secretariat began an Advanced Diploma in PFM, delivered by the UK’s Association of Chartered Certified Accountants (ACCA). This professional course, which runs from March 2016 to May 2017, involves 30 PFM staff from MoF.

Key Points
In 2008, a PFM Steering Committee (chaired by the Finance Secretary) and PEFA Secretariat (located in FCGO premises) were established to drive and coordinate PFM reform initiatives. The following indicators detail their progress.

Indicator 3.1: Over the past year, the PEFA Secretariat has conducted PFM orientation programmes at central, regional and district levels. The 2015 target had focused on the number of districts. However, given the small size of some districts, a supplementary approach was implemented to capture sufficiently large audiences through awareness raising programmes at the regional and central levels. In the case of districts, the Secretariat reached out to the more remote areas. Since the MDTF started, it has also supported the PEFA Secretariat to raise awareness on PFM through orientation events, newsletters and journals (newsletters and journals are published and circulated to every district). A radio programme, where public sector experts are interviewed to help disseminate information on PFM a reform was also broadcast twice a month through Radio Nepal. The Secretariat has a website to communicate its activities and disseminate PFM information: www.pega.gov.np. However it was noted during this review that some parts of the website have not been regularly updated, which limits the extent to which it can be regarded as an effective communication tool.

Indicator 3.2: Phase II of GoN’s PFM Reform Strategy (2016/17 – 2024/25) has been prepared, led by the Budget Division within the Ministry of Finance and the PEFA Secretariat, within the FCGO. The process has involved extensive stakeholder consultation and draws on a list of reference material, including on the July 2015 PEFA assessment. A consultant familiar with Nepal’s PFM system was contracted through the MDTF to provide support to GoN to enhance the strategic nature of the Reform Strategy. It appears to have not drawn specifically from the 2013 Operational Risk Assessment of PFM in Nepal[27] or the 2012 Public Expenditure Tracking Survey (PETS) for the education sector, which were studies previously commissioned under this work-stream. This review noted that the strategy has now been officially endorsed, although not within the scope of the PCR reporting period.[28]
[27] Operational Risk Assessment of PFM reform in Nepal: A Review of Challenges and Opportunities. Centre for Aid and Public Expenditure – August 2013.
[28] The Phase II PFM Reform Strategy is available at www.pega.gov.np.

A major achievement for the PEFA Secretariat during 2015 was the conclusion of the second PEFA assessment[29]. (The report was approved by the PEFA Secretariat in Washington DC in early 2015). This assessment had been led by the PEFA Secretariat with strong and inclusive GoN ownership. As a self-assessment, which acknowledges both the strengths and weaknesses within the PFM system in Nepal, this second PEFA assessment has been crucial for informing strategic and critical dialogue on PFM reforms between GoN and development partners, including DFID. Finally, five analytical studies have been completed over the past year[30]. The objective of these studies is to provide reference material and recommendations to influence policy making and the design of new initiatives. Most of these documents are available on the PEFA website, though do not appear to be disseminated further afield.
[29] http://www.pefa.gov.np/second-pefa-assessment-report-2015/
[30] These include studies on i) An Assessment on Internal Audit Reform in Nepal ii) A PFM training needs assessment iii) the impact of government investment in public enterprises in terms of loan and share investment iv) Impact of the implementation of TSA on public finance and v) The Pattern and Implication of off-budget items. Available at: http://www.pefa.gov.np/study-reports-in-different-pfm-areas/

Indicator 3.3: A PFM training needs assessment was completed by FCGO in July 2015. However the next logical step – to use it to devise a detailed capacity development plan – has not been completed. Instead, an ambition has been expressed to pilot a collaboration between a national institute (e.g. Nepal’s Administrative Staff College) and an international professional institute (e.g. CIPFA, ACCA and INGAF) to design and conduct accredited PFM courses in Nepal. Consultations during this review informed that an arrangement has recently been put in place involving the UK’s ACCA to start a diploma in PFM with 30 participants from March 2016. The draft Phase II PFM Reform strategy also states an objective to prepare and implement an action plan to establish a specialised PFM Institute.

The sustainability of capacity building activities is a major challenge for advancing Nepal’s PFM reforms. Given the two year transfer policy in the civil service, staff are rotated frequently and aside from accountants, there are no professional PFM cadres such as internal auditors or procurement specialists to ensure the retention of knowledge and skills. While the current vision is to draw from the aforementioned pilots to create a capacity building plan, the risk is that without some form of strategic plan prior to piloting, the pilot approaches become quickly systematised, without a proper consideration of how to sequence, integrate and resource PFM training, and ensure that approaches are cost-effective and build capacity sustainability. Given the rapid turnover of staff, a plan should also devise approaches that focus on building institutional, rather than individual capacity, to ensure that there is sufficient technical depth to provide continuity when staff leave.

Overall, while most of the indicators above are considered to be met, the PEFA Secretariat continues to face substantial challenges. Staff turnover remains problematic – the Secretariat head has changed 9 times in the last 8 years; coordination between national, sectoral and local PFM initiatives remains weak and; the extent of the Secretariat’s influence over the Ministry of Finance’s Budget Commission and National Planning Commission remains questionable.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2014 Review recommended:
- That the orientation of Government financial management should continue and all entities should be covered. Advanced training should be given to participants of the orientation to refresh them and give them the impression that it is not a one-off event. While some follow-up and advanced training has been conducted, it has still not occurred systematically;
- That the PEFA Secretariat should continue to work across Government, and should use the TA provided by DFID/Crown Agents to revive the PEFA implementation units in sector ministries – to strengthen national and sectoral linkages. This review noted that the DFID/Crown Agents TA embedded within the PEFA Secretariat has played a useful role, for example in supporting the preparation of GoN’s Phase II PFM Reform Strategy, a process that involved extensive cross-GoN consultations and workshop. However, consultations for this review confirmed that, more broadly, coordination across GoN on PFM reforms remains weak with frequent staff turnover and inter-GoN institutional dynamics contributing to constraints on the clout and capacity of the PEFA Secretariat to fulfil this function. PEFA implementation units are theoretically in place in sector ministries but there is little evidence to suggest that they are active and adding value to the PFM reform agenda.

Recommendations for future programmes
The draft Phase II PFM Reform Strategy significantly broadens the scope and enhances the complexity of planned PFM reforms in Nepal. Consultations suggested that the current structure and capacity of the PEFA Secretariat is not sufficient to effectively implement the strategy, both in terms of its capacity and its ability to convene and influence stakeholders across key PFM reform institutions. Future programmes should consider assisting GoN on how best to structure and capacitate a PEFA Secretariat so that it is able to drive effective inter-institutional GoN coordination on PFM reforms. To help secure stronger buy-in from other across the GoN system, the Operational Risk Assessment’s recommendation to staff the Secretariat with officials from other parts of the MoF (other than FCGO), line ministries and the National Planning Commission remains valid.

Echoing the 2014 Annual Review recommendation, a comprehensive capacity building plan should be developed as soon as possible. This should draw on FCGO’s July 2015 needs assessment and should be informed by a cost-benefit analysis on different approaches and delivery mechanisms (including using existing PFM related capacity building institutions) for building PFM capacity sustainably. Given high staff turnover rates in Nepali public service, the focus should be on establishing institutional capacity (rather than just individual capacity) and should consider training-of-trainer approaches to help ensure sustainability.

For future capacity building activities, there is also a need to establish approaches that assess the application of new skills and knowledge. This could include studies that monitor and assess individuals in order to trace the impact and sustainability of capacity building activities. This will help inform adaptive and cost effective approaches.

Discussions should be taken forward with the relevant GoN partners – likely in the context of broader public service management reforms - regarding the re-establishment of professional PFM cadres.

DFID Nepal should also open a conversation with the UK’s ACCA to information share and ensure that the ACCA’s approach is synergistic, or certainly does not create any longer-term challenges, for Nepal’s PFM capacity building strategy.

Finally, there is an on-going need to continue broadening the constituency for reform. The PEFA Secretariat should devise a communications strategy that continues its orientation programmes and explores other methods to create awareness and broad engagement with the PFM reform process. The benefits of PFM reforms, both on people and the GoN system, should also be actively communicated.
Consideration should be given to establishing a Communications Specialist position within the PEFA Secretariat. The Secretariat’s should also ensure that its website is kept up to date.

Output Title	Quality of public sector audits enhanced
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	2015 Target	Progress
4.1 Number of financial statement audits substantially within ISSAI framework.	28	28 (including audits of the financial statements of two NPSAS compliant ministries) / A
4.2 Frequency of in-depth performance audit reports.	3 per year	3 / A

Key Points

Indicator 4.1: Over the past two years, the MDTF has supported the gradual roll-out of pilots using a risk-based audit methodology consistent with the International Standards of Supreme Audit Institutions (ISSAI) framework. As at the end of December 2015, the cumulative target of 28 pilots was achieved.

Indicator 4.2: The following three in-depth performance audits were completed in 2015:
- Effectiveness of Social Security Programme and Effectiveness of Plan Selection and Implementation by Local Bodies – DDC of the districts Taplejung, Gorkha, Kalikot, Kailali and Baitadi;
- Effectiveness of Health Service Delivery System – in districts Ilam, Dhankuta, Siraha, Banke and Kalikot; and;
- Melamche Drinking Water Development Committee – Assessment of Project Implementation Status

All audits were quality assured and a workshop was conducted to exchange lessons learnt and refine methodologies. The majority of recommendations made for each audit were also accepted by the relevant entities. These audit reports will be submitted to the Public Accounts Committee, alongside the OAG’s Annual Report by its mandated 30th April 2016 deadline.

Overall, there have been a range of achievements to improve the quality of public sector audits since the sub-project to strengthen the capacity of the OAG commenced in February 2012. The financial audit manual has been updated, assisted by field testing on pilots, and translated into Nepalese; a bespoke computerised audit management system – the Nepal Audit Management System (NAMS) – has been developed; a range of capacity building activities have been undertaken – for example i) staff have been trained to use computer assisted audit techniques ii) NAMS end user roll-out training was delivered to 181 staff in OAGN in November 2015 - this included training of trainers (approx. 30 OAGN staff) who will now take the roll as in-house trainers and experts and iii) financial audit training was delivered to 20 FCGO staff in December 2015.

There have also been a number of informative study trips. Further to the catalytic work of the MDTF’s demand side component, PRAN (see output 5), the Auditor General visited the Philippines in November 2015 to learn about citizen participatory audit (CPA), which is considered to be strong there. With weak accountability at the local level and numerous remote districts, CPA could prove to be a highly valuable approach to improve the robustness and impact of audit reports. Further to this, CPA has now been included in the OAG’s long-term strategy and guidelines have been drafted to support its implementation. The OAG plans to introduce this approach gradually over the next 3-4 years. A delegation from the OAGN also visited Pakistan in December 2015 to receive training and share experiences on the auditing of rehabilitation and reconstruction projects. The plan ahead is for Pakistan’s Supreme Audit Institution and the OAG to sign an MoU to conduct joint auditing of rehabilitation and reconstruction projects, whilst continuing to share their experiences.

However, the original vision for this sub-project to enhance the impact of public sector audit has been difficult to realise due to factors beyond the MDTF’s control. There was no Public Accounts Committee (due to the absence of an elected Government) for the first two years of the project. Once established in April 2014, consultations for this review confirmed that it proved difficult to provide capacity building support (including site inspections) given the PAC’s size – it currently has 53 members and is known to be the largest in the world. The focus of the PAC after its establishment was also devoted to the political process to devise a new Constitution. In practice, this has meant that OAG reports have not been properly scrutinised for over three years while there are a number of unresolved issues from before 2010. Within the OAG, it was also noted that there was no permanent Auditor General from 2007-13.

This review noted that there have been clear synergies between this output and activities for the TSA (output 1), improved accounting standards (output 2) and advancing citizen participation in the audit process (output 5). Consultations suggested that the TSA has allowed a more efficient approach to auditing, assisted by computerised assisted audit techniques. The update to the financial audit methodology also takes into account IPSAS based financial statements.

Summary of Responses to Issues Raised in Previous Annual Reviews

The 2014 Annual Review recommended that the MDTF extends this area of support from June 2015 to December 2015 to finalise activities given the delay in hiring consultants at the start of the project. This extension was agreed. However, following the April 2015 earthquake, during which the OAG office in Kathmandu collapsed, a further extension was granted until June 2016 to enable activities, including those that had been halted, to be completed.

Recommendations for future programmes

The OAG faces a huge organisational challenge in coming years as it continues to strengthen the quality of it audits and in parallel, substantially extends its coverage to include municipalities and Village Development Committees as mandated in the 2015 Constitution. It was noted during this review that the OAG also plans to establish regional offices to fulfil its extended mandate. Consultations confirmed the need for continued support. Consideration should be given to substantially scaling up MDTF support to strengthen to OAG, in order to consolidate gains achieved and assist with the implementation of parts of its 2016-2020 Strategic Plan[31]. This should include activities to strengthen audit follow-ups[32] – the current overall compliance rate on implementing recommendations is low at around 50%[33] – and strategies to ensure that human resource capacity is sustainably built. Support should also be provided to strengthen CPA.
[31] http://oagnep.gov.np/uploads/05092072-%20SP%202016-20-Final_1451555461.pdf
[32] The NAMS will create a database of audit findings and recommendations, enabling the easier tracking and follow-up of audit recommendations.
[33] OAGN

While the Auditor General of Nepal is specified in the Constitution as an independent body, its budget and staffing levels continue to be controlled by the Ministry of Finance and Public Service Commission respectively. The OAG has submitted a request to the Ministry of Finance to amend the Audit Act to enable the PAC to approve its budget and staffing, thereby enforcing its independence. Development Partners should use influencing opportunities, including in high-level forums, to support the OAG’s bid.

Given weak accountability structures at the local level, the remoteness of some districts, and the lack of capacity at the OAG, the OAG should pilot test and if successful, scale up CPA approaches.

Support to the PAC should be re-visited. With the political context unlikely to substantially reduce the number of PAC members, support should nonetheless be provided to assist the PAC in devising effective operational approaches, building the capacity of its Secretariat and strengthening its relationship with the OAG.

Consideration should also be given to supporting activities to strengthen internal auditing to improve the internal control environment.

Output Title	Improved citizen engagement in PFM reform
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	2015 Target	Progress
5.1 Number of districts where Social Accountability media programmes targeting entitlements, budget awareness raising and main PFM issues are piloted.	15	15 / A
5.2 Number of Village Development Committees (VDCs) where procurement monitoring, expenditure tracking and budget awareness raising is undertaken.	300	300 VDCs are undertaking budget awareness raising activities / 100 VDCs are undertaking expenditure tracking activities / A
5.3 Percentage increase of entitlements being disbursed to the correct beneficiaries, on time and of the correct amount in at least 75% of the 90 targeted VDCs.	74.1%	Data not available.

Key Points
Activities under this output have been delivered by the Programme for Accountability for Nepal (PRAN), which focuses on developing the capacities of Nepali civil societies to use social accountability approaches to hold the GoN to account and demand better use and management of public finances. Over the duration of the programme, PRAN has been implemented in two phases – the first from 2012-2014, and following a re-design, a second phase was due to start in early 2015 but was delayed. CECI acts as the Grants Manager for the Program for Accountability in Nepal (PRAN), working with the range of civil society downstream partners.

Indicators 5.1 and 5.2
This review noted that it is difficult to objectively assess the performance of this output due to a number of factors:
- An insufficient implementation period due to factors both within and outside of the MDTF’s control: The start-up of activities under this output was delayed for nearly 6 months last year due to administrative problems associated with a lengthy process to obtain approval from the MoF for the programme, and protracted legal negotiations between the World Bank and EU on the overall MDTF. Budget awareness raising activities under 5.2 were also delayed in many VDCs in the Terai districts due to political unrest, which caused the closure of VDC offices (September 2015 – February 2016);
- Changed approach: During this review, it was also informed that the approach for indicator 5.2 was changed. Under PRAN 1, demand side activities were conducted in a ‘blanket approach’, implementing uniformly in all VDCs of operation. As part of the design process for PRAN 2 it was decided that demand side activities using the TSA, Grievance Redressal Mechanism, PETS, and Community Scored card tools, would be ‘clustered’, matching types of intervention to specific districts. This method was selected to improve the effectiveness of PRAN activities (enabling focus on certain activities in certain geographical locations) and facilitating ‘deep dives’ that were judged not as feasible in the previous approach. It was also decided that procurement monitoring would no longer go ahead. However budget awareness raising activities and public expenditure tracking of social security entitlements were both planned to continue. As the DFID log frame was not updated to reflect this changed approach, there is a mismatch between the framing of the 2015 target and the progress reporting;
- The World Bank verbally reported the progress achieved. However, it has been difficult to independently verify these results given the lack of concrete evidence.

This review noted that since October 2015, the project has initiated support to establish and improve local level grievance redress mechanisms (GRM). It has also been working to assist citizens to benefit from information generated by the TSA by involving local civil society to analyse real-time information on budget execution, and simplify and disseminate financial information from the system. The field trip inspection clearly showed that support for the GRM is highly valued. It appears to be premature to assess whether the initiative utilising TSA data will deliver effective results.

Indicator 5.3
Due to the significant political unrest in the Terai, the baseline survey could not go ahead – the survey results are not expected until May 2016. Together with the delayed start to the programme, there is no data to assess performance against this indicator.

Overall, this review is assessing performance to the end of December 2015. It is therefore noted that this review is unable to provide an assessment of the full PRAN implementation period, which is due to end in June 2016.

Over the first[34] and second phases of PRAN, results delivered have been good and the fieldwork undertaken for this review verified that PRAN has played an important role in raising awareness and empowering citizens at the grass roots level. PRAN achievements include:
[34] Under the first phase of PRAN, small grants (USD 15,000) were provided to 40 CSOs in ten districts of the Far West, Mid-West and Western regions covering 80 VDCs. Each CSO worked through a community-led process on four PFM areas of implementation: open budgets, gender and pro-poor budgets, PETS and procurement monitoring. The grants were for 8 to 11 months during FY14. The current (ongoing) PRAN program provides sub-grants to 30 CSOs (2 CSOs in each of the 15 districts of operation).
- 138 CSOs trained through PRAN social accountability schools;
- Production of information, education and communication materials on budgetary issues targeted to educate journalists;
- Training for CSOs on budget literacy, gender and pro-poor budget analysis, and public procurement monitoring
- Awareness raising on social security entitlements which have directly helped marginalised communities and disadvantaged people. For example, case study examples[35] show that:
  [35] How Social Accountability Can Make a Difference: Evidence from PRAN in Nepal. World Bank, 2014
- In Dubiya VDC, budget analysis orientation starting in 2013 increased awareness among women about their rights to draw on 10% of the VDC budget for funding initiatives aimed at their development. As a result NRs 222,000 (USD 2,288) was allocated for the Construction of a Women Community Centre. The construction is now completed;
- Participatory Budget Analysis conducted in Seram VDC in September 2013, with support of a PRAN funded CSO, resulted in increased awareness and activism among disadvantaged community groups about the budget and their entitlements to targeted financial allocations. As a result, in the 2013/14 FY, out of a total of NRs 1,450,000 (USD 14,948.45) transferred to Seram VDC as capital investments, NRs. 145,000 (USD 14,94.84) (10%) was assigned for addressing women’s issues, another NRs.145,000 (USD 14,94.84) (10%) was reserved for children and NRs. 217,500 (USD 2,242.27) (15%) was dedicated to the marginalised groups initiatives. This marks a substantial increase from the 2011/12 FY allocations of 3%, 3% and 9% for women, children and marginalised groups respectively.
- Additionally, 40 social accountability practitioners were trained on data collection through local PETS around three categories of government-provided social security entitlements (SSEs). They conducted PETS in all 80 VDCs of ten districts and collected 11,158 data sets. The survey was the first of its kind in Nepal regarding SSEs in terms of the size of the database and those who conducted it. The survey results have been analysed and compiled for discussion with the MoFALD officials as it includes a series of policy and programmatic recommendations to improve the SSE implementation.
- Six episodes of a MAHA national tele-drama, accompanied by public service announcements (both audio and video), were produced on misuse of SSEs for the marginalized and poor;
- At the national level, PRAN supported collaboration between the Office of the Auditor General (OAG) and CSOs/media. The intervention has led to the establishment of an on-going OAG-CSO consultative process providing support in the dissemination and follow-up of the OAG annual audit report, as well as the implementation of performance audits with community participation at the local level, and an innovative regional learning exchange process (led by the OAG) among the senior staff of the Supreme Audit Institutions in South Asia. Other outputs included workshops between the OAG and civil society on performance audits at the district level, the design of Citizen Engagement framework, and a draft of the operational manual to help CSOs and the OAG work collectively on performance audits. For further information on CPA, please refer back to output 4.

However, consultations for this review suggested that PRAN has been negatively impacted by short implementation timeframes and inadequate resourcing. There was also a year gap in the implementation period between the first and second phases, during which PRAN lost a number of strongly performing CSOs from its network. This review also noted that there is a strong sense amongst some that PRAN has not been “broadly owned” by the World Bank and some MDTF development partners, which contributed to the aforementioned problems. Overall, views expressed on PRAN are mixed. Some view it as an important approach for building demand side pressures in a country with weak and missing local accountability structures. Others criticise it for not being built into GoN systems, and therefore not “owned” by GoN; that it has limited potential to influence policy level PFM reforms; and that further effort is still required to ensure that it is properly coordinated with other local level social accountability initiatives, including through the Local Governance and Community Development Programme (LGCDP).

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2014 Annual Review recommended:
That PRAN i) works more closely to strengthen existing Governance structures (particularly Ministry of Federal Affairs and Local Development (MOFALD), Local Governance and Community Development Programme (LGCDP), OAG and the PEFA Secretariat) through which social accountability tools will be operationalised and ii) that PRAN continues to work closely with the DFID/DANIDA/Switzerland supported Governance facility programme to avoid duplication and complement the programme. This review noted that PRAN has been re-designed to help address these coordination challenges. However, consultations for this review confirmed that there are on-going concerns regarding PRAN’s coordination with other initiatives.

Recommendations for future programmes
Demand side initiatives to ensure that PFM systems are working effectively for the benefit of the people, particularly the poor, can play an extremely important role in a PFM reform programme. This is particularly the case in a country context such as Nepal, where accountability structures at the local level are weak. Although more recent GoN policies, acts, regulations and guidelines provide space to strengthen the application of social accountability approaches related to PFM reforms, the consistency of monitoring and compliance within local bodies in regard to these regulations has been problematic. This is due to the limited capacity of local government, irregular assessments, lack of PFM technical skills knowledge among CSOs, as well as the demanding geography and language and cultural diversity of this resource-constrained country. Despite these barriers, PRAN has achieved good results in some areas. However, there are a number of fundamental design questions and issues that still need to be addressed to ensure that it able to effectively contribute to MDTF objectives. Consultations during this review suggested that the following key questions still need to be properly addressed:
- How can demand side initiatives such as training CSOs in social accountability tools and techniques have a real impact on government policy? How can demand side initiatives create a critical mass of pressure to incentivise systemic PFM reforms?;
- What is the best approach to support CSO initiatives in the context of Nepal? Through GoN, such as the LGCDP approach? Or independently of GoN structures, such as the PRAN approach?

Consultations during this review also suggested that the following key design problems need to be properly resolved:
The length of the implementation period: Demand side initiatives, particularly those engaged on technical areas and working with marginalised communities and disadvantaged people, require long-term – multi-year, not as short as 18 months as for PRAN II - commitments to ensure that a platform for trust and voice is properly established. Future demand side initiatives should therefore be supported over longer timeframes and be better resourced
Coordination with other demand side initiatives on PFM related issues: This review noted on-going concerns regarding overlap between PRAN and MOFALD’s LGCDP initiatives, despite efforts (including a re-design) to avoid this. In practice, the fieldwork inspection showed that even with multiple initiatives in the same location, there remains a huge unmet need for support. In many cases, this reflects the over-stretched capacity and frequent turnover of VDC Secretaries and their staff. In any case, there is still a need for an on-going discussion regarding the coordination of demand side local level initiatives.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers remained unchanged throughout the implementation period. These include:
1. International and local technical assistance procured through the World Bank;
2. Software and hardware procured for IT based financial management and audit systems;
3. Analytical studies such as the operation risk assessment, second PEFA assessment,
4. Grants to civil society organisations (under the PRAN component) to hold GoN to account.

VfM performance compared to the original VfM proposition in the business case
No VfM metrics were established during implementation to routinely assess VfM performance. The assessment of VfM is also difficult as DFID’s log frame is an abridged version of a broader M&E framework and; detailed financial information is not available to assess the VfM of results delivered. The VfM assessment below therefore relates more broadly (than DFID’s log frame) to the MDTF activities.

Economy (quality and price of inputs)
To establish VfM from an economy perspective, the review considered procurement procedures, the range of actual consultancy rates for international personnel, and the cost of the TSA and NAMS. It also considered World Bank management charges.

This review confirmed that the programme adhered to existing World Bank rules and practices for procurement. This includes competitive and transparent recruitment and procurement processes, as well as cost effective selection. The World Bank also supervised the GoN, and provided no-objections for inputs procured by the GoN.

Details of World Bank consultancy rates cannot be disclosed for commercial sensitivity reasons. DFID relies on the effectiveness of World Bank assurance processes and has assessed that these provide adequate control and has confidence in World Bank procedures for the effective management of trust funds.

Throughout implementation of the programme, the World Bank has charged a 2% trust fund administration fee plus an additional 4% to manage the programme. The World Bank is widely viewed to have a comparative advantage on PFM. With its management of the MDTF, DFID has been able to support PFM improvements by leveraging its technical expertise, fiduciary oversight and convening power. It is unlikely that a private sector implementing partner would be able to deliver as effectively at a lesser cost, and would also likely have less convening power. Lessons from DFID Nepal’s sectoral and local level PFM programme and other programmes within the governance portfolio also suggest that alternative multilateral implementation partners would have been fundamentally unable to deliver results of a high quality and efficient nature. Overall, DFID has achieved good VfM through supporting PFM reforms using the World Bank as a delivery mechanism.

Efficiency (converting inputs into outputs)
To establish VfM from an efficiency perspective, the review intended to consider whether the outputs achieved required the type and level of spending provided. However, it was not possible to assess this without a more detailed breakdown of World Bank spending per activity, to determine the association between what was spent and what was achieved at the output level. It was also noted that there are no tracer studies to more accurately assess the impact and sustainability of capacity building activities. Where outputs were met ahead of schedule, for example the TSA roll-out, the lack of disaggregated data again does not allow a full analysis on whether efficiency gains were realised.

The review also considered data on the MDTF’s costs for the TSA roll-out, and available information on the benefits generated:
Financial support for implementing the TSA system totals around $4.3 million to date, composed of a $3.8 million contribution from the MDTF and an approximately $0.5 million contribution from GoN. DFID funding for the TSA is estimated at approximately $1.14 million, which equates to around 30%[36] of the donor contribution through the MDTF; Financial benefits have arisen from reduced interest payments on internal borrowings (given the consolidation of cash balances which the TSA system has enabled) and to a lesser extent, reduced commission paid by the Nepal Rastra Bank (NRB) to commercial banks following the closure of around 14,300-14,400 spending unit bank accounts held in commercial banks. The World Bank conservatively estimates that an annual interest saving of approximately $1million (NRs 112mn) is accruing to GoN on account of the consolidation of cash balances through the TSA concept.[37] On the assumption that DFID funded approximately 30% of the MDTF’s cost of the TSA implementation, and taking into consideration the additional cost made by GoN, approximately $265,000 of annual interest savings can be attributed to DFID. This is deemed to be a conservative estimate as DFID’s funding was first into the MDTF and during the period to roll-out the TSA system, it constituted more than 30% of the MDTF’s support for the TSA. Furthermore, there are financial benefits arising from reduced commission charges, which are difficult to quantify given that the reduction in number of bank accounts occurred in parallel to a restructuring of commission charges. Finally, there are a number of benefits which have not yet been quantified. For example, the reduction in financial leakages resulting from the improved control environment that the TSA system has introduced.
[36] Calculation is based on the fact that DFID had provided approximately 30% of the MDTF’s receipts by the end of December 2015.
[37] World Bank Project Paper for PFM MDTF Financed Strengthening Public Financial Management II Project – July 2015.

In cases where benefits are ‘hard to measure’, DFID also considers beneficiary feedback as an approach to assess VfM. Feedback on the TSA system[38] confirms a number of intangible benefits. Of 55 spending units across seven districts questioned:
[38] Impact Study of Implementation of the TSA in Public Finance in Nepal. Centre for Public Policy Dialogue
- 49% reported that their workload had decreased (27% reported no substantial change);
- 95% reported that DTCOs are now issuing cheques within the given timeframe;
- 95% reported that the quality of financial reports after the implementation of the system had improved;
- 53% felt that the system is supportive for maintaining financial discipline; additionally 34% to some extent;
Of eight DTCO questioned:
- 37% reported that the system reduced embezzlement of cash to a great extent with a further 63% citing to some extent;
- 75% reported that the system quickened their reporting time
However,
75% reported that their workloads had increased;

As documented earlier, there remain a number of outstanding challenges that were reported through this beneficiary feedback such as the need for continued capacity building, server upgrading and power outages. However overall, the feedback on the TSA from user level is positive.

Effectiveness (achieving outcomes with the outputs produced)
An independent mid-term review[39] concluded that the MDTF’s objectives were highly relevant for tackling challenges, such as unacceptable fiduciary risks in Nepal’s PFM system. Consultations for this review confirmed that this has remained the case. This strategic fit has therefore helped ensure that the programme is delivering VfM.
[39] Nepal Public Financial Management Support – Multi-Donor Trust Fund. Mid-Term Evaluation. Clay Wescott 2014

There are also a number of intangible benefits that the programme has to help set a positive momentum for reform going forward. Stakeholders interviewed strongly felt that the MDTF has been a key instrument for change, both in terms of the results it has helped deliver and the visibility that it has given to the PFM reform agenda. It was noted during this review that the MDTF is currently the only development partner-supported instrument working at the central policy level on PFM reforms. It includes several of the largest spending and most influential development partners. Overall, this has helped establish the MDTF not only as an instrument for donor coordination and harmonisation but also as a credible and influential instrument with convening power.

Equity
Equity considerations are strongly embodied into the PRAN design at various levels. For example, the overall PRAN objective is to i) empower communities to hold local government to account for participatory pro-poor and gender inclusive budgeting and ii) improve citizens access to individual social security entitlements including for single women, the disabled, elderly and disadvantaged groups.
CSO applications for grants from PRAN were required to include a clear strategy for the promotion of gender and social inclusion; PRAN has also actively aimed to recruit women as Social Accountability Practitioners; and PRAN reports to DPs using data disaggregated by key markers of exclusion (caste, ethnicity and sex).

Assessment of whether the programme represented value for money
For reasons identified above, it is judged that DFID’s funding to the MDFT to support Nepal’s PFM reform agenda has delivered very good value-for-money.

VfM Recommendation
Future programmes should ensure that metrics are agreed to monitor the VfM of the programme. The World Bank should also ensure that sufficiently disaggregated financial information is provided to enable this assessment.

Quality of financial management during programme
DFID has contributed a total of £3.5 million ($5.57 million) to the World Bank led Multi Donor Trust Fund over the course of the programme. Based on a first in first out principle, DFID was the first donor to join and contribute towards the trust fund arrangement following a three tranches payment schedule (2011 - £1,300,000; 2012 - £1,3000,000; and 2013 - £900,000). DFID funds were disbursed based on payment requests made by the World Bank. For the second tranche payment in 2012, DFID delayed payments given slow progress and remaining unutilized funds under the MDTF (for reference Quest no. 4249497).

The MDTF has seven funders with a total pledged amount of $20.92 million as at the end of December 2015. Over the duration of the programme, DFID funding therefore represented approximately 26% of the pledged amount.

DP Name	Pledged Amount		Receipts at January 2016
United Kingdom – Department for International Development (DFID)	GBP 3.5 m	Eqv. USD 5.57 m	USD 5.57 m
Royal Norwegian Embassy	NOK 15 m	Eqv. USD 2.62	USD 2.6 m
Embassy of Denmark	DKK 2 m	Eqv. USD 0.38 m	USD 0.38 m
Department of Foreign Affairs and Trade	AUD 2.85 m	Eqv. USD 2.99 m	USD 2.99 m
European Union	EUR 4.5 m	Eqv. USD 5.6 m	USD 5.1 m
Government of the Swiss Confederation	CHF 3.0 m	Eqv. USD 3.05 m	USD 1.02 m
United States Agency for International Development (USAID)	USD 0.71 m	Eqv. USD 0.71 m	USD 0.71 m

Reporting: The World Bank has provided timely progress reports including both narrative and financial reporting to partners on a six monthly basis. The last semi-annual progress report was received in August 2015 covering the period Jan-June 2015. DFID has been provided access to the Bank’s portal on ‘client connection’ where we can view the financial statements of this trust fund and audit reports for World Bank trust fund modalities globally. The last financial report was received for the period covering January 2016, although given trust fund arrangements, DFID funds are not separately identifiable.

Conversations with other development partner organisations and World Bank as part of this review, as well as minutes of Programme Coordination Committee (PCC) meeting in August 2015, suggest donor dissatisfaction in the quality of financial reporting. Currently, financial reporting is high level and lacks detailed information that would be helpful to understand the key cost drivers, planned vs actual spend, forecast and mapping of uncommitted funds under the MTDF.

Financial Arrangement: Decisions on activities to fund under the programme are approved by the PCC and managed by the Trust Fund Administrator. The World Bank has three key implementing partners under the programme: i) Public Expenditure and Financial Accountability (PEFA) Secretariat; ii) Office of the Auditor General (OAG); and iii) Centre for International Studies and Cooperation (CECI) who work with a range of downstream partners, including the Government, Civil Society Organizations/NGO’s and International Organisations such as Transparency International amongst others.

As per the Trust Fund arrangements, all standard MDTF procedures have been used under the programme, including both reimbursement and direct payment mechanisms. A special account has been set up for the government related programming. According to the Operational Manual all Recipient Executed projects are processed in accordance with World Bank Operational Policies and Procedures for investment lending operations, Trust Fund guidelines and SAR regional project processing guidelines; and all Bank Executed projects will be processed in accordance with Bank Administrative Procedures.

Audit and quality management: As per the Trust Fund Administration Agreement World Bank provides partners with an annual single audit report that reports on the internal control over financial reporting for all cash based trust funds as a whole. The last audit report by KPMG, received in September 2015 covering the 2014/15 FY, provides the assurance on satisfactory internal financial controls under the MDTF. As part of this review, the World Bank has not flagged any key concerns in terms their third party financial management arrangements, which the Bank reviews periodically via regular meetings and reporting schedules as specified in individual grants. The World Bank carries out two Financial Monitoring supervisions missions per year to ensure thorough financial management under the programme.

Date of last narrative financial report	August 2015 (narrative report).
Date of last audited annual statement	3rd September 2015 on the 2014/15 FY. / Quest: 5243937

E: RISK (½ page)

Quality of risk management over the life of the programme
At inception, the overall risk rating was assessed as high. However, the 2013 review recommended a downgrade to ‘medium’ as the programme was proving to be well-performing with activities either directly executed by the World Bank, or with robust Bank oversight for recipient-executed activities. In more recent years, DFID Nepal’s programme team has met monthly to review risks and subsequently update its risk matrix, including any necessary mitigating actions.

Key risks and mitigating actions taken over the life of the programme include:

Risk description	Mitigating Actions Taken
Lack of GoN ownership to PFM reform with potential resistance	The programme focused on aligning with GoN strategies and plans, and focusing on technical wins. This helped ensure the necessary support from GoN stakeholders. This review also noted that the success of the TSA roll-out has provided an important demonstration effect that maybe tempering resistance to PFM reforms and helping build GoN ownership. Potentially indicative of this was GoN’s strong and inclusive engagement in the process to devise the second PEFA assessment, and the wide consultation process undertaken to prepare the Phase II PFM Reform Strategy. / This review also noted that in the specific case of the TSA roll-out, initial resistance at the working level was successfully overcome through the use of financial incentives.
Frequent transfers of key staff in FCGO, MoF, line ministries and other agencies leading to a lack of continuity and ownership	Transfers remained frequent throughout the lifetime of the programme. In some cases, this presented opportunities for better quality engagement – in other cases it was disruptive to the momentum of the programme. During this review, some examples were cited of successful lobbying efforts to retain key people in their positions. However generally, the programme will have had limited potential to manage this risk as a solution requires civil service reforms.
Inadequate capacity of implementing agencies including the World Bank	Weak capacity contributed to operational and fiduciary risk but this was mitigated by technical support (including consultancy inputs) and oversight from the World Bank. / Throughout the lifetime of the programme, there were continual recommendations to strengthen the capacity of the PEFA Secretariat. This was never properly achieved and as a result, the Secretariat probably proved less effective than it could have been. However, the review noted that new staff joining the PEFA Secretariat in 2015 are very committed and have taken a leading role in the design of the second phase of GoN’s PFM reform strategy. The government-led process that delivered the second PEFA assessment was another demonstration of GoN ownership and increasing capacity. / Throughout most of the programme’s duration, DFID and other MDTF funders frequently and strongly expressed their dissatisfaction with the absence of a full-time resident World Bank MDTF Manager. World Bank technical leads also remained based in various locations i.e. Delhi and Washington DC. Whilst these World Bank arrangements have proved frustrating for MDTF funders, particularly from an administrative perspective, they have not had a significant negative impact on the delivery of the programme.
Mis-utilisation of funds, corruption and fraud.	The risk of mis-utilisation of funds, corruption and fraud remained low throughout the programme due to the nature of the activities funded and the World Bank’s robust oversight.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The MDTF started about one year late (November 2011) due to administrative challenges within the World Bank and negotiations with GoN. Once operational, further challenges were faced due to slow implementation from the GoN side as a consequence of a partial budget year. Thereafter the pace steadily improved and key activities under output 1 and 2 were delivered ahead of schedule. However, in the past year, the PRAN component (output 5) became off-track from its original timescale – see output 5.

Performance of partnership(s)
This review noted that some MDFT funders, including DFID, have been dissatisfied with some aspects of the World Bank’s administrative management of the MDTF – for example, its delays in formulating results frameworks, the lack of detailed financial information, inadequate communication of key decisions and dissemination of programme evidence products (studies etc.), and the long periods where there has been no locally based full time World Bank MDTF manager. While the partnership between funders and the World Bank is assessed as satisfactory overall, this review proposes a number of recommendations to ensure that a future programme avoids the above mentioned challenges:
- The long awaited recruitment in early 2016 of a locally-based senior full-time World Bank MDTF manager is widely viewed as highly positive. It will be essential to ensure that this position remains filled at an appropriately senior level as it is key for the continued engagement with GoN stakeholders, to maintain the programme’s strategic and technical momentum, to ensure coherence across the MDTF’s sub-projects/components, and ensure that MDTF funders are kept up to date and provided with requested information in a timely manner;
- More specifically, for future MDTF phases, it is recommended that the World Bank ensure that it embeds a sufficient level of dis-aggregated financial information to allow results to be costed and a more rigorous assessment of VfM. This will also help ensure that a flexible and adaptive approach, that delivers VfM, is employed;
- The World Bank should move beyond simple progress reporting to assess more systematically and strategically the ‘theories of change’ that help inform how the delivery of results at the output level lead to outcome level results;
- Development partners and the World Bank should work to align all MDTF funders behind a common annual review format, timeline and process to ensure effectiveness and minimise transaction costs on both itself and GoN.

The partnership between the World Bank and GoN is assessed as very good. Feedback received during this review confirmed that World Bank technical leads have closely interacted with GoN counterparts and have provided high quality support.

Feedback from GoN stakeholders and other development partners (DPs) confirmed that DFID has played an active and constructive role to support the implementation of the MDTF throughout the duration of its funding support. However for its own monitoring purposes, as cited earlier in this review, DFID missed key opportunities to update the logframe. Going forward, DFID should ensure that the logframe is purposefully up to date. DFID should also ensure that it, and other MDTF funders, align behind one annual review process as cited above.

Asset disposal and value obtained by DFID
The Trust Fund Arrangement Agreement states that the equipment, vehicles and supplies paid for by the contribution shall be transferred to recipients, local authorities or to the final recipients (excluding commercial contractors) in accordance to World Bank’s policies and asset management.

However the World Bank continues to monitor assets as part of the bi-annual financial supervision missions. According to the last Aide Memoire (September 2015) World Bank agreed to put in place an Asset Register for non-IT assets by October 2015. As part of this review the World Bank reported a delay on developing the non-IT register/taking forward activities under the programme owing to challenging situations in-country following the earthquake and border blockade. Data for the non-IT asset register is being collected by GoN currently. World Bank expect the register to be prepared by end April 2016.

 CONDITIONALITY (½ page)

No specific conditions were applied to this programme

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The World Bank commissioned an Operational Risk Assessment in 2013, which provided a political economy analysis of PFM in Nepal. This provided a strong evidence base, further to which a number of recommendations were made for “quick wins”, sustained engagement reforms, and longer-term reforms outside of the control of public officials. Implementation of some of these recommendations occurred during the programme period, and continue to be actioned beyond the review period of this PCR. For example, upgrading the audit techniques of the OAG and efforts to connect citizen based and social accountability initiatives with OAG audits. The implementation of other recommendations such as strengthening the PEFA Secretariat’s capacity continues to face challenges as documented earlier. Finally, there are a large number of recommendations that are likely to be taken forward in the context of MDTF support for a second phase GoN reform programme.

Additionally, a mid-term evaluation[40] was conducted and shared with DPs in November 2014. This concluded that the objectives for the MDTF were highly relevant and its design is substantially relevant as it “builds on a foundation of analytical work and commitment to reform, based on a theory-of-change recognising that success will only come from a sustained partnership bringing together responsible government agencies and CSOs with DPs”[41]. There have only been minor modifications in the supply side components, largely to build on completed activities and extend timeframes to complete activities. Hence this conclusion remains valid.
[40] Nepal Public Financial Management Support – Multi-Donor Trust Fund. Mid-Term Evaluation. Clay Wescott 2014; Consultations for the PCR
[41] Nepal Public Financial Management Support – Multi-Donor Trust Fund. Mid-Term Evaluation. Clay Wescott 2014

As detailed earlier, the PRAN component was re-designed following a World Bank study revealing a number of important structural impediments to advancing PFM reforms and social accountability initiatives in Nepal[42] and evidence gathered under the first phase of PRAN. The key change was a shift of focus away from empowering CSOs to work with communities, to instead ensuring that CSOs and civil society support sustainable community-local government relations so as to exercise accountability more effectively. The observation under the first phase - that multi-year periods are required for working with local bodies and communities - was not implemented for the second phase of PRAN, confirmed in the consultations undertaken for this review.
[42] World Bank Report No. 87922-NP, Local Service Delivery in Nepal, April 2014

Throughout the programme’s implementation, progress has been monitored and decisions made through the formal semi-annual Programme Coordination Committee (PCC) meetings. These meetings were attended by Heads of Missions, or their representatives, and chaired by the Finance Secretary, or his representative. In early 2015, a technical working group was also established to provide a forum for technical discussions before discussions took place at the PCC. This included DFID participation.
The World Bank produced six monthly progress reports. PRAN produced monthly newsletters and shared these with relevant stakeholders. The World Bank also organised various review missions where representatives of DPs were invited. In addition, DFID attended conducted field visits and attended relevant workshops and conferences in Kathmandu.

Monitoring progress throughout the programme
This Programme Completion Review was completed by Kerry Nelson, Economic Adviser for DFID Southern Africa, with support from Radha Verma and Surya Rana, programme managers for DFID Nepal. The process included a desk review of documents; consultations with GoN staff, civil society organisations, the World Bank and other MDTF funders; and direct observations from field visits to Palpa District. Matt Clancy, SRO, provided quality assurance and oversight. Tom Wingfield, GSD Leader provided final quality assurance. Government of Nepal representatives from the FCGO, OAG and MoF (International Economic Cooperation Coordination Divison) were invited to participate in this review and to join on the field trip to Palpa districts. Unfortunately due to time constraints, no GoN representatives were able to take part in the field trip. However, GoN stakeholders from OAG and FCGO were able to provide time to take part in the consultations referred to in this review and also provided written feedback on the draft PCR. The review team thank all stakeholders for their valuable inputs.