Business Case

Summary Sheet

Title: Building Resilience in Ethiopia (BRE)
Programme Summary: This programme will showcase the UK as a leading global humanitarian donor. It will support the Government of Ethiopia to deliver a more effective, self-financed and accountable response to humanitarian and climate shocks. This will save lives and build on UK expertise. It will: / Deliver technical assistance to the Government of Ethiopia to lead and deliver an effective, more self-financed and accountable response to climate and humanitarian shocks. / Deliver food and cash to people in humanitarian need in the most effective way. / Respond to non-food emergency humanitarian needs in the most effective way. / Monitor, evaluate and learn to strengthen humanitarian delivery in Ethiopia in accordance and contribute to global best practice. / Indicative results include: / Government of Ethiopia more able to lead, prepare for and self-fund an effective humanitarian response to crisis. / Improve nutrition for up to 2.3 million people who would otherwise go hungry / 1 million children vaccinated against terrible diseases. / 100 thousand people provided access to clean water
Programme Value: £168 million 2017/18-2021/22.		Country: Ethiopia
Programme Code: 300363	Start Date: 1 May 2017	End Date: 31 March 2022
Overall programme risk rating:	Medium

Intervention Summary (2 pages max)
Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver. Every year in Ethiopia, depending on the severity of climate and humanitarian shocks, between 11 and 18 million people are unable to meet their basic needs. This programme will meet emergency needs and support the Government of Ethiopia to lead a response that is effective, increasingly self-financed and accountable. This will include exploring the role of insurance in financial planning for disasters. This will mean that overtime Ethiopia will not need to rely on relatively expensive international funding and delivery bodies. In Ethiopia, January 2017, the Secretary of State spoke alongside the UN Secretary General and the Government of Ethiopia about the importance of delivering humanitarian aid through one Government led system. This vision will save lives and money.
BRE will run for five years from 2017/18 – 2021/22 and will be up to £168 million of DFID RDEL. The programme is 66% climate finance. It has three strands:
Technical assistance: £32 million. To support to Government of Ethiopia lead an effective response to climate and humanitarian shocks.
Delivering lifesaving humanitarian support: £133 million. This will include £25 million funding to the UN run Ethiopia Humanitarian Fund to provide emergency life saving interventions (e.g. access to clean water and shelter) and £47 million to the World Food Programme (WFP) to provide emergency food and cash. Funding for humanitarian response in the last three years of the programme will be allocated to where it can deliver the most results; we expect at least some of this to be through the Government of Ethiopia.
Evidence and learning: £3 million to understand what works in terms of system reform and most effective delivery and provide real-time monitoring information to the programme, including beneficiary feedback.

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
- BRE will deliver on three priorities of the UK Aid strategy – humanitarian response, effective climate spend and supporting the poorest to exit poverty.
- BRE supports the four pillars of the National Security Council (NSC) strategy. Stability: Ability to manage crisis and deliver for the poor, whilst retaining growth makes it more likely that Ethiopia will remain stable. Security: Ethiopia plays a critical role in regional stability; Ethiopia keeps at bay threats to the UK such as Al Shabab. Prosperity: Ethiopia needs stability and an effective workforce to grow as a UK trading partner. Migration: A more stable, prosperous Ethiopia is a more attractive prospect for Ethiopia’s youth.
- BRE is central to DFID Ethiopia’s Business Plan and falls under SO2.

What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
- Improve nutrition for up to 2.3 million people who would otherwise go hungry
- 1 million children vaccinated against terrible diseases.
- 100 thousand people provided access to clean water

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy? The international community is committed to supporting a GoE led humanitarian response that is sustainable, timely, cost efficient and effective. This will decrease dependence on the relatively costly international system.

Has the programme considered working with HMG Departments and accessing cross-HMG funds?
We are working closely with other HMG departments but all finance is from DFID.

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
- As part of an overall strategy to support the GoE to develop a single system that can work for the poorest, the programme will work with the national scalable safety net that supports the 8 million most vulnerable Ethiopians.
- BRE works within the context of DFID programming supporting the economic structural transformations necessary to sustain poverty reduction.
- This programme will work with the proposed London Centre of Excellence on sovereign risk insurance; deploying British Expertise to support Ethiopia.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
Provisions to ensure flexibility include: break points in the contract; evidence based decision points for the allocation of finance; independent monitoring so we have the data to make effective programme decisions in real time.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
Yes. There is also a clear risk management strategy.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
- Yes. We are also looking into a media announcement.
- The programme will be fully branded with the UK logo as appropriate.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
- The programme has been quality assured by the Head of DFID Ethiopia and was described as ‘Category One’ and ‘Excellent’ Quality Assurance Unit.
- An initial political economy analysis has been undertaken to inform design. There is strong political will from the Government of Ethiopia and humanitarian partners to deliver a more effective response to shocks.

Does the SRO and team have the capability and resources to deliver this programme?
- Yes. The SRO is an A2 Adviser supported by an A2 Humanitarian Adviser, and an experienced Programme Officer.
- A Building Resilience in Ethiopia Steering Committee will meet quarterly and report to the Head of Office.
Strategic Case

DFID Ethiopia’s vision is that by 2020, Ethiopia is transforming into an industrialised, resilient, more inclusive country that is more able to self-finance its way out of poverty and harness the potential of its youth. This is firmly in the UK’s national interest and aligned with the priorities of the UK Aid Strategy, Ethiopia’s Growth and Transformation Plan 2 (2015 – 2020) and the Sustainable Development Goals. This programme will focus on supporting Ethiopia to be more resilient and able to more effectively self-finance out of poverty. This programme will work within the context of our tax and private sector programmes, our work with refugees and migration, and basic services programming to contribute to the overall objective above. These programmes will work within the broader context of Ethiopia’s Growth and Transformation plan. Together these approaches will seek to increase resilience and reduce poverty.
[note] Ulrichs and Slater, How can social protection build resilience? Insights from Ethiopia, Kenya and Uganda, Working Discussion Papers, ODI,(London 2016)

Poverty and Vulnerability in Ethiopia

Ethiopia is one of the poorest countries in the world with a GDP per capita of just $619 per head in 2015. Impressive growth rates and pro-poor service delivery have led to significant poverty reduction but the poorest 10% were poorer in 2015 than they were in 2010. Across regions levels of poverty appear to have converged: poverty has fallen fastest in the regions which were poorest (Tigray, Amhara, SNNPR) but has risen in the remote regions of Afar and Somali. The highest rates of poverty are found in SNNPR, pockets of Amhara and the sparsely populated pastoral lowlands (Afar, Somali, parts of Oromia).
[note] World Bank, http://data.worldbank.org/indicator/NY.GDP.PCAP.CD?view=chart
[note] World Bank, Ethiopia Poverty Assessment 2014, published 2015

In Ethiopia, extreme poverty is manifested first and foremost as high levels of hunger and malnutrition. In an average year in Ethiopia between 10 and 11 million people need support to meet their basic needs. This rises in drought years with the numbers of people in need reaching 18.2 million in 2016. 8.2 million of these are regular beneficiaries under the Government of Ethiopia run Productive Safety Net Programme (PSNP), which provides cash or food assistance to the poorest families selected on the basis of having been humanitarian assistance beneficiaries for the past three years. The PSNP provides a predictable response to chronic food insecurity.
Poor people are the most vulnerable to environmental disasters but other factors also induce vulnerability. Ethiopia is subject to a wide range of natural and human-induced hazards, most notably drought. As a result, many Ethiopians are regularly pushed into transitory (temporary) food insecurity, as crops fail due to drought. Other shocks driving vulnerability include flooding and conflict that leads to displacement. Annually around 500,000 Ethiopians are displaced through conflict, drought and flooding and are in need of humanitarian support.
[note] The widespread impact of the 2016 drought meant that even relatively well-off pastoralists required humanitarian assistance as a result of herd loss.
[note] International Displacement Centre, http://www.internal-displacement.org/sub-saharan-africa/ethiopia/figures-analysis

Extremes in climate variability are set to increase with the onset of climate change. In Ethiopia, climate predications are: warming, more variable and less reliable rainfall and more severe and frequent extreme events. This could make the environmental factors behind humanitarian disasters in Ethiopia stronger and harder to deal with. Already, unreliable rainfall has made many rural livelihoods less viable, in particular in pastoralist regions and in areas where people have small land plots. The 2015/16 drought was considered a one in thirty year event but rising global temperatures may mean that this kind of severe weather event could become more frequent. Climate change if not well managed could be detrimental to Ethiopia’s economic growth rates and its ability to reduce poverty, and will make rural livelihoods even more vulnerable. Ethiopia needs to prepare for climate change and build management of climate variability into its disaster risk reduction and humanitarian systems. The GoE has shown leadership in attracting international climate finance. If this is spent effectively alongside development and humanitarian finance there is an opportunity to maximise results and embed sustainable systems.
[note] Ethiopian panel on Climate Change (2015), First Assessment Report, Working Group I Physical Science Basis, Published by the Ethiopian Academy of Sciences,
[note] Herring, S. C., A. Hoell, M. P. Hoerling, J. P. Kossin, C. J. Schreck III, and P. A. Stott, Eds., 2016: Explaining Extreme Events of 2015 from a Climate Perspective. Bull. Amer. Meteor. Soc., 97 (12), S1–S145.

Not responding to humanitarian crisis is costly for the economy. Ethiopia has managed to respond better to the 2016 El Nino crisis than to any other previous crisis of that magnitude. Growth has slowed down from 8.7% in 2015 to 6.5% in 2016 due both to the drought and the drastically weaker global economic environment but the impact on the economy is not predicted to be as protracted as in previous severe drought years. Drought-related international food purchases are also partially responsible for the potentially inflationary trade imbalance remaining wide. Ethiopia’s ability to manage the drought this year was partly through a more effective response (primarily through the Productive Safety Net Programme that meant that support for 8 million beneficiaries was planned, budgeted and prepared for) than in previous years and partly due to somewhat lower economic exposure to agriculture than in previous years. This is significant progress but the costs of the drought were still severe in both human and economic terms.
[note] The Federal Democratic Republic of Ethiopia, Staff Report for the 2016 Article IV Consultation, August 30, 2016
[note] IBID
[note] IBID
[note] For example Porter (2017) estimates that poverty depth increased amongst the poor (13% of poor households became poorer in 2015, whilst 19% poor households became poorer in 2016), whilst overall poverty is estimated to have increased by 2% in 2015 and 1% in 2016 as a result of the drought.

Not responding or responding slowly is costly in human terms, which in turn has negative economic impacts. The costs of lack of access to water, food, loss of assets and the lifelong impacts of under nutrition are significant. A recent study estimated that if the humanitarian response was insufficient (still a response but an insufficient one) in Ethiopia in 2016, the economic cost of this would be $1.3 billion. This is just based on the Humanitarian Response Document being underfunded – meaning this is just the economic cost of responding slowly when the emergency has already occurred. Malnutrition rates in Ethiopia including stunting (which affects just under 40% of children) is estimated to cost Ethiopia $4.7 billion dollars per year in loss of productivity, and additional costs to public services related to malnutrition.
[note] Venton, The VFM of Early Response, 2016
[note] WFP, The Cost of Hunger: Ethiopia 2013, 2014

Response post emergency is slow and expensive in human and economic terms. Preparedness and disaster risk reduction reduce human suffering and are more cost effective. While it is too simplistic to assume an overarching cost benefit ratio (often quoted at 1:4 or 1:7), studies have shown that appropriate prevention saves lives and money, and often prevents economic losses. In Afar, restocking sheep and goats costs at least 6 times more than supplementary feeding to prevent death, and restocking cattle cost 14 times more. Estimates suggest that if Ethiopia prepared better for crisis it could save $2 billion over 10 years.
[note] Referenced in Venton et al., The Economics of Early Response and Disaster Resilience: Lessons from Kenya and Ethiopia, Economics of Resilience, 2012,pg 74

Delivery through Ethiopian government systems is more cost effective and more sustainable. The Ethiopian government manages large scale development programmes that deliver results at low cost. Ethiopia’s spend on health is low both by international standards and for the outcomes achieved. The Government run Productive Safety Net Programme is cheaper per beneficiary than similar UN programmes. However, government systems cannot take on all humanitarian beneficiaries overnight. This will take time and will require support.
[note] World Bank Public Expenditure Review Ethiopia, 2014

People in Ethiopia’s emerging (peripheral) regions are particularly vulnerable and delivery is weakest in these regions. Systems in Ethiopia’s periphery regions are not as strongly entrenched as in the better developed regions and staff capacity is weaker. Effective monitoring and support to staff will need to be taken forward to ensure aid reaches those who need it most. We will ensure we have robust systems so that we can meet the needs of the most vulnerable. DFID will lead the way in ensuring strong beneficiary feedback so we know what works best for the poorest and most vulnerable. We will continue to deliver most difficult regions where the most vulnerable are present but ensure effective management of these programmes recognising the additional risks.

Drought in Ethiopia is a predictable event.

A large proportion of food security need in Ethiopia can be predicted and planned for and thus may be most effectively met through predictable national systems. Figure 1 shows a core case load of chronically food insecure beneficiaries supported under the PSNP programme (8 million) and an additional contingency case load (2 million) who are humanitarian beneficiaries in need of support every year. Additional people become food insecure in severe years. Despite the relative predictability of need in Ethiopia, humanitarian beneficiaries are reliant on annual underfunded appeals to meet their basic needs.

Extraordinary shocks, such as the drought in 2015/16, require these national systems to be able to flex or scale in a timely way to meet additional needs. For food security the most appropriate vehicle is the national rural safety net, PSNP. The vision – of a continuum of response between national safety net systems and relief (so that no one falls between the cracks) – requires planning and financing (this could include insurance). If effectively delivered this vision could lead to a ‘Dull Disaster’ – where by the natural event occurs but through effective preparedness and planning the system is able to respond and the dramatic human consequences do not arise. To deliver this Ethiopia needs a clear plan, clear early warning system, agreed (depoliticised) triggers for response, and financing on standby to ensure that this plan can be delivered. This will take time, at present the PSNP has a significant reach at 8 million beneficiaries, expanding this will take time.
[note] In 2015/16, the worst El Nino on record led to a total 18.2 million people in need (8 million PSNP, 10.2 million ad hoc humanitarian), or almost one-fifth of Ethiopia’s population.
[note] Clarke, Daniel Jonathan; Dercon, Stefan. 2016. Dull disasters? How planning ahead will make a difference. Washington, D.C. : World Bank Group

Figure 1: Ethiopia’s Continuum of Response – Food Security Needs

Non-food humanitarian needs (water and sanitation, nutrition and health) can also often be predicted and prepared for. Despite significant progress in service delivery from a low base, there is still high unmet basic services need in Ethiopia which becomes acute when there is a humanitarian crisis. Emergency support for non-food basic needs is provided to the same woredas year on year. This support is often for the same needs e.g. nutrition, water, sanitation and health. Sustainable Government systems are needed to fund recurrent repair costs of systems such as boreholes, to deliver appropriate and sufficient vaccination campaigns and to ensure adequate staffing in health facilities able to respond to both predictable and unpredictable needs. This would be more cost effective, and would reduce suffering.
[note] There are more than 700 woredas, or local administrative units, in Ethiopia.

Humanitarian System in Ethiopia

Ethiopia has a clear strategic direction and strong policies for managing humanitarian crises: but implementation is patchy. In theory, humanitarian coordination is led by the recently-established Ethiopian National Disaster Risk Management Commission (NDRMC), which reports directly to the Council of Ministers.  This Commission was brought out of the Food Security Directorate of the Ministry of Agriculture in 2015, in order to give humanitarian needs and response greater visibility and authority. However, the NDRMC has not yet managed to achieve full integration or coordination with the international humanitarian system or the Productive Safety Net Programme. It also lacks the convening power or technical capacity to implement Government humanitarian response in practice. Furthermore, the relationship between the NDRMC and the Climate Resilient Green Economy (CRGE) facility charged with managing international climate finance is not clear. Clarifying this relationship would ensure synergies and therefore better results for Ethiopia. The Government of Ethiopia is keen to see the full implementation of the Disaster Risk Management (DRM) policy and integration of the Commission into other systems and therefore a more effective response.  DFID support could help them get there.

Ethiopia has one of the most cost-effective grain reserves in the world but grain reserves are not part of a modern humanitarian system. Grain reserves play an important role in countries where markets do not function that are vulnerable to climate or humanitarian shocks leading to food insecurity. Ethiopia’s grain reserve has been successful in responding to recurring drought and other emergencies by lending grain to recognised national and international relief organizations, as well as to government agencies engaged in food security operations, under agreed-upon conditions of repayment. However, grain reserves are very expensive, as they require an institution, and rolling stocks of grain (a perishable asset). They also have indirect costs on food prices because grain has to be released on good years, as well as bad years artificially supressing prices which can give the wrong incentive to farmers.  Ethiopia’s grain reserve, by being efficient, having clear rules and triggers has been considered effective. However, since 2011 it has increasingly been used for price stabilisation in urban areas breaking the link with social protection. In the short term a strategic grain reserve could have a role in humanitarian response if managed effectively. However, as Ethiopia develops, market integration increases, and social protection moves to more efficient cash delivery there will be a limited case for a strategic grain reserve.

Ethiopia has a strong early warning system but no automatic triggers for action. Ethiopia has a nationally-led early warning system and is clear in the DRM strategy that there must be triggers for response within this system. However, the nature of these triggers needs development. Humanitarian needs are assessed bi-annually by a joint Government and UN-led international team. These results are affirmed and debated jointly, but final numbers assessed in need of humanitarian assistance are often prone to manipulation. An automatic system, based on agreed predictors of need, would reduce this manipulation and ensure swifter response – thus preventing a crisis before it occurs. To be most effective this system would action is taken early; before a crisis occurs.

Ethiopia has plans but these are not always fully funded or it is not clear where the funding will come from in the event of a crisis. Ethiopia has some contingency plans for response in the event of a disaster but these are not comprehensive, not fully financed and often aren’t clear on who is responsible for taking action. This causes delays in response. A more methodical and pre-agreed approach to financing disasters would generate a more effective system. Such a pre-agreed system is also likely to reduce detrimental parallel systems (between relief and safety net or other development programmes). Ethiopia is developing a comprehensive food security plan that will ensure that one system will meet all food security needs. DFID Ethiopia will support the evolution of this single system, through technical expertise and by making it our sole delivery mechanism for food security. We will also support where possible a government led system for emergency health, wash and nutrition.

Ethiopia has a large international humanitarian agency footprint. This is not appropriate for a middle income country (which Ethiopia aims to be in 8 years), or for a stable country with a proven track record of delivering large programmes. The UN is aware of this and appears committed to country ownership and leadership. However, their incentives are not aligned towards shifting delivery to government. This is because UN officials are judged on their ability to mobilise donor finance. DFID will lead the charge in ensuring that in Ethiopia UN reform is delivered meaning that the UN is more transparent, works more effectively with and through government and reaches those populations that need support the most. This will mean putting less finance through the relatively expensive UN system and more through the more cost effective government system. Retaining the UN and NGO support only for where the government is unable to deliver.

The World Bank is committed to supporting delivery through government systems and has a strong track record of doing this in Ethiopia. Notable examples are the Productive Safety Nets Programme, and work on health, education and WASH. All of these mechanisms have shown themselves to be capable of delivering through government and often at lower cost. They have also been able to flex in humanitarian emergencies. In the case of health often leadership is stronger and more capable from the government than UN agencies. The World Bank’s incentives are strongly aligned towards supporting Ethiopia to effectively deliver, and they have a track record of doing this.

Ethiopia plans to be a middle income country by 2025 and needs a middle income country financing system for humanitarian crisis. Ethiopia has high potential to finance and deliver a nationally-led humanitarian response. As it grows economically it is likely to be less able to draw upon the limited pot of international humanitarian funding. Most importantly, the international pot isn’t the best alternative for vulnerable Ethiopians. Waiting until there is a crisis to call for humanitarian funding leads to worse outcomes for the vulnerable at a higher cost, meaning fewer people can be reached with assistance.
[note] Venton et al., The Economics of Early Response and Disaster Resilience: Lessons from Kenya and Ethiopia, Economics of Resilience, 2012

Financing for response until 2015/ 16 was almost entirely dependent on international donors. Ethiopia has a pro-poor budget but very low levels of domestic taxation which reduces its ability to finance inter alia humanitarian spending. There is only patchy recognition of humanitarian need in key sector and related budgetary plans. Ethiopia has been dependent on international assistance for the majority of humanitarian response, and has not meaningfully planned for financing response to disasters. This cannot continue: international assistance is limited, with 50% of the 2015 global humanitarian appeals remaining unfunded. In November 2016, the Ethiopia appeal for the year was showing a $600 million shortfall. Humanitarian financing is increasingly prioritised for unstable states that cannot deliver for their people.

The Ethiopian Government put significant domestic finance into the 2015/16 humanitarian response. This finance was available due a low 2016 oil price, meaning there was finance ($700 million) in the Government’s Oil Stabilisation Fund. This level of unplanned in-year budget flexibility is unusual and future crises cannot be guaranteed to correlate with low oil prices. Had the oil price not been low resources would have needed to have been moved from other pro-poor or pro-growth elements, with expensive unintended consequences. This assessment of GoE contributions to the humanitarian appeal in 2016 does not account for government financing for broader preparedness for example health extension workers, vaccination campaigns, routine nutrition screening, nor does it fully account for contributions from regional governments that have not been fully reported to the federal level. Assessments suggest that in 2016, the GoE financed at least 50% of the overall humanitarian needs in country.

The Government of Ethiopia needs to financially plan for crisis to ensure swift and effective response. Ethiopia needs to plan for disaster management (risk) in its budgetary planning process. Ethiopia’s federal contingency is sufficient only for small budget shocks. It is a similar size to that of many developed countries that can smooth in-year budget shocks by borrowing off the financial markets, which whilst expensive is not imprudent. Ethiopia cannot at present prudently borrow off the financial markets, as they would struggle to find the additional foreign exchange needed to pay additional debts . Ethiopia therefore needs to plan for budget shocks. The UK and the World Bank have provided technical support on planning for budget shocks; this has included sovereign risk insurance. This programme will build on this support.
[note] The Federal Democratic Republic of Ethiopia, Staff Report for the 2016 Article IV Consultation, August 30, 2016

Ethiopia can allocate more finance to humanitarian spend with good financial planning but this will not be easy. Ethiopia has below the sub Saharan African average for tax returns at just 12.5% of GDP.  Ethiopia is working to increase its overall tax base but progress will be slow and demands are high in many pro development sectors (e.g. Ethiopia’s expenditure on health per capita is the third lowest of the 25 countries in Sub Saharan Africa with data available). Ethiopia’s federal budget for 2016/17 is $11 billion dollars and is considered to be well managed and pro-development. Immediate reallocations would be likely to come from other important growth and poverty reduction sectors.   It is also possible to envisage reduction in funding in other sectors that are considered less efficient but this is unlikely to be significant as Ethiopia’s budget is considered to be well managed. A combination of additional tax revenue and better financial planning would make additional allocations to humanitarian spend from the Ethiopian government realistic but challenging.

A potential way for the Ethiopian government to allocate more to coping with humanitarian and climate shocks is the reduction of inefficient subsidies. Wheat, kerosene and electricity subsidies represent ~1.3% of GDP and are a much more expensive way of supporting the poor than targeted social protection.  However, subsidy reform is very difficult and if not well managed can fail (e.g. Nigeria). Ethiopia will need support and willingness to take forward subsidy reform.

To deliver the greatest number of results for vulnerable people, different sources of finance to respond to disasters need to be coordinated. The Government will need to play a strong coordination role, via the Ministry of Finance with NDRMC and Line Ministries, to coordinate overall response. Coordination has not been effective in 2015/16 primarily because relief and PSNP systems for responding to food insecurity needs have operated almost entirely in parallel. This meant PSNP and relief systems were competing for limited staff time and logistical capacities (berths at Djibouti port, trucks and warehouse space), meaning that food did not, and does not reach beneficiaries as effectively as it may otherwise. Response needs to be increasingly led and delivered by government under one common system to ensure efficiency, effectiveness and sustainability.

The humanitarian system in Ethiopia still works primarily on an annual basis which makes coordination and planning difficult and makes the overall response more expensive. The full humanitarian requirements (often large portions of which are the same interventions year on year supporting the same people who are chronically the extreme poor) are initially released at the end of the year, and finalised in the January of the requirements year. The non-PSNP food and non-food needs for 2017 are 5.6 million people (higher than in a ‘normal’ year given Ethiopia will still be recovering from the 2015-16 drought, and is now facing the impacts of the Horn of Africa drought in the South and South-East). Despite being aware that there are humanitarian requirements year on year, appeals remain single year, representing short-term investments that are less good value for money.

There is strong evidence that where the markets can support it, cash it is the most effective method to address food insecurity. Despite this cash delivery is only a small portion of humanitarian delivery. The Productive Safety Nets Programmes is leading the way in Ethiopia on the use of cash programming rather than in-kind food assistance (with 60% of food security support delivered as cash), where the markets support the use of cash. Cash also affords choice to beneficiaries, ensuring they can meet their needs as they want. For example they may choose to buy water if it is not available in their woreda. In some Woredas food is traded for cash so people can access water or other needs, however the absolute amount of cash traded tends to be lower than the value of food (the terms of trade are not good). Furthermore, cash is cheaper to deliver due to significantly lower transport costs. However, food has had to be delivered in Afar and other areas where market systems are as yet unable to support cash. Despite this, most humanitarian delivery remains food. This needs to change to ensure better outcomes for vulnerable people.

Recent instability means that in some areas non-government delivery bodies will continue to be needed to ensure effective delivery of aid to those who need it most. Humanitarian aid should be given on an impartial, neutral and independent basis. Rising instability led to challenges with humanitarian access in 2016 – with accusations being laid at the door of both government and protestors. It is difficult to assess the actual situation without on-the-ground verification, but the risk of aid not reaching those who need it most will need to be mitigated. This will require providing the government with technical support on the impartiality of aid, maintaining the ability to deliver aid through others, and directly contracting independent monitoring.

Moving towards a government-led system that is effective and accountable.

This programme will support Ethiopia to move towards its vision of a nationally led, planned and prepared response to climate and humanitarian shocks. This means being able to respond swiftly on the basis of clearly agreed triggers with finance available and delivered through a coordinated system. Over time this will mean more government leadership and delivery and less delivery through the relatively expensive (though often more technically experienced) UN system. This is an ambitious vision that will take time to deliver but making progress towards this vision will deliver better value in saving lives in Ethiopia. This will free international humanitarian finance for responding to countries where Governments are unable to respond. It will also support GoE’s vision of moving to middle-income status by 2025 and becoming the role model for other countries in rolling out Grand Bargain commitments.

The vision is for a Government system that is:

- Government-led and increasingly Government-financed.
- Based on a clear plan with clear triggers for action that is well financed, potentially including risk financing – meaning it can respond swiftly.
- Effectively prepared for disasters and reduces the risk- preparation is critical to reducing the case load and areas for intervention, and reducing the irreversible costs of humanitarian need.
- Able to deliver to the most vulnerable people most effectively on an impartial and needs basis.
- Can effectively scale up and scale down so it can reach those who need it most when they need it most.
- Effectively monitored, building accountability to beneficiaries.
- Able to ensure delivery quality increases in peripheral ‘Developing Regional States’ (DRS), where delivery is often much weaker.
- Able to prepare for the challenges of climate change.

To support the shift towards this humanitarian system BRE will have four objectives:

1. To support the Government of Ethiopia to lead and deliver an effective and accountable response to climate and humanitarian shocks.
2. To deliver food and cash to people in humanitarian need in the most effective way.
3. To respond to non–food emergency humanitarian needs in the most effective way.
4. To monitor, evaluate and learn in order to strengthen humanitarian delivery in Ethiopia and contribute to global best practice.

Building Resilience in Ethiopia is consistent with the Grand Bargain. At the World Humanitarian Summit in 2016 the world’s largest donors and aid organisations came together to agree ten shared commitments to improve the efficiency of humanitarian funding these are known as the Grand Bargain. DFID played a leading role in this process showing global leadership and ensuring UN reform. The joined commitments included; greater financial transparency; more support to national responders (including governments and NGOs); greater use of cash transfers where appropriate; less duplication and lower management costs; a single comprehensive needs assessment based on need not what can be provided; more participation from affected people; more multi-year funding; less ear marked funding; harmonised and simplified reporting requirements and more collaboration between development and humanitarian donors to reduce the need for humanitarian assistance in the long term. BRE will deliver on these commitments and in particular focus on; working with and through national systems, cost effectiveness, working with development partners and better accountability to beneficiaries. We will also contribute to DFID’s commitment to double the use of cash transfers by 2025.

The BRE business case will deliver on the UK humanitarian policy. The UK humanitarian policy has five key elements. 1). Protecting people in crisis: upholding humanitarian norms and principles. 2). Best of British response to rapid onset disasters. 3). Managing the risk of disasters better: 4). Investing in resilient systems and better financial planning. 5). A new approach to protracted crises: investing in the future. Through BRE we will use the systems that can most effectively, and equitably meet people in need whilst ensuring principles are upheld. We will drive VFM so that the most beneficiaries (including the most vulnerable) can be met. We will support UN reform in Ethiopia holding the UN to account for delivery, increasing their VFM and ensuring they are focusing their delivery where the government cannot reach.

Gender Equality Act: This programme has the potential to make a positive impact on women and girls and reduce gender inequalities. Women, girls and boys face particular vulnerability during crises as a result of specific needs (e.g. feeding requirements of infants and pregnant and breastfeeding women); their status (e.g. lack of voice in decision making) and their gender roles (e.g. protection risks associated with women and girls’ collecting firewood and water; or with pastoralist boys being at risk of violence when travelling into other communities in search of pasture) . Climate change can exacerbate gender inequalities. But crises also represent opportunities for disrupting social norms. We will ensure implementing partners have sufficient capacity on gender to interpret and harness those opportunities and mitigate risks. The programme’s commitment to learning will include feedback loops from independent monitoring, including from women, men, boys and girls.
[note] Oxfam, Consolidated Gender Analysis of the Ethiopian Drought Response, 2016

Terrorism and financing: The risk of terrorism financing in Ethiopia is relatively low in most regions, with the exception of Somali and to a lesser extent Oromia. The Ethiopian Government has a good track record of managing terrorism threats and a strong anti-terrorist stance. We are putting in place a number of mitigation strategies to prevent terrorism financing. Firstly, all of our contract documents and MOUs will include specific language on managing the risk of financing terrorist groups, and be clear on the responsibility of partners. Secondly, we will ensure high standards of financial management in all organisations. Thirdly, as part of the inception phase we will conduct a thorough risk assessment of the risks of funding terrorism throughout Ethiopia, with a focus on the at-risk regions.

## Appraisal Case

The options appraisal will follow a three stage approach. Firstly options will be considered against how far they meet the objectives of the programme. The top options will then be considered against critical success criteria. An assessment of the costs and benefits of the remaining options will then be undertaken.

There are 4 options for the delivery of BRE objectives. We have not considered direct DFID funding to NGOs because our objectives are about supporting the government and to directly fund NGOs would require building their capacity whereas our focus under this business case is building the Government of Ethiopia’s capacity. Furthermore, other major donors in particular the EU and USAID have large programmes funding NGO partners. We are considering funding NGOs through the UN pooled fund (EHF) which on funds NGOs. We also have significant support to NGOs in Ethiopia via centrally-managed programmes.
DFID’s specific technical advantage in Ethiopia vis-à-vis other humanitarian donors is to work through Government, and the aim of this programme is to streamline systems in order to deliver more efficiently and sustainably, increasing the number of beneficiaries that are able to be met and building resilience in Ethiopia.

As Technical Assistance is the key way to build and support capacity we have included this in all options. Due to the critical nature of monitoring and evaluation in delivering objectives we have also included this in all options.

Do nothing counterfactual

It is firstly necessary to consider doing nothing, which is the baseline against which the other options are considered. If DFID does not intervene in this sector the following is likely:
1. Slower response – In 2015/16 DFID was the swiftest donor to respond in this year’s crisis – saving lives and delivering value for money.
2. Less system reform – DFID is the most forward leaning humanitarian donor – looking to work with the Government of Ethiopia so they can lead the response to climate and humanitarian shocks. Without DFID support the shift to a better value for money nationally-owned and led system is unlikely to occur.
3. Funding gap – the move towards a humanitarian system led and funded by government is critical. However, we have not yet reached this capability and in the meantime funding is needed to support this critical gap.
4. Less ability to deliver against Grand Bargain commitments and UK – Ethiopia itself and the UNSG have recently recognised Ethiopia’s forward-leaning stance in terms of systems reform and national ownership in response. There is a real chance for the UK to lead the way in supporting Ethiopia to deliver on humanitarian reforms related to GB commitments.
5. Less effective preparation for climate change risks.

Description of Feasible Options

Option 1
- Technical assistance delivered through a management agent.
- All finance to UN institutions- World Food Programme and Ethiopian Humanitarian Fund (a UN Pooled Fund). The UN institutions chosen are those with a track record of delivery in meeting emergency needs and those that are most able to work with and through government.
- Independent monitoring and potentially evaluation through a management agent.

Option 2
- Technical assistance delivered through a management agent.
- All finance to government institutions – this would mean that from the outset we would only give direct funding to the Government of Ethiopia to deliver humanitarian aid.
- Independent monitoring and potentially evaluation through a management agent.

Option 3
- Management agent to deliver technical assistance and finance to the most effective provider (s) (including the government) on the basis of agreed criteria. Under this option the management agent is also a fund manager.
- This would require DFID to do some interim work while the TA provider is put out to tender.
- Separate contract for independent monitoring and potentially evaluation delivered through a different service provider.

Option 4
- Management agent to deliver technical assistance and make recommendations on funding. The management agent will not directly manage operational funds.
- Administrative agreements (MoUs) for funding held by DFID.
- DFID would still need to contract some interim work while the TA provider is put out to tender.
- Independent monitoring and potentially evaluation to be taken forward by the management agent.

Ability to meet objectives

Scores on ability to meet objectives – the scores are considered on a sliding scale of 1-5 and whether the objectives will be met by the option, 0 being objectives not being met and 5 objectives being fully met. Independent monitoring can only be conducted by an independent contract and therefore the results for this objective are relatively similar.

	Objective 1. Government of Ethiopia leading and delivering an effective and accountable humanitarian response	Objective 2. / Deliver food and cash to people in humanitarian need in the most effective way	Objective 3. Deliver non-food needs in the most effective way	Objective 4. Monitoring, evaluation and learning to strengthen humanitarian delivery in Ethiopia	Total
Option 1	3	2	3	2	10
Option 2	4	2	2	3	11
Option 3	4	3	3	4	14
Option 4	4	4	4	4	16

Figure 2. Appraisal of options against objectives

Narrative Scores

Option One (Management agent delivers TA and independent monitoring and evaluation, operational funding goes to the UN)

Delivery of objectives strengths
- Technical assistance would support objectives.
- Scores well on being able to address acute shocks as the UN can be the quickest delivery body in Ethiopia.
- UN system critical for some areas in Ethiopia where government systems are less effective.

Delivery of objectives weaknesses.
- Moving to a government-led system difficult to do without direct delivery through government.
- UN technically capable in some areas (in particular logistics) but could be unable to provide the necessary capacity across the board to the Government of Ethiopia.
- UN system is designed to operate, in humanitarian situations, where governments do not function. This is not appropriate in Ethiopia where the government is able to function.
- UN organisations are often incentivised to use themselves as delivery channels rather than building broader longer-term capacity and ensuring system coherence.
- UN system is costly, which is not appropriate if alternatives are available/ can perform better.
- UN systems need to strengthen their monitoring in country.

Option Two (Management agent delivers TA and independent monitoring and evaluation, operational funding goes to the Government of Ethiopia)

Delivery of objectives strengths
- Technical assistance plus immediate delivery to government could deliver sustainable government-led system.
- Government of Ethiopia delivery is lower cost and where effective better value for money.
- Government of Ethiopia more capable of multi-year programming.
- Government of Ethiopia more capable (with support) of preparedness interventions which are better value for money.

Delivery of objectives weaknesses
- Government does not yet have the full capacity to lead delivery, with recently formed institutional structure. Conditions are not in place to finance immediately without effective joint planning and fiduciary risk assessment.
- Government delivery alone would be unable to reach all areas of Ethiopia – in particular the developing regional states and areas where the PSNP has no coverage.
- Whilst in the long term the government systems are better value for money and more sustainable – in the short term this option may not be able to deliver the necessary speed to save lives in all areas. It is still necessary to move to a more prepared system in Ethiopia.
- Shifting the humanitarian system dramatically before systems are ready to absorb humanitarian needs runs the high risk of making vulnerable people more vulnerable.

Option Three (Management agent delivers TA and independent monitoring and evaluation and manages all operations funds, allocating to the UN and to Government of Ethiopia as appropriate)

Delivery of objectives strengths
- Advantages of UN and government system, as in Options 1 and 2 above.
- Management agent with TA and all contracts. Streamlined and strategic.
- Management agent conducts a full appraisal of government systems and other delivery modalities and then delivers the right level of finance to the most appropriate delivery partners.
- Can ensure the management agent has the right expertise to deliver effectively –in areas where the system is failing to deliver.
- Could deliver through a variety of modalities therefore flexible.

Delivery of objectives weaknesses
- The VFM case for contracting a management agent to manage UN Funds is very difficult to make as it would reduce the number of results achieved via allocating funds to management agent fees without increasing effectiveness of delivery or freeing up significant DFID staff time. As this business case is about influencing systems it is critical that DFID retains the direct relationships in country.
- There is a reputational risk to the UK. It would be very difficult to justify to the Public Accounts Committee and the British Public that only 75p (Figure 4) in every pound is reaching operations with even less reaching beneficiaries.

Option Four (Management agent delivers TA and independent monitoring and evaluation, advises on fund allocation and delivery quality, DFID manages the funds holding MOUs directly with the delivery bodies with the exception of a small contingency fund).

Delivery of objectives strengths
- This option combines the advantages of using government systems (least cost, longer term, more sustainable) and UN systems (speed, responsive to acute need, able to respond in almost all political situations, accountability and monitoring.)
- This option includes the technical support necessary to deliver the vision and ensure high quality spend.
- Reduces staff time by using the management agent to consider key technical issues and provide data inputs but retains DFID direct relationships to maximise influence.
- This includes the option of putting additional finance through existing programmes for example national health programme.
- More cost effective as does not pay management costs where there is no absolute value to these. However, the management agent would still be responsible for ensuring and supporting quality of delivery, and ensuring risks are effectively managed.

Delivery of objectives weaknesses
- This option requires additional staff time – about 0.5 full time equivalent.
- Four contracts (MOU with EHF and WFP, contract with Management Agent to provide TA and one small contract for a mid-term review) for DFID to manage – the BRE steering board would need to ensure these are well managed and fully resourced.

Critical Success Criteria

As options 3 and 4 have scored highest, they will be appraised against the critical success criteria and a cost benefit analysis on them will be conducted. These options have scored higher because more than one delivery partner is needed if the programme is to both build capacity (slow and complex but sustainable) whilst meeting immediate needs (where reaching beneficiaries quickly is critical).

Critical Success Criteria.	Option 3	Option 4
	Rating	Rating	Narrative
Institutional - Likelihood of:
Facilitating GoE leadership of delivery, and planning of response to humanitarian and climate shocks.	4	4	Both options are focused on supporting effective, accountable and transparent government leadership. The large amount of technical assistance will be critical to achieving this goal.
Facilitating GoE financial planning of humanitarian aid.	4	4	This will be delivered through TA and working with a centrally managed programme on insurance premiums. This is similar to both options.
Strengthening harmonization and alignment between donors.	3	4	We judge DFID more direct ownership of delivery with support from the management agent will free up time for coordination whilst retaining the direct relationships with implementing partners to ensure coordination. Adding a fund management set of tasks to the management agents TORs (option 3) in an already crowded donor space with a similar mandate to the implementing agencies may add confusion.
Effective delivery - Likelihood of:	0	0
Delivering results at scale	3	4	Option 4 will be able to deliver more results due to having a lower fund management cost.
Moving towards a scalable social protection system.	4	4	This is a key focus and our work across delivery partners with associated TA makes this likely.
Shifting to government led delivery of nutrition outcomes.	3	4	TA and ability to flexibly allocate finance where it can deliver most results makes this possible under both options. Option 3 by removing the direct relationship with government could reduce the efficacy of delivery of this objective.
Ensuring fiduciary probity.	4	3	Marginally increased fiduciary risk if DFID is managing the funds through government. However, same amount of TA under both options that is designed to ensure effective delivery and will assess fiduciary risk of working through government, and then work to address any areas of weakness.
Ensuring transparent delivery.	4	4	Transparency will be a priority in both and we will use the TA body to ensure that this is effectively delivered.
Ensuring accountable delivery.	4	4	We will ensure this is taken forward and a key part of our MOUs. This will include regional support in areas where accountability is weak and independent monitoring that includes beneficiary feedback.
Effective management of input costs.	3	4	We will work throughout the programme to manage input costs and will deploy funding where the greatest number of results can be delivered. Option 3 has a fund management fee that is paying the management agent to fund manage and the UN agencies to do the same. This is duplication and is more difficult to justify.
Requirements for DFID Staff Time.	4	3	Option 3 requires between 0.5 -1 additional DFID FTE. It may be possible to programme fund a post to provide some support inside the TA unit which could reduce this burden to just 0.5 of an FTE which is acceptable, in particular for a cost saving of £10.5 million.
Inclusion- Likelihood of:	0	0
Reducing inequalities in access to humanitarian aid and in particular meeting the most vulnerable groups.	4	4	One of the key reasons we are deploying significant TA is to ensure that our aid will be able to meet those who are most in need.
Ensuring access to humanitarian aid takes into account gender inequalities and gender roles.	3	4	A critical challenge for women is food security. The current drought has seen pregnant and lactating women particularly vulnerable to food insecurity. A higher provision of food security support and nutrition as possible under option 4 (due to lower transaction costs) would not address inherent gender inequalities (these will be looked at in programme design and through TA, including ensuring voice/ feedback and monitoring unforeseen impacts) but will mean we can meet a greater number of vulnerable beneficiaries. This means that option 4 scores better on gender inequalities.
Ensuring effective access in the peripheries.	4	4	Both options will see a focus on effective delivery in the peripheries and areas where the most vulnerable are, as well as the most vulnerable beneficiaries (e.g. disabled).
Political - Likelihood of:	0	0
Supporting DFID and cross-HMG policies	4	4	Our options are consistent with the Grand Bargain. In particular the increase in cash programming necessary where appropriate to ensure the most effective delivery for beneficiaries.
Sustainability- Likelihood of:	0	0
Sustainability and effective exit strategy.	4	4	The focus on government leadership, financial planning and best value for money make it more likely that Ethiopia can develop a humanitarian system that is self-funded and managed.
Overall Assessment	60	63

Figure 3. Appraisal of Options against Critical Success Criteria

Costs and Benefits of Options 3 and 4
Overall the costs of the programme are £168 million and this does not differ between options. We have taken forward a comparison of costs and benefits which shows much higher benefits (£168mn costs to £559.5mn benefits) than costs despite conservative assumptions (details in Annex 11). These costs do not fully account for the positive benefits of saving lives and relieving suffering.

Fee for Fund Management
The critical difference between the two options is that option 3 includes fund management by the management agent. The tables below set out what this does to fund flows – reducing the overall finance for operations by between 13 and 13.5 pence in the pound. This would in aggregate account to reaching 343,000 less nutrition beneficiaries across the five year period, assuming finance was redeployed in to the Ethiopia Humanitarian Fund. If this finance were put into the Government of Ethiopia and spent effectively then it would reach even more beneficiaries. The saving that this approach would have in terms of FTEs as set out in the critical success criteria is just 0.5 of an FTE which is not judged sufficient to justify the reduced number of beneficiaries.

Costs of Fund Management in Option 3

Management Fee Percentages
	WFP	EHF	Government
Fund Manager	10.0%	10.0%	10.0%
Fund Management Fee	6.0%	6.0%	6.0%
Delivery body management fee	18.0%	3.0%	0.0%
Management fee of any on granted institutions	0.0%	7.0%	0.0%
Management fee of sub granted institutions (assuming this applies to 15% of funds)	0.0%	7.0%	0.0%
Total Finance for operations	69	75.5	85

Costs of Fund Management in Option 4

Management Fee Percentages
	WFP	EHF	Government
Delivery body management fee	18.0%	3%	100%
Management fee of any on granted institutions	0.0%	7%	100%
Management fee of sub granted institutions (assuming this applies to 15%)	0.0%	7%	100%
Total Finance for operations (pence per £)	82	89	100

Figure 4. Costs of Fund Management

Fund management fees are justified where they raise the quality of funds deployed. However, all of the modalities that we would be allocating the management fee to are already funded by DFID directly. The MAR has shown that OCHA and WFP are ‘good’ and therefore have proven their capability to manage funds. We are also funding the GoE directly through PSNP, ONE WASH and Education programmes, all of which scored well in their annual reviews. Furthermore, we are already paying the UN to manage some of these funds. We therefore judge that cost of the Fund Manager fee for funds to UN, EHF and GoE outweighs the benefit.

Fund Management fees could also be justified where they free up time for more strategic work that would ensure an overall more effective response. As we will have to have MOUs with EHF and WFP for the first year whilst we await the procurement of the management agent for TA, and DFID will in all cases attend key strategic meetings to influence and ensure effective direction of travel, we judge that the staff saving is not significant enough to justify the additional cost.

Conclusion
On the basis of the assessment of costs and benefits and the critical success criteria the best option for managing BRE is Option 4 where we have a management agent managing the technical assistance, monitoring and evaluation, and contingency funds. The management agent will also be responsible for advising on spend but DFID will hold the MOUs with WFP, OCHA (EHF) and the Government of Ethiopia.

Theory of Change of preferred option (Option 4)

Outputs
Outcome
Impact
Ethiopia more resilient to climate and humanitarian shocks.
A Government of Ethiopia to lead and deliver an effective, more self-financed and accountable response to climate and humanitarian shocks..
Technical assistance to the Government of Ethiopia to lead and deliver an effective and accountable humanitarian response
Effective response to meet food needs
Effective response to meet non-food needs
Effective monitoring, evaluation and learning.

Figure 5: Illustrative theory of change.

Narrative Theory of Change

If the Government of Ethiopia receives technical assistance that is well targeted and high quality. The GoE will have increased capacity. This capacity will be used to work to deliver the GoE’s own vision of a single humanitarian system, led and owned by government, and capable of planning, preparing and responding to climate and humanitarian shocks.  Key elements of this system will include better assessment, planning (including financial), better preparedness, better value for money, stronger ability to address the challenges of climate change, more delivery through government systems. This will save lives, livelihoods and money.

If at the same time the government is supported to deliver finance through their systems where they are capable.  These, systems will then begin to deliver humanitarian intervention/ plan for humanitarian need, and integrate climate change. This will mean more delivery through government which will cost less and therefore meet the needs of more beneficiaries. Over time, if delivery is successful we will be able to expand our humanitarian support through government.  This will lead to a single government-led humanitarian system in Ethiopia that is able to support Ethiopia to be more resilient to shocks. Our assessment is that this will be possible in higher capacity areas where governance is relatively effective. It is particularly likely that this can be the case for nutrition and health where the Ministry of Health is committed to taking leadership and has better capacity. This will be tested through a feasibility study.

If the government has greater capacity then humanitarian actors can focus delivery on areas where the government is too weak, has no access or are areas of extreme and emergency need.  This would downsize the international humanitarian foot print in Ethiopia. This would allow humanitarian agencies to focus their efforts where government is weak thus ensuring the needs of the most vulnerable can be met and humanitarian principles are upheld.

In order to save lives now it will be necessary to deliver through World Food Programme (WFP) and the OCHA-administered Ethiopia Humanitarian Fund (EHF) in the short to medium term.  This will allow for us to test scaling up delivery through government systems whilst not putting vulnerable people at risk. For example at present the Productive Safety Net Programme can deliver to 8.2 million people this is impressive. It will take time to expand this number. The same applies for other sectors where shifting delivery from NGOS and UN to government will take time.

If the programme is accompanied with high quality monitoring. It will be more effective because it will have real time information on what beneficiaries receive, whether it is the planned good/cash and whether this was appropriate. It will also more effectively manage risks including delivery and fiduciary risk.  This will increase effectiveness and programme learning and increase delivery quality for all, in particular the most vulnerable. This will reduce the risk of operating in areas where there is weak government capacity.

If the programme has effective evaluation it will be able to contribute to global evidence on what works. This will increase effectiveness of delivery in Ethiopia and further afield.

This programme will save lives (and livelihoods) and money whilst demonstrating that Ethiopia has a humanitarian system that is moving to be consistent with one of a middle income country.

Activities under each output

Output
1. Technical assistance to the Government of Ethiopia to lead and deliver an effective and accountable humanitarian response focusing on:	Planning for disasters including using use of depoliticised triggers- at the federal level and line ministry level. / Risk Financing – ensuring needs are planned for and therefore finance is available when needed. Includes support to considering insurance options. / Capacity support to the GoE, including via the DRM Commission, to ensure they can lead an effective, accountable and transparent response (including M and E). / Ensuring humanitarian disasters are fully accounted for in the next Growth and Transformation Plan (due in 2020) / Integration of the risks of climate change into humanitarian planning and preparedness / Support to effectively mobilise and deliver climate finance. / Support to GoE to ensure humanitarian links into broader poverty reduction efforts. / Support to understand the factors that cause and reinforce recurrent vulnerability in Ethiopia / Support to synthesis and generation of better data on humanitarian and development support in humanitarian woredas. / Value for money assessments. / Fiduciary risk assessments of spending options and assessment of the risks of funding terrorist organisations with agreed recommendations. / Support to local capacity to deliver in Ethiopia, in particular in areas where government is capable of delivering humanitarian response, such as health and nutrition .Recommendations to DFID on whether we should fund the government of Ethiopia to deliver humanitarian aid through this modality in the longer-term.
2. Effective response to meet food needs	Finance to the WFP to deliver food security support (through cash where markets support it) and technical assistance as consistent with supporting a government of Ethiopia-led and -owned system and also as a means of achieving this system shift. / Finance to the GoE through existing social protection systems to deliver scaled up food security support to meet expanded humanitarian needs as appropriate. / Support to ensure effective delivery e.g. M and E expertise. / Contingency to meet any emerging needs that have not been predicted. This will be managed either by the most appropriate partner to address the needs. If DFID does not have a contractual arrangement with the partner then the finance will be managed by the management agent. If DFID has a direct contractual arrangement the finance will be managed by DFID.
3. Effective response to meet non-food needs	Finance to the EHF to deliver immediate non-food needs (water, sanitation, nutrition, shelter / Technical assistance to the GoE to consider how to deliver nutrition support in humanitarian response woredas through prepared government systems and financial support to test approaches if appropriate. / Support to GoE to deliver emergency needs if appropriate and systems are ready to respond. / Potential TA to line ministries to scale up their emergency response plans. / Contingency to meet any emerging needs that have not been predicted.
4. Independent monitoring, evaluation and learning	Research synthesis pieces if necessary. / Independent monitoring to inform effective programme delivery and to improve outcome monitoring. / Beneficiary feedback including a focus on more marginalised groups, furthering the Grand Bargain commitment on Accountability to Affected Populations. / Support to local capacity building, in particular GoE staff. / Continued value for money assessments. / Independent review of programme at mid-term and end point. / Work to ensure that learning is built into programme design. / Assessment of the data available and the most effective way to provide independent monitoring. / Evaluability assessment. / Impact evaluation of nutrition and health outcomes delivered through government, and humanitarian partners. / Evaluation of effectiveness of overall programme.

Figure 6: Activities under each output.

The structure of BRE

Figure 7. Management structure of BRE

Key Roles and responsibilities

HMG: working with the Ethiopian Government to continue to support their leadership in meeting the needs of the Ethiopian people. This will require significant advocacy from DFID and FCO.
Management agent: to provide technical support to the Ethiopian Government in planning for crises and delivering humanitarian aid, where appropriate they will provide support to other actors such as NGOs working in areas where needs are particularly acute. The Management Agent will provide technical assistance where they are the best provider, there are some areas where other organisations do this, for example WFP may be the most appropriate body to provide technical assistance in food procurement as this is an area in which they specialise. The management agent will also contract monitoring and evaluation of the delivery partners under BRE.
Independent Reviewers: An independent review of the managing agent will be conducted to ensure that they are delivering on their responsibilities.
Government of Ethiopia: has the primary responsibility to meet humanitarian needs in Ethiopia and will need support to do this:
MOFEC (Ministry of Finance and Economic Cooperation): support in financial planning for disasters so the finance is available when needed to meet needs before they become critical and where possible to prevent needs arising.
NDRMC (National Disaster Risk Management Commission): are they primary body in the Ethiopian government that is responsible for the coordination of humanitarian affairs. They need support to do this effectively and to ensure full prioritisation.
Line Ministries (e.g. Ministry of Health): have a key role in response in particular for example in ensuring adequate health worker capability to respond to nutrition needs or the outbreak of cholera. Line ministries have shown leadership but need further support to be able to fully flex.
Local Administrations: need support deliver sufficient quality to be effective, for example some woredas are not yet able to effectively target the most vulnerable people.
World Bank: The World Bank is not funded by this Business Case but is funded by other DFID programmes and is a primary development partner. They will continue to have a role in working with DFID and the GoE in building response preparedness and capability in areas where they work.
OCHA: Has a continued key role in working with the Government to coordinate humanitarian affairs. Until the NDRMC can fully take on this role, OCHA will have a key role to play in Ethiopia.
World Food Programme: World Food Programme will deliver life saving support where it cannot be delivered through government. DFID funding through WFP will increasingly be through the social protection systems in country to deliver better value for money and save more lives, and increase the government capability to meet needs in hard to reach areas.
Ethiopia Humanitarian Fund: The EHF will meet lifesaving needs that the government does not yet have the capability to meet these.
DFID Human Development Programmes: DFID will work within the office to ensure our human development programmes can withstand disasters and where appropriate respond to them. This means for example ensuring the bore holes are built in vulnerable areas so people have access to clean water.

VFM statement.
Our assessment is that the option chosen represents VFM. Option 4 is likely to yield significant benefits and these outweigh the cost and risks and offer value for DFID’s investment. The programme combines technical assistance to raise overall effectiveness of delivery with a commitment to work through government which should be more cost effective and sustainable. At the same time the Business Case retains swift response and technical support capacity through humanitarian partners ensuring fast response where necessary and an ability to operate where government capacity is weaker. This is combined with strong commitment to beneficiary feedback, evaluation and independent monitoring to enable adaptations to the programme and learning.

How VFM will be monitored and measured.
VFM monitoring will be taken forward at key points in the programme cycle: (i) in assessing proposals for funding; (ii) at contract/ grant award stage; and (iii) at each review. Value for money will be built into the assessment criteria for competitive tenders, the logframe and the MOUs with partners. Evaluation and independent monitoring will be used to assess and strengthen outcomes. The programme inception will build on and develop metrics in order to assess value for money throughout the programme.

Economy
All partners must report on what actions they are taking to achieve maximum value with DFID money e.g. through their procurement systems. This must include not just unit costs but the full cost recovery to achieve any given output. Narrative reporting will accompany this, as in order to reach the most vulnerable, more expensive inputs are likely to be necessary (for example transport to Somali region is more expensive).

Efficiency
Key cost per output indicators will be tracked across the life of the programme. We expect a large amount of spend on areas where evidence is strongest. In line with this we will increase delivery of cash in Ethiopia where appropriate. To increase efficiency we will ensure where possible prepositioned government spend that can act before the crisis hits and therefore achieve more outputs per £ spent. The programme by working with and through one government led system will deliver efficiency gains by reducing duplication.

Effectiveness
Beneficiary feedback, and independent evaluation and monitoring will ensure that the programme is effective. We will also constantly review programmatic choices related to evidence that they are based upon, retaining the capacity to take forward swift evidence reviews. Monitoring will be critical to ensuring we can be confident that the most vulnerable are reached and that they are reached in a way that is effective and appropriate. It will also ensure that delivery overall is strong and that beneficiaries have a say, including vulnerable groups such as the disabled. We will feed lessons into future programmes and into BRE to ensure we are using the best knowledge to inform programme delivery.

Equity
We will ensure that we reach the most vulnerable by direct targeting, and will focus on building capacity in regions where the most vulnerable are located. We will ensure beneficiary feedback loops and tracking of distribution and usage of humanitarian assistance. The programme will ensure a clear focus on gender and assessment of differential impacts on women and girls, men and boys, and work to assess the challenges faced by the disabled in accessing humanitarian aid. Using more cost effective systems across the programme will free up capacity to reach the most vulnerable. At times reaching the most vulnerable or marginalised groups will be more expensive but is necessary to meet DFID’s commitment to ‘leave no-one behind’.

Commercial Case

BRE will deliver i) TA and monitoring via a Management Agent, and ii) humanitarian support via UN agencies, transitioning to Government, iii) Independent review of the overall programme. Commercial considerations for these delivery modalities are outlined below.

Management Agent – Direct Procurement.
The BRE Facility Managing Agent will be directly contracted through a competitive ‘Official Journal of the European Union’ (OJEU) procurement exercise, which will commence after the Business Case is approved. To increase competitive tension the contract will be advertised not only in OJEU but outside, with the intention to put the existing well-known market place under additional competitive pressure and hence aim to drive costs down and increase the quality of outputs.

The Building Resilience in Ethiopia programme contract will contain clauses on flexibility and adaptability to enable DFID to react to changing situations and opportunities. This will be in response to changing needs and changing political and social realities, as well as to the results of independent monitoring and lessons learned from early years of disbursement. Technical assistance will respond to opportunities to support and strengthen Government policy and practice in responding to crises as it evolves.

BRE requires a management agent for four years. The contract will have two break points: the first after a 5 month inception phase and the second after 2.5 years. A decision to continue with the contract in its current form will depend on the quality of delivery as set out in an externally contracted mid-term report. DFID will also reserve the right to break the contract if the management agent fails to comply with the terms and conditions.

How does the design use competition to drive commercial advantage for DFID? The BRE Managing Agent will be put out to open tender, and terms of reference will be drafted jointly by the DFID Ethiopia project team, working with DFID PCD. Market intelligence tells us there are at least six companies and not-for-profits able to operate in Ethiopia to deliver the kind of Management Agent functions we are looking for here. We will conduct early Market Engagement to increase the potential bidders and to generate additional competitive pressure which, in turn, will improve the quality of the bids. All bidders will have to map out their entire supply chain so that we can identify risks to VFM and to delivery.
### How will the contract be structured and how will performance be managed through the life of the intervention?
The contract will have three phases and will be managed through a mixture of milestones and outputs.

Phase i will be the inception phase – during the first six months the management agent will be expected to begin to set up in Ethiopia, and set out clearly how they will operate and deliver on programme objectives. The inception phase will review suggested allocations and in particular consider when it would be appropriate to allocate finance to government, and on what conditions. The contract continuation will be dependent on the quality of the inception report which will be due within 5 months of the contract start date. This will be the first potential break point in the contract. The first payment will be dependent on the quality of the inception phase.

Phase ii will be the first term of the contract. It will run for the first 2 years after the inception phase and a mid-term review will be conducted after this phase. Should the contract be not delivering at this point there will be a second break point in the contract. This break point also coincides with DFID’s decision-making over shifting systems to provide finance through GoE for humanitarian response. We would expect the TA provided by the Management Agent to have helped DFID with this decision-making process.

Phase iii – Phase iii is the final 2.5 years of the contract.
The contract will include a break clause at the end of Phases i. and ii. This is to encourage supplier performance and provide a means of managing risks. Supplier payments at the end of the inception phase will be linked to delivery of a set of pre-determined key deliverables that demonstrate the BRE management agent is up and running and able to deliver high quality support to GoE counterparts and the humanitarian system. This will include feedback from the GoE about their perceptions of the management agent, as the programme can only be successful if the management agent and TA have good relationships with the GoE. Under the first phase the payments for TA and for the management agent will be quarterly on the basis of agreed deliverables.

Indirect procurement for UN agencies and Government of Ethiopia.
As set out in the appraisal case, it is not possible to justify funding to the UN or Government of Ethiopia under a Fund Manager as the high additional cost would not generate proportionate additional value.

UN
The MOUs with UN agencies will be for 5 years with a reduction in funding amounts in the final 3 years. This longer-term commitment to multi-year funding is consistent with our commitments under the Grand Bargain. This will remain static if GoE systems are able to absorb humanitarian funding in those outer years of the BC. MOUs will, where possible, be based on detailed programme proposals received, with work plants, budget and key performance indicators. Funding will be dependent on performance and commitment to supporting government spending, delivering Grand Bargain commitments and demonstrating (including reporting on) VFM. More detail on management of WFP and UNOCHA can be found in Annexes 3 and 4. We will obtain full supply chain mapping and have regular discussions on VFM, outcomes and risk with both partners (minimum quarterly). If necessary we will provide technical support to the UN to ensure they can meet the highest standards e.g. in delivering against DFID VFM commitments.

Government of Ethiopia
If judged appropriate by the Management Agent and the BRE Steering Committee (see Management Case) we will support delivery through the GoE. The management agent will assess and report to DFID on whether it is appropriate to deliver through government. If it is deemed appropriate to deliver through the government, the management agent will then report on the most appropriate financial modality to deliver through government. This could, inter alia, be finance to the Ministry of Finance and Economic Cooperation, finance directly to a sector Ministry (e.g. the Ministry of Health) or finance to a World Bank pooled fund. The Management Agent alongside DFID will undertake fiduciary risk assessment(s) in order to mitigate any fiduciary risk associated with direct delivery. This will include transparency, accountability, cost savings and audits. We will work on the basis of best practice in other funding support through the DFID office to GoE. Prior to any funding to GoE, if appropriate, we will conduct a programme-specific Partnership Principles Assessment (PPA).

How will we drive savings and value for money through indirect procurement?
We will drive value for money in these agencies by:
- Delivery on the Grand Bargain commitments including a clear shift within the UN agencies to working to support the Ethiopian Government to lead the response; using more cash (where appropriate); moving to a better planned approach and clear reporting on how UN agencies are delivering cost savings including via full fund flows reporting.
- WFP to work with and through government systems (in particular the PSNP) to deliver better value in overall response and to be more effectively monitored. WFP has set out strategically that this is their intention. DFID’s funding will be used to hold them to account for this strategic intent.
- Prioritising delivery to where it is most needed - this may mean supporting some administrative costs (for example so NGOs can reach underserved areas) and some longer term funding.
- Ensuring clear break points in the MOU if the agencies fail to perform on key compliance areas e.g. gender reporting.
- Undertake specific work with the agencies on areas where we judge they could deliver cost savings.
- Contractual arrangements to report and build capacity on VFM.

Technical Assistance Posts.
- One DFID-funded post to support the Climate Resilient Green Economy Facility to ensure that this is consistent with the humanitarian narrative and to ensure that international funds to support the poorest countries to adapt to climate change flow to where they are needed most in Ethiopia.
- Potentially one DFID funded post to ensure effective delivery of the BRE business case and lesson learning. This post would be based in the GoE.

Small direct interim tenders for preparatory work while the procurement for the management agent is in train.
- An evaluability assessment to test what could and should be evaluated; this will in particular consider an impact evaluation of delivering scaled-up emergency nutrition through government. This will also consider what would be the most appropriate way to take forward independent monitoring.
  [note] Is a systematic process that helps identify whether program evaluation is justified, feasible, and likely to provide useful information. It is a key way of ensuring VFM in evaluations.
- Support to the DRM commission on strengthening DRM management, building on support and analysis to date (see Annex 9).
- Support to MOFEC on risk financing, building on support and diagnostics/ scoping to date (see Annex 8).
- A thorough value for money assessment of all the proposed partners.
- Internal work to see how far systems could be made more effective using results and targets – building on the lessons of deliverology.
- Unforeseen requests for technical assistance which will be appraised and approved by DFID on a case by case basis.

Each element of BRE has different key cost drivers:

	Key Cost Drivers	Action to be taken to keep them appropriate/proportionate
Management Agent	Fund management fees.	Fund management fees will be driven down by using effective procurement and their worth retained by careful management of the contract.
Independent Monitoring (including beneficiary feedback).	Salaries of monitors, transport, office costs.	Monitoring is relatively economical in Ethiopia. We will benchmark costs against other similar contracts. Competitive tender will be used to keep costs low and quality high.
Technical Assistance	Consultants’ fees, travel, the balance between national and international. The balance between short and long term. We will be seeking to have more long term consultants and more local consultants where the right skills set exists to ensure cost effective delivery.	We have benchmarked fee rates. Local consultants £200-400 per day and international £500 – 800 per day. Absolute no. of days will be as important as fees. We will also look at length of time; longer term support reduces rates and can be more effective. We will not pay day rates/ will ensure day rates are significantly below benchmarks for long term contracts. We will monitor quality to ensure effectiveness.
WFP	14.4% management costs, operational costs will primarily be cash transfers and technical assistance. Food and cash delivery costs $0.32 per day, a mega tonne of food is based on the cost of that commodity which was between $200-300 per MT in 2016 (depending on the commodity and the price at the time). Delivery costs can vary the Government of Ethiopia delivers for on average $120 per metric tonne. WFP full cost recovery is higher due to higher overheads, and less efficient use of transport. WFP is more expensive than government delivery but has a different reach. Until the government can reach all of the current WFP beneficiaries the WFP is the only alternative.	We will retain careful benchmarking between agencies. Agencies will report on key cost drivers. We will increase the delivery of cash, as cash transfers are cheaper to deliver than food. Food aid will still be delivered where markets cannot support cash. Furthermore, evidence suggests better nutrition outcomes per pound spent on cash than food. Detail on WFP costs can be found in Annex 11.
EHF	EHF has a variety of key cost drivers. 11% is management fee. 89% is operational delivery through NGOs.	EHF manages economy good examples of procurement scale, good budget management, benchmarking costs. We will continue to encourage strong prioritisation to ensure efficiency of delivery and reporting on key cost drivers. Details of EHF costs drivers can be found in Annex 10 in USD.
Support to GoE to manage nutrition outcomes.	Key inputs - health workers, nutrition treatment, training, capacity building, and capacity support.	These inputs should be cheaper working through government e.g. supplementary feeding costs $ dollars per day under EHF but is less than $1 via government systems. We will continually benchmark to ensure best value, and ensure we only use expensive modalities where Government Systems cannot deliver.

Figure 8. Key Cost Drivers

## Financial Case

Sources of Funding: Who are the recipients of all proposed payments?
This project will be funded from the DFID Ethiopia Programme resource allocation and has been budgeted for in the DFID Ethiopia Business Plan. There will be neither contingent nor actual liabilities under the project lifespan. It is noted that this programme commits funds beyond the current spending review period.

Indicative financing for partners per financial year (in £ millions)

Component title	2017/18	2018/19	2019/20	2020/21	2021/22	Total known
Management agent, Research and Technical Assistance	2	7	8	8	7	32
Delivering food security support through WFP	24	12	8	2	1	47
Response to humanitarian emergencies through EHF	9	8	5	2	1	25
Contingency budget	2	2	2	2	2	10
Funds to be allocated to the most effective delivery body. We expect this to be the Government of Ethiopia.	0	0	20	16	15	49
M and E	0.5	0.5	0.5	0.5	1	5
Total	38	30	44	29	27	168

Figure 9. Indicative financial allocations.

The highest funding is for the first year because 5.6 million people are projected to be in need, which is nearly double the normal annual humanitarian case load of ~3 million people. Furthermore, people are recovering from the 2015/16 drought and are therefore more vulnerable due to having employed negative coping strategies over the past two years. At this juncture we expect future caseloads for the duration of this business case (though it is difficult to predict – climatic changes may make this even more difficult) to be lower than 2017/18 but this cannot be guaranteed.

This BC will work to ensure a better planned and prepared for response that is supported by comprehensive financial preparedness for the cost of humanitarian shocks, ensuring an ability to act swiftly. In practice, we allow for some flexibility in funding to ensure that it is deployed when and where necessary.

Fund Flows Diagram
DFID HQ

WFP HQ
7% Admin
DFID ETH

Management Agent

MOFEC
OCHA HQ
3% Admin

WFP ETH
11% Admin1

Technical Assistance
  M&E

MOH
MOE
MOA
MOWR
NDRMC

WFP Hub
NDRMC
OCHA ETH/ EHF
RDPPB (bank account)

RDPPB
WoDDPs (bank account)
Gov.t Hub

 FDP’s

List of NGO’s and UN Agencies*
7% Admin, additional 7% if on granted to local NGOs (applies to 15% of funding).

WoFEC collect the money and disperse it.
ZoDPPB

 FDC’s

WoDPPB

Beneficiaries*

Keys / 1; WFP country office admin cost is different from project to project. It depends on the number of pocket area interventions and number of sub offices. 10% is the maximum admin cost charged by WFP at CO level when there is many sub offices. Ex. the average admin cost for the drought response programme from last year was around 18 / % / * Disaster affected populations identified by official need assessment / * Too early to identify the potential NGO’s list since selection of NGO’s will depend on the availability of funds, quality of proposal and scale of need / Relief food transfer in all regions except Somali / Relief food transfer in Somali Region / Relief cash transfer / Both reporting and transfer chain / Financial and relief food transfer / Reporting process / Potential organization expected to receive fund / Figure 10. Fund Flows Diagram / Acronyms / DPPB: Disaster Prevention and Preparedness Bureau / HRD: Humanitarian requirement document / FDC: Food Distribution Committee / FDP : Final Distribution Points / NDRMC: National disaster risk management commission / RDPPB: Regional DPPB / WoDPPB: Woreda DPPB / WoFEC: Woreda office of Finance and Economic Cooperation / ZoDPPB: Zonal DPPB

How expenditure will be monitored, reported and accounted.

The Management Agent and Technical Assistance
Key elements of reporting will include:
- Quarterly reports including spend, risk, assessment of key cost drivers, results and budgets.
- Regular spot checks of assets and following of best practice under the Smart Rules for the management of assets.
- Annual Accounts independently audited.
- Regular checks to ensure effective branding.
- Biannual independent process review.
- Regular meetings on key issues and quarterly management meetings.

UN Agencies
For the UN agencies, WFP and OCHA, we will ensure we are tracking best practice, monitoring global MAR-related issues for further follow up with these agencies, and feeling into new Global Partnership Arrangements to be negotiated with these agencies in 2018. Other specific aspects of how we will ensure good financial accountability with each of the agencies in country are outlined below:

WFP
DFID’s Due Diligence assessment of WFP, Dec 2016, concludes that WFP is generally efficient and well run. The key issue to be addressed was fraud awareness for staff and clear understanding on how any arising WFP- managed fraud cases should be addressed. DFID will monitor this issue throughout the life of the programme. Other means of ensuring WFP’s fiscal accountability include:

- Monitoring via annual financial and narrative reports that are publically available.
- Regular meetings with the WFP team in country on key issues, and quarterly management meetings.
- Scrutiny of WFP audits to the extent possible, conducted under UN rules.
- WFP has a renewed focus on VFM in order to meet as many beneficiaries a possible. We will support WFP in strengthening this focus.
- Management of assets according to UN standards and tracked by DFID. WFP, like other UN Agencies, will send DFID its asset register on an annual basis.
- We will support external monitoring, including regular spot checks of delivery and conduct our own visits (at least quarterly).
- To ensure alignment with Government vision of a single social protection system we will agree WFP project documents with the Government of Ethiopia and the World Bank.

EHF
DFID due diligence conducted in December 2016 identified that the EHF needs to strengthen risk management and value for money. It also needs to establish a conflict of interest register and a fraud reporting system. We are confident that the right steps are being put in place to take forward these recommendations and have regular meetings on the due diligence with the EHF team. OCHA has some work, for example on cost drivers, which is a good start to ensuring good VFM. The organisation still needs to work harder on prioritisation and performance monitoring but progress is being made on both of these issues. We are meeting with them regularly, minimum quarterly. Other aspects of ensuring fiscal accountability include:
- Tracking and reporting against publically available financial and narrative reporting for the EHF, provided annually for the previous UN financial year (Jan-Dec).
- Ensuring OCHA follows UN audit rules for funds they retain and spend, and scrutinising audit reports where we have access to these.
- Scrutiny of OCHA’s asset register, shared with DFID on an annual basis.
- Ensuring an inbuilt external evaluation, to be conducted under OCHA rules.
- We will support external monitoring and conduct our own visits.

Does the project involve financial aid to governments?
The DFID Ethiopia Building Resilience Steering Committee (see Management Case, below) will make a decision on whether the Government of Ethiopia is able to effectively spend, monitor and report on humanitarian finance in year 3 of the programme. There is no financial aid to Government for the first two years of the programme. If we judge that the right way to effectively reach the most beneficiaries is to work through Government then we will take forward due process including a programme level Partnership Principles Assessment. This decision will be taken in the context of the annual Partnership Principles Assessment submitted to the Secretary of State. Should we decide that it is not appropriate to put finance through the Government of Ethiopia we will support the same objectives through humanitarian and development organisations able to achieve the same results.

Financial Risk and Fraud
Our overall assessment is that the likelihood of financial risk and/or fraud is major because we seek to deliver humanitarian aid to some of the most vulnerable populations in the world.
The risk of the Management Agent and the technical assistance they provide is minor, due to the rigorous selection process that will be followed and the addition of increased independent monitoring.
 The UN agencies that we are working with have a strong track record of delivery, and are effective at managing and reporting fraud but as they are delivering in difficult environments we assess the risk to be major. To manage the risk we will ensure a country level fund flows assessment is taken forward by WFP and the EHF, examine previous audits, and we have just refreshed due diligence at the country level for both funds which raised no serious concerns.
The risk of fraud and corruption associated with any potential financial aid to GoE will be assessed through a fiduciary risk assessment. This will inform out risk management strategy.
All elements of BRE will be subject to an annual independent audit and periodic monitoring, to ensure that funds are used for the purpose intended.

Management Case
DFID Ethiopia Building Resilience Committee
The most critical element of the programme’s management is the DFID Ethiopia Building Resilience Committee that will be responsible for management of BRE and will meet at least quarterly. This committee will make all major strategic programme decisions. It will be chaired by the Senior Responsible Officer for the programme and will report to the DFID Ethiopia Head of Office. It will include the following members:

Chair: Senior Responsible Officer
Management Agent Senior Representatives
A2 DFID Ethiopia Lead Humanitarian Adviser
A2 DFID Ethiopia Humanitarian Adviser focusing on migration
A1 DFID Ethiopia Livelihoods and Humanitarian Team Leader
A1 Human Development Team Leader
A2 Water and Sanitation Adviser.
A2/A1 Health Adviser
A1 DFID Ethiopia Social Development Adviser
A2 Nutrition Adviser
A2 Private Sector Adviser, also economist

Other actors will be invited as appropriate.

Contract, Delivery and Operational Committee.
These structures will be complemented by meetings at least monthly of the Contract, Delivery and Operational Committee (CDO Committee). This Committee will include the Programme Officer, the SRO and the Management Agent. The Lead Adviser will attend as appropriate. The CDO committee will be responsible for regular programme decisions and detailed delivery discussions. It will refer any major decisions to the BRE Steering Committee.

Government of Ethiopia
We will engage with and report to the GoE as the primary recipient of funds. We will ensure that this is consistent with best practice as consistent with the principles of aid effectiveness.

Regular meetings with the Government of Ethiopia
The SRO and programme team will also meet regularly with the GoE (including the DRM Commission and the Ministry of Finance counterparts) to ensure they are content with the performance of the management agent and other delivery partners. This feedback will be critical. Performance of institutions will be reported on via embedded TA.

Once any agreement on humanitarian assistance via Government bodies is decided on, robust management, monitoring and regular meeting schedules will be set up with the relevant Government counterparts.

Reporting
The Management Agent will be required to report to DFID at least quarterly. These reports will be narrative, as well as against results (disaggregated by gender), and logframe reporting. Reports will include clear beneficiary feedback, a clear assessment of VFM against agreed indicators and an updated risk assessment. We will also expect the implementers to report on any potential or actual aid diversion, and to identify high risk areas for particular focus for monitoring.

UN agencies will report annually using their financial and narrative annual reporting formats. In the process of setting up contracts with these UN agencies we will discuss whether more frequent reporting is possible from the UN agencies on the basis of our financing. Quarterly management meetings with UN agencies will also be an opportunity to discuss programme progress and any potential bottlenecks or other issues for resolution.

Reporting against ad hoc TA in the first months of the project prior to the contracting of the Management Agent will be agreed on a case-by-case basis.

DFID Internal Monitoring
DFID Ethiopia will ensure the projects are visited by DFID staff at least 8 times per year (once per quarter by SRO, and once per quarter by other staff). These visits will be clearly documented, and in the main planned in advance (but at times will be with little warning to ensure we see a true picture) and any recommendations from these visits will be clearly documented and discussed with partners. We will reflect and follow up on the recommendations via the BRE Programme Delivery Plan. The log-frame will be formally reviewed on at least an annual basis.

Independent Monitoring and Evaluation contracted through the BRE Management Agent. We will contract independent monitoring and evaluation through the management agent. This will report to the BRE Steering Committee to ensure real time lessons from the programme delivery are learned and acted upon. The monitoring and evaluation element of BRE will report directly to the DFID Ethiopia Building Resilience Steering Committee to ensure a level of independence. As part of our broader technical assistance the programme will support to the Government of Ethiopia to take forward stronger monitoring and evaluation of the humanitarian response.

Monitoring and beneficiary feedback
An independent monitoring feasibility study will be conducted to assess what value can be added by independent monitoring through BRE and to ensure coherence. This will include focus on vulnerability and beneficiary feedback; ensure coherence with broader monitoring of development programmes and will look at grievance mechanisms, and how humanitarian funding can be linked into broader social accountability mechanisms. It will also look at fund flows and fraud risk.

All of our programme agreements will include agreement that DFID can take forward independent monitoring and a requirement that they have effective internal monitoring strategies.

Evaluation
BRE will contract the following evaluations, subject to an evaluability assessment and DFID evaluation product quality assurance systems:
- Evaluation of support to nutrition and health outcomes delivered through government.
- A multi-donor evaluation of WASH and Nutrition outcomes through the Ethiopia Humanitarian Fund. This will be contracted through the BRE management agent unless another donor wishes to take forward.

Independent Reviews.
DFID will also contract an independent review of BRE management agent at the mid-point and at the final point of the contract. This will be to assess their effectiveness, and support DFID to make decisions on future management at the mid-point of the programme. DFID will also contract an overall effectiveness of the BRE programme review using evaluative methods at the end of the programme for future learning.

Risk Register A full risk register is included as Annex 2. A summary of key risks follows below:
Risk	Impact	Cause	Mitigation Actions
Delivery: Actors unable/ unwilling to deliver humanitarian aid according to need.	Aid doesn’t reach those who need it most.	Instability Local politics Weak capacity Politicisation of numbers Weak data. Instability	Cash Independent monitoring Sufficient variety of partners Strong focus on resilience Sufficient spread of partners Political economy analysis.

Fiduciary: Fraud and corruption	Aid doesn’t reach those who need it most.	Weak capacity Speed of delivery Too many partners	Independent monitoring Fiduciary risk assessments. Fund flow exercises Audits Part of DFID Ethiopia assurance programme.

Delivery: Slow delivery	Aid doesn’t reach those who need it most at the right time.	Too many partners, poor planning, lack of capacity	More preparedness. More capacity support to ensure effective delivery. Tracking. Independent monitoring.
External: Large scale instability in Ethiopia	Aid unable to reach those who need it worse.	State failure, crisis worsens, conflict driven humanitarian crisis.	Ensure a spread of partners and that the UN is able to play its critical monitoring role.
Delivery: Changes in delivery partners (from UN to Government puts beneficiaries at risk).	Aid doesn’t reach people previously reached.	Poor management of transition.	Monitoring / Piloting / Governments systems can meet more people with the same amount of finance but we must ensure this includes the most vulnerable.
Delivery: The UK decides not to provide direct aid to GoE	Programme deliveries disrupted leading to major gaps in meeting humanitarian needs	Lack of commitment and political will from the GoE to take actions in opening up political space.	Continued political dialogue

Figure 11. Summary Risk Register